## How to fill , RACI & issue log
Version 1, Issued 14th November 2025 |  | Bobby Moinazad, Mobile Infrastructure Forum
How to fill
1) Designer and Principal Designer complete the Building Regulations Compliance sections of the Approved Document worksheets at General Arrangement phase. 2) Designer and Principal Designer complete the Construction Control input sections outside of the print areas of the Approved Document (AD) worksheets at the end of the the general arrangement phase, 3) Contractor and Principal Contractor select Contractors for each scope element and complete the construction control inputs in the AD worksheets 4) Construction Control Plan and Fire and Emergency File fields filled by designer and principal designer at detailed design, in consultation with the principal accountable person and the client. 5) Principal Contractor and Contractors complete competency sections of the construction control plan. 6) All duty holders meet to review the draft Gateway 2 application at site and revise the worksheets. 7) Principal Contractor authors the Construction Control Plan, Change Control Plan and Mandatory Occurrence Reporting Plan documents in Word, and extracts respective forms from the Building Regulation Compliance System (BRCS) for insertion in to each document in their appendix sections. 8) Principal Designer extracts the Building Regulations Compliance Statement from the BRCS together with the approved documents and compiles a Building Regulations Compliance Statement. 9) Principal Designer extracts the Fire and Emergency File , Golden Thread Arrangements, and Gateway 2 application documents from the BRCS and converts to PDF 10) All documents saved in the project folders by the authors 11) Duty holders and Dependency Manager review the documents , correct errors, and re-print. 12) All documents converted to PDF using Adobe Pro or Nitro Pro 13) Draft Gateway 2 documents issued to client, principal accountable person, and consultants 14) Client authorises Gateway 2 documents to be issued to the Building Safety Regulator 15) Dependency Manager submits the Gateway 2 application.
RACI and completion register
| Is the sheet applicable to the works? | Designer | Principal Designer | Contractor | Principal Contractor | Duty Holder comments | Duty holder assessment of completion
Principal Designer to select)
Form | [6 empty] | in progress
Site and contact details | Yes | Responsible | Accountable | Informed | Informed |  | in progress
Document Issue Control Sheet | Yes | Responsible | Accountable | Informed | Informed | In progress | in progress
Structure: Approved Document A | Yes | Responsible | Accountable | Consulted | Informed | Needs structural calculations revised - 185 mm slab thickness. Insufficient information on… | information missing
Fire safety: Approved Document B | Yes | Responsible | Accountable | Consulted | Informed | Using Roxtec product would require xxx transits. Must use xx product instead in 13th floor riser to stairwell . Floors are 90 minute rated | risk
Site preparation and resistance to contaminates and moisture: Approved Document C | Yes | Responsible | Accountable | Consulted | Responsible | 80%. PAP concerned about the number of penetrations and wants proof of consultation with xyz and www | risk
Toxic substances: Approved Document D | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Resistance to sound: Approved Document E | Yes | Consulted | Consulted | not applicable | not applicable | Minor issue. xxxx | information missing
Ventilation: Approved Document F | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Sanitation, hot water safety and water efficiency: Approved Document G | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Drainage and waste disposal: Approved Document H | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Combustion appliances and fuel storage systems: Approved Document J | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Protection from falling, collision and impact: Approved Document K | Yes | not applicable | not applicable | not applicable | not applicable | No identified issues. | not applicable
Conservation of fuel and power: Approved Document L | Yes | Responsible | Accountable | Consulted | Informed | Comments on insulation / warm roof. Insert | in progress
Access to and use of buildings: Approved Document M | Yes | Consulted | Accountable | Informed | Informed | PD to complete. No identified issue. | in progress
Overheating: Approved Document O | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Electrical safety: Approved Document P | Yes | Responsible | Accountable | Responsible | Informed | Contractor to complete | in progress
Security in dwellings: Approved Document Q | No | not applicable | not applicable | not applicable | not applicable | Completed by PD | not applicable
Infrastructure for electronic communications: Approved Document R | Yes | Consulted | Accountable | Consulted | Responsible | Completed by PD | complete
Infrastructure for charging electric vehicles: Approved Document S | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Toilet accommodation: Approved Document T | No | not applicable | not applicable | not applicable | not applicable | not applicable | not applicable
Material and workmanship: Approved Document 7 | Yes | Completed | Completed | Completed | Completed | Completed by PD | complete
| responsibility | Status | COMMENTS |  |  |  | Date
BR compliance statement'!A1 | PD | 25% | Need calculations to be corrected |  |  |  | 2025-06-27
Construction Control Plan'!A1 | PD AND PC | 50% | PC inputs required
Project Change Control'!A1 | PC | Complete | Standard document
Project Change Control Notes'!A1 | PC | Complete | Standard document
Mandatory Occurrence Form'!A1 | PC | Complete | Standard document
Golden Thread Arrangements'!A1 | PD AND PC | 75% | Once construction control complete this will be complete.
Fire and Emergency File '!A1 | PD AND PC, RESPONSIBLE PERSON | 75% | 75% complete. In progress 24/06/25. Need to confirm who will install the call point/ sounder (responsible person to confirm) |  |  |  | 2025-06-24

## Site and contact Details
Site and contact details |  |  | Back to RACI
Site Details
Site Name | Site Name
Site Address | Site Address
Postcode | Site Postcode
High risk building reference | HRB000000000
Principal Accountable Person | Site PAP company
Principal Accountable Person | PAP dutyholder name
Position | PAP dutyholder position
email address | PAP dutyholder email
Phone number | PAP dutyholder phone
Client
Contact Name | Client contact name
Position | Client contact position
email address | Client email address
Phone number | Client phone number
Company name | Client company name
Address and postcode | Client company address
Principal Designer |  | Webpage
Contact Name | Individual Principal Designer Name
Position | Individual Principal Designer position
email address | Individual Principal Designer email
Phone number | Individual Principal Designer telephone number
Company name | Principal Designer Company
Address and postcode | Principal Designer address
Individual Principal Designer #2 |  | Webpage
Contact Name | Organisational Principal Designer name
Position | Organisational Principal Designer position
email address | Organisational Principal Designer email
Phone number | OPD telephone
Company name | OPD company name
Address and postcode | Organisational Principal Designer address
Principal Contractor |  | Webpage
Contact Name | Individual Principal Contractor Name
Position | Individual Principal Contractor position
email address | Individual Principal Contractor email
Phone number | Individual Principal Contractor phone number
Company name | Individual Principal Contractor Company
Address and postcode | Individual Principal Contractor address
Principal Contractor #2 |  | Webpage
Contact Name | Organisational Principal Contractor Name
Position | Organisational Principal Contractor Position
email address | Organisational Principal Contractor email
Phone number | OPC phone number
Company name | Organisational Principal Contractor company name
Address and postcode | Organisational Principal Contractor address
Designer |  |  | Structural Engineer
Contact Name | Designer name |  | Contact Name | Structural Engineer Name
Position | Designer position |  | Position | Structural Engineer position
email address | Designer email |  | email address | Structural Engineer email
Phone number | 073 8669 8053 |  | Phone number | 073 8669 8053
Company name | This_Company UK Limited |  | Company name | This_Company UK Limited
Address and postcode | Unit 27F-G Hartlebury Trading Estate Crown Lane Hartlebury Worcestershire DY10 4JD |  | Address and postcode | Unit 27F-G Hartlebury Trading Estate Crown Lane Hartlebury Worcestershire DY10 4JD
Designer |  |  | Designer
Contact Name |  |  | Contact Name
Position |  |  | Position
Phone number | Designer phone number |  | Phone number | Structural Engineer phone number
Phone number |  |  | Phone number
Company name | Designer company |  | Company name | Structural Engineer Company Name
Address and postcode | Designer address |  | Address and postcode | Structural Engineer Address
Civils Contractor | Contractor X Installations Limited | Webpage
Contact Name | Contractor 1 Name
Position | Contractor 1 Position
email address | Contractor 1 email
Phone number | Contractor 1 phone number
Company name | Contractor 1 company name
Address and postcode | Contractor 1 address
Electrical Contractor | Summarise work scope of this contractor here
Contact Name | Electrical Contractor Name
Position | Electrical Contractor Position
email address | Electrical Contractor email
Phone number | Electrical Contractor Phone number
Company name | Electrical Contractor Company Name
Address and postcode | Electrical Contractor address
Fire System Contractor | Summarise work scope of this contractor here
Contact Name | Subcontractor 1 Name
Position | Subcontractor 1 Position
email address | Subcontractor 1 email
Phone number | Subcontractor 1 Phone number
Company name | Subcontractor 1 company name
Address and postcode | Subcontractor 1 address
Roofing company |  | https://www.Contractor Zroofing.co.uk/
Contact Name | Subcontractor 2 Name
Position | Subcontractor 2 Position
email address | Subcontractor 2 email
Phone number | Subcontractor 2 Phone Number
Company name | Subcontractor 2 Company name
Company website
Address and postcode | Subcontractor 2 Address
Supplier 1 | Summarise work scope of this contractor here | eg fabricator) | Supplier 2 | Summarise work scope of this contractor here | (eg handrail)
Contact Name | Supplier 1 Name |  | Contact Name | Supplier 2 Name
Position | Supplier 1 Position |  | Position | Supplier 2 Position
email address | Supplier 1 email |  | email address | Supplier 2 email
Phone number | Supplier 1 phone number |  | Phone number | Supplier 2 phone number
Company name | Supplier 1 company |  | Company name | Supplier 1 company
Address and postcode | Supplier 1 address |  | Address and postcode | Supplier 2 address

## Document Issue Control Sheet
Document Issue Register and Control Sheet |  |  |  |  | Back to RACI
Version of this document | Reason for revision |  |  | Date of issue | Add additional rows where needed and adjust the compliance statement or approved document document reference tables to match
Manifest of documents submitted to support Building Regulations Compliance Statement
Competency declaration and contractor appointment related documents
Document Name | Filename | Version | Version date | Summary of content
Declaration
appointment
Drawings
Document Name | Filename | Version | Version date | Summary of content
Drawing 1 | Client's Filename convention | A | 2025-09-15 | Detailed design drawings in PDF
Drawing 2 | Client's Filename convention other drawing | C | 2025-09-15 | Detailed design drawings in .dwg
DRA | Client's Filename convention DRA | - | 09.04.25 | DRA for CDM
Structural documents
Document Name | Filename | Version | Version date | Summary of content
Structural Calculations | adcde | a | 2025-04-01 | Structural calculation
Other structural calculations or GDC | fghij | a | 2025-04-02 | GDC calculation
STRUCTURAL INVESTIGATION | klmno | b | 2025-04-03 | xxxx report on structural investigations including roof.
Ground Penetrating radar scan |  |  | 2024-04-17
Steel work certificate. |  |  | 2024-04-17 | Expires 20/05/2027
Fire Safety related documents
Document Name | Filename | Version | Version date | Summary of content
Fire strategy plan | Fire strategy plan filename | 1 | 2024-02-22 | Existing Golden Thread Fire strategy issued by xxx
Fire compartmentation survey | SURVEY REPORT filename | 1 | 2023-06-06 | Existing compartmentation survey issued by xxxx on
Fire Risk Assessment | FRA 1 filename | 1 | 2021-02-01 | Site provider's specification for previous electrical works, including fire alarm system installation and integration
FRA- External walls | FRA - EW fiilename | 1 | 2022-09-23 | FRA EW issued by company x
Other fire safety document | Other fire-filename | 1 | 2025-06-23 | Describe
Electrical Safety related documents
Document Name | Filename | Version | Version date | Summary of content
Electrical calculations | Electrical calculations filename | A | 2024-07-09 | Electrical calculations by . AC calculations, DC calculations.
Rooftop waterproofing related documents (Approved document C)
Document Name | Filename | Version | Version date | Summary of content
Existing roofing warranty | Warranty filename | 1 | 2022-01-20 | Warranty
Manufacturer's document | Filename | 1 | UNDATED | Drawing of standard detail of waterproofing requirements supplied by xxxx .
Manifest of additional documents submitted to support Construction Control Plan
Document Name | Filename | Version | Version date | Summary of content
See above

## Gateway 2 application
Gateway 2 Application
Fill the following fields in readiness to input the answers into the Gateway 2 web-form.
Main Duty holders | Name | Address | Telephone number | email address
Client | Client contact name Client company name | Client company address | Client phone number | Client email address
Principal Contractor | Individual Principal Contractor Name Individual Principal Contractor Company | Individual Principal Contractor address | Individual Principal Contractor phone number | Individual Principal Contractor email
Principal Designer | Individual Principal Designer Name Principal Designer Company | Principal Designer address | Individual Principal Designer telephone number | Individual Principal Designer email
This application is made under the terms of The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023
Provide a description of the existing higher-risk building by filling the following fields.
Describe the current use of the Higher Risk Building , including the current use of each storey; | WRITE DESCRIPTION IN THIS BOX
| Answer here |  | Answer here
State the building's height as determined in accordance with regulation 5 of the Higher-Risk Buildings (Descriptions and Supplementary Provisions) Regulations 2023(1); height from ground level to the top floor, not the roof: | 34 | State the number of storeys it has above ground as determined in accordance with regulation 6 of the Higher-Risk Buildings (Descriptions and Supplementary Provisions) Regulations 2023; | 14
|  | Flats | Residential rooms | Commercial units
State the number of flats, the number of residential rooms and the number of commercial units contained in the higher-risk building; |  | 79 | 0 | 0
Describe the proposed work
THESE FIELDS AUTOPOPULATE FROM APPROVED DOCUMENTS
Civil and structural works, including Building Works as defined in the Building Regulations 2010. |  | INPUT SCOPE ELEMENTS INTO 'APPROVED DOCUMENT A' NOTE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT A
Works relating to fire safety, including Building Works as defined in the Building Regulations 2010 |  | USE APPROVED DOCUMENT B SCOPE FIELD TO INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT B , CONSIDERING ALL SECTIONS BE1 TO B5
Works relating to site preparation and resistance to contaminates and moisture, including Building Works as defined in the Building Regulations 2010 |  | INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD
Works relating to Electrical Safety, including Building Works as defined in the Building Regulations 2010 |  | P Scope
Any other works not covered by any of the above sections |  | Other works not summarised above are described in the Building Regulations compliance statement.
The following are general questions about the effect of the proposed work on the higher risk building |  | Yes/ No response here | Written response here.
Does the work change the use of any part of the higher-risk building ? If so provide details of the intended use of each storey |  | No
Is the height of any part of the higher-risk building changing? Provide the height of the building after the proposed work as determined in accordance with regulation 5 of the Higher-Risk Buildings (Descriptions and Supplementary Provisions) Regulations 2023; |  | No
Is the number of storeys in the higher-risk building changing? State the number of storeys as determined in accordance with regulation 6 of the Higher-Risk Buildings (Descriptions and Supplementary Provisions) Regulations 2023; |  | No
If the number of flats or residential rooms in the higher-risk building is changing state the number of flats or residential rooms to be contained in the higher-risk building; |  | No change
Is provision to be made for the drainage of the building or extension? |  | No | if provision is to be made, list the precautions to be taken in the building over a drain, sewer or disposal main to comply with the requirements of paragraph H4 of Schedule 1 to the 2010 Regulations
Describe any steps to be taken to comply with any applicable, local enactment
Commencement date and nominal project plan
|  |  | Date | Add comment here
Provide the date when it is proposed the work will reach the point when it is to be regarded as commenced in accordance with regulation 46A (lapse of building control approval: commencement of work) of the 2010 Regulations: |  |  | 2026-04-06 | INPUT This date is dependent on client approvals.
Provide the date when it is proposed that the Building Work is considered by the client to be 15% complete. |  |  | 2026-04-09
Provide details of the work which the client considers amounts to 15% of the proposed work | INPUT . EXAMPLE By day three of the mobilisation the tripod and grillage upstands will have been installed and re-dressed. The core drills through the risers will have been completed and the Roxtec glands installed . Electrical switchgear will have been mounted but not commissioned. Tripod and grillage steel members will be in the process of assembly on the roof for mounting on the upstands. See also the construction phase plan (CDM) , appendix B of the Construction Control Plan

## BR compliance statement
Building Regulations Compliance Statement |  |  |  |  | Back to RACI
IMPORTANT NOTE: the statement summaries below are populated via the respective approved document worksheet. Select whether the approved document is applicable to the works, confirm that that the respective worksheets are complete, and sign the bottom of this sheet.
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Duty Holders
Duty holder | Name | Phone | email | Company
Individual Principal Designer | Individual Principal Designer Name | Individual Principal Designer telephone number | Individual Principal Designer email | Principal Designer address
Individual Principal Contractor | Individual Principal Contractor Name | Individual Principal Contractor phone number | Individual Principal Contractor email | Individual Principal Contractor Company
Principal Accountable Person | PAP dutyholder name | PAP dutyholder phone | PAP dutyholder email | Site PAP company
Client | Client contact name | Client phone number | Client email address | Client company name
Competency declaration and contractor appointment related documents
Document Name | Filename | Version | Version date | Summary of content
Declaration
appointment
Existing Safety Case and Comments
INSERT AN IMAGE HERE |  | SUMMARISE THE SAFETY CASE, REFERENCING FIRE AND STRUCTURAL GOLDEN THREAD
Building Regulations Compliance Statement By Approved Document
Link to Approved Document (England) | Scope summaries from the Approved Document Spreadsheets | FILL THIS FIELD Applicable to works y/n Is the work Category A or B | General compliance Statement Summary from approved document worksheets.
Structure: Approved Document A | INPUT SCOPE ELEMENTS INTO 'APPROVED DOCUMENT A' NOTE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT A | Yes Category A | Write a general statement to describe how the design is compliant. Describe the calculation evidence that the design complies. Cite any BSEN codes that relate to the compliance. Note if the building pre-dated the codes applied, and provide a structural justification for the design and structutal calculation approaches adopted.
Fire safety: Approved Document B | USE APPROVED DOCUMENT B SCOPE FIELD TO INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT B , CONSIDERING ALL SECTIONS BE1 TO B5 | Yes Category A | USE APPROVED DOCUMENT B GENERAL STATEMENT OF COMPLIANCE FIELD TO WRITE A GENERAL STATEMENT OF COMPLIANCE, REFERENCING THE SCOPE ELEMENTS AND THE EXISTING SAFETY CASE.
Site preparation and resistance to contaminates and moisture: Approved Document C | INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD | Yes Category A | WRITE A GENERAL STATEMENT OF COMPLIANCE, REFERENCING THE SCOPE ELEMENTS AND THE EXISTING SAFETY CASE. DESCRIBE THE MEASURES PROPOSED TO MEETTHE RELEVANT REQUIREMENTS.
Toxic substances: Approved Document D | D scope | No | D Compliance
Resistance to sound: Approved Document E | E scope input | Yes Category B | E compliance input
Ventilation: Approved Document F | F Scope | No | F compliance
Sanitation, hot water safety and water efficiency: Approved Document G | G Scope | No | Not applicable.
Drainage and waste disposal: Approved Document H | H Scope | Yes Category B | H compliance :
Combustion appliances and fuel storage systems: Approved Document J | J scope | No | J compliance
Protection from falling, collision and impact: Approved Document K | K scope | No | K compliance
Conservation of fuel and power: Approved Document L | L Scope | Yes Category B | L Compliance
Access to and use of buildings: Approved Document M | M Scope | No | There will be effect on access through the building
Overheating: Approved Document O | O Scope | No | O Compliance
Electrical safety: Approved Document P | P Scope | Yes Category B | P Compliance
Security in dwellings: Approved Document Q | Q Scope | No | Q Compliance
Infrastructure for electronic communications: Approved Document R | R Scope | Yes Category B | R compliance
Infrastructure for charging electric vehicles: Approved Document S | S Scope | No | S compliance
Toilet accommodation: Approved Document T | T Scope | No | T compliance
Material and workmanship: Approved Document 7 | 7 scope | Yes Category B | 7 compliance
Other Standards where Approved Document does not apply |  | No | No works not covered within approved documents.
The Construction Control Plan will meet the requirements of the Approved Documents and related Building Regulations as described in the Building Regulations Compliance Statement
| Signature | Name | email | Phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
Manifest of documents submitted to support Building Regulations Compliance Statement
Document Name | Filename | Version | Version date | Summary of content
Drawing 1 | Client's Filename convention | A | 2025-09-15 | Detailed design drawings in PDF
Drawing 2 | Client's Filename convention other drawing | C | 2025-09-15 | Detailed design drawings in .dwg
DRA | Client's Filename convention DRA | - | 09.04.25 | DRA for CDM
Structural documents | 0 | 0 |  | 0
Document Name | Filename | Version | Version date | Summary of content
Structural Calculations | adcde | a | 2025-04-01 | Structural calculation
Other structural calculations or GDC | fghij | a | 2025-04-02 | GDC calculation
STRUCTURAL INVESTIGATION | klmno | b | 2025-04-03 | xxxx report on structural investigations including roof.
Fire Safety related documents | 0 | 0 |  | 0
Document Name | Filename | Version | Version date | Summary of content
Fire strategy plan | Fire strategy plan filename | 1 | 2024-02-22 | Existing Golden Thread Fire strategy issued by xxx
Fire compartmentation survey | SURVEY REPORT filename | 1 | 2023-06-06 | Existing compartmentation survey issued by xxxx on
Fire Risk Assessment | FRA 1 filename | 1 | 2021-02-01 | Site provider's specification for previous electrical works, including fire alarm system installation and integration
FRA- External walls | FRA - EW fiilename | 1 | 2022-09-23 | FRA EW issued by company x
Other fire safety document | Other fire-filename | 1 | 2025-06-23 | Describe
0
Rooftop waterproofing related documents
Document Name | Filename | Version | Version date | Summary of content
Existing roofing warranty | Warranty filename | 1 | 2022-01-20 | Warranty
Manufacturer's document | Filename | 1 | UNDATED | Drawing of standard detail of waterproofing requirements supplied by xxxx .
0 | 0 | 0 | 0 | 0

## CCP SUPERSEDED BY WORD
Construction Control Plan
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Duty Holders
Duty holder | Name | email | telephone number | Company
Individual Principal Designer | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number | Principal Designer Company
Individual Principal Contractor | Individual Principal Contractor Name | Individual Principal Contractor email | Individual Principal Contractor phone number | Individual Principal Contractor Company
Principal Accountable Person | PAP dutyholder name | PAP dutyholder email | PAP dutyholder phone | Site PAP company
Client | Client contact name | Client email address | Client phone number | Client company name
Objective of Construction Control Plan
The objective of this Construction Control Plan (CCP) is to plan the installation of telecommuinications infrastructure on the rooftop of Site Name to complay with The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 and HRB SCHEDULE 1, Paragraph 2, Building Regulations 2010 and the Construction (Design and Management) Regulations 2015 (CDM 2015) to safeguard workers, residents, and the surrounding environment.
The Construction Control Plan set out details of work, and the appropriate reasonable steps to control the building work and ensure it is in accordance with all applicable requirements of the building regulations. It ensures management arrangements are in place to plan, manage and monitor the works . It ensure that when built, the building does satisfy all applicable functional requirements of building regulations. It sets out the management arrangements have been made to ensure sufficient evidence of the as built is captured to support the completion certificate application and what arrangements are made for ensuring the information, instruction and training provided to those carrying out the building work is sufficient.
The Construction Control Plan set out details of work, and the appropriate reasonable steps to control the building work and ensure it is in accordance with all applicable requirements of the building regulations. It ensures management arrangements are in place to plan, manage and monitor the works . It ensure that when built, the building does satisfy all applicable functional requirements of building regulations. It sets out the management arrangements have been made to ensure sufficient evidence of the as built is captured to support the completion certificate application and what arrangements are made for ensuring the information, instruction and training provided to those carrying out the building work is sufficient.
Legal provisions
The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 and HRB SCHEDULE 1, Paragraph 2 The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 – Regulation 2 The Higher-Risk Buildings (Descriptions and Supplementary Provisions) Regulations 2023 (defines a HRB and separate sections of the building). The Building Safety Act 2022 Building Regulations 2010 (as amended). Construction (Design and Management) Regulations 2015 (CDM 2015). Work at Height Regulations 2005. Lifting Operations and Lifting Equipment Regulations 1998 (LOLER). Health and Safety at Work Act 1974.
Key Duties
In accordance with the Building Regulations 2010, the Client’s key duties during the project are:- To make suitable arrangements for planning, managing and monitoring a project. Reg 11A(1) To ensure sufficient time and resources are allocated. Reg 11A(1) To ensure that the design work is carried out so that the building work to which the design relates, if built, would be in compliance with all relevant requirements. Reg 11A(2)(a) To ensure the building work is carried out in accordance with all relevant requirements. Reg 11A(2)(b) To ensure that effective mechanisms are in place for members of the project team to communicate and cooperate with each other and coordinate their activities. Reg 11A(2)(c) & Reg 11(5) To ensure periodic review of the design and building work is included in the project so as to identify whether it is higher-risk building work. Reg 11A(2)(d) To ensure that arrangements, as listed above, are maintained and reviewed throughout the project. Reg 11A(3) To provide building information as soon as is practicable to every designer and contractor on the project. Reg 11A(4) To make suitable arrangements to periodically review the design and building work and ensure information is provided to designers and contractors working on a project which includes any higher-risk building. Reg 11B(1) and (2) To ensure that a designer with control over the design work is appointed as the principal designer. Reg 11D(1)(a) & Reg 11D(7)(a) & (b); a contractor with control over the building work is appointed as the principal contractor. Reg 11D(1)(b) & Reg 11D(6) To ensure that people and organisations whom they appoint have the necessary skills, knowlContractor Y, experience and behaviours and if an organisation the organisational capability to undertake their duties. Reg 11E, 11F, 11G, 11H |  | VMO2 plans, manages and monitors the project through the appointment of a project team. It has management tools in place, including Siteflo, which facilitate the flow of site, design and construction information between the project team. Designs are progressed through specific phases during which the relevant requirements, risks and issues related to the design are resolved until the design is ready for detailed design and design validation. VMO2 publishes its own telecommunications related design specifications and guidance, which collectively set out its requirements . These specifications reference relevant requirements were they relate. VMO2 employs or contracts its own structural engineers, electrical engineers, design auditors, and building regulations inspectors to review designs and construction plans in accordance with a strictly maintained milestone process. Design and construction activities are coordinated through a general policy to contract design and construction to the same company. Where this approach is not possible the designer and contractor hold handovers and subsequent progress meeting and a prestart meeting, attended but the designer and the contractor are held in advance of construction. Designs are reviewed to identify building work and higher-risk building work from pre-survey to detailed design. The project team is retained throughout the project to ensure continuous design review and to manage change. Siteflo and other document management systems are used to track the progress of the project, and to manage the review of document deliverables by engineers, auditors, and inspectors. VMO2 maintains archive drawings and documents accessible to the designer. Some Golden Thread information is not stored by VMO2 . Fire information in particular is managed by the site provider's Principal Accountable Person or Responsible Person. VMO2 supports access to this information through its site acquisition activities. Design and construction plans are reviewed at milestone events and at any change even through standard processes. VMO2 has appointed This_Company Limited as the principal designer. VMO2 has appointed This_Company Limited as the principal contractor/ VMO2 has assessed This_Company for its necessary organisational and individual skills, knowlContractor Y, experience and behaviours to undertake their duties. Reg 11E, 11F, 11G, 11H
The Principal Designer’s key duties are:- •To not undertake any design work, nor act as the principal designer, if they do not satisfy the requirements in Reg. 11F(1) and (2) (competence: general requirement) and 11G(1) (competence: principal designer) at the time of appointment. Reg 11E(6) & (7)(a) •To ensure that any person carrying out design work must have - • the necessary skills, knowlContractor Y, experience and behaviours Reg 11F(1)(a), 11F(2)(a), 11G(1)(a), 11G(3) • and if an organisation, the organisational capability. Reg 11F(1)(b), 11F(2)(b), 11G(1)(b) To carry out the design work so that the building to which the design relates, if built, would be in accordance with all relevant requirements. Reg 11F(1)(b)(ii) To designate an individual tasked with managing the functions of the principal designer. Reg 11G(2) To plan, manage and monitor design work so that the design is such that if built, would be in accordance with all relevant requirements. Reg 11J(4), 11M(1)(a) & (b) To communicate, cooperate and coordinate with other members of the project team. Reg 11J(2), 11K(3),(4) & (5), 11M(2)(a), (b) & (c), 11M(3)(a) & (b), 11M(4) To ensure the Client is aware of their duties and assist them in carrying out their duties. Reg 11K(1) To assist the Client in providing information to other designers and contractors. Reg 11M(5)(a) To liaise with the principal contractor. Reg 11N(4) |  | This_Company Limited has been appointed as principal designer by VMO2 as it has satisfied itself that meets the requirements of regulation 11 F (1) and (2) and 11G (1). This_Company employs and contracts persons with the necessary skills, knowlContractor Y , experience and behaviours to undertake the design as further detailed in the Building Regulations Compliance Statement and the Construction Control Plan . This_Company has appointed Michael Noel as the Individual Principal Designer for this project. This_Company has produced the design and design documents that constitute this Gateway 2 application to plan and manage the design such that if built, would be in accordance with all relevant requirements. Reg 11J(4), 11M(1)(a) & (b) This_Company is also acting as designer for some elements and is acting as Principal Contractor. As Principal Designer it communicates with other duty holders, designers and contractors, during the design phase and through construction. This_Company has made VMO2 aware of its duties as client, and assists them with their duties, which includes the dissemination of its information to designers and contractors
The Principal Contractor’s key duties are:- To not undertake any building work, nor act as the principal contractor, if they do not satisfy the requirements in Reg. 11F(1) and (2) (competence: general requirement) and 11H(1) (competence: principal contractor) at the time of appointment. Reg 11E(6) & (7)(b) To ensure that any person carrying out building work must have - • the necessary skills, knowlContractor Y, experience and behaviours Reg 11F(1)(a), 11F(2)(a), 11H(1)(a), 11H(3) • and if an organisation, the organisational capability. Reg 11F(1)(b), 11F(2)(b), 11H(1)(b) to carry out the building work in accordance with all relevant requirements. Reg 11F(1)(b)(i) To designate an individual tasked with managing the functions of the principal contractor. Reg 11H(2) To plan, manage and monitor building work so as to be in compliance with all relevant requirements. Reg 11J(1), 11N(1)(a) & (b) To communicate, cooperate and coordinate with other members of the project team. Reg 11J(3), 11L(3),(4) & (5), 11N(2)(a), (b) & (c), 11N(3)(a) & (b), 11N(4), 11N(5)(a) To ensure the Client is aware of their duties and assist them in carrying out their duties. Reg 11L(1) To assist the Client in providing information to other designers and contractors. Reg 11N(5)(a) To liaise with the principal designer. Reg 11N(4) |  | This_Company Limited has been appointed as principal contractor by VMO2 as VMO2 has satisfied itself that This_Company meets the requirements of regulation 11 F (1) and (2) and 11H (1) through its own compliance assessment. This_Company employs and contracts persons with the necessary skills, knowlContractor Y , experience and behaviours to undertake the design as further detailed in the Building Regulations Compliance Statement and the Construction Control Plan . This_Company has appointed Simon Siu as the Individual Principal Contractor for this project. This_Company will plan, manage, and monitor its building work so that it is in accordance with all relevant requirements. Reg 11J(4), 11M(1)(a) & (b) This_Company is also acting as designer for some elements and is acting as Principal Designer. As Principal Contractor r it communicates with other duty holders, designers and contractors, prior to and during the build phase. This_Company has made VMO2 aware of its duties as client, and assists them with their duties, which includes the dissemination of its information to designers and contractors
Summary of Responsibilities The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 and HRB SCHEDULE 1, Paragraph 2 (a) the strategies, policies and procedures the client has adopted for planning, managing and monitoring the HRB work, a stage of HRB work or work to existing HRB so as to ensure compliance with— (i) the applicable requirements of the building regulations and to record evidence of that compliance including describing the arrangements the client has adopted to maintain the golden thread information; (ii) the duties in Chapter 4 (duties of duty holders) of Part 2A of the 2010 Regulations; (b) The strategies, policies and procedures the client has adopted to identify, assess and keep under review the competence of the persons carrying out the HRB work, a stage of HRB work or work to existing HRB or involved in the design of the higher-risk building or design of the building work to the higher-risk building, including the procedures to be followed— (i) to determine whether a serious sanction (as defined in regulation 11E of the 2010 Regulations) has occurred in relation to a person to be appointed; (ii) to consider any past behaviour in relation to any serious sanction which might call into question the suitability of a person to be appointed; (iii) if a person in relation to which a serious sanction has occurred is appointed, to prevent a repeat of the behaviour; (c) The strategies, policies and procedures the client has adopted to support co-operation between designers, contractors and any other persons involved in the HRB work, a stage of HRB work or work to existing HRB, including the sharing of all necessary information; (d) a schedule of each appointment which has been made as at the date of the application, giving the name of— (i) the person who the client has appointed as the principal contractor (or sole contractor); (ii) the person who the client has appointed as the principal designer (or sole or lead designer); (iii) any other person (excluding individuals except where they are a sole trader) the client has appointed to work on the project; (iv) any person (excluding individuals except where they are a sole trader) the principal contractor (or sole contractor) has appointed to work on the project, and (v) any person (excluding individuals except where they are a sole trader) the principal designer (or sole or lead designer) has appointed to work on the project, and a summary of their responsibilities; (e) the policies the client has adopted to review the construction control plan.
The Principal Designer (BR) is responsible for ensuring compliance with Building Regulations and managing design-related risks and ensuring compliance with The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 regulation 31.
The Principal Contractor (PC) oversees construction safety, site management, and coordination between subcontractors and ensures compliance with The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 regulation 31.
Project Organisation and Responsibilities
| #REF! | #REF! |  |  | Revise as required
Construction Management - Strategies, Policies and Procedures
Planning , Managing and Monitoring Works
Include a detailed strategy for: ● Method Statements: Site-specific method statements for steelwork installation, lifting operations, and electrical works. ● Risk Assessments: How risks (e.g., working at height, crane operations) will be identified, managed, and mitigated. ● Programme Management: Integration of the CCP with the overall project programme and milestones. | 0 | 0
Checking the CCP remains effective
Expand on the mechanisms to ensure the CCP adapts to changes: ● Dynamic Risk Assessments: Conduct periodic assessments to address evolving risks during construction. ● Feedback Loops: Include feedback from site operatives, residents, and health and safety audits to refine the CCP. | 0 | 0
Capturing ' As Built' Evidence
● Detail the types of evidence to be captured, such as structural testing reports, photos of completed works, and inspection certificates. ● Specify who will be responsible for maintaining and submitting this evidence. | 0 | 0
Competency and Behaviour Management
● Clarify the processes for disciplinary action in case of non-compliance. ● Include methods for promoting a positive safety culture, such as reward systems for exemplary
Site-Specific Requirements
Crane access | This position and overfly of the crane will be confirmed at Gateway 3.
Rooftop works, including pedestal construction, steelwork assembly, and testing. | Detailed in later pages
Core-drilling penetrations for the routing of submain and fibre cables from the ground floor to the exterior | Detailed in later pages
Misconduct and Sanctions Check
Use the box below to note any events of misconduct or sanctions - see also Company Handbooks 014 Subcontractor Management
Link to 014 Subcontractor Management | Answer | Name and company
Have any of the named individuals in this construction control plan been subject to any sanction or non-conformance investigation? | No
Have any of the Contractors or Companies identified in this construction control plan been subject to any sanction or non-conformance investigation? | No
The Construction Control Plan will meet the requirements of the Approved Documents and related Building Regulations as described in the Building Regulations Compliance Statement
| Signature | Name | email | Phone number
Signature of Individual Principal Contractor | #VALUE! | 0 | 0 | 0
Signature of Individual Principal Designer | #VALUE! | Michael Noel on behalf of This_Company Limited | michael.noel@circet.co.uk | 07376739642

## Construction Control Plan
Construction Control Plan Part 2 (Appendix A) |  |  |  |  | Back to RACI
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Duty Holders
Duty holder | Name | email | telephone number | Company
Individual Principal Designer | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number | Principal Designer Company
Individual Principal Contractor | Individual Principal Contractor Name | Individual Principal Contractor email | Individual Principal Contractor phone number | Individual Principal Contractor Company
Principal Accountable Person | PAP dutyholder name | PAP dutyholder email | PAP dutyholder phone | Site PAP company
Client | Client contact name | Client email address | Client phone number | Client company name
Notes on this plan
This section of the Construction Control Plan describes the works to be undetaken to ensure that the design work, when built, will be in accordance with all relevant requirements of the listed approved documents. Category A building works have been described as they relate to each approved document. Contractors are identified and their competencies to complete the applicable works are described. The tests, photographs, certificates, and inspections required to be recorded as evidence that the building works have been completed to meet the relevant requirements of the Building Regulations are listed under each approved document seciton.
Commencement date and nominal project plan
Provide the date when it is proposed the work will reach the point when it is to be regarded as commenced in accordance with regulation 46A (lapse of building control approval: commencement of work) of the 2010 Regulations: |  |  | 2026-04-06 | INPUT This date is dependent on client approvals.
Provide the date when it is proposed that the Building Work is considered by the client to be 15% complete. |  |  | 2026-04-09
Provide details of the work which the client considers amounts to 15% of the proposed work | INPUT . EXAMPLE By day three of the mobilisation the tripod and grillage upstands will have been installed and re-dressed. The core drills through the risers will have been completed and the Roxtec glands installed . Electrical switchgear will have been mounted but not commissioned. Tripod and grillage steel members will be in the process of assembly on the roof for mounting on the upstands. See also the construction phase plan (CDM) , appendix B of the Construction Control Plan
Structure: Approved Document A
Describe any applicable elements of the scope.
INPUT SCOPE ELEMENTS INTO 'APPROVED DOCUMENT A' NOTE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT A | 0 | 0
Main Contractor(s) to undertake structural works
Contractor Name | Person in Charge of Works | Person in Charge of Works email and mobile number | Competencies and Accreditations
Contractor 1 company name | Contractor 1 Name | Contractor 1 email Contractor 1 phone number | 20 plus years experience. ; Alcumus Safe Contractor Certificate - 18092024
CONSTRUCTION CONTROL PLAN - Contractor Competencies
Work element | Applicable standard(s) | Contractor to complete this element (Name) | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
Fabrication of Pedestals | BS EN 1090-2 exec 2 | Supplier 1 company | Fill as required
Fabrication of General steelwork (tripod and grillage assemblies | BS EN 1090-2 exec 2 | Supplier 1 company | Fill as required
Pedestal installation | 0 | Contractor 1 company name | Fill as required
Tripod and grillage assembly | 0 | Contractor 1 company name | Fill as required
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
Supplier 1 company | SO9001:2015 ; BS EN 1090 Execution Class 2 of steel structures and aluminium structures. | Supplier 1 Name | See https://www.shearfab.co.uk/quality/ ; Shearfab ISOQAR UK BSEN 1090 certificate of conformity FPCShearfab ISOQAR ISO 9001 2015 certificate of registration | 35 years
Contractor X Limited | 0 | Contractor 1 Name | Alcumus Safe Contractor Certificate - 18092024 | 20 years
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents)
Pedestal fabrication | BS10025 S355 steel and 8.8 fixings | SO9001:2015 ; BS EN 1090 Execution Class 2 of steel structures and aluminium structures. | Shearfab ISOQAR UK BSEN 1090 certificate of conformity FPC
All other steel | BS10025 S275 steel and 8.8 fixings | SO9001:2015 ; BS EN 1090 Execution Class 2 of steel structures and aluminium structures. | Shearfab ISOQAR UK BSEN 1090 certificate of conformity FPC
All galvanising | All steel galvanised | EN ISO 1461 | 0
0
INPUTS FOR CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | Inspection (When, Responsibility )
Tripod pedestal and cabinet pedestal pre-construction | Photos of rooftop opening for all pedestal locations to present slab surface prior to drilling. | Photos at each pedestal location taken from 5 m (for context) and 1 m (to show slab condition |  | During pedestal installation ; Contractor X
Anchor installation | Proof of depth of anchor drills - provide evidence that rebar embedments are 110 mm depth into the existing slab. | Photos at each pedestal location from 1 m to show evidence of anchor depth to 110 mm. (2 photos per plinth location). |  | During anchor embedment construction ; Contractor X
Anchor installation - pull out tests |  | 10 kN Pull out tests in accordance with BS 8539:2012+A1:2021 Code of practice for the selection and installation of post-installed anchors in concrete and masonry; Test one quarter of all anchors at each tripod and grillage location |  | Post anchor cure ; Contractor X
Pedestal installation | Photos of pedestal installation | Take before and after photos of pedestal installations, demonstrating level with a spirit level. | As built photos | Prior to tripod and grillage installations., Contractor X PICW and Contractor
Pedestal installation | Photos of pedestal installation | Take photos to demonstrate the setting out, using guide steelwork to show positioning of pedestals relative to roof edge and to eachother. | As built photos | Prior to tripod and grillage installations., Contractor X PICW and Contractor
INPUTS for CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
As built drawings | Set of redline drawings based on 601 to 612 capturing any deviation from position, design and construction of pedestals.
Steel certificates of conformity from supplier. | Certificates from fabricator with accreditations and competencies (steel grade, galvanising)
General Statement of Contractor Competencies |  |  | Describe how the contractors are competent for their duties , referencing their skills, experience and behaviours
Contractor X is a civil engineering contractor with over 20 years of experience in the telecoms sector. They specialise in delivering high-quality infrastructure solutions, including concrete plinths, steelwork, fire stopping, handrails, and roofing. Their civil construction teams are competent through on-site training and experience . Contractor X Limited is listed in Circet's approved contractor list. They are also on the MBNL (telecom tower company) approved contractor list (MBNL H&S Bulletin Issue 019 August 2024) published by Turner and Townsend
INSPECTION REQUIREMENTS - Additional comments |  |  | Principal Contractor to fill | 0
INPUT SCOPE ELEMENTS INTO 'APPROVED DOCUMENT A' NOTE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT A
Fire safety: Approved Document B
Describe any applicable elements of the scope.
USE APPROVED DOCUMENT B SCOPE FIELD TO INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT B , CONSIDERING ALL SECTIONS BE1 TO B5
General statement of compliance to Approved Document
USE APPROVED DOCUMENT B GENERAL STATEMENT OF COMPLIANCE FIELD TO WRITE A GENERAL STATEMENT OF COMPLIANCE, REFERENCING THE SCOPE ELEMENTS AND THE EXISTING SAFETY CASE.
CONSTRUCTION CONTROL PLAN - Contractor Competencies
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
0 | 0 | 0 | Use the cell below to describe the competencies of the company to undertake the work.
Fire stopping | BS EN1366-3 & EN13501-2:2016 | Contractor 1 company name | bmtrada Q-mark ; UKAS Product Certification 0142
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  | 0 | 0 | 0
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
Contractor 1 company name | bmtrada Certificate of Registration Certificate Number 3626 for Group A and Group B fire stopping filename Contractor X Installations Ltd Hickman 3626 05b FINAL 061124 | Contractor 1 Name | - | 20+
CONSTRUCTION CONTROL PLAN -Material compliance |  | 0 | 0 | 0
Work element | Materials used in this work (add lines) | Applicable standards | Datasheet or certificate filename ( (Supply copy in Construction Control Supporting Documents) | Notes
Fire stopping of sub-main route |  | BS EN1366-3 & EN13501-2
Fire stopping of fibre route |  | BS EN1366-3 & EN13501-2 |  | No fibre plan under current scope
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during and after construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | 0
Fire stopping of sub-main route | none | Photos of fire stopping at each surface , 5m photos to be taken so that the identity of the location is clear; 1m photos to show workmanship | Photos of decals at each surface , showing context to show location
Fire stopping of fibre route | none | Photos of fire stopping at each surface , 5m photos to be taken so that the identity of the location is clear; 1m photos to show workmanship | Photos of decals at each surface , showing context to show location | Note assumes fibre to be installed under this scope of works. Virgin Media may install fibre under separate scope of works (under separate Gateway 2 application)
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | 0 | 0
Fire stopping of sub-main route | As built drawing to capture position and type of each fire stop
Fire stopping of fibre route | As built drawing to capture position and type of each fire stop
Site preparation and resistance to contaminates and moisture: Approved Document C | 0 | 0 | 0 | go back
Describe any applicable elements of the scope. |  | 0 | 0
INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD
Contractors to undertake Roofing works
Contractor Name | Person in Charge of Works | Person in Charge of Works email and mobile number | Competencies and Accreditations
Subcontractor 2 Company name | Subcontractor 2 Name | Subcontractor 2 email Subcontractor 2 Phone Number | NFRC, Construction Line, Approved Langley Waterproofing System installer.
General Statement of Contractor Competencies |  |  | Principal Contractor | Principal Contractor to fill
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
|  |  | Use the cell below to describe the competencies of the company to undertake the work. | 0
Cutting open roof material | BS 6229:2018 | Subcontractor 2 Company name | Approved Langley contractor. The site provider requires the appointment of Contractor Z Roofing. NFRC, CHAS, Construction Line Gold Member
Pedestal dressing | BS 6229:2018 | Subcontractor 2 Company name | Approved Langley contractor. The site provider requires the appointment of Contractor Z Roofing. NFRC, CHAS, Construction Line Gold Member
CONSTRUCTION CONTROL PLAN -Pre-construction evidence of material compliance | 0
Work element | Materials used in this work (add lines) | Certificate of datasheet or material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Applicable standards | Blank
Redressing of plinths | The pedestals will be dressed using Langley approved materials. | To be supplied at Gateway 3 | BS 6229:2018
CONSTRUCTION CONTROL PLAN - Evidence of workmanship to be taken during construction
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | Inspection (When, Responsibility, Deliverables)
Cutting open | 10 photos taken at each rooftop opening location to present : 1) 5m context shot of location 2) 1 m distant shots of rooftop opening, presenting layers exposed |  |  | During works; Contractor, Photo report
Pedestal installation |  | 10 1 m photos taken at each installation to show pedestal redressing, including overlaps. Use measuring stick to photo overlap distances , Show depth and quality of chamfering at base of plinth . Show sufficient overlap of felt and waterproof layers under cowl. | Letter of re-warranty from roofing manufacturer; letter of completion by Rooftopworker competent person. | During works; Contractor & PICW, Photo report
CONSTRUCTION CONTROL PLAN - As Built requirements | 0 | 0 | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
As built | Redline any deviations for detailed design |  | None | N/a
Warranty letter from roofing contractor. |  |  | None | N/a
Certificates of Material Conformity. | Data sheets of materials used in the roofing works |  | None | N/a
INSPECTION REQUIREMENTS
Scope |  | Principal Contractor Notes following inspection
INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD
Electrical safety: Approved Document P |  |  |  | go back
Describe any applicable elements of the scope.
Installation and commissioning of electrical equipment in the cabin, installation and commissioning of low power DC supplied equipment on the equipment grillages.
INPUTS TO CONSTRUCTION CONTROL PLAN - Contractor Competencies | 0
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work (Use the cell below to describe the competencies of the company to undertake the work) | 0
Installation of switchgear and associated cabling | BS7671 Requirements for Electrical Installations [2008+ A1:2011 [IET Wiring Regulations 18th Edition | Contractor Y Electrical Solutions | NICEIC Competent Person Scheme
CONSTRUCTION CONTROL PLAN - Contractor appointments. | 0
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
Electrical Contractor Company Name | NICEIC | Electrical Contractor Name | NICEIC Competent Person Scheme and telecoms specific | >10
CONSTRUCTION CONTROL PLAN -Material compliance | 0
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Notes on fire ratings.
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction | 0 | 0 | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | 0
CONSTRUCTION CONTROL PLAN - As Built requirements | 0 |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)
Electrical schematic | Updated electrical schematic presenting works in accordance with the detailed design and any variation from the detailed design in redline. |  | None
Electrical calculations | Updated electrical calculations |  | None
Material and workmanship: Approved Document 7
Describe any applicable elements of the scope.
7 scope | 0 | 0 | 0 | 0
Use the box below to note measures taken to ensure compliance to material and workmanship standards listed in Approved Document 7 Applicable Standards
Misconduct and Sanctions Check
Use the box below to note any events of misconduct or sanctions - see also Company Handbooks 014 Subcontractor Management
Link to 014 Subcontractor Management
Have any of the named individuals in this construction control plan been subject to any sanction or non-conformance investigation? | No | Name and company
Have any of the Contractors or Companies identified in this construction control plan been subject to any sanction or non-conformance investigation? | No | Name and company
Forecast Safety Case at the end of the construction works
input the forecast changes to the existing safety case at the end of the building works.
The existing safety case will be largely unchanged. The installation of the two grillages and three tripods will have increased roof loading . The structural calculations demonstrate the adequacy of the steelwork construction, the rooftop interface or connection, and the primary load bearing elements of the roof to withstand the proposed static and dynamic loads of the telecommunications equipment to be installed. Pull out tests will have been completed on the Hilti fixed anchors holding down the pedestals. New penetrations requred to route the proposed submain cable and an associated earth from the switch room to the rooftop mounted VMO2 cabinet grillage will be fire-stopped using Roxtec transits and Quel-fire firestopping. The firestopping will be fitted with decals to indentify who installed the firestopping, and on what date. The existing residential fire strategy of stay put will not be affected by the installation. Rooftop evacuation in the eventof fire during the building works will by managed in accordance with the works related. risk assessment and method statement. The building works will not affect evacuation through the building. The Langley waterproofing system will be penetrated by 17 pedestals to support the cabinet grillages and antenna tripods. The pedestal waterproofing, designed in collaboration with Langley Limited and Contractor Z roofing, will have been completed to the satisfaction of Langley Limited, and a letter of rewarranty published by Langley Limited. Evidence that the building works have been completed in accordance with the relevant requirements of each applicable approved document will have been recorded via the Golden Thread Arrangements proforma supplied.
The Construction Control Plan will meet the requirements of the Approved Documents and related Building Regulations as described in the Building Regulations Compliance Statement
| Signature | Name | email | Phone number
Signature of Individual Principal Contractor |  | Organisational Principal Contractor Name | Organisational Principal Contractor email | OPC phone number
Signature of Organistional Principal Contractor |  | Individual Principal Contractor Name | Individual Principal Contractor email | Individual Principal Contractor phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
Manifest of additional documents submitted to support Construction Control Plan
Drawings
Document Name | Filename | Version | Version date | Summary of content
Cornerstone Unwind Construction drawings | E365323_CTIL_30322100_VMO2_88942_VF_28842_DD_REV_C | C | 2025-09-15 | Detailed design drawings in PDF
Cornerstone Unwind Construction drawings | E365323_CTIL_30322100_VMO2_88942_VF_28842_DD_REV_C | C | 2025-09-15 | Detailed design drawings in .dwg
Design Risk Assessment | E365323_CTIL_30322100_VMO2_88942_VF_28842_DRA | - | 09.04.25 | DRA for CDM
Structural documents
Document Name | Filename | Version | Version date | Summary of content
Structural Calculations | adcde | a | 2025-04-01 | Structural calculation
Other structural calculations or GDC | fghij | a | 2025-04-02 | GDC calculation
STRUCTURAL INVESTIGATION | klmno | b | 2025-04-03 | xxxx report on structural investigations including roof.
Fire Safety related documents
Document Name | Filename | Version | Version date | Summary of content
Fire strategy plan | 9117191605~21-04-2023#Site Name L25 7UZ Fire strategy plan | - | 2024-02-22 | Existing Golden Thread Fire strategy
Fire compartmentation survey | 1-79 Site Name L25 7UZ SURVEY REPORT | 1 | 2023-06-06 | Existing Golden Thread
Electrical Services Technical Specification, including fire alarm system | 5495-KGA-00-XX-SP-E-0001 - Electrical Specification | 1 | 2021-02-01 | Site provider's specification for previous electrical works, including fire alarm system installation and integration
Fire Risk Assessment | 9117191605~23-09-2022 FRA | 1 | 2022-09-23 | Savills Limited FRA. The document expiry was 23/09/2023 but document referenced for general information.
Fire stopping detail | Roxtec R100 with modules (zip file) | 1 | 2025-06-23 | Proposed cable transit used for submain, earthing and Openreach/ Virgin media fibre routing . Consolidated transit gland to avoid further cable routing by others.
Rooftop waterproofing related documents
Document Name | Filename | Version | Version date | Summary of content
Drawing L42669 | Site Name Tower CTF Drawing | 1 | 2022-01-20 | Drawing of Langley Parafoam Ultra F foam insulation system. This drawing is included in the detailed design.
506-HANDRAIL/SAFETY BARRIER OR SIMILAR | RBM-W-506-V11112024 | 1 | UNDATED | Drawing of standard detail of waterproofing requirements supplied by Langley. This detail has been applied to the rooftop pedestal design.
509-SVP WITH WEATHERING COLLAR | RBM-W-509-V03122019-PIPE WITH WEATHERING COLLAR | 1 | UNDATED | Drawing of standard detail of waterproofing requirements supplied by Langley. This detail has been applied to the rooftop pedestal design.

## Change Control SUPERSEDED
Change Control Plan
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Duty Holders
Duty holder | Name | email | telephone number | Company
Individual Principal Designer | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number | Principal Designer Company
Individual Principal Contractor | Individual Principal Contractor Name | Individual Principal Contractor email | Individual Principal Contractor phone number | Individual Principal Contractor Company
Principal Accountable Person | PAP dutyholder name | PAP dutyholder email | PAP dutyholder phone | Site PAP company
Client | Client contact name | Client email address | Client phone number | Client company name
Objective of Change Control Plan
Schedule 1, The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023, states the requirements for a Change Control Plan are:
3 (1) A change control plan must set out the strategies, policies and procedures the client has adopted to ensure any controlled change takes place in accordance with regulation 18 (change control), and to log each controlled change in accordance with regulation 19 (change control: record-keeping) including explaining - (a) How proposed changes will be identified and to whom they must be reported; (b) How the impacts of proposed changes are identified and considered; (c) In relation to proposed changes, the decision-making procedures adopted for agreeing a change including whose advice is to be sought; (d) How changes are recorded and by when; (e) The procedure to identify which changes require notification to the regulator and which changes require a change control application; (f) How the effectiveness of the change control plan will be reviewed by dutyholders periodically.
The Change Control Plan sets out how This_Company will manage the change control process in engagement with other duty-holders, contractors and designers. It sets out how changes will be assessed for their impact, how they will be recorded, and how the Building Safety Regulator will be notified of the changes which affect building works.")
Legal provisions
The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 regulation 26 The Higher-Risk Buildings (Descriptions and Supplementary Provisions) Regulations 2023 The Building Safety Act 2022 Building Regulations 2010 (as amended). regulations 18 (5) , 19(1), schedule1 paragraph 3, regulation 26 Construction (Design and Management) Regulations 2015 (CDM 2015).
Change Control Plan
The Dutyholders must analyse the effect of change on the original Gateway 2 and Gateway 3 approval applications before the changes are implemented. Changes that affect the building works must be recorded by a change control form, and by revisions to documents and drawings which will collectively show the change for approval. Such accepted changes will subsequently be presented in the as built drawings and documents for inclusion in the 'Golden Thread', alongside a change log record.
Reg.18(1) controlled changes can be any one of the following: (a) a change to any current plans of any work or proposed work or the carrying out of work otherwise than in accordance with the current plans; (b) a change to any stage of HRB work, including adding or removing a stage; (c) a change to any strategies, policies or procedures described in any current agreed document. There are three district categories of “Controlled Change”
a) Major change A major change undermines the basis by which building control approval was granted and an application MUST be made to the Building Safety Regulator BEFORE it can be commenced | A major change undermines the basis by which building control approval was granted and means an application must be made to the Building Safety Regulator before it can be commenced . • a change which is a material change of use to any part of a proposed higher-risk building; • a change to the number of storeys in a proposed higher-risk building (including adding or removing a mezzanine or gallery floor) • a change to the structural design or structural loading of the building • a change to the number or width of the staircases or a change to the length of any other escape route or the number or width of any escape route (including evacuation lift) within the proposed building; • a change to the external wall of a proposed higher-risk building including a wall tie, wall restraint fixing or support system in the wall; • a change to any part of the active fire safety measures or passive fire safety measures referred to in the fire and emergency file; • a change to the layout or dimensions of the common parts of the building. • change of any construction product or building element to be used, such that its replacement is of a lower classification under the reaction to fire classification • (within the meaning in regulation 2(6) of the 2010 Regulations(2)); • a change to any assumptions made in the design as set out in the Building Regulations compliance statement; • a change which would propose early occupation of any part of the proposed higher-risk building before all the work is completed.
b) Notifiable change one that potentially has an impact on compliance. The Building Safety Regulator must be notified. | A notifiable change potentially has an impact on compliance. The Building Safety Regulator must be notified. A notifiable change can be started once the Building Safety Regulator has been notified. A Notifiable change within the scope of this specific project could include: • a change to the construction control plan; • a change to the change control plan; • a change to the layout of a room; • a change to the number or dimensions of any openings in any wall, ceiling or other building element for any pipe, duct or cable; • a change to the wall tie, wall restraint fixing or support system in any wall or proposed wall (excluding an external wall); • a change of any construction product or building element to be used in or on a proposed higher-risk building (or to be used as part of works) where its replacement • is of the same or higher classification under the reaction to fire classification (within the meaning in regulation 2(6) of the 2010 Regulations); • any other change to the fire and emergency file or the fire safety compliance information; • a change specified by the regulator as a notifiable change by notice given in accordance with regulation 25 (change control: regulator power to specify notifiable • changes and major changes); • a change to the partial completion strategy or a change to a staged work statement or a subsequent stages statement (as defined in regulation 4(3)
C) Recordable change | A change that has no effect on the Building Regulation Application or impact on compliance.
Change Control Process
All site changes, deviations from those specified in the detailed design must be reported to the PICW to log within the Circet IMS-FRM-240B Project Change Control form. (A Blank Copy is inserted into Appendix A) All change requests MUST be logged and approved before the change is carried out. The flow chart below presents the change management flow required for building regulations management. All contractors and personnel working on site will be inducted and this process detailed to all to ensure compliance.
Change Control Application
Where the controlled change is a major change, the client must make an application for building control approval in respect of the change (a “change control application”) to the Building Safety Regulator in accordance with Reg.21 (change control applications). A major change must not be carried out, and the work to which it relates must not start, until the change control application is granted; a record is made of the controlled change in the Change Control Log; and a revised version of any agreed document(s) affected by the change is produced. Requirements: • A major change application must be in writing, signed by the client, and must include - (a) the name, address, telephone number and (if available) email address of the client , (b) the name, address, telephone number and (if available) email address of the principal contractor (or sole contractor) and the principal designer (or sole or lead designer), (c) a statement that the application is made under this regulation, and (d) a description of the proposed controlled change. • The application must be accompanied by - (a) an explanation of the reasons why the change has been proposed, (b) a list of the name and occupation of each person, if any, whose advice was sought in relation to the proposed change and a summary of any advice provided, (c) where the change is to the number of flats or residential rooms, plans showing the number of flats or residential rooms it is proposed the higher-risk building will contain, (d) an assessment of the agreed documents affected by the proposed change, (e) a compliance explanation in relation to the proposed change, and (f) where the application is made by someone on behalf of the client, a statement signed by the client confirming they agree to the application being made and that the information contained in the application is correct, b) and the application must be accompanied by the revised version of the agreed document(s). For information, the Building Safety Regulator must determine a valid major change application within 6 weeks beginning with the date the application is received or within such longer period as at any time the regulator and the applicant agrees in writing.
Notifiable Change
Where the controlled change is a notifiable change, the client must notify the regulator in accordance with Reg.20 (change control: notification requirements). A notifiable change must not be carried out, and the work to which it relates must not start, until the notification to the Building Safety Regulator has occurred; a record is made of the controlled change in the Change Control Log; and a revised version of any agreed document(s) affected by the change is produced. Requirements: A notifiable change must be in writing, signed by the client, and must include - a) a description of the proposed controlled change, b) an explanation of the reasons why the change has been proposed, c) a list of the name and occupation of each person, if any, whose advice was sought in relation to the proposed change and a summary of any advice provided, d) an assessment of the agreed documents affected by the proposed change, e) a compliance explanation in relation to the proposed change, and f) where the notification is made by someone on behalf of the client, a statement signed by the client confirming they agree to the notification being given and that the information contained in the application is correct, and the notice must be accompanied by the revised version of the agreed document(s) The Building Safety Regulator may, by notice in writing, require the person giving the notification to provide further information in relation to the proposed controlled change. This is to be provided within 10 working days of receipt of the notice.
Recordable Change
Recordable changes do not require notification / application to the Building Safety Regulator, but must be recorded on the Change Control Log as detailed below.

## Project Change Control Form 2
Project Change Control Form
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
1 | Project Details
Project Title: |  | Site Name
Client |  | Client company name
2 | Instruction
All site changes, deviations from those specified in the detailed design must be reported to the PICW to log within this Project Change Control form. All change requests MUST be logged and approved before the change is carried out. All sub contractors and personnel working on site will be inducted and this process detailed to all to ensure compliance.
Section 3 is completed by the Person in Charge of Works. The PICW is to issue the form to the Principal Contractor and Principal Designer by email. The client in communication with the dutyholders complete the evaluation
On completion of the evaluation by the Dutyholders this file is either submitted to the BSR under the change control application process, or submitted to the BSR under the notification process or recorded as a recordable change in the Sitelive project folders (05. Handover Pack Site Acceptance / 05. Golden Thread). The Change is logged in the Sitelive site area / change folder.
3 | Change Request
Originator Name (Person in Charge of Works): |  |  | Date of Request:
Contact Information: |  |  | Change ID:
Items to be changed:
Items to be changed:
Change Type as assessed by the PICW |  | Select | This is the assessment from the PICW. It is NOT the assessment of the Client and Dutyholders
Major / Notifiable/ Recordable)
Instruction (auotpopulated)
Completed by the Person In Charge of Works |  | By completing the below, you confirm that the information in this form is (to the best of your knowlContractor Y) true and accurate.
Full Name: |  |  | Position:
Signature: |  |  | Date:
This form is to be sent to the Dutyholders by the Person In Charge of Works by email
4 | Change Evaluation by The Client and dutyholders |  | CROSS REFERENCE TO MANDATORY OCCURRENCE REPORTING
What design elements are impacted by this change ?
How does the change affect Building Regulations Compliance? Is the alteration material to a relevant reequipment , resulting in the building, service or fitting becoming non-compliant or less compliant?
If the change affects compliance, is the change MAJOR as defined to the change control plan? |  | TRUE | Complete sections 5 to 8
If the change affects compliance, is the change NOTIFIABLE as defined to the change control plan? |  | TRUE | Complete Sections 6 to 8.
5 | Major Change Application |  | Complete this section if the change is 'Major'
Main Duty holders | Name | Address | Telephone number | email address
Client | Client contact name Client company name | Client company address | Client phone number | Client email address
Principal Contractor | Individual Principal Contractor Name Individual Principal Contractor Company | Individual Principal Contractor address | Individual Principal Contractor phone number | Individual Principal Contractor email
Principal Designer | Individual Principal Designer Name Principal Designer Company | Principal Designer address | Individual Principal Designer telephone number | Individual Principal Designer email
This application is made under the terms of The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023
6 | Details of change (whether major or notifiable) |  | Complete this section whether the change is major or notifiable
What design elements are impacted by this change ?
List the relevant requirements that have been affected by this change, adding lines as required.
Referencing the relevant requirements, how does the change affect Building Regulations Compliance? Is the alteration material to a relevant reequipment , resulting in the building, service or fitting becoming non-compliant or less compliant?
Additional Comments
Who was consulted in relation to this proposed change?
Role | Name | Company | email address | Summary of advice provided
Has the change affected the number of flats, residential units? If so provided plans to show this change. |  |  | Drawing / document reference.
List the documents affected by the change , and state the changes made.
Document Name | Filename | Version | Summary of change to content
Explain how the change complies to the relevant requirement
If the change is not notifiable or major it is still recordable. Make a record of the change in the change log.
7 | Client Signature and Submission
Completed by the Client |  | By signing below, you confirm that the Change Application has been reviewed for submission to the Building Safety Regulator By signing below the Client agrees to communicate this change to the Building Safety Regulator in accordance with the evaluation
Full Name: |  |  | Position:
Signature: |  |  | Date:
7.1 | Submission on behalf of the Client
Completed by the Client |  | By signing below, you confirm that the Change Application has been reviewed and the Principal Contractor has been authorised to submit the Change Application to the Building Safety Regulator
Full Name: |  |  | Position:
Signature: |  |  | Date:
Completed by the Principal Contractor |  | By signing below, you confirm that you are submitting the application on behalf of the Client By signing below the Principal Contractor agrees to communicate this change to the Building Safety Regulator in accordance with the evaluation
Full Name: |  |  | Position:
Signature: |  |  | Date:
8 | Change Log (CUMULATIVE) | This form is part of a Building Regulations Compliance workflow system which records change | Each change to be saved as a pdf in the Sitelive project folder (05. Handover Pack Site Acceptance / 05. Golden Thread). The live version of this document is saved in Building Regulations Compliance Workflow Tool
PDF filename of THIS change | Major, Notifiable, Recordable | Date | Evaluation Date | Approval Date
Yes
Yes

## MORP SUPERSEDED
Mandatory Occurrence Reporting System
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Reference Document | Reference | Version | Created by
Adverse Events Policy | IMS-POL-032 | 2 | Scott Millington
Adverse Events Procedure | IMS-PRO-032 | 3 | Scott Millington
Uses and Definitions
The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 have brought in duties for the principal dutyholders of projects in relation to higher-risk building work, a stage of higher-risk building work or work to an existing higher-risk building. This requires the Client to take all reasonable steps to satisfy themselves that a suitable mandatory occurrence reporting system is in place prior to the construction phase and to ensure it is maintained throughout the construction phase. Reg. 32 and 33.
The works to this project relate to a higher-risk building and therefore the above applies.
Regulations 32 and 33 of The Building (Higher-Risk Buildings Procedures) (England) Regulations 2023 read as follows
32 | (1) The principal dutyholders must -
(a) | before the construction phase begins, establish a system which enables as far as is reasonably practicable the prompt reporting of every safety occurrence to the principal dutyholders by reporting persons, and
(b) | maintain the system throughout the construction phase.
(2) the principal dutyholders must take reasonable steps to ensure each reporting person is provided with adequate instruction and information on the system established by virtue of Reg.32(1) and the incidents or situations that should be reported by the reporting person through the system -
(a) | in the case of a designer or contractor, before beginning any work;
(b) | in the case of any other person, as soon as reasonably practicable after first entering the site of the work.
(3) The principal contractor (or sole contractor) must ensure an appropriate frequency of inspections of the work for safety occurrences throughout the construction phase.
(4) The principal designer (or sole or lead designer) must ensure an appropriate frequency of inspections of HRB design work for safety occurrences throughout the construction phase.
(5) The requirements of this regulation do not apply to work to existing HRB which consists only of -
(a) | exempt work, or
(b) | work to which regulation 10 (notification of emergency repairs to existing HRB) applies.
Mandatory occurrence reporting: reporting to the regulator
33 | (1) Where there is a safety occurrence during the construction phase, a principal dutyholder must follow the reporting procedure on becoming aware of the occurrence.
(2) For the purposes of this regulation, “the reporting procedure” means -
(a) | notifying the regulator of the safety occurrence by the quickest practicable means without undue delay, and
(b) | providing a written report of the occurrence containing the required information (as set out in paragraph (3)) to the regulator within the period of 10 days beginning with the date the principal dutyholder becomes aware of the safety occurrence.
(3) The required information referred to in paragraph (2) is -
(a) | the date and time of the safety occurrence;
(b) | the address of the site at which the occurrence happened;
(c) | the name, address, telephone number and (if available) an email address of the principal dutyholder making the report;
(d) | the type and details of the occurrence (including the nature of the risk);
(e) | details of remedial measures or mitigation carried out.
(4) Information provided by a person under the reporting procedure is not admissible in evidence against that person in criminal proceedings except -
(a) | in proceedings for an offence under section 35 of the 1984 Act (offence of contravening building regulations etc) relating to breach of the duty in paragraph (1),
(b) | in proceedings for an offence under section 24 of the 2022 Act (provision of false or misleading information to regulator),
(c) | in proceedings for an offence of perverting the course of justice, or
(d) | if in the proceedings -
(i) in giving evidence the person makes a statement inconsistent with the information, and
(ii) evidence as to the information that was provided is adduced, or a question relating to it is asked, by or on behalf of the person.
(5) The requirements of this regulation do not apply to work to existing HRB which consists only of -
(a) | exempt work, or
(b) | work to which regulation 10 (notification of emergency repairs to existing HRB) applies.
1. Definitions
In the above regulations -
1984 Act means The Building Act 1984
2022 Act means The Building Safety Act 2022
“HRB or higher-risk building” means a building at least 18m in height or has at least 7 storeys and being of a description specified in regulations made by the Secretary of State;
“construction phase” means the period of time beginning when the HRB work, a stage of HRB work or work to existing HRB starts and ending when the work is completed;
“HRB design work” means design of any HRB work, stage of HRB work or work to existing HRB;
“principal dutyholders” means the principal contractor (or sole contractor) and the principal designer (or sole or lead designer); as defined in PART 2A Dutyholders and competence, The Building Regulations 2010; These are detailed below.
“reporting person” means -
(a) | any designer (including the principal designer),
(b) | any contractor (including the principal contractor), and
(c) | any other person who is a periodic visitor on the site of work;
“safety occurrence” means—
(a) | in relation to a design, an aspect of the design relating to the structural integrity or fire safety of a higher-risk building that would, if built, meet the risk condition;
(b) | otherwise, an incident or situation relating to the structural integrity or fire safety of a higher-risk building that meets the risk condition.
(2) In the definition of “safety occurrence”, the “risk condition” is that use of the building in question without the incident or situation being remedied would be likely to present a risk of a significant number of deaths, or serious injury to a significant number of people.
What is a Building Safety Occurrence?
A building safety occurrence is an incident involving, or risk that could cause:
· structural failure, which poses a risk to people in and around the building;
· the spread of fire or smoke, which poses a risk to people in and around the building
If the incident or risk could cause either of these a mandatory occurrence report must be issued to the Building Safety Regulator. The Mandatory Occurrence Form links the user to the Evotix reporting system which outputs reports to the duty holders and to the health and safety team.
What must be reported to the Building Safety Regulator ?
Mandatory occurrence reports only relate to the building in construction or to the building undergoing building work. They do not relate to the construction site in general or any temporary structures.
A mandatory occurrence report must be submitted for all building safety occurrences that resulted in, or are likely to result in:
· the death of a significant number of people
· serious injury that needs immediate treatment in hospital for a significant number of people
· a permanent or irreversible disabling condition to a significant number of people
Mandatory occurrences must always be reported, even if the cause of the incident or risk is immediately fixed.
For these works, the Principal Contractor has a duty to make a mandatory occurrence report. It is noted that where the relevant dutyholder has a duty to make a mandatory occurrence report and knowingly fails to make a report, the relevant designated individual can be subject to enforcement action including prosecution.
Examples of building safety occurrences that could meet the criteria of what must be reported to Building Safety Regulator, include:
· defective building work, including defective competent person scheme work that has been done as part of the wider building work
· fire safety issues likely to result in the spread of fire
· the use of non-compliant products or incompatible compliant products in the construction of the building
· inappropriate or incorrect installation of construction products
· product failure against specification and claimed performance
The relevant Dutyholder will report faults discovered in the design if these resulted in or are likely to result in the above reporting criteria.
Mandatory Occurrence Form
The Mandatory Occurrence Form is an link enabled Excel form that a reporting person uses to initiate Evotix incident processes on-line. These online system enables the prompt reporting of every safety occurrence to the Principal Duty Holders and the Circet HSEQT team. The instructions are provided in the form and are further provided through the online process.
Mandatory Occurrence Notice
The relevant Dutyholder will submit a notice as soon as possible when an incident occurs, or if they have discovered a risk that meets the criteria of what must be reported to the Building Safety Regulator.
The notice will contain the following, as noted on the template in Mandatory Occurrence Form
· Designated individual’s name and contact details
· the building control application reference, or the building’s registration number
· if the building is occupied, complete but not occupied, or under construction
· the site or building address
· a brief description of the risk or incident
· the date and time the risk or incident happened or was identified
The relevant Dutyholder will also note if action has already been taken or if they have a plan in place to keep people safe.
Mandatory Occurrence Report
Following submission of a notice, a full report will be provided by the relevant dutyholder to the Building Safety Regulator within 10 days of the incident occurring, or the risk being discovered, if the information is not immediately available. In addition to the information contained within the initial notice the full report will include the following, as noted on the template in Appendix A:
· Details of the principal contractor and principal designer
· Whether it is a report for an incident or a risk
· Details of whether the incident or risk relates to structural failure or the spread of fire, or both
· What happened and what caused it
· Who has been affected and in what way
· What has been done to keep people safe, which includes any action taken to address the incident or risk
· How the incident or risk was discovered
· Details of any supporting information, for example scanned documents or photographs.
Change Management
The dutyholders will assess if a change control application is required if any incident, heads up, or accident has occurred. Change management processes will be initiated following this access
Golden Thread
A log of all Mandatory occurrences is included in Golden Thread documentation

## Mandatory Occurrence Form
Mandatory Occurrence Reporting Form
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Reference Document |  | Reference | Version | Created by | Dated
Adverse Events Policy |  | IMS-POL-032 | 2 | Scott Millington
Adverse Events Procedure |  | IMS-PRO-032 | 3 | Scott Millington
This form is to be used to record all Building Safety Occurrences on High-Risk Buildings. All Safety Occurrences MUST be recorded on the Adverse Event Register and completed forms MUST be held in the secure case file in the Adverse Event Library.
1 | General Details
Circet Division: |  |  |  | Department:
Client: |  |  |  | Site Supervisor:
Project: |  |  |  | Project Manager:
2 | Location Details
Site ID: |  |  |  | Building Address:
Site Name: |  |  |  | (Inc Postcode)
Building Type:
Specific Location of Safety Occurrence:
3 | Safety Occurrence Details
Case Reference: |  |  |  | Investigator:
Incident Date: |  | Select Date |  | Incident Time:
Summary of
Safety Occurrence:
4 | Witness Details
Full Name |  | Job Title | Company | Contact Details
5 | Safety Occurrence Category
Structural Failure |  | Tick | Spread of Fire / Smoke |  | Tick
RISK | The Potential for Structural Failure |  | RISK | The Potential for the Spread of Fire or Smoke
INCIDENT | Structural Failure: Serious Injury for a Significant Number of People |  | INCIDENT | Spread of Fire or Smoke: Serious Injury for a Significant Number of People
INCIDENT | Structural Failure: Permanent Disabling Condition to a Significant Number of People |  | INCIDENT | Spread of Fire or Smoke: Permanent Disabling Condition to a Significant Number of People
INCIDENT | Structural Failure: Death of a Significant Number of People |  | INCIDENT | Spread of Fire or Smoke: Death of a Significant Number of People
Building Safety Occurrences (High Risk Buildings)
Safety Occurrence Notices, Reports and guidance can be found online using https://www.gov.uk/guidance/submit-a-mandatory-occurrence-notice-and-report. For ALL Safety Occurrences the Building Safety Regulator (BSR) MUST be notified by submitting a [Mandatory Occurrence Notice] as soon as possible, and a [Mandatory Occurrence Report] within 10 days of the Safety Occurrence being identified. For more information contact the Safety Occurrence Help Centre using 0300 7906787.
Building Registration Reference: |  |  | Building Control Reference:
Mandatory Occurrence Notice
Reference: |  |  | Submitted By:
Submission Date: |  |  | Submission Time:
Mandatory Occurrence Report
Reference: |  |  | Submitted By:
Submission Date: |  |  | Submission Time:
7 | Timeline of Events
Add More Rows as Required
Reference |  | Date / Time | Description
Event -8
Event -7
Event -6
Event -5
Event -4
Event -3
Event -2
Event -1
Event
Event +1
Event +2
Event +3
Event +4
Event +5
Event +6
Event +7
Event +8
8 | Information Gathering
Building Materials
EG Compatibility, Integrity, Quality etc.
Work Environment
EG Site Conditions, Weather, Workplace Layout etc.
Safe System of Work
EG Suitability of RAMS, DRA, CPP, Permits, Isolations etc.
Competency
EG Training, KnowlContractor Y and Experience of Individuals Involved
PPE, Tools and Equipment
EG Suitability, Condition, Servicing, Maintenance, Inspection, Calibration etc.
Mental Health and Wellbeing
EG Medical Fitness, Drugs, Alcohol, Fatigue, Stress, Medications etc.
Other Factors
EG Contractors, External Influences
9 | Causation Analysis |  |  |  | Responsibility of Duty Holders
Immediate Cause:
The Direct Cause of the Safety Occurrence
Immediate Cause |  |  | Explanation / Justification
Underlying Cause(s):
Unsafe Acts , Unsafe Conditions and factors that contributed to the Safety Occurrence
Unsafe Act, Conditions, and factors |  | Explanation / Justification | Explanation / Justification
Training, skills and competency
Inadequate design or engineering
Select
Select
Select
Select
Select
Use the box below to describe any further causes not categorised in the above selection lists.
10 | Supporting Evidence
Title and Description |  | Attach | Title and Description |  | Attach
Title |  |  | Title
Description |  |  | Description
Title |  |  | Title
Description |  |  | Description
Title |  |  | Title
Description |  |  | Description
Title |  |  | Title
Description |  |  | Description
Title |  |  | Title
Description |  |  | Description
11 | Action Plan
ALL identified actions MUST be added to the [Action Log] and closed out within required timescales.
Action ID | Description | Description | Priority | Action Owner(s) | Due Date
12 | People Involved in the Investigation
Full Name |  | Job Title | Company | Signature | Date
13 | RIDDDOR |  |  | LINK Make a RIDDOR report - How to make a RIDDOR report - HSE
Has a RIDDOR notice been submitted |  |  | Date of submission
RIDDOR reference |  |  | Who submitted the RIDDOR form
14 | Declaration
Completed by the Investigator |  | I confirm that the information in this report is (to the best of my knowlContractor Y) true and accurate. |  |  |  | Select
Full Name: |  |  | Position: |  |  | Fire safety issue or risk related to building works
Signature: |  |  | Date: |  |  | Fire safety issue or risk related to building
Completed by the Duty Holder |  | I confirm that I have read this report, and agree with the information, conclusions, and actions to be taken to prevent a recurrence. |  |  |  | Structural issue or risk relating to building works
Full Name: |  |  | Position: |  |  | Structural issue or risk relating to building
Signature: |  |  | Date: |  |  | Product non-compliance or incompatibility
Inadequate design or engineering
Inadequate change management
Insufficient training or skills
Insufficient competency for task
Failure of management or supervision
Failure to follow procedure
Improper use of tools or equipment
Use of defective tools or equipment
Other tool or equipment related.
Lack of use of protective method
Improper use of protective method
Lack of protective method
Inattention /lack of awareness
Inadequate of defective protective systems
Inadequate or defective tools, equipment and plant
Exposure to a hazard
Workplace environment hazard
Training, skills and competency
Physical capability or condition
Mental state and mental stress
Behaviour
None of the above categories - detail below

## Golden Thread Arrangements
Golden Thread Arrangements |  |  |  |  | Back to RACI
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Structure: Approved Document A
GOLDEN THREAD - Evidence of workmanship recorded before and during construction |  |  | Contractor to fill
| Required evidence pre-construction | Zip file here (or document reference) | Required evidence to be recorded during construction | Zip file here (or document reference)
Tripod pedestal and cabinet pedestal pre-construction | Photos of rooftop opening for all pedestal locations to present slab surface prior to drilling. |  | Photos at each pedestal location taken from 5 m (for context) and 1 m (to show slab condition
Anchor installation | Proof of depth of anchor drills - provide evidence that rebar embedments are 110 mm depth into the existing slab. |  | Photos at each pedestal location from 1 m to show evidence of anchor depth to 110 mm. (2 photos per plinth location).
Anchor installation - pull out tests |  |  | 10 kN Pull out tests in accordance with BS 8539:2012+A1:2021 Code of practice for the selection and installation of post-installed anchors in concrete and masonry; Test one quarter of all anchors at each tripod and grillage location
Pedestal installation | Photos of pedestal installation |  | Take before and after photos of pedestal installations, demonstrating level with a spirit level.
Pedestal installation | Photos of pedestal installation |  | Take photos to demonstrate the setting out, using guide steelwork to show positioning of pedestals relative to roof edge and to eachother.
Golden Thread- As Builts |  |  | Contractor to fill
Deliverable | Describe requirement |  | Zip file or document reference
As built drawings | Set of redline drawings based on 601 to 612 capturing any deviation from position, design and construction of pedestals.
Steel certificates of conformity from supplier. | Certificates from fabricator with accreditations and competencies (steel grade, galvanising)
GOLDEN THREAD -INSPECTION REPORTS |  |  | Inspector's reports.
#REF! | #REF! | INSPECTION REPORT FILE REFERENCE OR COMMENTS
INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD |  | 0
Fire safety: Approved Document B
GOLDEN THREAD - Evidence of fire safety workmanship recorded during and after construction
Work description | Required evidence to be recorded during construction | Zip file here (or document reference) | Required documents to be recorded post construction | Zip file here (or document reference)
Fire stopping of sub-main route | Photos of fire stopping at each surface , 5m photos to be taken so that the identity of the location is clear; 1m photos to show workmanship |  | Photos of decals at each surface , showing context to show location
Fire stopping of fibre route | Photos of fire stopping at each surface , 5m photos to be taken so that the identity of the location is clear; 1m photos to show workmanship |  | Photos of decals at each surface , showing context to show location | Note assumes fibre to be installed under this scope of works. Virgin Media may install fibre under separate scope of works (under separate Gateway 2 application)
GOLDEN THREAD - As Built requirements
Deliverable | Describe requirement |  | As Built File reference
Fire stopping of sub-main route | As built drawing to capture position and type of each fire stop
Fire stopping of fibre route | As built drawing to capture position and type of each fire stop
Site preparation and resistance to contaminates and moisture: Approved Document C
Golden Thread - Evidence of moisture resistance workmanship taken during construction |  | 0
Work description | Required evidence pre-construction | Zip file here (or document reference) | Required evidence to be recorded during construction | Zip file here (or document reference)
Cutting open | 10 photos taken at each rooftop opening location to present : 1) 5m context shot of location 2) 1 m distant shots of rooftop opening, presenting layers exposed
Pedestal installation | 10 1 m photos taken at each installation to show pedestal redressing, including overlaps. Use measuring stick to photo overlap distances , Show depth and quality of chamfering at base of plinth . Show sufficient overlap of felt and waterproof layers under cowl. |  | 10 1 m photos taken at each installation to show pedestal redressing, including overlaps. Use measuring stick to photo overlap distances , Show depth and quality of chamfering at base of plinth . Show sufficient overlap of felt and waterproof layers under cowl.
0 | 0
Golden Thread - As Builts |  | 0 | Contractor to fill
Deliverable | Describe requirement |  | Applicable test standards | Zip file here (or document reference)
As built | Redline any deviations for detailed design |  | None
Warranty letter from roofing contractor. | Letter from roofing contractor confirming that the works have been completed in accordance with design and that the existing warranty terms and period remain applicable. |  | None
Certificates of Material Conformity. | Data sheets of materials used in the roofing works |  | None
INSPECTION REQUIREMENTS |  | Inspector |  | 0
Scope |  | INSPECTION REPORT FILE REFERENCE OR COMMENTS
INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD
Electrical safety: Approved Document P
Describe any applicable elements of the scope.
Installation and commissioning of electrical equipment in the cabin, installation and commissioning of low power DC supplied equipment on the equipment grillages.
CONSTRUCTION CONTROL PLAN -Material compliance
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Notes on fire ratings.
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | 0
CONSTRUCTION CONTROL PLAN - As Built requirements
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)
Electrical schematic | Updated electrical schematic presenting works in accordance with the detailed design and any variation from the detailed design in redline. |  | None
Electrical calculations | Updated electrical calculations |  | None
DISTRIBUTION LIST
Name | Role | email |  | Date issued
PAP dutyholder name | PAP dutyholder position | PAP dutyholder email
Client contact name | Client contact position | Client email address
Individual Principal Contractor Name | Individual Principal Contractor position | Individual Principal Contractor email
Individual Principal Designer Name | Individual Principal Designer position | Individual Principal Designer email
Organisational Principal Designer name | Organisational Principal Designer position | Organisational Principal Designer email
The Golden Thread material presents compliance to the applicable requirements of Approved Documents and related Building Regulations as described in the Building Regulations Compliance Statement
| Signature when completed | Name | email | Phone number
Signature of Individual Principal Contractor |  | Organisational Principal Contractor Name | Organisational Principal Contractor email | OPC phone number
Signature of Organistional Principal Contractor |  | Individual Principal Contractor Name | Individual Principal Contractor email | Individual Principal Contractor phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number

## Fire and Emergency File
Project Fire and Emergency File |  |  |  |  | Back to RACI
Site Name | Site Address | Post code | High risk building reference | Project Name
Site Name | Site Address | Site Postcode | HRB000000000 | Unwind
Contacts
Name and company | Role | email | mobile number | Activity
PAP dutyholder name , Site PAP company | PAP dutyholder position | PAP dutyholder email | PAP dutyholder phone | Building Safety Manager
Individual Principal Designer Name , Principal Designer Company | SCRIPT | Individual Principal Designer email | Individual Principal Designer telephone number
ENTER | ENTER | ENTER | ENTER | ENTER
ENTER | ENTER | ENTER | ENTER | ENTER
ENTER | ENTER | ENTER | ENTER | ENTER
Existing fire and emergency file document references
Document Name | Filename | Version | Version date | Summary of content
Fire strategy plan | Fire strategy plan filename | 1 | 2024-02-22 | Existing Golden Thread Fire strategy issued by xxx
Fire risk assessment | SURVEY REPORT filename | 1 | 2023-06-06 | Existing compartmentation survey issued by xxxx on
| FRA 1 filename | 1 | 2021-02-01 | Site provider's specification for previous electrical works, including fire alarm system installation and integration
| FRA - EW fiilename | 1 | 2022-09-23 | FRA EW issued by company x
| Other fire-filename | 1 | 2025-06-23 | Describe
Existing site information
| Entry | Version | Entry
Number of floors | 9 | Recommended evacuation strategy | Stay put
Number of apartments | 48 | Last FRA rating | Low
Ground floor area | 26 m x 32 m = 832 m2 | Risk rating post remedial works | Tolerable
Existing Safety Case and Comments
Site Name is a thirteen storey residential building , 36.4 m to the highest occupied floor. It contains 79 self-contained 1 & 2 bedroom flats, all accessed by internal common lobbies. The building is of a reinforced concrete construction with a reinforced concrete flat roof. It's external wall is masonry. All flats are provided single directional escapes via the central stairwell. The stairs are the firefighting stair. The dry rising inlet is located externally on the north east elevation. The outlet is in the common lobby . Both lifts are provided with a fireman's override. The roof is accessed via the stairwell through a roof access door. There are extinguishers provided in the tank room and the lift motor room. There is a Grade A automatic fire detection/alarm system within the ground floor ancillary accommodation of the building comprising of a fire alarm panel, manual call-points, smoke detectors and sounders. Grade D smoke detection is provided in the flats and lobbies for the control of the smoke ventilation system.
Work scope
Describe any applicable elements of the scope.
USE APPROVED DOCUMENT B SCOPE FIELD TO INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT B , CONSIDERING ALL SECTIONS BE1 TO B5
General statement of compliance to Approved Document
Describe how the works affect the fire strategy
USE APPROVED DOCUMENT B GENERAL STATEMENT OF COMPLIANCE FIELD TO WRITE A GENERAL STATEMENT OF COMPLIANCE, REFERENCING THE SCOPE ELEMENTS AND THE EXISTING SAFETY CASE.
Effect of scope on existing fire strategy
Describe how the works affect the fire strategy
The proposed firestopping of the penetrations will be compatible with the fire ratings of the respective walls and panels through which the penetrations are proposed . There will be no changes in the fire ratings of the walls at the end of the works. There is currently no fire alarm sounder or call point on the Site Name roof. The roof is accessible via a door at the top of the stairwell. Travel distances on the roof are less than 60m and is fully open to air. XXXX operates a stay-put strategy at XXXXX, meaning that there are no manual call points through communal areas. There will be no change to the resident's stay-put strategy Rooftop workers will complete and record risk assessments prior to construction and maintenance activities on site, and will apply risk mitigations during the works. During the building works the contractor will appoint its own fire warden. In the event of fire workers will leave the rooftop via the roof door, close the roof door, and exit the building through the protected staircase and call emergency services.
Comments on the spread of fire and structural resistance.
The proposed firestopping of the penetrations will be compatible with the fire ratings of the respective walls and panels through which the penetrations are proposed . There will be no changes in the fire ratings of the walls at the end of the works.
Fire Evacuation
Describe how the works affect the fire evacuation strategy
The VMO2 cell installation will increase the frequency of access events to the the roof, predominantly by two person teams appointed by VMO2 or its contracted companies to maintain, inspect, and upgrade cabinet contents and radio equipment at each tripod . Cable tray installations to these location will not impede evacuation routes to the roof top access door. As telecoms cell sites may require access at night a luminaire will be fitted above the plant room door.
Comments on fire evacuation during construction
Fire safety measures during construction The lack of a fire sounder or call point on the roof increases the risk that workers will be trapped on the roof in the event of a fire during the works. An on-site fire marshal will be appointed during the works and local fire alarm and evacuation procedures will be listed in the health and safety file for the project. NO hot works are required as part of the building works on the rooftop . Cold applied sealants will be used to restore the Langley roofing system. Fire-fighting equipment will be available on the roof throughout the duration of the building works.
Effect on fire and rescue measures and effect on water-supply for fire-fighting
Describe how the works affect existing fire-fighting measures
There will be no effect on fire and rescue measures inside the building. An additional fire extinguisher will be kept on the roof during the works. The pedestal installation work will not involve hot works.
Review and expiry dates
This Fire and Emergency File shall be reviewed at the pre-start meeting by the Duty holders in consultation with XXX This File shall expire on 12 of May 2026
Golden Thread Arrangements
As builts , images, and certificates will be produced by the Principal Contractor and the Principal Designer in accordance with Golden Thread Arrangements. The Fire Strategy and Fire Strategy Drawing will be updated using this information by the Responsible Person's appointed fire company under their instruction.
This Fire and Emergency File is compliant to the requirements of Approved Documents and related Building Regulations as described in the Building Regulations Compliance Statement
| Signature | Name | email | Phone number
Signature of Individual Principal Contractor |  | Organisational Principal Contractor Name | Organisational Principal Contractor email | OPC phone number
Signature of Organistional Principal Contractor |  | Individual Principal Contractor Name | Individual Principal Contractor email | Individual Principal Contractor phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number

## Approved Document A
Structure: Approved Document A |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope. |  |  |  | Responsible: Designer ; PD
INPUT SCOPE ELEMENTS INTO 'APPROVED DOCUMENT A' NOTE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT A
General statement of compliance to Approved Document |  |  |  | Principal Designer
Write a general statement to describe how the design is compliant. Describe the calculation evidence that the design complies. Cite any BSEN codes that relate to the compliance. Note if the building pre-dated the codes applied, and provide a structural justification for the design and structutal calculation approaches adopted.
Applicable Standards Compliance (note only standards listed in Approved Document A are considered) |  |  |  | Structural Engineer and Principal Designer
Standard Reference | Applicable / Non-applicable (select) | If applicable cite drawing or document references where standard has been applied. | Notes on design compliance . How will the design meet this Regulation?
BS EN 1990 + UK National Annex (NA) (BS NA EN 1990: UK National Annex for Eurocode. Basis of structural design) | APPLICABLE
BS EN 1991 + UK NA Multi-part Document BS EN 1991-1 - Eurocode 1. Actions on structures Part 1 Eurocode 1. Actions on structures. General actions. Densities, self-weight, imposed loads for buildings Part 2 Eurocode 1. Actions on structures. General actions. Actions on structures exposed to fire not applied Part 3 Eurocode 1. Actions on structures. General actions. Snow loads Part 4 Eurocode 1. Actions on structures. General actions. Wind actions Part 5 Eurocode 1. Actions on structures. General actions. Thermal actions not applied . Part 6 Eurocode 1. Actions on structures. General actions. Actions during execution Part 7 Eurocode 1. Actions on structures. General actions. Accidental actions applied. | APPLICABLE PARTS
BS EN 1992 + UK NA Multi-part Document BS EN 1992 - Eurocode 2. Design of concrete structures Part 1-1 Eurocode 2: Design of concrete structures. General rules and rules for buildings Part 1-2 Eurocode 2. Design of concrete structures. General rules. Structural fire design Part 4 Eurocode 2. Design of concrete structures. Design of fastenings for use in concrete | APPLICABLE PARTS
BS EN 1993 + UK NA Multi-part Document BS EN 1993 - Eurocode 3. Design of steel structures Part 1-1 Eurocode 3. Design of steel structures. General rules and rules for buildings Part 1-7 Eurocode 3. Design of steel structures. Plated structures subject to out of plane loading Part 1-8 Eurocode 3. Design of steel structures. Design of joints Part 1-9 Eurocode 3. Design of steel structures. Fatigue Part 1-10 Eurocode 3. Design of steel structures. Material toughness and through-thickness properties Part 1-11 Eurocode 3. Design of steel structures. Design of structures with tension components Part 3-1 Eurocode 3. Design of steel structures. Towers, masts and chimneys. Towers and masts Part 3-2 Eurocode 3. Design of steel structures. Towers, masts and chimneys. Chimneys | APPLICABLE PARTS |  | Calculations demonstrate that the proposed and reused existing steel work and concrete plinth interfaces and concrete rooftop will be sufficient to bear dead, design, dynamic and accidental loads on parts, assemblies and existing structures .
BS EN 1996 + UK NA Multi-part Document BS EN 1996 - Eurocode 6. Design of masonry structures Part 1-1 Eurocode 6. Design of masonry structures. General rules for reinforced and unreinforced masonry structures Part 1-2 Eurocode 6. Design of masonry structures. General rules. Structural fire design Part 2 Eurocode 6. Design of masonry structures. Design considerations, materials and execution of masonry Part 3 Eurocode 6. Design of masonry structures. Simplified calculation methods for unreinforced masonry structures | APPLICABLE PARTS
ETA 11/0493 | Injection system Hilti HIT-HY 200-A
EOTA TR029 Design of Bonded Anchors TR 029 Edition June 2007 Amended September 2010 | Applicable |  | This document provides type proof of adequacy of the proposed bonded anchors for the proposed application .
BS 8500 - Method of Specifying Concrete) | Not applicable |  | Revision 3 of the detailed design changed upstand designs from reinforced concrete plinth to steel pedestals. This has eliminated the requirement to complete concrete works on the Langley Waterproofing warm roof.
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Structure: Approved Document A
| Signature | Name and company | email | Phone number
Signature of Structrural Engineer |  | Structural Engineer Name , Structural Engineer Company Name | Structural Engineer email | Structural Engineer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
Approved Document A Relevant Requirements
Building Regulations 2010 |  | Response
A1,(1) The building shall be constructed so that the combine dead, imposed, and wind loads are sustained and transmitted by it to the ground: |  | Compliant | The existing construction of the rooftop slab and its supporting elements has been confirmed via calculation
(a) safely; and |  | Compliant | Calculations demonstrate that the additional loading imposed by the telecommunications equipment on the rooftop slab and its supporting elements will be transmitted to the ground safely.
(b) without causing such deflection or deformation of any part of the building, or such movement of the ground, as will impair the stability of any part of another building. |  | Compliant | The capacity of the existing construction of the rooftop slab and its supporting elements has been confirmed to be adequate by calculation
Ground Movement
A2. The building shall be constructed so that ground movement caused by: |  | No change from existing compliance.
(a) swelling, shrinkage or freezing of the subsoil; or |  | No change from existing compliance.
(b) land-slip or subsidence (other than subsidence arising from shrinkage), in so far as the risk can be reasonably foreseen, will not impair the stability of any part of the building. |  | No change from existing compliance.
Introduction
0.2 The safety of a structure depends on the successful combination of design and completed construction, particularly: |  | Noted
The design should be based on the identification of the hazards to which the building is likely to be subjected and assessment of the risks. The selection of relevant critical situations for design should be made reflecting the conditions that can reasonably be foreseen during future use. |  | Noted
Loading. Dead load, imposed load and wind load should be in accordance with the current Codes of practice referred to in Section 1 of the approved document |  | Noted
Properties of materials. |  | Compliant
Detailed design and assembly of structure. |  | Compliant
Safety factors. |  | Compliant
Workmanship. |  | Noted
The numeric values of safety factors, whether expressed explicitly or implicitly in design equations, or design values, should be derived from considerations of the above aspects of design and construction as a whole. A change in any one of these aspects may disturb the safety of the structure. |  | Noted
Loads used in calculations should allow for possible dynamic, concentrated and peak load effects that may occur. |  | Noted
Grandstands and structures erected in places of public assembly may need to sustain the synchronous or rhythmic movement of numbers of people. It is important to ensure that the design of the structure takes these factors into account so as to avoid the structure being impaired or causing alarm to people using the structure. |  | Not applicable
Eurocode 0: Basis of structural design
BS EN 1990 Basis of structural design with UK annex to BS EN 1990: 2002 + A1:2005 |  | Compliant |  |  | Compliant
Noted
Eurocode 1: Actions on structures |  |  |  |  | Not compliant
BS EN 1991-1-1 General actions - Densities, self-weight, imposed loads for buildings; with UK National Annex to BS EN 1991-1-1:2002 |  | Compliant |  |  | No change from existing compliance.
BS EN 1991-1-2 General actions - Actions on structures exposed to fire |  | No change from existing compliance. |  |  | Not applicable
BSI PD 6688-1-1:2011 Published Document - Recommendations for the design of structures to BS EN 1991-1-1 |  | Compliant
BS EN 1991-1-3 General actions - Snow loads; with UK National Annex to BS EN 1992-1-3:2003 |  | Compliant
BS EN 1991-1-4 General actions - Wind actions; with UK National Annex to BS EN 1991-1-3:2003 |  | Compliant
BSI PD 6688-1-4:2009 Published Document - Background information to the National Annex to BS EN 1991-1-4 and additional guidance |  | Noted
BS EN 1991-1-5 General actions - Thermal actions with UK National Annex to BS EN 1991-1-5 :2003 |  | Compliant
BS EN 1991-1-6 General actions - Actions during execution with UK National Annex to BS EN 1991-1-6:2005 |  | Compliant
BS EN 1991-1-7 General actions - Accidental actions with UK National Annex to BS EN 1991-1-7:2006 |  | Compliant
BSI PD 6688-1-7:2009 Published Document -Recommendations for the design of structures to BS EN 1991-1-7 |  | Compliant
BS EN 1991-3 Actions induced by cranes and machinery with UK National Annex to BS EN 1991-3 |  | Not applicable
Eurocode 2: Design of concrete structures
BS EN 1992-1-1: 2004 General rules and rules for buildings with UK National Annex to BS EN 1992-1-1: 2004 |  | No change from existing compliance.
BSI PD 6687-1:2010 Published Document - Background paper to the UK National Annexes to BS EN 1992-1 and BS EN 1992-3. |  | No change from existing compliance.
EN 1992-1-2 General rules - Structural fire design |  | No change from existing compliance.
Eurocode 3: Design of steel structures
EN 1993-1-1 General rules and rules for buildings; with UK National Annex to BS EN 1993-1-1 :2005 |  | Compliant
BS EN 1993-1-2 General rules - Structural fire design |  | No change from existing compliance.
BS EN 1993-1-3 Eurocode 3: General rules - Supplementary rules for cold formed members and sheeting; with UK National Annex to BS EN 1993-1-3 :2006 |  | Compliant
BS EN 1993-1-4 General rules - Supplementary rules for stainless steels with UK National Annex to BS EN 1993-1-4 :2006 |  | Not applicable
BS EN 1993-1-5 General rules - Supplementary rules for planar plated structures without transverse loading ; with UK National Annex to BS EN 1993-1-5:2006 |  | Not applicable
BS EN 1993-1-6 General rules - Supplementary rules for the shell structures |  | Not applicable
BS EN 1993-1-7 General rules - Supplementary rules for planar plated structural elements with out of plane loading |  | Not applicable
BS EN 1993-1-8 Design of joints; with UK National Annex to BS EN 1993-1-8 :2005 |  | Compliant
BS EN 1993-1-9 Fatigue; with UK National Annex to BS EN 1993-1-9:2005 |  | Compliant
BS EN 1993-1-10 Material toughness and through-thickness properties; With UK National Annex to BS EN 1993-1-10 :2005 |  | Compliant
BSI PD 6695-1-10:2009 Published Document - Recommendations for the design of structures to BS EN 1993-1-10 |  | Compliant
BS EN 1993-1-11 Design of structures with tension components ; with UK National Annex to BS EN 1993-1-11 :2006 |  | Not applicable
BS EN 1993-1-12 Additional rules for the extension of EN 1993 up to steel grades S 700;with UK National Annex to BS EN 1993-1-12 :2007 |  | No change from existing compliance.
EN 1993-3-1 Towers, masts and chimneys - Towers and masts |  | Compliant
BS EN 1993-5 Piling; with UK National Annex to BS EN 1993-5:2007 +A1:2012 |  | Not applicable
BS EN 1993-6 Crane supporting structures; with UK National Annex to BS EN 1993-6 :2007 |  | Not applicable
BS EN 1090-2:2008 + A1:2011 Execution of steel structures and Aluminium structures - Part 2: Technical requirements for the execution of steel structures |  | Compliant
BRE Digest 437 Industrial platform floors: mezzanine and raised storage. |  | Not applicable
Eurocode 4: Design of composite steel and concrete structures
BS EN 1994-1-1 General rules and rules for buildings; with UK National Annex to BS EN 1994-1-1 :2004 |  | Not applicable
BSI PD 6693-1:2012 Published Document - Recommendations for the design of timber structures to Eurocode 5: Design of timber structures Part 1: General - Common rules and rules for buildings. |  | Not applicable
BS 8103 -3 :2009 Structural design of low-rise buildings - Part 3: Code of practice for timber floors and roofs for housing. |  | Not applicable
Eurocode 5: Design of timber structures
BS EN 1995-1-1 General - Common rules and rules for buildings; with UK National Annex to BS EN 1995-1-1 :2004+ A1:2008 |  | Not applicable
Eurocode 6: Design of masonry structures
BS EN 1996-1-1:2005 + A1:2012 General rules for buildings - Rules for reinforced and unreinforced masonry structures; with UK National Annex to BS EN 1996-1-1:2005 + A1:2012 |  | Not applicable
BS EN 1996-2:2006 General rules - Design considerations, selection of materials and execution of masonry; with UK National Annex to BS EN 1996-2:2006 |  | Not applicable
BS 8103 - Structural design of low-rise buildings BS 8103-1:2011 Structural design of low-rise buildings - Code of practice for stability, site investigation, foundations, precast concrete floors and ground floor slabs for housing
BS 8103-2:2013 Structural design of low-rise buildings - Code of practice for masonry walls for housing |  | Not applicable
Eurocode 7: Geotechnical design
BS EN 1997-1 General rules; with UK National Annex to BS EN 1997-1 :2004 |  | Not applicable
BS EN 1997-2 Ground investigation and testing; with UK National Annex to BSEN 1997-2:2007 |  | Not applicable
Not applicable
Eurocode 8: Design of structures for earthquake resistance
BS EN 1998-1 :2004 + A1:20213 General rules, seismic actions and rules for buildings; with UK National Annex to BS EN 1998-1 :2004 |  | Not applicable
BS EN 1998-5 Foundations, retaining structures and geotechnical aspects; with UK National Annex to BS EN 1998-5:2004 |  | Not applicable
EN 1998-6 Towers, masts and chimneys |  | Not applicable
BSI PD 6698:2009 Published Document - Recommendations for the design of structures for earthquake resistance to BS EN 1998 |  | Not applicable
Eurocode 9: Design of aluminium structures
EN 1999-1-1 General rules - General rules and rules for buildings |  | Not applicable
EN 1999-1-2 General rules - Structural fire design |  | Not applicable
EN 1999-1-3 Additional rules for structures susceptible to fatigue |  | Not applicable
EN 1999-1-4 Supplementary rules for trapezoidal sheeting |  | Not applicable
EN 1999-1-5 Supplementary rules for shell structures |  | Not applicable
Section 2 : Sizes of structural elements for certain residential buildings and other small buildings of traditional construction.
Section 2 does not apply to this building because the building is more than 3 storeys high |  | Not applicable
Section 3: Wall Cladding
Section 3 : Wall Cladding . |  | Not applicable | No work is to be completed on the external fascia of this building.
Section 4: Roof covering
4.1 All materials used to cover roofs, excluding windows of glass in residential buildings with roof pitches of not less than 15o, shall be capable of safely withstanding the concentrated imposed loads upon roofs specified in BS EN1991-1-1:2002 with its National Annex. Transparent or translucent covering materials for roofs not accessible except for normal maintenance and repair are excluded from the requirement to carry the concentrated load upon roofs if they are non-fragile or are otherwise suitably protected against collapse. |  | No change from existing compliance.
4.2 The recovering of roofs is commonly undertaken to extend the useful life of buildings. Roof structures may be required to carry underdrawing or insulation provided at a time later than their initial construction. This section provides guidance on determining whether such work to a roof constitutes a material alteration under the Building Regulations. |  | Noted
4.3 Where the work involves a significant change in the applied loading the structural integrity of the roof structure and the supporting structure should be checked to ensure that upon completion of the work the building is not less compliant with Requirement A1than the original building. |  | Compliant | This section relates to roof covering, but is applicable in content . Structural calculations provide evidence that the building will not be less compliant with Requirement A1 upon the completion of the building works.
4.4 A significant change in roof loading is when the loading upon the roof is increased by more than 15%. Consideration might also be given to whether the roof covering being replaced is the original as-built covering. |  | Noted
4.5 Where such checking of the existing roof structure indicates that the construction is unable to sustain any proposed increase in loading (e.g. due to overstressed members or unacceptable deflection leading to ponding), appropriate strengthening work or replacement of roofing members should be undertaken. This is classified as a material alteration. |  | Noted | This section relates to roof covering, but is applicable in content . No rooftop elements or members have been shown to require strengthening or replacement as a result of the additional roof load.
4.6 In carrying out the checks mentioned in paragraph 4.3 an increase of stress in a structural member arising from increased loading does not necessarily indicate that the roof structure is less compliant than the original roof provided an adequate factor of safety is maintained. |  | Noted
4.7 Where work will significantly decrease the roof dead loading, the roof structure and its anchorage to the supporting structure should be checked to ensure than an adequate factor of safety is maintained against uplift of the roof under imposed wind loading. |  | Noted
Section A3: Disproportionate Collapse
A3, The building shall be constructed so that in the event of an accident the building will not suffer collapse to an extent disproportionate to the cause. |  | No change from existing compliance. | The building meets the criterion of Consequence Class XX . No disproportionate collapse assessment has been done under this project becauseitis not considered reasonanbly practicable to do so. The consequence class of this building is 2b. At this consequence level the building will have been required to have either been built with or upgraded with these additional measures effective horizontal ties, designed according to BS 5628: Part 1: 1992, clause 37.3 and Table 13, plus vertical loadbearing members being able to act as vertical ties according to clause 37.4 and Table 14 of BS 5628: Part 1 or to have been assessed for disproportionate collapse risk u by modelling the effect of the removal of load bearing elements It is not known if the building does include these measures. The proposed building works will not affect any existing additional measures and hence the existing disproportionate collapse assessment has not been affected.’ The assessment of the risk of disproportionate collapse would require information on the tie measures originally installed or installed as additional measures The Principal Accountable Person may adopt the approach is to show that loadbearing members can be notionally removed, one at a time, without causing collapse of a part of the building exceeding the limits given in consideration of the removal of loadbearing members. .
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor to complete this element (Name) | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
Fabrication of Pedestals | BS EN 1090-2 exec 2 | Supplier 1 company | https://www.shearfab.co.uk/quality/ See Alcumus Isoqar UK CERTIFICATE of conformity Factory Production Control Certificate No: 0513-CPR-201-004
Fabrication of General steelwork (tripod and grillage assemblies | BS EN 1090-2 exec 2 | Supplier 1 company | https://www.shearfab.co.uk/quality/ See Alcumus Isoqar UK CERTIFICATE of conformity Factory Production Control Certificate No: 0513-CPR-201-004
Pedestal installation |  | Contractor 1 company name | 20 plus years experience. ; Alcumus Safe Contractor Certificate - 18092024
Tripod and grillage assembly |  | Contractor 1 company name | 20 plus years experience. ; Alcumus Safe Contractor Certificate - 18092024
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
Supplier 1 company | SO9001:2015 ; BS EN 1090 Execution Class 2 of steel structures and aluminium structures. | Supplier 1 Name | See https://www.shearfab.co.uk/quality/ ; Shearfab ISOQAR UK BSEN 1090 certificate of conformity FPCShearfab ISOQAR ISO 9001 2015 certificate of registration | 35 years
Contractor X Limited |  | Contractor 1 Name | Alcumus Safe Contractor Certificate - 18092024 | 20 years
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
Pedestal fabrication | BS10025 S355 steel and 8.8 fixings | SO9001:2015 ; BS EN 1090 Execution Class 2 of steel structures and aluminium structures. | Shearfab ISOQAR UK BSEN 1090 certificate of conformity FPC
All other steel | BS10025 S275 steel and 8.8 fixings | SO9001:2015 ; BS EN 1090 Execution Class 2 of steel structures and aluminium structures. | Shearfab ISOQAR UK BSEN 1090 certificate of conformity FPC
All galvanising | All steel galvanised | EN ISO 1461
INPUTS FOR CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | Inspection (When, Responsibility )
Tripod pedestal and cabinet pedestal pre-construction | Photos of rooftop opening for all pedestal locations to present slab surface prior to drilling. | Photos at each pedestal location taken from 5 m (for context) and 1 m (to show slab condition |  | During pedestal installation ; Contractor X
Anchor installation | Proof of depth of anchor drills - provide evidence that rebar embedments are 110 mm depth into the existing slab. | Photos at each pedestal location from 1 m to show evidence of anchor depth to 110 mm. (2 photos per plinth location). |  | During anchor embedment construction ; Contractor X
Anchor installation - pull out tests |  | 10 kN Pull out tests in accordance with BS 8539:2012+A1:2021 Code of practice for the selection and installation of post-installed anchors in concrete and masonry; Test one quarter of all anchors at each tripod and grillage location
Pedestal installation | Photos of pedestal installation | Take before and after photos of pedestal installations, demonstrating level with a spirit level. | As built photos | Prior to tripod and grillage installations., Contractor X PICW and Contractor
Pedestal installation | Photos of pedestal installation | Take photos to demonstrate the setting out, using guide steelwork to show positioning of pedestals relative to roof edge and to eachother. | As built photos | Prior to tripod and grillage installations., Contractor X PICW and Contractor
INPUTS for CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
As built drawings | Set of redline drawings based on 601 to 612 capturing any deviation from position, design and construction of pedestals.
Steel certificates of conformity from supplier. | Certificates from fabricator with accreditations and competencies (steel grade, galvanising)

## Approved Document B
Fire safety: Approved Document B |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
USE APPROVED DOCUMENT B SCOPE FIELD TO INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT B , CONSIDERING ALL SECTIONS BE1 TO B5
General statement of compliance to Approved Document
USE APPROVED DOCUMENT B GENERAL STATEMENT OF COMPLIANCE FIELD TO WRITE A GENERAL STATEMENT OF COMPLIANCE, REFERENCING THE SCOPE ELEMENTS AND THE EXISTING SAFETY CASE.
Applicable Standards Compliance
Standard Reference and main title | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
BS 476-6:1989+A1:2009. | NOT APPLICABLE
BS EN1366-3: 2009 Fire resistance tests for service installations | APPLICABLE |  | COMPLIANT
BS476: Part 20: 1987. Fire tests on building materials and structures. Method for determination of the fire resistance of elements of construction (general principles) | NOT APPLICABLE |  | NOT APPLICABLE
EN 13501-2 | APPLICABLE |  | COMPLIANT
BS EN 13501-5. Fire classification of construction products and building elements. Classification using data from external fire exposure to roofs tests | APPLICABLE |  | COMPLIANT
EN 13163 / EN 14303. | APPLICABLE |  | COMPLIANT
CEN/TS 45545-2 | APPLICABLE |  | COMPLIANT
BS EN 15725:2023 Extended application on the fire performance of construction products and building elements: Principle of EXAP standards and EXAP reports | NOT APPLICABLE |  | NOT APPLICABLE
EN1026 (air tightness) | NOT APPLICABLE |  | NOT APPLICABLE
ISO 7240-11:2011 ISO 7240-11:2011-Fire detection and alarm systems-Part 11: Manual call points | NOT APPLICABLE |  | NOT APPLICABLE
Document references |  |  |  | Designer
Document Name | Filename | Version | Version date | Summary of content
Fire strategy plan | Fire strategy plan filename | 1 | 2024-02-22 | Existing Golden Thread Fire strategy issued by xxx
Fire compartmentation survey | SURVEY REPORT filename | 1 | 2023-06-06 | Existing compartmentation survey issued by xxxx on
Fire Risk Assessment | FRA 1 filename | 1 | 2021-02-01 | Site provider's specification for previous electrical works, including fire alarm system installation and integration
Other fire safety document | Other fire-filename | 1 | 2025-06-23 | Describe
Responsible Person and other contacts
Name | Role | Company | email | Phone number
PAP dutyholder name | PAP dutyholder position | Site PAP company | PAP dutyholder email | PAP dutyholder phone
INSERT OTHER | INSERT OTHER | INSERT OTHER | INSERT OTHER | INSERT OTHER
Insert Images and other references applicable to compliance statement
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Fire safety: Approved Document B
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
COMPLIANCE ASSESSMENT TO REQUIREMENTS B1 TO B5
Requirement B1: Means of warning and escape
Reference survey notes and existing golden thread information |  |  | Describe the effect of the design proposal on the relevant requirement
| Pre-construction |  | Post -construction
Detail the BS5839 electrical fire detection and alarm (or detection only) system comprising manual call points and/or automatic detection, providing product name, installer detail, existing rooftop sounder / call point information , nearest point of interconnection to the roof. | A BS 5839 Part 1 Category L5 fire detection system is in place in designated risk areas , interlinked with AOVs, situated at either end of the communal lobbies |  | There will be no change to the existing category 5 fire detection system
Describe the existing and future route of fire escape from the roof to the fire exit, stating the fire rating of any stairwells, construction, fire door types and ratings, electrically operated access controls, key control, access to fire-fighting, signage and lighting, and any identified non-compliances | The roof is accessible via a door at the top of the stairwell. Travel distances on the roof are less than 60m and is fully open to air, this is deemed as acceptable. The one stairwell serving all floors in the building terminates the roof plant room. It is treated as a firefighting stair, the stair discharges into fresh air in front of the building.
Photos of the access door to the roof.
Is there a secondary means of exit anywhere along this route? | No, the single stairwell is the means of exit in the even of a fire.
Is the escape route adequately lit? | Yes
Is the escape route free of obstructions | Yes
Requirement B2: Internal fire spread (linings)
Inhibit the spread of fire over internal linings of buildings. | Pre-construction |  | Post -construction
Referencing Golden Thread fire information, are all surface linings in the common areas accessible via the access route to the roof rated to C-ds3, d2, or conformant to BS EN15102 ? Will the construction effect any of these elements? |  |  | No change to existing compliance
Referencing Golden Thread fire information and survey information confirm if any rooflights, insulating core panels, suspended ceilings, or lighting diffusers in accessible common areas have been assessed as non-compliant. Note the effect of the construction project on any internal element. |  |  | No change to existing compliance
Requirement B3: Internal fire spread (structure)
The building must be built such that all of the following are achieved in the event of a fire: a. the premature collapse of the building is avoided ;b. sufficient fire separation is provided within buildings and between adjoining buildings; c. automatic fire suppression is provided where necessary ;d. the unseen spread of fire and smoke in cavities is restricted.
Response to these questions assumes access to existing fire risk assessment information alongside survey notes | Answer | Comment | Instruction
Are any new cable, cable ducts, or replacement cable or ducts to be installed from the ground floor and through the building ? This includes electrical cables, fibre cables, and RF feeders. | Yes |  | Completed sections A & D
Are any new cables or ducts or replacement cables or ducts to be installed on any elevation? | Yes |  | Completed sections B & D
Are existing cables going to be re-routed or replaced? | No |  | Sections C & D
Are any existing cables going to be reused? | No |  | Sections C & D
Will any new air conditioning pipes be installed through walls/floors | No |  | Sections C & D
Section A Proposed internal cable routing |  |  |  | Applicable
Describe the cables to be routed, including their size, function, and their covers or jackets | L/N 4Cx25mm² SWA/PVC70/Cu L:60m CPC armour submain and a 35 mm tri-rated earth.
Summarise their routes through the building, from their point of origin to their connection to cell equipment. Add additional lines for each cable. | The submain and earth will be routed from the landlords switch room through a core drilled penetration in to a redundant gas main riser. 100 mm core drilled penetrations will be made through thirteen 185 mm thick reinforced concrete floors to floor thirteen. A 50 mm penetration will be drilled at circa 2.5 m above floor level between the gas main riser and floor 13 of the stairwell to enter a proposed 1 m length of galvanised steel trunking. A further 50 mm hole will be core drilled through the roof of the thirteenth floor stairwell for the submain to route into the rooftop access room / top of the stairwell. The cable will enter a Roxtec gland for exit to the roof. The cable will be routed 2 .2 m down the plant room masonry face on cable tray to transition to a Sure foot mounted cable tray to the VMO2 cabinet grillage. No other cables are proposed to route through the building under this scope. Note that Virgin Media is proposing a fibre installation via a separate wayleave proposal. This is to be routed externally.
Use this section to summarise the existing or new penetrations between compartments through which the cables will be routed, stating wall / floor construction , fire rating REI, thickness. Add sketches and image mark ups below. | The submain will be routed from the landlords switch room through a core drilled 100 mm diameter penetration into a redundant gas main riser. This is a 60 min REI wall. 100 mm core drilled penetrations will be made through thirteen 185 mm thick floors to floor thirteen. Each floor is rated 90 minute REI. A 50 mm penetration will be made to the stairwell at floor 13 through a 60 minute rated wall A further 50mm penetration will be made through the 90 minute rated roof of the floor 13 stairwell into the roof access room, from which it will exit on to the plant room via a Roxtec gland on to the roof via a masonry 60 minute rated. wall
INTERNAL SUBMAIN ROUTE
Show by photo mark up how cables are to route through each penetration. Add a caption to state the penetration location, and note the construction of the wall/floor. Note or sketch how the cables are to enter and exit the penetration . Add lines as required.
Photos of wall/ floor with mark up of penetration point
Caption/ comment
Proposed firestopping product (including rating and BS compliance)
Photos of wall/ floor with mark up of penetration point
Caption/ comment
Proposed firestopping product
INTERNAL FIBRE ROUTE
Photos of wall/ floor with mark up of penetration point
Caption/ comment
Proposed firestopping product (fire company to fill)
Photos of wall/ floor with mark up of penetration point
Caption/ comment
Proposed firestopping product
Photos of wall/ floor with mark up of penetration point
Caption/ comment
Proposed firestopping product
Routes through internal public areas |  |  |  | Not applicable
If cables must be routed through common areas such as corridors or stairwells, describe the cable management to be proposed to house the cables from point of entry to the point of exit.
Photos of Common area with mark up | Not applicable
Caption/ comment
Proposed conduit or trunking, providing fire rating or BS compliance.
Section B Proposed external cable routing to roof |  |  |  | Not applicable
Describe the cables to be routed, including their size, function, and their covers or jackets | NOTE Virgin Media have a separate fibre proposal, which is to be externally routed up the north elevation to the roof. The Virgin Media scope is not presented in this design.
Summarise their routes out of the building, where applicable from their point of origin to the exterior . Add additional lines for each cable. Comment on the choice of external route
Use this section to summarise the route to the roof, noting any existing or new cable management to be reused or installed.
Show by photo mark up how cables are to route externally . Add a caption to identify the face /location for this exterior route. State the construction of the wall, roof or fascia.
Photos
Caption/ comment
Proposed firestopping product (including rating and BS compliance)
Transition to the roof |  |  |  | Not applicable
Describe how the cable is to transition over the parapet or rooftop Contractor Y , and how it will be routed to the cell equipment. | Not applicable to this scope.
Photos of route to cabinet locations.
Caption/ comment
Proposed connection detail to wall, roof, or external cladding
Section C Proposed reuse of existing submain and fibre. |  |  |  | Not applicable
Take context and close up photos of the existing submain and fibre routes from the point of supply to the roof at accessible points along the route. | Not applicable
Photo any decal stickers applied to existing fire stopping. | Not applicable
Take context and close up photos of any evidence of missing or defective firestopping | Not applicable
Section D Cable routing across the roof. |  |  |  | Applicable
Show by photo mark up how cables are to route across the roof . Provide commentary on proposed cable management and measures taken to facilitate emergency escape where cable management will cross access routes.
Photos here
Caption/ comment
Requirement B5: Access and facilities for the fire service
Response to these questions assumes access to existing fire risk assessment information alongside survey notes | Answer
Will the proposed cell site affect access for fire-fighting
CONSTRUCTION CONTROL PLAN - Contractor Competencies
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
Fire stopping | BS EN1366-3 & EN13501-2:2016 | Contractor 1 company name | bmtrada Q-mark ; UKAS Product Certification 0142
CONSTRUCTION CONTROL PLAN - Contractor appointments.
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
Contractor 1 company name | bmtrada Certificate of Registration Certificate Number 3626 for Group A and Group B fire stopping filename Contractor X Installations Ltd Hickman 3626 05b FINAL 061124 | Contractor 1 Name | - | 20+
CONSTRUCTION CONTROL PLAN -Material compliance
Work element | Materials used in this work (add lines) | Applicable standards | Datasheet or certificate filename ( (Supply copy in Construction Control Supporting Documents) | Notes
Fire stopping of sub-main route |  | BS EN1366-3 & EN13501-2
Fire stopping of fibre route |  | BS EN1366-3 & EN13501-2
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during and after construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
Fire stopping of sub-main route | none | Photos of fire stopping at each surface , 5m photos to be taken so that the identity of the location is clear; 1m photos to show workmanship | Photos of decals at each surface , showing context to show location
Fire stopping of fibre route | none | Photos of fire stopping at each surface , 5m photos to be taken so that the identity of the location is clear; 1m photos to show workmanship | Photos of decals at each surface , showing context to show location
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement
Fire stopping of sub-main route | As built drawing to capture position and type of each fire stop
Fire stopping of fibre route | As built drawing to capture position and type of each fire stop

## Approved Document C
Site preparation and resistance to contaminates and moisture: Approved Document C |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
INPUT SCOPE ELEMENTS THAT WILL OR COULD CAUSE A MATERIAL ALTERATION RELEVANT TO APPROVED DOCUMENT C IN APPROVED DOCUMENT C SCOPE FIELD
General statement of compliance to Approved Document
WRITE A GENERAL STATEMENT OF COMPLIANCE, REFERENCING THE SCOPE ELEMENTS AND THE EXISTING SAFETY CASE. DESCRIBE THE MEASURES PROPOSED TO MEETTHE RELEVANT REQUIREMENTS.
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
BS 6229:2018 Flat roofs with continuously supported flexible waterproof coverings. Code of practice
BS 5250:2021 Management of moisture in buildings. Code of practice
BS EN ISO 13788:2002
BS 8500 - Method of Specifying Concrete
BS 8500 - Method of Specifying Concrete
BS 8500 - Method of Specifying Concrete
Document references |  |  |  | Designer
Document Name | Filename | Version | Version date | Summary of content
Drawing 1 | Client's Filename convention | A | 2025-09-15 | Detailed design drawings in PDF
Drawing 2 | Client's Filename convention other drawing | C | 2025-09-15 | Detailed design drawings in .dwg
DRA | Client's Filename convention DRA | - | 09.04.25 | DRA for CDM
Existing roofing warranty | Warranty filename | 1 | 44581 | Warranty
Manufacturer's document | Filename | 1 | UNDATED | Drawing of standard detail of waterproofing requirements supplied by xxxx .
0 | 0 | 0 | 0 | 0
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Site preparation and resistance to contaminates and moisture: Approved Document C
| Signature | Name | email | Phone number
Signature of Designer |  | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
Cutting open roof material | BS 6229:2018 | Subcontractor 2 Company name | Approved Langley contractor. The site provider requires the appointment of Contractor Z Roofing. NFRC, CHAS, Construction Line Gold Member
Pedestal dressing | BS 6229:2018 | Subcontractor 2 Company name | Approved Langley contractor. The site provider requires the appointment of Contractor Z Roofing. NFRC, CHAS, Construction Line Gold Member
CONSTRUCTION CONTROL PLAN - Individual appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name and number | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
Subcontractor 2 Company name | NFRC, Construction Line, Approved Langley Waterproofing System installer. | Subcontractor 2 Name |  | >10
CONSTRUCTION CONTROL PLAN -Pre-construction evidence of material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Certificate of datasheet or material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Applicable standards | Blank
Redressing of plinths | The pedestals will be dressed using Langley approved materials. | To be supplied at Gateway 3 | BS 6229:2018
CONSTRUCTION CONTROL PLAN - Evidence of workmanship to be taken during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction | Inspection (When, Responsibility, Deliverables)
Cutting open | 10 photos taken at each rooftop opening location to present : 1) 5m context shot of location 2) 1 m distant shots of rooftop opening, presenting layers exposed |  |  | During works; Contractor, Photo report
Pedestal installation |  | 10 1 m photos taken at each installation to show pedestal redressing, including overlaps. Use measuring stick to photo overlap distances , Show depth and quality of chamfering at base of plinth . Show sufficient overlap of felt and waterproof layers under cowl. | Letter of re-warranty from roofing manufacturer; letter of completion by Rooftopworker competent person. | During works; Contractor & PICW, Photo report
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
As built | Redline any deviations for detailed design |  | None | N/a
Warranty letter from roofing contractor. | A letter to confirm that the remaining period of the existing warranty remains in effect. |  | None | N/a
Certificates of Material Conformity. | Data sheets of materials used in the roofing works |  | None | N/a

## Approved Document D
Toxic substances: Approved Document D |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
D scope
General statement of compliance to Approved Document
D Compliance
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Toxic substances: Approved Document D
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)

## Approved Document E
Resistance to sound: Approved Document E |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
E scope input
General statement of compliance to Approved Document
E compliance input
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Resistance to sound: Approved Document E
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)

## Approved Document F
Ventilation: Approved Document F |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
F Scope
General statement of compliance to Approved Document
F compliance
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
BS EN13141-1 Ventilation for buildings. | not applicable. |  |  | Internal room…
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Ventilation: Approved Document F
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
Ventilation: Approved Document F pre-construction supporting documents |  |  | Insert a zip file into the supplied box to provide any supporting evidence of compliance, contractor accreditations, membership accreditations,, certificates of material supply, qualifications,
Documents in Zip file
Ventilation: Approved Document F Workmanship supporting evidence recorded during build |  |  | Insert a zip file into the supplied box containing any evidence of workmanship during build, including medium sized images of measures taken to meet ventilation related relevant requirements during and after installation
Documents in Zip
Ventilation: Approved Document F As Built documents |  |  | Insert a zip file into the supplied box to provide the deliverables listed in the as built requirements.

## Approved Document G
Sanitation, hot water safety and water efficiency: Approved Document G |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
G Scope
General statement of compliance to Approved Document
Not applicable.
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Sanitation, hot water safety and water efficiency: Approved Document G
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
Sanitation, hot water safety and water efficiency: Approved Document G pre-construction supporting documents |  |  | Insert a zip file into the supplied box to provide any supporting evidence of compliance, contractor accreditations, membership accreditations,, certificates of material supply, qualifications,
Documents in Zip file
Sanitation, hot water safety and water efficiency: Approved Document G Workmanship supporting evidence recorded during build |  |  | Insert a zip file into the supplied box containing any evidence of workmanship during build, including medium sized images of measures taken to meet ventilation related relevant requirements during and after installation
Documents in Zip
Sanitation, hot water safety and water efficiency: Approved Document G As Built documents |  |  | Insert a zip file into the supplied box to provide the deliverables listed in the as built requirements.

## Approved Document H
Drainage and waste disposal: Approved Document H |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
H Scope
General statement of compliance to Approved Document
H compliance :
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Drainage and waste disposal: Approved Document H
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)
Drainage and waste disposal: Approved Document H pre-construction supporting documents |  |  | Insert a zip file into the supplied box to provide any supporting evidence of compliance, contractor accreditations, membership accreditations,, certificates of material supply, qualifications,
Documents in Zip file
Drainage and waste disposal: Approved Document H Workmanship supporting evidence recorded during build |  |  | Insert a zip file into the supplied box containing any evidence of workmanship during build, including medium sized images of measures taken to meet ventilation related relevant requirements during and after installation
Documents in Zip
Drainage and waste disposal: Approved Document H As Built documents |  |  | Insert a zip file into the supplied box to provide the deliverables listed in the as built requirements.

## Approved Document J
Combustion appliances and fuel storage systems: Approved Document J |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
J scope
General statement of compliance to Approved Document
J compliance
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Combustion appliances and fuel storage systems: Approved Document J
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename ( (Supply copy in As Built Supporting Documents)

## Approved Document K
Protection from falling, collision and impact: Approved Document K |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
K scope
General statement of compliance to Approved Document
K compliance
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Protection from falling, collision and impact: Approved Document K
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document L
Conservation of fuel and power: Approved Document L |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
L Scope
General statement of compliance to Approved Document
L Compliance
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
BS 6229: 2018
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Conservation of fuel and power: Approved Document L
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document M
Access to and use of buildings: Approved Document M |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
M Scope
General statement of compliance to Approved Document
There will be effect on access through the building
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Access to and use of buildings: Approved Document M
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document O
Overheating: Approved Document O |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
O Scope
General statement of compliance to Approved Document
O Compliance
Applicable Standards Compliance
Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
Document references |  |  |  | Designer
Document name | File name | Document description | Version number | Date
Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Overheating: Approved Document O
| Signature | Name | email | Phone number
Signature of Designer | 0 | Designer name | Designer email | Designer phone number
Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the the competencies of the company to undertake the work.
CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document P
| Electrical safety: Approved Document P |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
P Scope
. | General statement of compliance to Approved Document
P Compliance
Applicable Standards Compliance
| Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
| BS7671 Requirements for Electrical Installations [2008+ A1:2011 [IET Wiring Regulations 18th Edition | Applicable |  | Compliant
| BS EN 62305 2011 | Applicable |  | Compliant
| BS 7430 2015 | Applicable |  | Compliant
| Document references |  |  |  | Designer
| Document name | File name | Document description | Version number | Date
| Electrical calculations | Report Export-89149 | Electrical calculations | 1 | 2024-11-28
| Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Electrical safety: Approved Document P
|  | Signature | Name | email | Phone number
| Signature of Designer |  | Designer name | Designer email | Designer phone number
| Signature of Electrical Designer |  | Electrical Contractor Name | Electrical Contractor email | Electrical Contractor Phone number
| Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
| INPUTS TO CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
| Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work (Use the cell below to describe the competencies of the company to undertake the work)
| Installation of switchgear and associated cabling | BS7671 Requirements for Electrical Installations [2008+ A1:2011 [IET Wiring Regulations 18th Edition | Contractor Y Electrical Solutions | NICEIC Competent Person Scheme
| CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
| Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
| Contractor Y Electrical Solutions | NICEIC | Dan Thacker | NICEIC Competent Person Scheme
| CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
| Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Notes on fire ratings.
| CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
| Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
| CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
| Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)
| Electrical schematic | Updated electrical schematic presenting works in accordance with the detailed design and any variation from the detailed design in redline. |  | None
| Electrical calculations | Updated electrical calculations |  | None

## Approved Document Q
| Security in dwellings: Approved Document Q |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
Q Scope
. | General statement of compliance to Approved Document
Q Compliance
Applicable Standards Compliance
| Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
| Document references |  |  |  | Designer
| Document name | File name | Document description | Version number | Date
| Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Security in dwellings: Approved Document Q
|  | Signature | Name | email | Phone number
| Signature of Designer | 0 | Designer name | Designer email | Designer phone number
| Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
| CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
| Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the the competencies of the company to undertake the work.
| CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
| Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
| CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
| Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
| CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
| Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
| CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
| Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)
| Security in dwellings: Approved Document Q pre-construction supporting documents |  |  | Insert a zip file into the supplied box to provide any supporting evidence of compliance, contractor accreditations,membership accreditations,, certificaties of material supply, qualifications,
Documents in Zip file
| Security in dwellings: Approved Document Q Workmanship supporting evidence recorded during build |  |  | Insert a zip file into the supplied box containing any evidence of workmanship during build, including medium sized images of measures taken to meet Approved Document Q related relevant requirements during and after installation
Documents in Zip
| Security in dwellings: Approved Document Q As Built documents |  |  | Insert a zip file into the supplied box to provide the deliverables listed in the as built requirements.

## Approved Document R
| Infrastructure for electronic communications: Approved Document R |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
R Scope
. | General statement of compliance to Approved Document
R compliance
Applicable Standards Compliance
| Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
| Document references |  |  |  | Designer
| Document name | File name | Document description | Version number | Date
| Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Infrastructure for electronic communications: Approved Document R
|  | Signature | Name | email | Phone number
| Signature of Designer |  | Designer name | Designer email | Designer phone number
| Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
| CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
| Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the the competencies of the company to undertake the work.
| CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
| Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
| CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
| Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
| CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
| Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
| CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
| Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document S
| Infrastructure for charging electric vehicles: Approved Document S |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
S Scope
. | General statement of compliance to Approved Document
S compliance
Applicable Standards Compliance
| Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
| Document references |  |  |  | Designer
| Document name | File name | Document description | Version number | Date
| Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Infrastructure for charging electric vehicles: Approved Document S
|  | Signature | Name | email | Phone number
| Signature of Designer |  | Designer name | Designer email | Designer phone number
| Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
| CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
| Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
| CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
| Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
| CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
| Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
| CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
| Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
| CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
| Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document T
| Toilet accommodation: Approved Document T |  |  |  | go back | Back to RACI
Describe any applicable elements of the scope.
T Scope
. | General statement of compliance to Approved Document
T compliance
Applicable Standards Compliance
| Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
| Document references |  |  |  | Designer
| Document name | File name | Document description | Version number | Date
| Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Toilet accommodation: Approved Document T
|  | Signature | Name | email | Phone number
| Signature of Designer | 0 | Designer name | Designer email | Designer phone number
| Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number
| CONSTRUCTION CONTROL PLAN - Contractor Competencies |  |  |  | go back
| Work element | Applicable standard(s) | Contractor Name to complete this element | Competency statement and accreditations of Contractor completing work
Use the cell below to describe the competencies of the company to undertake the work.
| CONSTRUCTION CONTROL PLAN - Contractor appointments. |  |  |  | go back
| Contractor Name | Accreditations (memberships) . Supply copy in Construction Control Supporting Documents | Person in Charge of works (name) | Qualifications (Supply copy in Construction Control Supporting Documents) | Years of experience in role.
| CONSTRUCTION CONTROL PLAN -Material compliance |  |  |  | go back
| Work element | Materials used in this work (add lines) | Applicable standards | Certificate of material conformance filename ( (Supply copy in Construction Control Supporting Documents) | Blank
| CONSTRUCTION CONTROL PLAN - Evidence of workmanship during construction |  |  | Consult with Principal Designer | Principal Contractor
| Work description | Required evidence pre-construction | Required evidence to be recorded during construction | Required documents to be recorded post construction
| CONSTRUCTION CONTROL PLAN - As Built requirements |  |  | Consult with Principal Designer | Principal Contractor
| Deliverable | Describe requirement |  | Applicable test standards | Certificate filename (Supply copy in As Built Supporting Documents)

## Approved Document 7
| Material and workmanship: Approved Document 7 |  |  |  |  | Back to RACI
Describe any applicable elements of the scope.
7 scope
. | General statement of compliance to Approved Document
7 compliance
Applicable Standards Compliance
| Standard Reference | Applicable / Non-applicable | If applicable cite drawing or document references where standard has been applied. | Compliant / Non-compliant | Notes on compliance
| BS 8000-1 Workmanship on building sites 1989 | applicable |  | compliant
| BS8000-2-1 Workmanship on building sites. Code of practice for concrete work. Mixing and transporting concrete | applicable |  | compliant
| BS8000-2-2 Workmanship on building sites. Code of practice for concrete work. Sitework with in situ and precast concrete 1990 | applicable |  | compliant
| BS8000-3 | applicable |  | compliant
| BS8000-4 Workmanship on building sites. Code of practice for waterproofing | applicable |  | compliant
| BS8000-9 Workmanship on building sites. Cementitious levelling screeds and wearing screeds. Code of Practice | not applicable ( no plan to re-level) |  | compliant
| Document references |  |  |  | Designer
| Document name | File name | Document description | Version number | Date
| Insert Images and other references applicable to compliance statement |  |  |  | Optional
The Design presented in the drawings and documents listed under Document references are compliant to the Building Regulations listed and to the relevant requirements of Material and workmanship: Approved Document 7
|  | Signature | Name | email | Phone number
| Signature of Designer |  | Designer name | Designer email | Designer phone number
| Signature of Individual Principal Designer |  | Individual Principal Designer Name | Individual Principal Designer email | Individual Principal Designer telephone number