## Budget Detail Worksheet (hidden)
Casa de Esperanza
OVW-TA Promoting Latina Advocacy
2 Years - $450,000
Budget Detail Worksheet
A. Personnel |  |  |  | Computation
Staff | Title | Cost | % | Curr Salary | Year 1 | Year 2
Juan Carlos Arean | NLN Director | 21767.616 | 10% | 102600 | 10670.4 | 11097.216 | (4% ann. incr.)
Patricia Tototzintle | CEO | 46634.8896 | 20% | 109905 | 22860.24 | 23774.6496 | (4% ann. incr.)
Amy Sanchez | CEER-Consultant/Trainer | 23315.3232 | 10% | 109895 | 11429.08 | 11886.2432 | (4% ann. incr.)
Rosario de la Torre | Family Advocacy Manager | 27103.0157 | 20% | 63874 | 13285.792 | 13817.2237 | (4% ann. incr.)
Heidi Notario-Smull | Training & TA Coordinator | 12687.168 | 10% | 59800 | 6219.2 | 6467.968 | (4% ann. incr.)
TBD | Trainer | 61632.48 | 50% | 58100 | 30212 | 31420.48 | (4% ann. incr.)
TBD | Family Advocate | 3496.0786 | 5% | 32957 | 1713.764 | 1782.3146 | (4% ann. incr.)
Maritza Valdez | Comm Assistant/Website Dev | 1634.4806 | 2% | 38520 | 801.216 | 833.2646 | (4% ann. incr.)
Cassie Amundson-Munoz | Program Assistant | 1712.5555 | 2% | 40360 | 839.488 | 873.0675 | (4% ann. incr.)
Juan Carlos Areán, Director of the National Latin@ Network for Healthy Families and Communities (NLN), will serve as the primary contact for the project, oversee all grant activities and supervise staff. Amy Sánchez, Chief Executive Officer for External Relations, will supervise all national work and product development and provide targeted training on organizational development. Patti Tototzintle, CEO, will supervise fiduciary oversight for the organization and provide TA on organizational and leadership development and Latina advocacy. Rosario de la Torre, Family Advocacy Manager, will provide training and TA on Latina Advocacy and collaboration with local consulates. Training and TA will be coordinated and provided by the Heidi Notario Smull, Training and TA Coordinator. The Trainer (TBD) will implement much of the specific training and technical assistance components of this project. A Family Advocate (TBD) will share first hand experience and realities facing Latinas during webinars and other trainings, as well as serve as a valuable resource for other staff. Maritza Valdez will provide logistal support for all training events, coordinate related communication needs, and ensure Casa de Esperanza's National Latin@ Network website provides relevent resource material for other organizations who serve Latina victims. Cassie Amundson-Munoz will provide database management and logistical assistance.
Total Personnel |  | 199983.6072
B. Fringe Benefits
Staff | Title | Cost |  | Computation
Juan Carlos Arean | NLN Director
Employer's FICA |  | 1665.2226 |  | 21767.616 | 7.65%
Health Insurance |  | 2198.5292 |  | 21767.616 | 10.1%
Workers Compensation |  | 261.2114 |  | 21767.616 | 1.2%
Unemployment Comp |  | 222.0297 |  | 21767.616 | 1.02%
Patricia Tototzintle | CEO
Employer's FICA |  | 3567.5691 |  | 46634.8896 | 7.65%
Health Insurance |  | 4710.1238 |  | 46634.8896 | 10.1%
Workers Compensation |  | 559.6187 |  | 46634.8896 | 1.2%
Unemployment Comp |  | 475.6759 |  | 46634.8896 | 1.02%
Amy Sanchez | CEER-Consultant/Trainer
Employer's FICA |  | 1783.6222 |  | 23315.3232 | 7.65%
Health Insurance |  | 2354.8476 |  | 23315.3232 | 10.1%
Workers Compensation |  | 279.7839 |  | 23315.3232 | 1.2%
Unemployment Comp |  | 237.8163 |  | 23315.3232 | 1.02%
Rosario de la Torre | Family Advocacy Manager
Employer's FICA |  | 2073.3807 |  | 27103.0157 | 7.65%
Health Insurance |  | 2737.4046 |  | 27103.0157 | 10.1%
Workers Compensation |  | 325.2362 |  | 27103.0157 | 1.2%
Unemployment Comp |  | 276.4508 |  | 27103.0157 | 1.02%
Heidi Notario-Smull | Training & TA Coordinator
Employer's FICA |  | 970.5684 |  | 12687.168 | 7.65%
Health Insurance |  | 1281.404 |  | 12687.168 | 10.1%
Workers Compensation |  | 152.246 |  | 12687.168 | 1.2%
Unemployment Comp |  | 129.4091 |  | 12687.168 | 1.02%
TBD | Trainer
Employer's FICA |  | 4714.8847 |  | 61632.48 | 7.65%
Health Insurance |  | 6224.8805 |  | 61632.48 | 10.1%
Workers Compensation |  | 739.5898 |  | 61632.48 | 1.2%
Unemployment Comp |  | 628.6513 |  | 61632.48 | 1.02%
TBD | Family Advocate | 267.45 |  | 3496.0786 | 7.65%
Employer's FICA |  | 353.1039 |  | 3496.0786 | 10.1%
Health Insurance |  | 41.9529 |  | 3496.0786 | 1.2%
Workers Compensation |  | 35.66 |  | 3496.0786 | 1.02%
Unemployment Comp
Maritza Valdez | Comm Assistant/Website Dev
Employer's FICA |  | 125.0378 |  | 1634.4806 | 7.65%
Health Insurance |  | 165.0825 |  | 1634.4806 | 10.1%
Workers Compensation |  | 19.6138 |  | 1634.4806 | 1.2%
Unemployment Comp |  | 16.6717 |  | 1634.4806 | 1.02%
Cassie Amundson-Munoz | Program Assistant
Employer's FICA |  | 131.0105 |  | 1712.5555 | 7.65%
Health Insurance |  | 172.9681 |  | 1712.5555 | 10.1%
Workers Compensation |  | 20.5507 |  | 1712.5555 | 1.2%
Unemployment Comp |  | 17.4681 |  | 1712.5555 | 1.02%
Fringe Benefits for all staff includes FICA, Medical Insurance, Dental Insurance, Life Insurance, Long Term Disability Insurance, Workers Compensation Insurance and Unemployment Insurance. The current total rate for these payroll taxes and fringe benefits is 19.97% of salary cost.
Total Fringe Benefits |  | 39936.7264
C. Travel
Purpose of Travel/Location | Computation | Cost
Planning Meeting/St. Paul, MN | 3 staff x 2 Meetings x 2 nights
| Airfare - 3 staff x 2 trips x $550/flight | 3300
| Lodging - 3 staff x 2 meetings x 2 nights x $121/night | 1452
| Per diem - 3 staff x 1 day x $71/day x 2 meetings; plus 3 staff x 2 travel days x $53/day x 2 meetings | 1062
| Local Transportation Taxi - 3 x 2 x $80 | 480
Latina Advocacy Institutes/Various | 4 staff x 4 Institutes x 2 nights
| Airfare - 4 staff x 4 trips x $550/flight | 8800
| Lodging - 4 staff x 4 trips x 2 nights x $140/night | 4480
| Per diem - 4 staff x 4 days x $66/day; plus 4 staff x 8 travel days x $49/day | 2624
| Local Transportation Taxi - 4 x 4 x $80 | 1280
OVW Mandated Provider Meetings/ | 3 staff x 2 meetings x 2 nights
Washington D.C. | Airfare - 3 staff x 2 trips x $675 | 4050
| Lodging - 3 staff x 2 trips x 2 nights x $183/night | 2196
| Per diem - 3 staff x 2 days x $71/day; plus 3 staff x 4 travel days x $53/day | 1062
| Local Transportation Taxi - 3 x 2 x $80 | 480
OVW Mandated TA Meetings/ | 3 staff x 2 meetings x 2 nights
Washington D.C. | Airfare - 3 staff x 2 trips x $675 | 4050
| Lodging - 3 staff x 2 trips x 2 nights x $183/night | 2196
| Per diem - 3 staff x 2 days x $71/day; plus 3 staff x 4 travel days x $53/day | 1062
| Local Transportation Taxi - 3 x 2 x $80 | 480
Local Travel - mileage | 40 miles/mo x .565/mi x 24 months | 542.4
Travel includes two project planning meetings in St. Paul, MN, where three of Casa de Esperanza's national staff members will be able to meet in person with local staff and a key representative of project partner, Voces Latina. These meetings will help set timelines for deliverables and specific plans for instititutes. For each of the planned institutes, three staff will travel to sites to provide training and facilitation; while one staff will provide logistical support. OVW provider and TA meetings are included for three staff as required. Local travel is estimated for minimal project related automobile travel for key staff - including to airport and various local meetings.
Total Travel |  | 39596.4
E. Supplies
Supply Item | Computation | Cost
Laptop Computer - Trainer | $1,100 x 50% | 550
Program Supplies - binders, flipcharts, etc. | $100/institutes x 4 institutes | 400
Printing Projects - General Training material | $120/institutes x 4 institutes | 480
Printing Projects - Latina Advocacy Manual | 50 pages x $.70/page x 200 copies | 7000
Shipping of Materials-Regional Meetings | $150/institute x 4 institues | 600
Office Supplies - specific to project | $10/mo x 24 months | 240
Laptop will be needed for Trainer for use while traveling to institutes as well as in office - 50% of cost to be covered by other sources. Program supplies (including presentation materials, handouts, flipcharts, etc.) and related printing and shipping were estimated for each of the institutes based on recent similar sized convenings. The Latina Advocacy Manual will focus on the unique realities, legal issues, language barriers, etc. facing Latinas and their communities. This product development, and its availability to other organizations, is a key component to the success of our project. Office supplies are estimated based on past needs for project specific items such paper, pens, folders, etc.
Total Supplies |  | 9270
G. Consultants/Contracts
Consultants/Contracts Service | Service Provided | Cost |  | Computation
Voces Latina | Project Partner Organization | 39000 |  | 60 days x $650/day
TBD-various | Multimedia Product Development | 40000 |  | 500 days x $80/hour
TBD-various | Institutes - Accessibility Services -Interpretation, Translation, CART, Transcription, etc. | 21760 |  | 4 Institutes x 4 accessibility-related services: Interpreting, ASL,etc./institute x 16 hours each meeting x $85/hour
TBD-various | General Accessibility Services -Interpretation, Translation, CART, Transcription, etc. | 2640 |  | Estimate 1 hour/mo x 24 months for Accessiblity-related services: Interpreting, ASL, etc. x $85/hour = $2,040; plus translation of estimated 2000 words/year x 2 years x $.15/word = $600
GoToMeetings.com (24 x $110 x .25) | Webinars unlimited up to 100 people per | 660 |  | $110/mo x 24 mos x 25% of organization usage
Infinite Conferencing | Conference Calls | 2160 |  | 5 part. x 600 min./mo x .03/minute/line x 24 mo.
Voces Latina is an organization that works to reduce HIV transmission among immigrant Latinas by empowering, educating, and promoting leadership and advocacy from within Latino communities. As a collaborating organization, Casa de Esperanza will work closely with Voces Latina to develop tools for Latina and sexual assault, stalking and trafficking. Specifically we will work together with overall project planning (4-6 days); product/toolkit development (15-20 days); planning and implementing institutes (20-30 days); planning and implementing webinars (4-6 days); and providing follow-up technical assistance (15-25 days). Total estimated days of collaboration is 60 days. Multimedia product development include video content with Latina survivor stories and insights; fact sheets and other written material around Latinas and sexual assault and stalking; a train-the-trainer module for managers of shelters, transitional housing programs, advocacy programs, etc. to effectively support Latinas experiencing violence; and a self-administered learning tool that individuals can use on their own schedule and pace. We are estimating 500 hours from various consultants to accomplish this product development component of our project.
Casa de Esperanza, along with our project partners, are fully committed to providing accessibilty for individuals with disabilities and deaf individuals. To ensure that our services are accessible Casa de Esperanza surveys the participants for upcoming meetings, institutes, webinar trainings, and conference calls. We provide training material in advance to interpreters and ensure the layout of the room is conducive to successful interpretation. Webinars are recorded so that individuals can access materials at their own convenience and allows for transcriptions. Likewise, for individuals with Limited English Proficiency, we strive to ensure that our services support interpretation and translation services. We offer all of our materials in Spanish and will seek other language interpreters as needed. Additionally, Casa de Esperanza owns its own simultaneous interpretation equipment for individuals who speak a language other than English. We are estimating approximately four interpreters for each of our four institutes, knowing some will require more, while others will need less. We also will need general interpreting and translation services for webinars and conference calls as well as products, other printed material, and website content. Webinars thru GoToMeeting.com allow unlimited webinar usage (up to 100 participants per call) for approximately $110/mo. This cost will be split throughout organization, based on usage, but we are planning at least 12 webinars over the grant period. All consultants and contracts will be procured in a manner that provides maximum open, free and fair competition and follows the rules specified in the Code of Federal Regulations.
Subtotal - Consultants/Contracts Service |  | 106220
Consultants/Contracts Travel
Purpose of Travel/Location | Computation | Cost
Planning Meeting/St. Paul, MN | 1 partner x 2 Meetings x 2 nights
| Airfare - 1 partner x 2 trips x $550/flight | 1100
| Lodging - 1 partner x 2 nights x 2 trips x $121/night | 484
| Per diem - 1 partner x 1 day x $71/day x 2 meetings; plus 1 partner x 2 travel days x $53/day x 2 meetings | 354
| Local Transportation Taxi - 1 x 2 x $80 | 160
Latina Advocacy Institutes/Various | 1 partner x 4 Institutes x 2 nights
| Airfare - 1 partner x 4 trips x $550/flight | 2200
| Lodging - 1 partner x 4 trips x 2 nights x $140/night | 1120
| Per diem - 1 partner x 4 days x $66/day; plus 1 partner x 8 travel days x $49/day | 656
| Local Transportation Taxi - 1 x 4 x $80 | 320
Travel includes two project planning meetings in St. Paul, MN, where a key representative of Voces Latina will be able to meet in person with Casa de Esperanza's staff members. These meetings will help set timelines for deliverables and specific plans for instititutes. For each of the planned institutes, the Voces Latina representative will provide training and facilitation.
Subtotal Consultants/Contracts Travel |  | 6394
Total Consultants/Contracts |  | 112614
H. Other Costs
Description | Computation | Cost
Latina Advocacy Institutes | 40 participants from 10 OVW grant organizations for 4 institutes (160 particpants representing 40 organizations in total) also 4 staff and 1 partner
Room rental and AV equipment | 45 attendees/meeting x $20/attendee x 4 institutes | 3600
Four institutes throughout the United States, hosted by Casa de Esperanza and Voces Latina, will bring together multi-disciplinary teams from at least ten grantee organizations (40 participants in each institute) to increase the depth and impact of the collective learning. Each organization will be encouraged to participate in these Institutes, (as well as other trainings), with their local law enforcement and judicial partners. These "teams" will leave the institutes with concrete steps to implement at their organizations and in their communities. In total 160 individuals will receive this intensive, targeted training. Four Casa de Esperanza staff and a representative from Voces Latina will coordinate, facilitate and provide training at each of these institutes.
Total Other Costs |  | 3600
Total Direct Costs Budget |  | 405000.7336
I. Indirect Costs
Description | Computation | Cost
11.7% of Direct Expenses | $405,001 x 11.7% | 47385.0858
exclude subcontracts in excess of $25,000 | less $14,000 x 11.7% | -1638
exclude participant & partner travel expenses | less $6,394 x 11.7% | -748.098
The provisional Indirect Cost Rate Agreement was approved by the Division of Cost Allocation of the Department of Health and Human Services on February 21, 2013. A copy of this agreement is attached.
Total Indirect Costs |  | 44998.9878
Total Project Costs |  | 449999.7214
Budget Summary
Budget Category |  | Amount
A. Personnel |  | 199983.6072
B. Fringe Benefits |  | 39936.7264
C. Travel |  | 39596.4
D. Equipment |  | 0
E. Supplies |  | 9270
F. Construction |  | 0
G. Consultants/Contracts |  | 112614
H. Other Costs |  | 3600
Total Direct Costs |  | 405000.7336
I. Indirect Costs |  | 44998.9878
Total Project Costs |  | 449999.7214
Note on A87: Juan Carlos Arean: Don't we need justification for travel?

## Implementation Plan + Timeline
Global Grants Program
Implementation Plan: [INSERT PROJECT TITLE]
Bloomberg Philanthropies Data for Health Initiative
General Information
Name of Organization
Country
Project Focal Point
First Name
Last Name
Email Address
Project Activities |  |  | Project Timeline - fill in the table below to propose a timeline for the activities and outcomes the project will setout to complete/achieve. You can insert an "X" in the cell to represent when you estimate an activity to be completed.
List the key activities intended through this project and detail the intended impact(s). |  |  | 2023 |  |  | 2024
Key Activities (should be supported by budget) | Outcome/Deliverable: How was a system or process changed? (What will success look like?) | Person(s) Responsible | Q2 | Q3 | Q4 | Q1 | Q22 | Q33
Maintenance and Sustainability - What will be needed to maintain and/or further the project outcomes following completion of the project timeline? | How will these be carried forward, implemented etc. during the project timeframe? | Agency/Person(s) Responsible

## Budget Summary
This budget template is designed for NGO applicants to assist with developing project budgets. Please fill in the tab labeled budget detail. For further guidance on budget development, please download the applicant budget guidance document the adjacent cell. Please also fill in the tab labeled Implementation Plan + Timeline |  | Applicant Budget Guidance
Name of Organization:
Project Title:
Grant/Project Period: [Insert Start Date] - [Insert End Date]
Budget Summary |  | Reconciliation (for internal use)
Budget Category | Amount Budgeted | Expended | Balance
A. Personnel | 0 | 0 | 0
B. Fringe Benefits | 0 | 0 | 0
C. Travel/Meetings/Workshops | 0 | 0 | 0
D. Supplies | 0 | 0 | 0
E. Contracts/Consulting | 0 | 0 | 0
F. Other Direct Costs | 0 | 0 | 0
G. [Add Budget Line Item] | 0 |  | 0
Total Direct Costs | 0 | 0 | 0
Total Indirect Costs | 0 | 0 | 0
Grand Total | 0 | 0 | 0
Note on B11: Jeremiah Martin: Cells will auto-populate as you fill in the budget details tab.

## Budget Detail
Name of Organization:
Country:
Project Title:
Grant/Project Period: [Insert Start Date] - [Insert End Date]
A. Personnel
Name | Title | Cost | Year 1 Salary | Year 1 - FTE | Year 1 Total | Year 2 Salary | Year 2 - FTE | Year 2 Total
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
|  | 0 |  |  | 0 |  |  | 0
Total Personnel |  | 0
Please summarize the role of each project team member here.
B. Fringe Benefits (flat % rate is acceptable) - update formula in cell C21
Total Fringe |  | 0
| Total Personnel and Fringe | 0
C. Travel/Meetings/Workshops
Purpose of Travel/Location | Computation | Cost
Total Travel |  | 0
Please provide a description of each travel/meeting/workshop activity here.
D. Supplies
Item | Computation | Cost
Total Supplies |  | 0
Please summarize the use of project supplies and equipment items here.
E. Contracts/Consulting
Item | Computation | Cost
Total Contracts/Consulting |  | 0
Please provide a description of the role/purpose of contractors/consultants here.
F. Other Direct Costs
Item | Computation | Cost
Total Other Direct Costs |  | 0
Provide Description of advertising/media/communications
G. [Add Budget Line Item]
Item | Computation | Cost
Total Other Direct Costs |  | 0
Total Direct Costs Budget |  | 0
Total Indirect Costs |  | 0
Total Project Costs |  | 0
Note on C8: Jeremiah Martin: Cells highlighted gray will auto-calculate.
Note on C23: Jeremiah Martin: cell will auto-populate

## Expense Reporting (hidden)
Date | Description of Expense | Expense Type | Amount | Budeget Line Item

## Sheet2 (hidden)
Personnel
Fringe
Travel/Meetings/Workshops
Supplies
Contracts/Consulting
Other Direct Costs
Indirect Costs