## Sheet1
CLAIMS TRACKER |  | SAMPLE | CMG GERARD O SULLIVAN 2026 | [7 empty] | CLAIM TIMETABLE DETAILS | [16 empty] | PROGRAMME IMPACT |  |  |  |  | COSTS VALUATION
Claim description and respone
Claim No. | Contractor/Employer Ref. | Status | Rev clause | Summary Description | Claimed Schedule K 1 event(s) | Other Claims | ER's response to Employer liability issue | 10.4 proposal | delay event | compensation event | Date notice received | Date issue of Proposed Instruction by ER | Last Date for receipt of Claim details | Date for receipt of Contractor's proposal | Date receipt of Contractor's claim /proposal | Continuing effect notified | Continuing effect Monthly update | Date period of recipricol cooperation commences | Date co-operation meeting concludes | Last date for ER request for add info | Date of ER request for add info | Last date for receipt of add info | Date add info received | Date for Contractor to respond to 10.9 | Last Date for ER Determination | Date of ER determination | Last date for parties to refer ER's determination to dispute process | Contractor delay /compensation days | Contractor delay only days' | Determination delay by ER | Programme Contingency Thresholds Extent to be set off-against overall time allowed | Determination of extension of time | Contractor's 10.7 claim for Contract Sum adjustment per delay claimed | ER's adjustment of contract sum per delay /compensation determined | Contractor's 10.6 claim for adjustment of contract sum advised per final info issued | Contractor's response valaution of 10.9 claims | ER's adjustment to contract sum per 10.6 valuation per determination | ER's adjustment to contract sum per 10.9 valuation per determination | Contractor's combined total claimed for adjustment of contract sum | ER's combined determination for adjustment of contract sum | Delta between Contractor combined sum and ER's determined sum
ER ref | Notice ref. no | Open/closed | 9.3/10.3/10.9 |  |  | eg. Claimed ER direction as instruction ; Employer's claim | Bried summary of ER's response in determination |  | schd 1 k | sche 1 k | Within 20 working days 10.3 | clu 10.4 | Within 20 working days of receipt of notice (note 4.1.9) | Within 20 working days of receipt of proposed instruction 10.4 | actual date | 10.3.3.- |  | All notices suspended bar first notice 4.1.9 | Suspension lifted 3 working days after conclusion | Within 20 working days of receipt of claim details 10.5.1 | actual date | within 10 working days of request 10.5.1 | actual date | within 20 working days of receipt of 10.9 claim | 10 working days from receipt of info /or 20 working days from receipt of claim/proposal/ response if no request for info made | Actual date or date determination ought to be made 10.5.3 | 28 days from date of ER determination |  |  |  | For delay compensation only T1 …days T 2 ….days' 9.4.3 | adjusted after used of programme contingency | daily delay rate per sch 2 D | daily delay rate per sch 2 D |  |  |  |  | Plus 10.6 claim and 10.7 claim and 10.9 response | Plus 10.6 claim and 10.7 claim and 10.9 response
CO1 | 10.3.001 | closes | 10.3 | removal of overhead cables poles | K21 |  |  |  | yes | no | 2026-04-10 |  | 2026-05-13 |  | 2026-05-10 | no |  |  |  | 2026-06-06 | 2026-06-06 | 2026-06-20 | 2026-06-18 |  | 2026-07-04 | 2026-07-03 |  | 5 | 5 | 2