## Document Map
Project Document Map
Document | Purpose and Content | Owner | Contributors | Approver | When Issued
Charter | Formally authorises the Project and the Project Manager. Provides high-level requirements. Lists major Assumptions and Constraints. | Sponsor | PM & Sponsor | Sponsor | Project Start
Stakeholder Register | Identifies Stakeholders. Provides Contact Details and lists Stakeholder involvement. | PM | PM & Team | PM | After the Charter and on update
Requirements Document | Records Requirements. Lists Requirement Categories, Descriptions and Source Stakeholders. | PM | PM, Team, Sponsor & other Stakeholders | PM, Sponsor & Client | After the Charter and on update
Issue Log | Lists, tracks and records resolutions to elements and unplanned events under discussion or in dispute between stakeholders. | PM | PM & Team | PM | After the Charter and on update
Document Distribution Matrix | Maps anticipated project documents to their Originators/Publishers and to their Receivers | PM | PM & Team | PM | After the Charter and on update
Scope Statement | Describes in detail the Deliverables and the work required to create them. Lists Project Exclusions. Describes major Objectives (Time, Cost, Performance). | PM | PM, Team, Sponsor & Primary Stakeholders | PM (& Sponsor) | After the Charter and on update
Work Breakdown Structure (WBS) | A hierarchical organisation of the total work to be carried out to accomplish the Project Objectives and produce the required Deliverables. Presented as an Organisation Chart of Work. | PM | PM, Team, Sponsor & Primary Stakeholders | PM | After Scope Statement 0.1 and on update
Schedule | Scope superimposed on a calendar scale. Displays the planned sequence of Work, Milestones and Resource assignments. Can display Critical Path, Baseline Data and Tracked Progress. | PM | PM & Team | PM | After WBS 0.1 and on update
Responsibility Assignment Matrix (RAM) | Table that maps Stakeholders to Scope based on 'Participation; Accountability; Review; Input; Sign-Off' | PM | PM, Team, Sponsor & Primary Stakeholders | PM | After WBS 0.1 and on update
Risk Register | Documents Risks identified/anticipated and provides management focus (High;Medium;Low). Documents Response Plans and results if implemented. Documents Risk Status (Open/Closed). | PM | PM & Team | PM | After WBS 0.1 and on update
Change Request Form | Formal request to change Scope, Documentation, Budgets, Resources etc. Evaluates the consequences of Change (Time, Cost, Performance). Records the Approval or Rejection of the Change. | PM | PM, Team, Sponsor & other Stakeholders | PM; PM and/or Sponsor and/or Primary Stakeholders | After Baselining (Scope Statement 1.0 etc.) and on update
Progress Report | Records overall Project Status and specific Deliverable Status (On Track/Off Track) and Progress (% Complete) | PM | PM & Team | PM | Agreed Intervals with the Sponsor, e.g. Weekly; last Friday of the month etc.
Closeout Report | Formal review of Project outcomes and success. Summary of the Lessons Learned gathered throughout the Lifecycle. Formally Closes the Project. | PM | PM & Team | PM & Sponsor | At Project Closeout
Created by:
Alan McLoughlin
KM Consultancy Services
alan@kmconsult.ie

## Project Charter
Project Charter |  |  | Logo
Project Name |  | Project No.
1. Project Description [Describe what the overall project output, service or result will be]
2. Business Need/Justification [Descibe the reason(s) for the project; a specific contract; expected benefits to be realised]
3. High Level Milestones [List significant Deliverables and expected achievement dates]
4. High Level Risks [List any risks anticipated for this project]
5. Expected Primary Stakeholders [List Individual or Group Stakeholders anticipated at this time]
6. Assumptions [Describe any assumptions being made, e.g., staff will be made available by Line Managers]
7. Expected Finish Date | 8. Expected Cost
9. Project Manager | 10. Project Sponsor
Sponsor Signature:
Date:

## Stakeholder Register
Stakeholder Register
Project Name: | 0 |  |  |  | Project No.: | 0 | Revision Date: |  | Revision No.: | 0
Stakeholder Details | [5 empty] | Describe Involvement & Expectations |  | Engagement Strategy |  | Category
Name | Role/Title/Position | Organisation/Dept | Contact Number(s) | Email | Location

## Requirements Doc
Requirements Document | [7 empty] | Project Manager: | 0
Project Name: |  | 0 |  | Project No.: |  | 0 | Revision Date: |  | Revision No.:
Requirement ID | Date Identified | Requirement Description | Category | Source Stakeholder | Priority | Acceptance Criteria | Dependencies | Assumptions | Constraints | Status | Verification Method

## Issue Log
Issue Log | [7 empty] | Project Manager: | 0
Project Name: |  | 0 |  | Project No.: | 0 | Revision Date: |  |  | Revision No.: |  | 0
Issue No. | Date Raised | Issue Name | Issue Description and Area it affects | Issue Source | Issue Owner | Actions Taken | Issue Priority | Actions To be Taken | Review Date | Open/Closed | Date Closed

## Doc Distribution
Document Distribution Matrix
| Project Name: |  | 0 |  |  | Project No. | 0 | Date:
| Originators |  |  |  |  | Receivers
Document Name | Project Manager | Project Team | Project Participants (incl. Contractors) | Sponsor | Primary Stakeholders | Project Manager | Project Team | Project Participants (incl. Contractors) | Sponsor | Primary Stakeholders
Project Charter
Stakeholder Register
Requirements Document
Scope Statement
Work Breakdown Structure
Gantt Chart
RAM
Risk Register
Change Requests
Status/Progress Report
Project Closure Report
Lessons Learned Report
|  | Once Off |  |  |  |  | Once per Month
|  | Once per Week |  |  |  |  | On Update/Change
|  | Once per Fortnight |  |  |  |  | As Required

## Scope Statement (Rev 0.0)
Project Scope Statement
Project Name | 0 |  | Project No. | 0 | Revision No. | 0.0
1. Project Description [Describe in detail what the overall project output, service or result will be]
2. Project Deliverables [List the tangible, verifiable subproducts of the project]
3. Project Exclusions [List specific items or outputs that the project will not address or deliver]
4. Project Objectives [Describe the Time, Cost and Performance elements of the project]
5. Assumptions [Describe any assumptions being made which facilitate planning of the project]
6. Constraints [Describe any restrictions which may impact on the project objectives]
7. Project Team and Participants [List core team members and key participants such as divisions and/or contractors]
8. Planned Finish Date: |  | 10. PM: |  | 0
9. Planned Cost: |  | PM Signature:
Date:

## Schedule
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Project Name: | 0 |  |  |  |  | Legend:
A legend is in cells I2 through AC2. | Project No. | 0 |  |  |  |  | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date: |  | 2026-10-05
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | October | [27 empty] | November
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2026-10-05 to 2026-11-29
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Deliverable/Task | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Project Management Plan
| Project Charter | High Risk | John Smith | 100% | 2026-10-05 | 1
| Scope Statement | On Track |  | 75% | 2026-10-06 | 7
| WBS | Low Risk |  |  | 2026-10-09 | 8
| WBS Complete | Milestone |  |  | 2026-10-16 | 1 | bar: F
| Task 5 | Med Risk |  | 10% | 2026-10-11 | 6
Deliverable 2
| Task 1 | High Risk | Jane Doe | 60% | 2026-10-11 | 13
| Task 2 | On Track |  | 50% | 2026-10-13 | 9
| Task 3 | Low Risk |  | 33% | 2026-10-18 | 11
| Milestone 4 | Milestone |  |  | 2026-10-20 | 1 | bar: T
| Task 5 |  |  |  | 2026-10-21 | 24
Deliverable 3
| Task 1 | On Track |  |  | 2026-10-20 | 4
| Task 2 | Med Risk |  |  | 2026-10-23 | 14
| Task 3 | On Track |  |  | 2026-11-07 | 6
| Task 4 | Low Risk |  |  | 2026-11-12 | 1
| Task 5 | Milestone |  |  | 2026-11-13 | 1 | bar: F
Deliverable 4
| Task 1 |  |  |  | 2026-11-15 | 2
| Task 2 |  |  |  | 2026-11-17 | 5
| Task 3 | Goal |  |  | 2026-11-22 | 1 | S: 2
Task 4
Task 5
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## RAM
Responsibility Assignment Matrix | [5 empty] | Project Manager: | 0
Project Name: | 0 |  | Project No.: | 0 | Revision Date: |  | Revision Number: | 0
WBS No. | Deliverable/Work Package/Activity | Stakeholders
P = Participant; A = Accountable; R = Review Required; I = Input Required; S = Sign-Off Required

## Risk Register
Project Risk Register | [7 empty] | Project Manager: | 0
Project Name: |  | 0 |  | Project No.: | 0 | Revision Date: |  |  | Revision Number:
Risk No. | WBS No. | Risk Description & Effect | Risk Type | Prob. of Occur. (P) | Impact (I) | Risk Measure (P x I) | Risk Response | Person/Group Assigned | Control Risk Results | Open or Closed?
0
0
0
0
0
0
0

## Change Request Form
Project Change Request Form
Project Name | 0 |  |  |  | Project No. | 0
1. Change Requested [Reference Drawings, WBS Codes, SOP's, Documents etc.]
2. Reason for Change
Processed by: | [5 empty] | Date Rec'd
3. Estimated Performance Impact [Scope, Quality, Health & Safety)]
4. Estimated Schedule Impact
5. Estimated Cost Impact
Recommended For Approval: [The stakeholders listed below are likely to be affected by the requested change]
Name |  |  | Position | Approved? | Comments |  | Date
Result [Please specify the appropriate outcome with a 'Yes']
Approved: |  |  | Approved with Conditions: |  |  | Rejected:
Approved Conditional On
Rejected Because
PM Signature: |  |  |  | Sponsor Signature:
|  | 0 |  |  |  | 0
Date: |  |  |  | Date:

## Project Progress Report
Project Progress Report |  |  |  |  | Date:
Project Name: | 0 |  |  |  | Project No.: | 0
1. Overall Project Status [State position in the Lifecycle, whether On Track or Off Track etc.]
2. Project Deliverables [List the high level outputs, service or results of the project as referenced in the Scope Statement]
Deliverable Name |  |  | Progress [Mark % Complete from 0 to 100] |  | Status [On Track, Off Track] | Comments
3. Issues/Concerns [List any points or matters under discussion that may affect the progress of the project and need to be addressed]
4. Requests [List any information, meetings, reports, resources, access, permits, funds etc. that may be required]
5. Progress Comments [Describe general progress with respect to the overall project objectives as listed in the Scope Statement, what corrective action is being undertaken to get the project back on track etc.]
6. Activities for Review [List the activities which will continue or are scheduled to begin prior to the next Progress Meeting. These will be reviewed during the next Meeting]
Project Manager Signature:
0
Date:
Status Indicators: |  | On Track |  | Off Track, Recoverable |  |  | Off Track, Unrecoverable

## Project Closeout Report
Project Closeout Report |  |  | Date
Project Name | 0 |  | Project No. | 0
1. Evaluate the following:
1.1 Project Objectives [List how the project performed in terms of meeting the objectives - as outlined in the Scope Statement - under the headings, Time, Cost & Performance]
1.2 Project Deliverables [List how the project performed in terms of producing the delieverables - as outlined in the Scope Statement]
1.3 Communications [How were communications between the Project Team and other Stakeholders]
1.4 Procedures/Systems [How did the procedures, systems and processes work, eg. Did the Change Control System work, was the Scope Statement detail adequate?]
1.5 Project Management [Was the project managed well? Was the required documentation produced and available? Were identified resources available and adequately skilled/trained?]
2. What went well and could be implemented on future projects?
3. What could have been better and be improved on future projects?
Project Manager Signature:
0
Date:
Sponsor Signature:
0
Date:

## Requirements Info
Requirement Category | Some Category Examples
Functional requirements define what the solution must do | Technical Behaviour
Non-Functional requirements relate to system quality attributes | Reliability, User Experience (UX)
Business requirements define the outcomes the business needs to achieve | Business As Usual (BAU), Profit Contribution, Efficiency Improvement, Waste Reduction
Regulatory/Compliance requirements ensure adherence to mandatory rules | Health & Safety, Security, Privacy
Operational/Support requirements ensure ongoing service and continuity | Training, FAQs, Guidelines, Short Term Support Desk

## Risk Info
Project Objective | Impact Rating
| Very Low | Low | Moderate | High | Very High
| 1 | 2 | 3 | 4 | 5
Cost | Negligible cost increase | < 5% cost increase | 5 - 10% cost increase | 10 - 20% cost increase | > 20% cost increase
Time | Negligible schedule slippage | Schedule slippage < 5% | Schedule slippage 5 - 10% | Schedule slippage 10 - 20% | Schedule slippage > 20%
Performance | Negligible affect on performance | Minor affects on performance | Performance reduction requiring Sponsor/Client approval | Performance reduction unacceptable to Sponsor/Client | Product or deliverables unusable - 'Show Stopper'

## Gantt Info
About The Gantt Chart Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.

## Excel Tips
1 | Project Name, Number and Project Manager
Type the Project Name into Cell B2 on the Project Charter Template
If applicable type the Project No. into Cell H2
Type the Project Managers Name into Cell A42
Type the Sponsors Name into Cell F42
2 | To create more space in a document section (e.g. the Project Charter):
If you wish to create additional space for text in a section of the Project Charter such as
'1. Project Description':
With the Mouse or Laptop Touch Pad, Click on a Row Number on the Left Hand Side of the
spreadheet, Right Click and from the pop-up menu select Insert.
This action gives you an additional Blank Row. Repeat to add more.
3 | To create new lines of Text in a document section (e.g. the Project Charter):
After typing text into a section you may wish to add additional information but on a new
line. For example:
To create a New line in a section, hold down the Alt key on the keyboard and press the
Return or Enter key.
4 | To recreate Calculated Cells with Conditional Formatting (e.g. Risk Measure Field in the Risk Register)
After inserting additional rows to the Risk Register the Calculated and Conditional Formatted
properties (Red, Amber, Green) need to be copied to your new row.
Hover the mouse over the Fill Handle (the square in the bottom right-hand corner of a cell above
the newly inserted row). When you see the 'Cross-Hairs' click and drag to the cell below.
This action copies the formula and formatting from the selected cell to the cell below.

## Lists
Requirements Document |  | Reqs Doc/Issue Log/Risk Register |  | Stakeholder Register | Project Progress Report
Category | Status | Priority | Open/Closed | Category | Status
Business | Draft | Low | Open | Primary-Internal | On Track
Functional | In Review | Medium | Closed | Secondary-Internal | Off Track, Recoverable
Non-Functional | Approved | High |  | Primary-External | Off Track, Unrecoverable
Operational Support | Rejected |  |  | Secondary-External
Regulatory/Compliance |  |  |  | Tertiary-External