## Dash
[7 empty] | #VALUE! | Employee Training Roadmap
[8 empty] | Employee / Juicer / Manager Name_ ---> | New Employee / Manager | [64 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22
[8 empty] | Store Opening Date: ---> | 2026-04-13 |  | <-- Choose a Monday
[8 empty] | District Manager: ---> | [65 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25
[74 empty] | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | time axis 2026-04-06 to 2026-05-31
|  | Team Performance Dashboard |  |  |  |  | WBS | TASK | Description |  | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | [56 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | time axis 2026-04-06 to 2026-05-31
[7 empty] | 1 | NEW JUICER TRAINING | Ideal: 26 Hours OH | OH: Hours |  |  |  | - |  |  | -
[7 empty] | 1.1 | Onboarding & Introduction | Ideal: 1 Hour OH Training | 1 | Store Manager |  | 2026-04-06 | 2026-04-06 | 1 | 100% | 1 | [56 empty] | 1 | bar: 2026-04-06
FT Hours | PT Hours |  | New Employee / Manager |  |  |  | 1.2 | Food Station | Ideal: 4 Hours OH Training / 1st day OH / 3 Days Pratise / 1 Day Validation | 4 | Store Manager |  | 2026-04-13 | 2026-04-17 | 5 | 20% | 5 | 2026-04-13: 4 | [7 empty] | 4
37 | 15 |  | FULL NAME | START DATE (M/D/Y) | TENURE IN MONTHS | PT/FT | 1.3 | Juice Station | Ideal: 4 Hours OH Training / 1st day OH / 3 Days Pratise / 1 Day Validation | 4 | Store Manager |  | 2026-04-20 | 2026-04-24 | 5 | 20% | 5 | 2026-04-20: 4 | [14 empty] | 4
|  | STM | John Doe | 2022-08-01 | 43 | FT | 1.4 | Coffee Station | Ideal: 3 Hours OH Training / 1st day OH / 3 Days Pratise / 1 Day Validation | 3 | Store Manager |  | 2026-04-27 | 2026-05-01 | 5 | 20% | 5 | 2026-04-27: 3 | [21 empty] | 3
|  | A.STM |  |  |  |  | 1.5 | Till Station | Ideal: 2 Hours OH Training / 1st day OH / 2 Days Pratise / 1 Day Validation | 2 | Store Manager |  | 2026-05-04 | 2026-05-06 | 3 | 35% | 3 | 2026-05-04: 2 | [28 empty] | 2
|  |  | Peter |  | 12 | FT | 1.6 | Closing Shift | Ideal: 6 Hours OH Training / 1st day 3 Hous OH / 2nd day 3 hours OH | 6 | Store Manager |  | 2026-04-16 | 2026-04-17 | 2 | 100% | 2 | 2026-04-16: 3; 2026-04-17: 3 | [10 empty] | 3 | 3
|  | SM |  |  |  |  | 1.7 | Open Shift | Ideal: 6 Hours OH Training | 6 | Store Manager |  | 2026-04-23 | 2026-04-24 | 2 | 100% | 2 | 2026-04-23: 3; 2026-04-24: 3 | [17 empty] | 3 | 3
[7 empty] | 1.8 | Performance Shift | 1 Full Day BTC |  | Store Manager |  | 2026-05-13 | 2026-05-13 | 1 | 0% | 1
|  | Grad |  |  |  |  | 1.9 |  |  |  | Store Manager |  |  |  |  | 0% | -
[7 empty] | 1.10 | Actual Planned Training Hours |  | 26 | Store Manager |  |  |  |  | 0% | -
|  | JQ Juicers |  |  |  |  | 1.11 | Budget Training Hours |  | 26 | Store Manager |  |  |  |  | 0% | -
[7 empty] | 2 | SHIFT MANAGER (15 Hours) | Ideal: 15 Hours OH |  |  |  |  | - |  |  | -
[7 empty] | 2.1 | Role Introduction & Align Training Plan |  | 1 | Store Manager |  | 2026-04-06 | 2026-04-06 | 1 | 100% | 1 | [56 empty] | 1 | bar: 2026-04-06
[7 empty] | 2.2 | JOE Management |  | 1 | Store Manager |  | 2026-04-06 | 2026-04-06 |  | 100% | 1 | [56 empty] | 1 | bar: 2026-04-06
[7 empty] | 2.3 | Hell Week |  | 0 | Store Manager |  | 2026-04-13 | 2026-04-17 | 5 | 0% | 5
[7 empty] | 2.4 | Cleaning Day |  | 1 | Store Manager |  | 2026-04-13 | 2026-04-13 | 1 | 100% | 1 | [63 empty] | 1 | bar: 2026-04-13
[7 empty] | 2.5 | Food & Bar Safety |  | 1 | Store Manager |  | 2026-04-13 | 2026-04-13 |  | 100% | 1 | [63 empty] | 1 | bar: 2026-04-13
[7 empty] | 2.6 | Count & Stock Management | Focus on Delivery sequence and execution | 1 | Store Manager |  | 2026-04-20 | 2026-04-20 |  | 100% | 1 | [70 empty] | 1 | bar: 2026-04-20
[7 empty] | 2.7 | Take Delivery and Counts |  | 0 | Store Manager |  | 2026-04-20 | 2026-04-24 | 5 | 0% | 5
[7 empty] | 2.8 | Auto-count |  | 1 | Store Manager |  | 2026-04-21 | 2026-04-21 |  | 100% | 1 | [71 empty] | 1 | bar: 2026-04-21
[7 empty] | 2.9 | Store Task Manual |  | 1 | Store Manager |  | 2026-04-21 | 2026-04-21 |  | 100% | 1 | [71 empty] | 1 | bar: 2026-04-21
[7 empty] | 2.10 | 1st Validation |  | 0 | Store Manager |  | 2026-04-24 | 2026-04-24 |  | 0% | 1
[7 empty] | 2.11 | Coffee Management & Maintenance |  | 1 | Store Manager & Local Facility |  | 2026-04-27 | 2026-04-27 |  | 100% | 1 | [77 empty] | 1 | bar: 2026-04-27
[7 empty] | 2.12 | Optics & Activity Plan |  | 1 | Store Manager |  | 2026-04-27 | 2026-04-27 |  | 100% | 1 | [77 empty] | 1 | bar: 2026-04-27
[7 empty] | 2.13 | Show time |  | 0 | Store Manager |  | 2026-04-29 | 2026-04-29 |  | 100% | 1 | 2026-04-29: 0 | [23 empty] | 0
[7 empty] | 2.14 | Becoming a Trainer |  | 1 | Store Manager |  | 2026-05-04 | 2026-05-04 |  | 100% | 1 | [84 empty] | 1 | bar: 2026-05-04
[7 empty] | 2.15 | 2nd Validation |  | 0 | Store Manager |  | 2026-05-06 | 2026-05-06 |  | 0% | 1
[7 empty] | 2.16 | Activating on the go |  | 1 | Store Manager |  | 2026-05-10 | 2026-05-10 |  | 100% | 0 | [90 empty] | 1 | bar: 2026-05-10
[7 empty] | 2.17 | Br-Behavior Management |  | 1 | Store Manager |  | 2026-05-11 | 2026-05-11 |  | 100% | 1 | [91 empty] | 1 | bar: 2026-05-11
[7 empty] | 2.18 | Elderflower Management |  | 1 | Store Manager |  | 2026-05-11 | 2026-05-11 |  | 100% | 1 | [91 empty] | 1 | bar: 2026-05-11
[7 empty] | 2.19 | Commercial Management |  | 1 | Store Manager |  | 2026-05-11 | 2026-05-11 |  | 100% | 1 | [91 empty] | 1 | bar: 2026-05-11
[7 empty] | 2.20 | Manager Shift |  | 1 | Store Manager |  | 2026-05-15 | 2026-05-15 |  | 100% | 1 | [95 empty] | 1 | bar: 2026-05-15
[7 empty] | 2.21 | Validation & Exam Period |  |  | Store Manager |  | 2026-05-18 | 2026-05-22 | 5 | 0% | 5
[7 empty] | 2.22 |  |  |  | Store Manager |  |  | - |  | 0% | -
|  | NEW Juicers |  |  |  |  | 2.23 | Actual Planned Training Hours |  | 15 | Store Manager |  |  | - |  | 0% | -
[7 empty] | 2.24 | Budget Training Hours |  | 15 | Store Manager |  |  | - |  | 0% | -
[7 empty] | 3 | ASSISTANT STORE MANAGER (15 Hours OH) | Ideal: 15 Hours OH |  |  |  |  | - |  |  | -
[7 empty] | 3.1 | Introduction to MB 2.0 |  | 1 | District Manager |  | 2026-04-06 | 2026-04-06 |  | 100% | 1 | [56 empty] | 1 | bar: 2026-04-06
[7 empty] | 3.2 | Basic Shiftplanning |  | 2 | District Manager |  | 2026-04-08 | 2026-04-08 |  | 100% | 1 | 2026-04-08: 2 |  |  | 2
[7 empty] | 3.3 | Advanced: Optics & Activity Plan |  | 0 | District Manager |  | 2026-04-08 | 2026-04-08 |  | 100% | 1 | 2026-04-08: 0 |  |  | 0
[7 empty] | 3.4 | Food & Bar Safety |  | 1 | District Manager |  | 2026-04-10 | 2026-04-10 |  | 100% | 1 | [60 empty] | 1 | bar: 2026-04-10
[7 empty] | 3.5 | Critical Thinking |  | 1 | District Manager |  | 2026-04-10 | 2026-04-10 |  | 100% | 1 | [60 empty] | 1 | bar: 2026-04-10
[7 empty] | 3.6 | Supply Chain Management |  | 2 | District Manager |  | 2026-04-13 | 2026-04-13 |  | 100% | 1 | 2026-04-13: 2 | [7 empty] | 2
[7 empty] | 3.7 | Store Maintenance |  | 1 | District Manager |  | 2026-04-15 | 2026-04-15 |  | 100% | 1 | [65 empty] | 1 | bar: 2026-04-15
[7 empty] | 3.8 | Pipeline |  | 1 | District Manager |  | 2026-04-27 | 2026-04-27 |  | 100% | 1 | [77 empty] | 1 | bar: 2026-04-27
[7 empty] | 3.9 | Virtue-based Leadership |  | 1 | District Manager |  | 2026-04-27 | 2026-04-27 |  | 100% | 1 | [77 empty] | 1 | bar: 2026-04-27
[7 empty] | 3.10 | Employee Engagement |  | 1 | District Manager |  | 2026-04-27 | 2026-04-27 |  | 100% | 1 | [77 empty] | 1 | bar: 2026-04-27
|  |  | 0 |  |  |  | 3.11 | Onboarding |  | 1 | District Manager |  | 2026-04-29 | 2026-04-29 |  | 100% | 1 | [79 empty] | 1 | bar: 2026-04-29
|  | Number of staff | 2 |  |  |  | 3.12 | Torch Barrier |  | 1 | District Manager |  | 2026-05-05 | 2026-05-05 |  | 100% | 1 | [85 empty] | 1 | bar: 2026-05-05
[7 empty] | 3.13 | Brand Behavior |  | 1 | District Manager |  | 2026-05-05 | 2026-05-05 |  | 100% | 1 | [85 empty] | 1 | bar: 2026-05-05
|  |  | 2026-04-13 |  | (INSERT 2nd MONTH) |  | 3.14 | Store Performance - BB |  | 1 | District Manager |  | 2026-05-11 | 2026-05-11 |  | 100% | 1 | [91 empty] | 1 | bar: 2026-05-11
[7 empty] | 3.15 |  |  |  | District Manager |  |  | - |  | 0% | -
|  | DIFFERENCE IN FTE | 296 |  | 0 |  | 3.16 | Actual Planned Training Hours |  | 15 | District Manager |  |  | - |  | 0% | -
|  |  | 0 |  | 0 |  | 3.17 | Budget Training Hours |  | 15 | District Manager |  |  | - |  | 0% | -
|  |  | 296 |  | 0 |  | 4 | STORE MANAGER | Ideal: 20% OH BTC ratio During Training | OH: Hours |  |  |  | - |  |  | -
[7 empty] | 4.1 | Introduction to MB 2.0 |  | 1 | District Manager |  | 2026-04-06 | 2026-04-06 |  | 100% | 1 | [56 empty] | 1 | bar: 2026-04-06
[7 empty] | 4.2 | Introduction 'Store Performance': PNL & BB |  |  | District Manager |  | 2026-04-06 | 2026-04-06 |  | 100% | 1 | 2026-04-06: 0 | 0
[7 empty] | 4.3 | Critical Thinking |  | 1 | District Manager |  | 2026-04-13 | 2026-04-13 |  | 100% | 1 | [63 empty] | 1 | bar: 2026-04-13
[7 empty] | 4.4 | Food & Bar Safety |  | 1 | District Manager |  | 2026-04-15 | 2026-04-15 |  | 100% | 1 | [65 empty] | 1 | bar: 2026-04-15
[7 empty] | 4.5 | Store Maintenance |  | 2 | District Manager & Local Facility Manager |  | 2026-04-22 | 2026-04-22 |  | 100% | 1 | 2026-04-22: 2 | [16 empty] | 2
[7 empty] | 4.6 | Operational Requirements Validation |  |  | District Manager |  | 2026-04-24 | 2026-04-24 |  | 0% | 1
[7 empty] | 4.7 | Pipeline, Mentoring & Value-based Leadership (3 modules) |  | 2 | District Manager |  | 2026-04-28 | 2026-04-28 |  | 100% | - | 2026-04-28: 2 | [22 empty] | 2
[7 empty] | 4.8 | Follow up |  | 1 | District Manager |  | 2026-05-05 | 2026-05-05 |  | 100% | 1 | [85 empty] | 1 | bar: 2026-05-05
[7 empty] | 4.9 | Communication |  | 1 | District Manager |  | 2026-05-05 | 2026-05-05 |  | 100% | 1 | [85 empty] | 1 | bar: 2026-05-05
[7 empty] | 4.10 | Emplyee Engagement Validation |  |  | District Manager |  | 2026-05-08 | 2026-05-08 |  | 100% | 1 | 2026-05-08: 0 | [32 empty] | 0
[7 empty] | 4.11 | Torch Barrier |  | 1 | District Manager |  | 2026-05-13 | 2026-05-13 |  | 100% | 1 | [93 empty] | 1 | bar: 2026-05-13
[7 empty] | 4.12 | Brand Behavior |  | 1 | District Manager |  | 2026-05-13 | 2026-05-13 |  | 100% | 1 | [93 empty] | 1 | bar: 2026-05-13
[7 empty] | 4.13 | Store Performance - BB |  | 2 | Operational Manager |  | 2026-05-20 | 2026-05-20 |  | 100% | 1 | 2026-05-20: 2 | [44 empty] | 2
[7 empty] | 4.14 | Strategic Thinking |  | 2 | Operational Manager |  | 2026-05-20 | 2026-05-20 |  | 100% | 1 | 2026-05-20: 2 | [44 empty] | 2
[7 empty] | 4.15 | 360 Store Review |  |  | District Manager |  | 2026-05-25 | 2026-05-25 |  | 100% | 1 | 2026-05-25: 0 | [49 empty] | 0
[7 empty] | 4.16 | Exam Week |  |  | STM Preparation |  | 2026-05-25 | 2026-05-29 | 5 | 0% | 5
[7 empty] | 4.17 | Exam & Business Review |  | 1 | District Manager & Operational Manager |  | 2026-05-29 | 2026-05-29 |  | 100% | 1 | [109 empty] | 1 | bar: 2026-05-29
[7 empty] | 5 | STORE MANAGER (Support Functions)
[7 empty] | 5.1 | Shift Planning (1–3) |  | 7 | Operational Planning |  | 2026-04-13 | 2026-04-24 | 12 | 0% | 10
[7 empty] | 5.2 | Supply Chain Management |  | 2 | Supply Chain |  | 2026-04-20 | 2026-04-24 | 5 | 0% | 5
[7 empty] | 5.3 | [6 empty] | - |  | 0% | -
[7 empty] | 5.4 | Employee Engagement |  | 4 | HR |  | 2026-04-27 | 2026-05-01 | 5 | 0% | 5
[7 empty] | 5.5 | Development Talks |  |  | Recruitment |  | 2026-04-27 | 2026-05-01 | 5 | 0% | 5
[7 empty] | 5.6 | Onboarding |  | 4 | HR |  | 2026-05-04 | 2026-05-08 | 5 | 0% | 5
[7 empty] | 5.7 | Recruitment |  |  | HR |  | 2026-05-04 | 2026-05-08 | 5 | 0% | 5
[7 empty] | 5.8 | Disciplinary Actions |  |  | HR |  | 2026-05-04 | 2026-05-08 | 5 | 0% | 5
[7 empty] | 5.9 | [6 empty] | - |  | 0% | -
[7 empty] | 5.10 | Exam Week |  |  | Operational Manager |  | 2026-05-25 | 2026-05-29 | 5 | 0% | 5
[7 empty] | 5.11 | Exam |  |  | Operational Manager |  | 2026-05-29 | 2026-05-29 |  | 0% | 1
[7 empty] | 5.12 | [6 empty] | - |  | 0% | -
[7 empty] | 5.13 | [6 empty] | - |  | 0% | -
[7 empty] | 5.14 | [6 empty] | - |  | 0% | -
[7 empty] | 5.15 | [6 empty] | - |  | 0% | -
[7 empty] | 5.16 | [6 empty] | - |  | 0% | -
[7 empty] | 5.17 | Actual Planned Training Hours |  | 33 |  |  |  | - |  | 0% | -
[7 empty] | 5.18 | Budget Training Hours |  | 33 |  |  |  | - |  | 0% | -
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
[7 empty] | 1 | [ Level 1 Task or Phase ] | [5 empty] | - |  |  | -
[7 empty] | 1.1 | . [ Level 2 Task ] | [5 empty] | - |  |  | -
[7 empty] | 1.1.1 | . . [ Level 3 Task ] | [5 empty] | - |  |  | -
[7 empty] | 1.1.1.1 | . . . [ Level 4 Task ] | [5 empty] | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on S8: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on T8: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on W8: Task Lead Enter the name of the Task Lead in this column.
Note on X8: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on Y8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on Z8: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on AA8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on AB8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on AC8: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Control
|  | Week day nr | Variable | Week day | 1 | January
Start Planning (12 weeks) | 2026-04-06 | 7 | -5 | Saturday | 2 | February
Start Planning week | 15 | 6 | -4 | Friday | 3 | March | [5 empty] | Week 15
Start Planning day | 2 | 5 | -3 | Thursday | 4 | April |  | 2026-03-01
Correct date | 2026-04-06 | 4 | -2 | Wednesday | 5 | May | [5 empty] | 2026-04-06
|  | 3 | -1 | Tuesday | 6 | June | [5 empty] | 2026-04-06
|  | 2 | 0 | Monday | 7 | July
|  | 1 | 1 | Sunday | 8 | August | NEW JUICER TRAINING
[5 empty] | 9 | September | Onboarding & Introduction |  | 46118 | 46137 | 20
[5 empty] | 10 | October | Food Station |  |  |  | 5
[5 empty] | 11 | November | Juice Station |  | 0 |  | 5
[5 empty] | 12 | December | Coffee
[9 empty] | 46118 |  | 30
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 46118 |  | 10
[9 empty] | 46118 |  | 10
[9 empty] | 46118 |  | 10
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[8 empty] | Order in trash bins and order pick up (decide on frequency) if relevant. Company depends on location. | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 0 |  | 5
[9 empty] | 46118 |  | 5
[9 empty] | 0 |  | 5