## Timeline
Whether you’re reviewing dailies, setting up a virtual video village, or anything else, Evercast is a production staple for the top studios and production companies in the business. Video conference with your team as you stream content from live cameras, media files, or any creative software in 4K/60fps with ultra low latency (<100ms globally). Each virtual room offers the ability to draw, chat, take notes, and record so you can not only discuss every detail, but clearly document every piece of feedback.
Department | Task | Assigned To | Status | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05
Directing / Production Office
| Shot list & storyboards finalized | Director | Completed
| Daily call sheet distribution | Production Coordinator | In Progress
| Production reports | Production Coordinator | Not Started
Assistant Director Team
| Crew call times | 1st AD | Not Started
| Talent call times | 2nd AD | Not Started
| Safety meetings | 1st AD | Not Started
Camera / Cinematography
| Camera prep & lens tests | Director of Photography | Not Started
| Pre-light day(s) | Director of Photography | Not Started
| Shooting days (by week/block) | Director of Photography | Not Started
Grip & Electric
| Lighting setup / rigging | Gaffer | Not Started
| Wrap-out dates | Gaffer | Not Started
Sound Department
| On-set audio recording schedule | Sound Mixer | Not Started
| Wild tracks / room tone days | Sound Mixer | Not Started
Art Department
| Set builds completed | Production Designer | Not Started
| Set dressing days | Art Director | Not Started
| Strike dates | Production Designer | Not Started
Wardrobe, Hair & Makeup
| Costume fittings | Wardrobe Supervisor | Not Started
| Hair & makeup call times | Key Hair & Makeup | Not Started
Talent
| Principal photography start | Producer | Not Started
| Final wrap day | Producer | Not Started
Locations
| Permits secured | Location Manager | Not Started
| Location prep days | Location Manager | Not Started
| Shoot days at each location | Location Manager | Not Started
| Location strike / wrap | Location Manager | Not Started
Transportation & Logistics
| Company moves | Transportation Captain | Not Started
Transportation & Logistics
| Catering start | Caterer | Not Started

## Shooting Schedule
Scene | Synopsis | INT/EXT & Day/Night | Set / Location | Shoot Location | Cast | Pages | Est. Time | Start Time | Notes
1 | Alex rushes into the coffee shop, scanning for someone. | INT – Day | Coffee Shop – Front Counter | Downtown Café | ALEX, BARISTA | 0.8 | 2h |  | Need clearance for exterior establishing shot.
2 | Jordan waits by the window, checking phone repeatedly. | INT – Day | Coffee Shop – Window Table | Downtown Café | JORDAN | 0.5 | 1.5h |  | Quiet background required, minimal extras.
3 | Alex and Jordan argue about the missing notebook. | INT – Day | Coffee Shop – Back Booth | Downtown Café | ALEX, JORDAN | 1.4 | 3h |  | Dialogue-heavy; plan multiple angles.
4 | Car pulls up quickly outside the shop. | EXT – Day | Street – Curbside | Suburban Street | ALEX, DRIVER | 0.6 | 1.5h |  | Need vehicle stunt driver.
5 | Briefcase handoff takes place in a dimly lit parking lot. | EXT – Night | Parking Lot | Warehouse District | JORDAN, DEALER | 1.1 | 3h |  | Lighting setup required for shadows/mood.
6 | Alex calls Maya in desperation. | INT – Night | Apartment – Living Room | Studio Backlot | ALEX, MAYA (voice on phone) | 0.7 | 2h |  | Simple coverage; one setup.
7 | Maya discovers the notebook hidden in her desk drawer. | INT – Night | Apartment – Bedroom | Studio Backlot | MAYA | 0.9 | 2h |  | Close-up insert shots needed.
8 | Chase sequence through narrow alleyways. | EXT – Night | Alley – Exterior | Old Town | ALEX, DEALER, STUNT EXTRAS | 2.2 | 5h |  | Requires stunt coordinator & police permit.

## Tasks & Assignments
Department | Task | Assigned To | Start Date | End Date | Duration (days) | Status | % Done | Dependencies | Notes
Directing / Production Office | Shot List & Storyboards Finalized | Director | 2025-04-01 | 2025-04-03 | 3 | Completed | 100% | -
Directing / Production Office | Distribute Daily Call Sheets | Production Coordinator | 2025-04-04 | 2025-04-30 | 27 | In Progress | 50% | Shot List & Storyboards Finalized | Ongoing task during shoot
Directing / Production Office | Submit Daily Production Reports | Production Coordinator | 2025-04-04 | 2025-04-30 | 27 | Not Started | 0% | Distribute Daily Call Sheets | Ongoing task
Assistant Director Team | Crew Call Times | 1st Assistant Director | 2025-04-04 | 2025-04-30 | 27 | Not Started | 0% | Distribute Daily Call Sheets
Assistant Director Team | Talent Call Times | 2nd Assistant Director | 2025-04-04 | 2025-04-30 | 27 | Not Started | 0% | Crew Call Times
Assistant Director Team | Safety Meetings | 1st Assistant Director | 2025-04-04 | 2025-04-30 | 27 | Not Started | 0% | Crew Call Times
Camera / Cinematography | Camera Package Prep & Lens Tests | Director of Photography | 2025-04-01 | 2025-04-02 | 2 | Completed | 100% | -
Camera / Cinematography | Pre-light Day(s) | Director of Photography | 2025-04-03 | 2025-04-03 | 1 | Not Started | 0% | Camera Package Prep & Lens Tests
Camera / Cinematography | Shooting Block 1 | Director of Photography | 2025-04-04 | 2025-04-10 | 7 | Not Started | 0% | Pre-light Day(s)
Grip & Electric | Lighting Setup / Rigging | Gaffer | 2025-04-03 | 2025-04-10 | 8 | Not Started | 0% | Pre-light Day(s)
Grip & Electric | Wrap-out | Gaffer | 2025-04-29 | 2025-04-30 | 2 | Not Started |  | Shooting Block 1
Sound Department | Mic Tests & Prep | Sound Mixer | 2025-04-02 | 2025-04-02 | 1 | Completed | 100% | -
Sound Department | Record Production Sound | Sound Mixer | 2025-04-04 | 2025-04-30 | 27 | Not Started | 0% | Mic Tests & Prep
Sound Department | Capture Wild Tracks / Room Tone | Sound Mixer | 2025-04-15 | 2025-04-15 | 1 | Not Started | 0% | Record Production Sound
Art Department | Set Builds Completed | Production Designer | 2025-03-25 | 2025-03-31 | 7 | Completed | 100% | -
Art Department | Set Dressing Days | Art Director | 2025-04-01 | 2025-04-03 | 3 | In Progress | 50% | Set Builds Completed
Art Department | Strike / Wrap Sets | Production Designer | 2025-04-29 | 2025-04-30 | 2 | Not Started | 0% | Shooting Block 1
Wardrobe, Hair & Makeup | Costume Fittings | Wardrobe Supervisor | 2025-03-28 | 2025-04-02 | 6 | Completed | 100% | -
Wardrobe, Hair & Makeup | Daily Hair & Makeup Prep | Key Hair & Makeup | 2025-04-04 | 2025-04-30 | 27 | Not Started | 0% | Costume Fittings
Talent | Principal Photography Start | Producer | 2025-04-04 | 2025-04-04 | 1 | Not Started | 0% | Crew Call Times
Talent | Final Wrap Day | Producer | 2025-04-30 | 2025-04-30 | 1 | Not Started | 0% | Shooting Block 1
Locations | Permits Secured | Location Manager | 2025-03-20 | 2025-03-27 | 8 | Completed | 100% | -
Locations | Location Prep Days | Location Manager | 2025-03-28 | 2025-04-02 | 6 | Not Started | 0% | Permits Secured
Locations | Shoot Days (per location) | Location Manager | 2025-04-04 | 2025-04-28 | 25 | Not Started | 0% | Location Prep Days
Locations | Strike / Wrap Locations | Location Manager | 2025-04-29 | 2025-04-30 | 2 | Not Started | 0% | Shoot Days (per location)
Transportation & Logistics | Company Moves | Transportation Captain | 2025-04-10 | 2025-04-20 | 11 | Not Started | 0% | Shooting Block 1
Catering & Craft Services | Catering Start | Caterer | 2025-04-04 | 2025-04-04 | 1 | Completed | 100% | Crew Call Times

## Budget
Department | Category | Item | Estimated Cost | Actual Cost | Variance | Vendor/Provider | Payment Status | Notes
Cast | Personnel | Talent (Lead + Supporting + Extras) | 26000 | 10000 | 16000 | Agencies / Casting | Partial | Consolidated talent costs
Crew | Personnel | Director & AD Team | 13000 | 3500 | 9500 | Prod Office | Partial
Crew | Personnel | Camera Dept. (DP & ACs) | 9000 | 3000 | 6000 | Camera Team | Partial
Crew | Personnel | Sound Dept. | 4000 | 0 | 4000 | Sound Team | Not Paid
Crew | Personnel | G&E Dept. | 8000 | 0 | 8000 | G&E Team | Not Paid
Crew | Personnel | Art Dept. & Wardrobe/HMU | 11500 | 0 | 11500 | Art & HMU Teams | Not Paid | Merged Art + Wardrobe/HMU
Equipment | Rental | Camera Package (incl. lenses/accessories) | 8500 | 6000 | 2500 | Camera Rental House | Paid | Merged lenses/accessories
Equipment | Rental | Lighting Package | 5500 | 0 | 5500 | Lighting Rental | Not Paid
Equipment | Rental | Grip Package | 4500 | 0 | 4500 | Grip Rental | Not Paid
Equipment | Rental | Sound Equipment | 2000 | 0 | 2000 | Audio Rental | Not Paid
Locations | Permits | City/Agency Permits | 1800 | 0 | 1800 | City Film Office | Not Paid
Locations | Rental | Location Rentals (incl. site fees/utilities) | 8600 | 0 | 8600 | Location Owner | Not Paid | Merged utilities + site fees
Transportation | Vehicles | Equipment Trucks | 2500 | 0 | 2500 | Truck Rental | Not Paid
Transportation | Fuel | Fuel / Mileage | 1500 | 0 | 1500 | Various | Not Paid
Catering | Catering | Meals | 4000 | 0 | 4000 | Caterer | Not Paid | Dropped separate craft service
Insurance & Contingency | Insurance | Production Insurance | 3000 | 3000 | 0 | Insurance Co. | Paid
Insurance & Contingency | Contingency | Contingency Fund | 5000 | 0 | 5000 | - | Not Paid | Reserve for overruns
TOTAL BUDGET |  |  | 118400 | 25500 | 92900 | Remaining Budget: | 78.46%
Department Summaries | Estimated Cost | Actual Cost | Percentage Used
Cast | 26000 | 10000 | 38.46%
Crew | 45500 | 6500 | 14.29%
Equipment | 20500 | 6000 | 29.27%
Locations | 10400 | 0 | 0%
Transportation | 4000 | 0 | 0%
Catering | 4000 | 0 | 0%
Insurance & Contingency | 8000 | 3000 | 37.5%