## Timeline
Whether you’re reviewing sequences, VFX shots, music, or any other piece of the puzzle, Evercast has become a post-production staple for the top studios and editors in the business. Video conference with your team as you stream content from Media Composer, Pro Tools, Premiere, Maya, or any other software in 4K, HDR, 10-bit 4:4:4 with ultra low latency (<100ms). Each virtual room offers the ability to draw, chat, take notes, and record so you can not only discuss every detail, but clearly document every piece of feedback.
Department | Task | Assigned To | Status | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-06-17 | 2025-06-24 | 2025-07-01 | 2025-07-08 | 2025-07-15 | 2025-07-22 | 2025-07-29 | 2025-08-05
Editorial
| Assembly Cut | Editor | Completed
| Rough Cut | Editor | In Progress
| Fine Cut | Editor | Not Started
| Picture Lock | Editor | Not Started
| Final Cut | Editor | Not Started
Visual Effects
| VFX Prep/Breakdown | VFX Artist | Not Started
| Track/Match/Roto/Key | VFX Artist | Not Started
| Asset Creation | VFX Artist | Not Started
| Simulation/FX/Dynamics | VFX Artist | Not Started
| Compositing/Rendering | VFX Artist | Not Started
| Final Adjustments/QC | VFX Artist | Not Started
| VFX Approval | VFX Supervisor | Not Started
| VFX Delivery | VFX Supervisor | Not Started
Sound
| Dialogue Cleanup/ADR/Sync | Dialogue Editor | Not Started
| SFX Editing | SFX Editor | Not Started
| Sound Design | Sound Designer | Not Started
| Music Composition | Composer | Not Started
| Music Editing | Music Editor | Not Started
| Mixing (Balance/Pan/EQ/FX) | Mixer | Not Started
| Sync/Audio Reference/Delivery | Mixer | Not Started
Color
| Color Prep/Ingestion | Colorist | Not Started
| Color Correction | Colorist | Not Started
| Masking/Tracking | Colorist | Not Started
| Look Development | Colorist | Not Started
| Final Adjustments | Colorist | Not Started
| Rendering & QC | Colorist | Not Started
Finishing
| Titles, Graphics, Credits | Designer | Not Started
| Final VFX Integration | VFX Supervisor | Not Started
| Final Color Grade/Mastering | Colorist | Not Started
| Final Mix/Master | Sound Supervisor | Not Started
| Final QC |  | Not Started
| Deliverable Production |  | Not Started
| Approval & Distribution |  | Not Started

## Tasks & Assignments
Department | Task | Assigned To | Start Date | End Date | Duration | Status | % Done | Dependencies | Notes
Editorial | Assembly Cut | Lead Editor | 2025-04-01 | 2025-04-07 | 7 days | Completed | 100% | -
Editorial | Rough Cut |  | 2025-04-08 | 2025-04-15 | 8 days | In Progress | 50% | Assembly Cut
Editorial | Fine Cut |  | 2025-04-16 | 2025-04-21 | 6 days | Not Started | 0% | Rough Cut
Editorial | Picture Lock |  |  |  |  | Not Started |  | Fine Cut
Editorial | Final Cut |  |  |  |  | Not Started
VFX | VFX Breakdown | VFX Supervisor | 2025-04-10 | 2025-04-14 | 5 days | Not Started | 30% | Rough Cut
VFX | Track/Match/Roto/Key |  |  |  |  | Not Started
VFX | Asset Creation |  |  |  |  | Not Started
VFX | Simulation/FX/Dynamics |  |  |  |  | Not Started
VFX | Compositing/Rendering |  |  |  |  | Not Started
VFX | Final Adjustments/QC |  |  |  |  | Not Started
VFX | VFX Approval |  |  |  |  | Not Started
VFX | VFX Delivery |  |  |  |  | Not Started
Sound | Dialogue Cleanup/ADR/Sync | Sound Editor | 2025-04-16 | 2025-04-20 | 5 days | Not Started | 0% | Fine Cut
Sound | SFX Editing |  |  |  |  | Not Started
Sound | Sound Design |  |  |  |  | Not Started
Sound | Music Composition |  |  |  |  | Not Started
Sound | Music Editing |  |  |  |  | Not Started
Sound | Mixing (Balance/Pan/EQ/FX) |  |  |  |  | Not Started
Sound | Sync/Audio Reference/Delivery |  |  |  |  | Not Started
Color | Color Prep | Colorist | 2025-04-22 | 2025-04-22 | 1 day | Not Started | 0% | Picture Lock
Color | Color Prep/Ingestion |  |  |  |  | Not Started
Color | Color Correction |  |  |  |  | Not Started
Color | Masking/Tracking |  |  |  |  | Not Started
Color | Look Development |  |  |  |  | Not Started
Color | Final Adjustments |  |  |  |  | Not Started
Color | Rendering & QC |  |  |  |  | Not Started
Finishing | Titles, Graphics, Credits | Designer |  |  |  | Not Started
Finishing | Final VFX Integration |  |  |  |  | Not Started
Finishing | Final Color Grade/Mastering |  |  |  |  | Not Started
Finishing | Final Mix/Master |  |  |  |  | Not Started
Finishing | Final QC |  |  |  |  | Not Started
Finishing | Deliverable Production |  |  |  |  | Not Started
Finishing | Approval & Distribution |  |  |  |  | Not Started

## Budget
Department | Category | Item | Estimated Cost | Actual Cost | Variance | Vendor/Provider | Payment Status | Notes
Editorial | Software | Editing License | 1200 | 1200 | 0 | Adobe | Paid
Editorial | Personnel | Editor Fees | 6000 | 3000 | 3000 | John Smith | Partial | 50% paid
Editorial | Hardware | Hard Drives | 800 | 950 | -150 | Tech Shop | Paid | Over budget
VFX | Software | VFX Software | 1500 | 1500 | 0 | Blackmagic | Paid
VFX | Personnel | VFX Artists | 8000 | 0 | 8000 | VFX Team | Not Paid | Pending work
Sound | Facility | Studio Rental | 3500 | 0 | 3500 | Audio Post | Not Paid
TOTAL BUDGET |  |  | 21000 | 6650 | 14350 | Remaining Budget: | 68.33%
Department Summaries | Estimated Cost | Actual Cost | Percentage Used
Editorial | 8000 | 5150 | 35.62%
VFX | 9500 | 1500 | 84.21%
Sound | 3500 | 0 | 100%