## Checklist
Step # | Phase | Task | Owner | Due date | Status | Notes | Rollback plan
1 | Plan | Define scope and success |  |  | Not started |  | Not applicable
1.1 | Plan | List every object to migrate, with record counts and the date range for each |  |  | Not started
1.2 | Plan | Record what is staying behind in the source system and why |  |  | Not started
1.3 | Plan | Write the success measures (for example record counts per object and named users signing off) |  |  | Not started
1.4 | Plan | Agree the cutover date and the freeze window for changes in the source |  |  | Not started
2 | Prepare | Back up source and target |  |  | Not started |  | Backups are the restore point for every step below
2.1 | Prepare | Export the source data untouched, before any cleanup |  |  | Not started |  | Re-run transformations from this copy if a cleanup goes wrong
2.2 | Prepare | Back up the target org records the load will update or relate to |  |  | Not started |  | Restore previous field values from this backup after a bad update
2.3 | Prepare | Store backups somewhere the project team can reach, and note where |  |  | Not started
3 | Plan | Map every field |  |  | Not started |  | Not applicable
3.1 | Plan | Map each source column to an object and field API name (for example Account.Industry) |  |  | Not started
3.2 | Plan | List required fields, picklist values, record types and record owners per object |  |  | Not started
3.3 | Plan | Decide how combined source rows split into separate Salesforce objects |  |  | Not started
3.4 | Plan | Get the field map signed off by the business owner |  |  | Not started
4 | Prepare | Add external IDs |  |  | Not started |  | External IDs identify exactly which records a load created or changed
4.1 | Prepare | Create an External ID field (for example Legacy_Id__c) on every object you load |  |  | Not started
4.2 | Prepare | Fill it with the source system's ID in every file |  |  | Not started
4.3 | Prepare | Use upsert on the external ID so a re-run updates records instead of duplicating them |  |  | Not started
5 | Plan | Set the load order |  |  | Not started |  | Delete in reverse load order: children first, then parents
5.1 | Plan | Users and reference data first (for example Product2 and PricebookEntry) |  |  | Not started
5.2 | Plan | Then Account, Contact, Opportunity and OpportunityLineItem |  |  | Not started
5.3 | Plan | Then Task, Event and files |  |  | Not started
5.4 | Plan | Note any objects that point at each other and how you will update the second lookup |  |  | Not started
6 | Prepare | Clean and transform the data |  |  | Not started |  | Keep the untouched source export from step 2.1
6.1 | Prepare | Remove duplicates |  |  | Not started
6.2 | Prepare | Standardise formats: dates as YYYY-MM-DD, 18-digit Salesforce IDs, phone numbers and addresses |  |  | Not started
6.3 | Prepare | Check picklist values against the target org's active values |  |  | Not started
6.4 | Prepare | Compare against existing Salesforce data so you update records instead of duplicating them |  |  | Not started
7 | Prepare | Prepare the target org |  |  | Not started |  | Record the original state of anything you switch off
7.1 | Prepare | Decide which flows, validation rules and triggers to pause or allow for during the load |  |  | Not started |  | Note each one so it can be switched back on
7.2 | Prepare | Check the loading user's object, field and record type permissions |  |  | Not started
7.3 | Prepare | Enable Set Audit Fields upon Record Creation if you need to keep original CreatedDate values |  |  | Not started
8 | Test | Run a sample load in a sandbox |  |  | Not started |  | Practise the rollback on the sample too
8.1 | Test | Load a small, representative set end to end, including child records and edge cases |  |  | Not started
8.2 | Test | Fix the errors in the error file and re-run until the sample is clean |  |  | Not started
8.3 | Test | Have users check the sample against real tasks and sign off |  |  | Not started
9 | Plan | Write the rollback plan |  |  | Not started |  | This row is the rollback plan
9.1 | Plan | Decide how you will identify the records a job created or changed (success files, external IDs, a CreatedDate or LastModifiedDate window) |  |  | Not started
9.2 | Plan | Decide how you will undo them: delete inserted records, restore updated values from the backup |  |  | Not started
9.3 | Plan | Name who makes the rollback call and what triggers it |  |  | Not started
10 | Cut over | Cut over, reconcile and keep the logs |  |  | Not started |  | Use the plan from step 9 if reconciliation fails
10.1 | Cut over | Tell users about the freeze window and the go-live date |  |  | Not started
10.2 | Cut over | Freeze changes in the source system |  |  | Not started
10.3 | Cut over | Run the full load in the agreed order |  |  | Not started
10.4 | Cut over | Compare record counts per object with the source and spot-check records |  |  | Not started
10.5 | Cut over | Keep the success and error files from every job with the project documentation |  |  | Not started
10.6 | After go-live | Monitor for data issues reported by users in the first weeks |  |  | Not started