## Dashboard
Campaign Dashboard
Key Metrics
Total Tasks | 205
Completed Tasks | 13
% Tasks Completed | 6.341%
Overdue Tasks | 0
Campaign Health Score | 6.341%
Phase Completion
Define frontline sales challenges and business objectives for enablement tool procurement | 8.696% | ¦
Map technical and IT integration requirements for CRM and existing systems | 4.762%
Conduct vendor landscape research prioritizing AI playbooks and just-in-time content | 7.692% | ¦
Shortlist top vendors and schedule customized platform demos | 4.762%
Execute vendor demos with cross-functional core stakeholders | 4.762%
Conduct sandboxed technical evaluation and usability testing | 4.762%
Review information security compliance and data governance standards | 4%
Negotiate commercial terms and define service level agreements | 9.524% | ¦
Present final vendor recommendation for executive review and sign contract | 7.692% | ¦

## Project Tracker
Task ID | Task Name | Phase / Milestone | Owner | Start Date | End Date | Duration (Days) | Status | Priority | Effort | KPI / Success Metric | Assets Required | Dependency | Send for Review | Reviewer Email | Not Started
1 | Define frontline sales challenges and business objectives for enablement tool procurement | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-30 05:30 | 2026-06-02 05:30 | 3 | Done | High | M | Approved business requirements document aligning with 2026 growth goals | Current sales performance data, feedback from frontline managers | Requires input from Regional Sales Directors and CRO |  |  | WIP
1.1 | Frontline Field Discovery & Sentiment Mapping | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-14 05:30 | 2026-05-21 05:30 | 7 | Not Started | High | M | Completed sentiment analysis from 50+ frontline agents across 3 target industries | Interview scripts, survey forms, regional sales feedback summary | Approval from regional sales heads to access distributed field teams |  |  | Done
1.1.1 | In-Person Shadowing and Field Ethnography Sessions | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-04-15 05:30 | 2026-04-25 05:30 | 10 | Done | High | L | Documented count of real-world friction points in current sales execution workflows | Field observation checklist, audio recording equipment, mobile-first ethnographic survey tool | Selection of diverse geographic territories representing both high and low performance clusters
1.1.2 | Frontline Tool Sentiment and Friction Survey Deployment | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-04-25 05:30 | 2026-05-02 05:30 | 7 | Not Started | High | M | Completion rate exceeding 40% across the distributed frontline agent workforce | Mobile-optimized survey platform, communication templates for Regional Managers, incentive structure documentation | Preliminary shadowing insights to ensure survey questions address actual field realities
1.1.3 | Regional Sales Leader Depth Interviews | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-02 05:30 | 2026-05-07 05:30 | 5 | Not Started | Medium | M | Synthesis of top 3 systemic barriers to sales playbook adoption across regions | Structured interview guide focusing on execution consistency and capability gaps, scheduling automation tool | Initial quantitative data from field surveys to validate specific sentiment trends
1.1.4 | Sales Content Wastage and Usage Audit | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-07 05:30 | 2026-05-21 05:30 | 14 | Not Started | High | L | Percentage of corporate-approved marketing assets that remain unused by the field | Content repository logs, CRM engagement analytics, 'Dark Social' sharing interview questionnaire | Access to existing legacy content management systems and frontline file-sharing logs
1.2 | Sales Content & Tooling Friction Audit | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-21 05:30 | 2026-05-26 05:30 | 5 | Not Started | High | M | Report identifying top 3 content-related bottlenecks in the current sales cycle | Current sales collateral inventory, tool usage logs, friction point heatmap | Access to existing CRM data and content management system analytics
1.2.1 | Frontline Agent Workflow Shadowing & Friction Mapping | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-04-13 05:30 | 2026-04-23 05:30 | 10 | Not Started | High | M | Count of documented friction points in content retrieval | Field Interview Guide, Workflow Observation Templates, Agent Persona Profiles | Sales Leadership approval for field access
1.2.2 | Legacy Content Utilization & Effectiveness Audit | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-04-23 05:30 | 2026-04-30 05:30 | 7 | Not Started | Medium | S | Percentage of unused vs high-impact sales assets | CMS Analytics Access, Content Inventory Spreadsheet, Sales Feedback Survey | Access to existing CRM and Content Management data
1.2.3 | Buyer Journey Content Gap Analysis | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-04-30 05:30 | 2026-05-14 05:30 | 14 | Not Started | High | L | Content coverage ratio for critical sales stages | Customer Journey Maps, Sales Stage Playbook, Objection Handling Battlecards | Results from Agent Workflow Shadowing
1.2.4 | Mobile Performance & Tech Stack Integration Assessment | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-14 05:30 | 2026-05-19 05:30 | 5 | Not Started | Medium | S | Latency and load-time metrics for field assets | IT Infrastructure Overview, Mobile Connectivity Field Test Report | Interviews with IT and Security compliance teams
1.2.5 | Enablement Tool Business Case & ROI Framework | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-19 05:30 | 2026-05-26 05:30 | 7 | Not Started | High | M | Projected percentage increase in frontline productivity | ROI Calculator, Strategic Procurement Deck, Vendor Comparison Matrix | Completion of Gap Analysis and Friction Mapping
1.3 | Strategic Objective & KPI Alignment | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-26 05:30 | 2026-05-29 05:30 | 3 | Not Started | High | S | Signed-off document linking enablement features to 2026 revenue growth targets | Business goal documentation, KPI framework (Lead conversion, Pitch consistency) | Executive interview with Chief Revenue Officer or Business Head
1.3.1 | Identify sector-specific sales bottlenecks for frontline teams in Banking and Automotive | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-01 05:30 | 2026-05-08 05:30 | 7 | Not Started | High | M | Documented list of top 5 friction points per industry segment | Industry benchmark reports 2026, current frontline performance data, ICP interview transcripts | None
1.3.2 | Establish baseline performance metrics and target KPIs for sales enablement impact | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-08 05:30 | 2026-05-13 05:30 | 5 | Not Started | High | S | KPI Scorecard covering lead activation rates and pitch consistency scores | Historical sales conversion data, time-to-productivity logs for new agents | Identify sector-specific sales bottlenecks
1.3.3 | Conduct executive alignment sessions with CRBOs and Sales Leaders to define procurement goals | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-13 05:30 | 2026-05-23 05:30 | 10 | Not Started | High | L | Signed Strategic Alignment Document detailing prioritized business outcomes | Executive summary of identified bottlenecks, proposed KPI framework | Establish baseline performance metrics
1.3.4 | Construct a localized ROI model linking Sharpsell.ai features to frontline revenue growth | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-23 05:30 | 2026-05-29 05:30 | 6 | Not Started | High | M | Approved Business Case for procurement committee review | Sharpsell.ai product capability map, ROI calculation template | Conduct executive alignment sessions
1.4 | Enablement Business Requirement Document (BRD) Development | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-29 05:30 | 2026-06-02 05:30 | 4 | Not Started | Medium | S | Finalized BRD highlighting 5 critical use cases for procurement evaluation | Persona-based use case deck, technical requirement checklist | Consolidated findings from Field Discovery and Friction Audit
1.4.1 | Conduct Frontline Capability Gap Analysis & Stakeholder Interviews | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-01 05:30 | 2026-05-11 05:30 | 10 | Not Started | High | M | List of 10-15 validated friction points in the current frontline sales cycle | Stakeholder interview guide, current sales process map, field observation log | Initial alignment with Sales Leadership on evaluation scope
1.4.2 | Define Functional Requirements for AI-Led Execution and Personalization | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-11 05:30 | 2026-05-18 05:30 | 7 | Not Started | High | M | Prioritized functional requirement list signed off by Sales Operations | Product feature matrix (PitchWiz, Copilot), content personalization checklist | Completion of Gap Analysis to ensure requirements solve real field issues
1.4.3 | Draft Technical Integration and Data Security Specifications | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-18 05:30 | 2026-05-23 05:30 | 5 | Not Started | Medium | S | Finalized technical spec sheet for Lead Management System and CRM sync | CRM/LMS architecture diagrams, enterprise security compliance questionnaire | Functional requirements to determine necessary data touchpoints
1.4.4 | Build ROI Framework and Success Metric Definitions | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-23 05:30 | 2026-05-29 05:30 | 6 | Not Started | High | M | Documented set of 5 primary KPIs for evaluating tool performance post-implementation | ROI calculator, baseline sales conversion data, capability scoring rubric | Input from CRO and Business Officers on top-line growth targets
1.4.5 | Consolidate and Socialize the Final Enablement BRD | Define frontline sales challenges and business objectives for enablement tool procurement |  | 2026-05-29 05:30 | 2026-06-02 05:30 | 4 | Not Started | High | S | Formal approval of the BRD by the Chief Revenue Officer | Final BRD document, executive summary deck for procurement | Completion of functional, technical, and ROI sub-tasks
2 | Map technical and IT integration requirements for CRM and existing systems | Map technical and IT integration requirements for CRM and existing systems |  | 2026-06-02 05:30 | 2026-06-04 05:30 | 2 | Not Started | High | M | Finalized technical specification and data security checklist | Current IT architecture mapping, compliance guidelines | Dependent on completion of business requirements definition
2.1 | Audit existing CRM and field-force automation tools for API compatibility | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-10 05:30 | 2026-05-17 05:30 | 7 | Not Started | High | M | Completion of a compatibility matrix mapping Sharpsell.ai features to existing CRM data fields | Current tech stack inventory, API documentation from CRM vendors (e.g., Salesforce, Microsoft Dynamics, or custom legacy systems) | Access to internal IT system architects and CRM administrators
2.1.1 | Catalog CRM and SFA System Architecture and Access Credentials | Map technical and IT integration requirements for CRM and existing systems |  | 2026-04-26 05:30 | 2026-05-01 05:30 | 5 | Done | High | M | Comprehensive inventory of all sales-facing software with confirmed API status (Open, Restricted, or Proprietary). | Current IT infrastructure map, vendor contracts, and API access keys for CRM (e.g., Salesforce, Oracle) and Field-Force Automation tools. | Requires meeting with the Sales Operations and IT departments to identify all legacy systems currently in use by frontline teams.
2.1.2 | Assess Technical API Documentation for Real-Time Lead and Content Sync | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-01 05:30 | 2026-05-08 05:30 | 7 | Not Started | High | L | Technical feasibility report highlighting potential bottlenecks for real-time lead activation and content delivery to frontline agents. | Technical documentation for existing CRM/SFA endpoints, Sharpsell.ai integration specifications, and Postman or similar API testing environment. | Depends on the successful cataloging of systems in the initial inventory phase.
2.1.3 | Map Data Flow for Sharpsell.ai Lead Management and PitchWiz Modules | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-08 05:30 | 2026-05-13 05:30 | 5 | Not Started | High | M | Documented data flow diagram showing how leads and sales assets transition from the CRM to the Sharpsell.ai mobile interface. | Field mapping spreadsheet, Sharpsell.ai PitchWiz configuration guide, and data privacy impact assessment (DPIA) templates. | Must be completed after the technical API assessment to ensure data fields are compatible between systems.
2.1.4 | Validate Security and Authentication Protocols for Single Sign-On (SSO) | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-13 05:30 | 2026-05-17 05:30 | 4 | Not Started | Medium | S | Confirmed SSO compatibility ensuring frontline agents can access Sharpsell.ai tools using existing enterprise credentials without friction. | Security protocols (OAuth 2.0, SAML), enterprise security policy document, and Sharpsell.ai security whitepaper. | Dependent on IT security clearance and validation of existing authentication methods used by the enterprise.
2.2 | Design bidirectional data flow for real-time lead activation and sales reporting | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-17 05:30 | 2026-05-27 05:30 | 10 | Not Started | High | L | Approved technical architecture diagram showing sync frequency and data residency protocols | Data mapping template, Sharpsell.ai integration technical specs, Lead Management System (LMS) workflows | Finalization of lead distribution logic from the business operations team
2.2.1 | Map Lead Activation Data Flows for CRM Integration | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-01 05:30 | 2026-05-08 05:30 | 7 | Not Started | High | M | Number of qualified leads requesting technical integration walkthroughs | Data flow diagrams, API documentation summaries, CRM mapping templates | Review of current CRM field structures in Banking and Insurance sectors
2.2.2 | Develop ROI Case Study on Reduced Lead Response Time | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-08 05:30 | 2026-05-18 05:30 | 10 | Not Started | High | L | Percentage increase in lead-to-meeting conversion rates reported by prospects | Customer testimonial video, data-backed PDF case study, LinkedIn carousel | Access to 2025 performance data from an existing Automotive or NBFC client
2.2.3 | Design Frontline Sales Activity Reporting Mockups | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-18 05:30 | 2026-05-23 05:30 | 5 | Not Started | Medium | M | Demo conversion rate from 'Sales Leader' personas | Dashboard UI mockups for SVPs, field activity heatmaps, reporting feature list | Interviews with Chief Business Officers to define critical field execution metrics
2.2.4 | Create Enterprise Data Security and Privacy Whitepaper | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-23 05:30 | 2026-05-27 05:30 | 4 | Not Started | High | S | Reduction in average time spent in the legal/procurement stage of the sales cycle | Security compliance one-pager, SOC2/ISO certification overview, data encryption guide | Finalization of 2026 updated data handling and privacy protocols
2.3 | Draft security and compliance specifications for mobile-first deployment | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-27 05:30 | 2026-06-01 05:30 | 5 | Not Started | Medium | S | Validated security checklist ensuring the platform meets industry-specific compliance (e.g., BFSI or Pharma standards) | Enterprise security questionnaire, SOC2/ISO certification requirements, SSO/SAML configuration guides | CISO office guidelines for mobile application security and offline data storage
2.3.1 | Develop a Security Compliance and Data Sovereignty Fact Sheet | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-10 05:30 | 2026-05-17 05:30 | 7 | Not Started | High | M | Completion of a client-facing security packet for IT procurement officers. | SOC2/ISO certification summaries, data encryption standards document, and PII protection overview. | Technical review with the product engineering team to confirm current encryption protocols.
2.3.2 | Create a Mobile Device Management (MDM) and MAM Compatibility Guide | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-17 05:30 | 2026-05-22 05:30 | 5 | Not Started | High | S | Direct inclusion of the guide in 100% of enterprise RFP responses. | Integration technical specs for common MDM providers like Intune, AirWatch, and Jamf. | Identification of the most common MDM solutions used by enterprise automotive and banking clients.
2.3.3 | Draft an Offline-First Data Sync and Security Protocol Brief | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-22 05:30 | 2026-05-28 05:30 | 6 | Not Started | Medium | M | Reduction in security-related friction during the technical evaluation phase. | Whitepaper explaining secure local storage and background sync for field agents in low-connectivity areas. | Input from frontline sales leads regarding data access requirements in remote geographies.
2.3.4 | Design an Interactive Security Comparison Matrix for Procurement Teams | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-28 05:30 | 2026-06-01 05:30 | 4 | Not Started | High | S | Lead capture through the 'Evaluation Kit' download on the website. | Web-based comparison tool or PDF matrix showing Sharpsell.ai security features vs generic sales tools. | Competitive analysis of security features offered by standard CRM-linked enablement tools.
2.4 | Conduct technical feasibility workshop with IT and InfoSec stakeholders | Map technical and IT integration requirements for CRM and existing systems |  | 2026-06-01 05:30 | 2026-06-04 05:30 | 3 | Not Started | High | M | Signed-off technical feasibility report for the procurement committee | Integration roadmap presentation, API sandboxing credentials, pilot testing parameters | Completion of the data flow design and security specification draft
2.4.1 | Compile Sharpsell.ai Security and Data Privacy Dossier | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-21 05:30 | 2026-05-24 05:30 | 3 | Not Started | High | S | Full documentation package accepted for review by the InfoSec team. | SOC2 Type II certificates, ISO 27001 documentation, and Data Encryption Whitepapers for field data security. | Product engineering verification of 2026 security compliance and encryption standards.
2.4.2 | Map API Integration Architecture for Frontline CRM Systems | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-24 05:30 | 2026-05-29 05:30 | 5 | Not Started | High | M | IT leadership sign-off on data sync reliability and integration feasibility for distributed agents. | API endpoint documentation and visual data-flow diagrams for Salesforce and Microsoft Dynamics 365. | Completion of the technical audit of the enterprise's existing legacy CRM infrastructure.
2.4.3 | Develop Technical Stakeholder Presentation for IT and InfoSec Leadership | Map technical and IT integration requirements for CRM and existing systems |  | 2026-05-29 05:30 | 2026-06-02 05:30 | 4 | Not Started | Medium | M | Formal alignment on technical feasibility reached during the workshop session. | Presentation deck covering SSO implementation, on-device data encryption, and offline-sync protocols. | Approval of the Security and Data Privacy Dossier by the procurement lead.
2.4.4 | Create Technical FAQ and Mobile Security Battlecards | Map technical and IT integration requirements for CRM and existing systems |  | 2026-06-02 05:30 | 2026-06-04 05:30 | 2 | Not Started | Medium | S | Resolution of all technical objections raised by IT stakeholders within the workshop cycle. | Document addressing system latency, Mobile Device Management (MDM) compatibility, and local storage encryption. | Preliminary discovery session with IT infrastructure leads to identify specific security concerns.
3 | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-06-04 05:30 | 2026-06-08 05:30 | 4 | Not Started | High | M | Vendor comparison matrix with top contenders identified | Industry benchmark data | Dependent on technical and business requirements
3.1 | Define Industry-Specific Feature Benchmarking Criteria | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-05 05:30 | 2026-05-10 05:30 | 5 | Not Started | High | M | Approval of benchmarking parameters by the Sales Operations Head | Requirement Checklist, Feature Matrix Template | Initial internal stakeholders interview to capture field-level pain points
3.1.1 | Map Sector-Specific Frontline Sales Friction Points | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-06 05:30 | 2026-04-16 05:30 | 10 | Not Started | High | M | Documented list of 10 critical friction points per target industry | Stakeholder interview guides, Industry-specific workflow diagrams for Insurance, Pharma, and Automotive | Initial industry research and ICP interviews
3.1.2 | Develop Weighted Feature Evaluation Matrix | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-16 05:30 | 2026-04-23 05:30 | 7 | Not Started | High | S | Standardized evaluation scorecard for procurement teams | Benchmarking spreadsheet, Sharpsell.ai feature capability list including PitchWiz and Copilot | Map Sector-Specific Frontline Sales Friction Points
3.1.3 | Define Technical Scalability and Integration Benchmarks | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-23 05:30 | 2026-04-28 05:30 | 5 | Not Started | Medium | M | Minimum technical threshold document for enterprise deployment | Technical compliance checklist, API documentation, Offline-sync requirement spec | None
3.1.4 | Build Industry-Specific ROI Modeling Templates | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-28 05:30 | 2026-05-10 05:30 | 12 | Not Started | High | L | Validated ROI model for C-suite approval cycles | ROI calculator for BFSI and Consumer Durables, Business value projection deck | Develop Weighted Feature Evaluation Matrix
3.2 | Evaluate AI Sales Playbook and Copilot Capabilities | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-10 05:30 | 2026-05-20 05:30 | 10 | Not Started | High | L | Comparison report of AI accuracy in objection handling and role-play modules | Vendor Technical Documentation, AI Performance Scorecard | Completion of benchmarking criteria
3.2.1 | Audit and Map Sales Content for AI Playbook Readiness | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-22 05:30 | 2026-04-29 05:30 | 7 | Not Started | High | M | Percentage of legacy content structured for AI Playbook ingestion | Current sales collateral, top-performing pitch recordings, and Sharpsell AI Playbook templates | Mapping of high-impact sales behaviors across the frontline teams
3.2.2 | Design Frontline Pilot Success Metrics and Feedback Loops | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-29 05:30 | 2026-05-09 05:30 | 10 | Not Started | High | L | Adoption rate of interactive product illustrators within the pilot group | User feedback surveys, performance tracking dashboards, and Copilot usage logs | Selection of a specific regional sales unit for the 2026 pilot program
3.2.3 | Develop Business Case and ROI Model for CRO Approval | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-09 05:30 | 2026-05-14 05:30 | 5 | Not Started | High | M | Project sign-off from Chief Revenue or Business Officers | ROI calculator, competitive gap analysis matrix, and cost-of-inaction report | Data on current lead conversion bottlenecks in the sales cycle
3.2.4 | Configure AI Role-Play Scenarios for Consumer Durable Use Cases | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-14 05:30 | 2026-05-20 05:30 | 6 | Not Started | Medium | S | Score improvement in automated AI role-play sessions by frontline agents | Objection handling scripts, battlecards, and industry-specific product data | Access to field logs highlighting common 2026 market objections
3.3 | Assess Just-in-Time Content Delivery and Mobility UX | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-20 05:30 | 2026-05-27 05:30 | 7 | Not Started | Medium | M | Validation of offline access and content personalization speed on field devices | User Experience Audit Log, Mobile Capability Report | Shortlisting of top 5 vendors from the AI capabilities audit
3.3.1 | Audit Content Accessibility and Search Latency for Field Teams | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-04-29 05:30 | 2026-05-06 05:30 | 7 | Not Started | High | M | Percentage reduction in time spent by frontline agents locating relevant sales assets. | Current sales collateral map, agent search query logs, and time-to-retrieval data. | Detailed inventory of existing product brochures and technical specification sheets.
3.3.2 | Execute Frontline Mobility UX Field Testing | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-06 05:30 | 2026-05-16 05:30 | 10 | Not Started | High | L | Agent adoption rate and Mobile App Ease of Use score from field surveys. | Pilot access to mobile interfaces, agent UX feedback forms, and field device specifications. | Selection of a diverse sample of agents across different regional geographies.
3.3.3 | Verify Dynamic Personalization of Just-in-Time Collaterals | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-16 05:30 | 2026-05-21 05:30 | 5 | Done | Medium | S | Average number of personalized brochures generated per agent per customer meeting. | Standard brand templates, customer data fields for integration, and Interactive Product Illustrators. | Marketing and compliance approval on editable content zones within sales assets.
3.3.4 | Test Offline Synchronization Reliability in Low-Bandwidth Zones | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-21 05:30 | 2026-05-27 05:30 | 6 | Not Started | High | M | Zero-failure rate for accessing critical sales playbooks in offline mode. | Regional network reliability data and vendor technical specifications for offline caching. | Security clearance for local data encryption on field-agent mobile devices.
3.4 | Conduct Integration and Enterprise Scalability Audit | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-27 05:30 | 2026-06-04 05:30 | 8 | Not Started | High | L | Finalized technical feasibility report for Lead Management System integration | CRM Integration Map, Data Security Compliance Document | Vendor technical disclosure agreements
3.4.1 | Map Current CRM and Lead Management Ecosystem for Data Flow Integration | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-09 05:30 | 2026-05-14 05:30 | 5 | Not Started | High | M | Documented data flow map showing bi-directional sync between Sharpsell.ai and existing CRM | Current Tech Stack Diagram, API Documentation, Data Field Mapping Template | Requires input from Sales Operations and IT Infrastructure teams
3.4.2 | Develop Enterprise-Grade Security and Compliance Checklist for Procurement | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-14 05:30 | 2026-05-21 05:30 | 7 | Not Started | High | M | Finalized vendor evaluation checklist approved by Compliance and Legal | Security Questionnaire, SOC2/ISO Certification Requirements, Data Privacy Standards Document | Internal InfoSec team review of vendor security protocols
3.4.3 | Execute Mobile Performance Audit for High-Volume Distributed Field Teams | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-21 05:30 | 2026-05-25 05:30 | 4 | Not Started | High | S | Content accessibility and sync performance validation under low-connectivity scenarios | Low-Bandwidth Testing Protocol, Mobile App Latency Report, Offline Sync Checklist | Access to Tool Sandbox or Pilot Environment
3.4.4 | Design Scalability Stress Test Scenarios for Multi-Geography Deployment | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-25 05:30 | 2026-06-04 05:30 | 10 | Not Started | Medium | L | Documented report confirming system stability for over 10,000 concurrent frontline users | User Concurrency Plan, Geography-Specific Server Latency Report, Load Testing Script | Historical frontline agent activity data from regional managers
3.5 | Synthesize Competitive Landscape Recommendation Report | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-06-04 05:30 | 2026-06-08 05:30 | 4 | Not Started | High | S | Presentation of top 3 vendor recommendations to the Chief Revenue Officer | Vendor Landscape Presentation, ROI Projection Model | Completion of all previous evaluation sub-tasks
3.5.1 | Industry-Specific Feature Gap Analysis for Frontline Teams | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-23 05:30 | 2026-05-28 05:30 | 5 | Not Started | High | M | Completed comparison matrix across 5 key industry verticals | Competitor Feature Matrix, Industry Use Case Library (Automotive, Banking, Consumer Durables) | None
3.5.2 | Mobile-First UX and Offline Capability Benchmarking | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-05-28 05:30 | 2026-06-01 05:30 | 4 | Not Started | Medium | M | Technical scorecard measuring usability for distributed field agents | UX Evaluation Rubric, Field Connectivity Performance Benchmarks | Industry-Specific Feature Gap Analysis for Frontline Teams
3.5.3 | Total Cost of Ownership (TCO) and ROI Modeling | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-06-01 05:30 | 2026-06-04 05:30 | 3 | Not Started | High | L | Price-to-value report highlighting scalability costs for enterprise teams | TCO Calculator, Competitor Pricing Intelligence Data | Industry-Specific Feature Gap Analysis for Frontline Teams
3.5.4 | Executive Recommendation Report and Evaluation Scorecard | Conduct vendor landscape research prioritizing AI playbooks and just-in-time content |  | 2026-06-04 05:30 | 2026-06-08 05:30 | 4 | Done | High | S | Finalized procurement-ready recommendation report for C-suite stakeholders | Executive Summary Deck, Decision-Matrix Template, Procurement Checklist | Total Cost of Ownership (TCO) and ROI Modeling
4 | Shortlist top vendors and schedule customized platform demos | Shortlist top vendors and schedule customized platform demos |  | 2026-06-08 05:30 | 2026-06-10 05:30 | 2 | Not Started | Medium | S | Confirmed demonstration sessions with core evaluation team | Use case scenarios, scoring rubrics for stakeholders | Dependent on vendor landscape research
4.1 | Develop Enterprise-Grade Sales Enablement Vendor Comparison Matrix | Shortlist top vendors and schedule customized platform demos |  | 2026-05-22 05:30 | 2026-05-27 05:30 | 5 | Not Started | High | M | Full comparison of 5 vendors against critical frontline needs like Lead Activation and PitchWiz | Feature list of Sharpsell.ai offerings, G2/Gartner competitive reports, and internal sales tech stack audit | Completion of internal requirements gathering and feature prioritization
4.1.1 | Define Enterprise-Specific Evaluation Criteria | Shortlist top vendors and schedule customized platform demos |  | 2026-05-13 05:30 | 2026-05-16 05:30 | 3 | Not Started | High | M | List of 15+ weighted criteria for enterprise frontline teams | ICP Pain Point Report, Industry Capability Lists | Marketing Research Data
4.1.2 | Audit Competitor Capabilities for Frontline Use Cases | Shortlist top vendors and schedule customized platform demos |  | 2026-05-16 05:30 | 2026-05-21 05:30 | 5 | Not Started | High | L | Comprehensive data points for top 5-7 competitors in BFSI and Pharma | Competitor Portfolios, 2026 Sales Enablement Market Reports | Evaluation Criteria
4.1.3 | Build Weighted Scoring Model for Procurement | Shortlist top vendors and schedule customized platform demos |  | 2026-05-21 05:30 | 2026-05-23 05:30 | 2 | Done | Medium | S | Finalized logical framework for the comparison tool | ROI Calculator, Procurement Checklist Template | Competitor Audit
4.1.4 | Develop Comparison Matrix Lead Magnet and Visual Asset | Shortlist top vendors and schedule customized platform demos |  | 2026-05-23 05:30 | 2026-05-27 05:30 | 4 | Not Started | High | M | Downloadable PDF and Interactive Matrix tool for Sales Leaders | Design Software, Brand Guidelines, Copywriting Drafts | Scoring Model
4.2 | Design Industry-Specific Demo Scenarios and Sales Playbook Scripts | Shortlist top vendors and schedule customized platform demos |  | 2026-05-27 05:30 | 2026-06-03 05:30 | 7 | Not Started | High | L | Approval of 3 distinct use-case flows targeting Automotive, Banking, and Insurance segments | Industry-specific objection handling logs, interactive product illustrator specs, and current field sales scripts | Identification of top 3 vendor candidates from the comparison matrix
4.2.1 | Map High-Friction Procurement Stages for Sales Leaders in Consumer Sectors | Shortlist top vendors and schedule customized platform demos |  | 2026-05-14 05:30 | 2026-05-19 05:30 | 5 | Not Started | High | M | Documented matrix of 5 critical procurement roadblocks per target industry | ICP research reports and 2026 industry landscape data for Automotive and BFSI | Completion of preliminary industry-specific market analysis
4.2.2 | Design Demo Scenarios for PitchWiz to Show Executive Alignment on Sales KPIs | Shortlist top vendors and schedule customized platform demos |  | 2026-05-19 05:30 | 2026-05-25 05:30 | 6 | Not Started | High | L | 3 high-impact demo flows optimized for C-suite and CRBO personas | Interactive Product Illustrator templates and standard sales metric benchmarks | Procurement friction mapping and stakeholder identification
4.2.3 | Script Sales Playbooks Addressing Procurement Objections like Integration and Scalability | Shortlist top vendors and schedule customized platform demos |  | 2026-05-25 05:30 | 2026-05-30 05:30 | 5 | Not Started | Medium | M | Finalized playbook scripts for handling IT, security, and integration queries | Sharpsell.ai technical capability documentation and legacy system API guides | Demo scenario design and technical feasibility review
4.2.4 | Develop Frontline-Specific Evaluation Checklists for Field-Tested Enablement | Shortlist top vendors and schedule customized platform demos |  | 2026-05-30 05:30 | 2026-06-03 05:30 | 4 | Not Started | High | S | Standardized evaluation checklist shared with 100% of the sales team | Competitive feature matrices and frontline agent feedback logs | Procurement roadblock identification and script drafting
4.3 | Create Stakeholder Demo Scorecards for Business Impact Assessment | Shortlist top vendors and schedule customized platform demos |  | 2026-06-03 05:30 | 2026-06-06 05:30 | 3 | Not Started | Medium | S | Signed-off evaluation criteria by the CRO and SVPs of Sales | ROI calculation models, frontline adoption metrics, and CRM integration requirements | Finalization of demo scenarios to ensure evaluation criteria match real-world usage
4.3.1 | Define Persona-Specific KPI Categories for Consumer Enterprise Segments | Shortlist top vendors and schedule customized platform demos |  | 2026-05-19 05:30 | 2026-05-22 05:30 | 3 | Not Started | High | M | Approval of the KPI framework by the Sales Operations and Strategy teams. | Stakeholder persona map, industry benchmark reports for Banking and Insurance, KPI registry. | Completion of ICP pain-point analysis for CRBOs and Sales Managers.
4.3.2 | Design Weighted Scoring Matrix for Business Value vs. Technical Fit | Shortlist top vendors and schedule customized platform demos |  | 2026-05-22 05:30 | 2026-05-27 05:30 | 5 | Not Started | High | L | 100% alignment between scorecard metrics and Sharpsell.ai core offerings like PitchWiz and AI Role-plays. | Excel-based scorecard logic, feature-to-value mapping document, weighted logic guide. | Finalization of KPI categories from the previous task.
4.3.3 | Develop Stakeholder Instruction Guides for Real-Time Demo Evaluation | Shortlist top vendors and schedule customized platform demos |  | 2026-05-27 05:30 | 2026-05-31 05:30 | 4 | Not Started | Medium | S | Completion of user-friendly documentation for non-technical evaluators. | PDF Evaluation Guide, 2-minute instructional video for evaluators, digital scorecard portal access. | Finalized weighted scoring matrix and logic.
4.3.4 | Build Automated ROI Projection Summary within the Scorecard Tool | Shortlist top vendors and schedule customized platform demos |  | 2026-05-31 05:30 | 2026-06-06 05:30 | 6 | Not Started | High | L | Generation of a summary report that correlates demo scores with potential revenue growth. | ROI calculator script, 2026 industry case study data, financial impact modeling logic. | Historical performance data from frontline sales deployments.
4.4 | Execute Technical Compliance Pre-Checks and Demo Logistics | Shortlist top vendors and schedule customized platform demos |  | 2026-06-06 05:30 | 2026-06-10 05:30 | 4 | Not Started | High | M | 100% of shortlisted vendors cleared for technical demo phase | IT security questionnaire, data privacy standards for 2026, and stakeholder availability calendars | Confirmation of vendor ability to support distributed frontline teams in 2026
4.4.1 | Validate Data Security and Regional Compliance Standards | Shortlist top vendors and schedule customized platform demos |  | 2026-05-22 05:30 | 2026-05-29 05:30 | 7 | Not Started | High | M | Documented clearance from client security/IT audit teams | SOC2/ISO Certification docs, Data Privacy Impact Assessment (DPIA) template, Security whitepaper | Initial legal and compliance team stakeholder meeting
4.4.2 | Map API Integrations for Frontline CRM and Lead Systems | Shortlist top vendors and schedule customized platform demos |  | 2026-05-29 05:30 | 2026-06-03 05:30 | 5 | Not Started | High | M | Successful data handshake verification between Sharpsell.ai and client CRM | Integration documentation, API endpoint list, Webhook configuration guide | Technical architecture review with the client's IT lead
4.4.3 | Develop Industry-Specific Demo Scenarios and Field-Tested Scripts | Shortlist top vendors and schedule customized platform demos |  | 2026-06-03 05:30 | 2026-06-07 05:30 | 4 | Not Started | Medium | S | Stakeholder sign-off on demo flow and persona relevance | Interactive Product Illustrator assets, Custom AI Role-play scenarios, Vertical-specific battlecards | Finalization of industry-specific ICP pain points (e.g., Insurance or Automotive)
4.4.4 | Configure Sandbox Environment for Pilot User Testing | Shortlist top vendors and schedule customized platform demos |  | 2026-06-07 05:30 | 2026-06-10 05:30 | 3 | Not Started | Medium | S | Successful login and feature access for all designated pilot users | Anonymized dummy data sets, Admin login credentials, Sandbox environment URL | Completion of technical integration mapping
5 | Execute vendor demos with cross-functional core stakeholders | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-10 05:30 | 2026-06-15 05:30 | 5 | Not Started | High | L | Completed evaluation scorecards for all participating vendors | Demo scorecards, frontline agent feedback forms | Dependent on demo scheduling
5.1 | Develop Industry-Specific Demo Scenarios and Frontline Success Metrics | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-27 05:30 | 2026-06-01 05:30 | 5 | Not Started | High | M | 100% alignment between demo scenarios and the specific operational challenges of the frontline sales team. | Industry pain point maps for Banking and Automotive, ROI projection templates, lead activation workflow diagrams | Must follow the identification of core frontline challenges such as lead leakage or pitch inconsistency.
5.1.1 | Map Vertical-Specific Use Case Scenarios for Frontline Teams | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-08 05:30 | 2026-05-13 05:30 | 5 | Not Started | High | M | Finalization of 4 industry-specific sales playbooks covering lead activation to closing | Customer journey maps for Automotive, BFSI, and Pharma; current field sales pain-point logs; competitive analysis | Completion of initial industry persona research
5.1.2 | Define Frontline Execution Metrics and ROI Benchmarks | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-13 05:30 | 2026-05-17 05:30 | 4 | Not Started | High | M | Documented framework of 5 leading and 5 lagging indicators for procurement evaluation | Platform analytics templates, industry standard conversion rates, adoption tracking methodology | Map Vertical-Specific Use Case Scenarios for Frontline Teams
5.1.3 | Configure Interactive Demo Assets for PitchWiz and Product Illustrator | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-17 05:30 | 2026-05-27 05:30 | 10 | Not Started | High | L | Ready-to-present demo environment featuring personalized frontline sales execution paths | Sharpsell.ai platform access, industry-specific product brochures, AI Role-play scripts | Define Frontline Execution Metrics and KPI Benchmarks
5.1.4 | Produce Procurement Evaluation Matrix for Enterprise Stakeholders | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-27 05:30 | 2026-06-01 05:30 | 5 | Not Started | Medium | S | A single-page scorecard for Chief Revenue Officers to evaluate tool readiness for distributed teams | Security compliance checklists, technical integration specs, frontline usability survey results | Configure Interactive Demo Assets for PitchWiz and Product Illustrator
5.2 | Create Cross-Functional Demo Scorecards and Feature Weighting Rubrics | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-01 05:30 | 2026-06-04 05:30 | 3 | Not Started | High | S | Stakeholder consensus reached on top 3 critical features for enterprise-wide deployment in 2026. | Digital evaluation form, feature comparison matrix including AI Role-plays and Interactive Product Illustrators | Requires confirmation of the stakeholder group including CROs, IT for security, and Sales Ops for integration.
5.2.1 | Identify Cross-Functional Stakeholder Evaluation Criteria | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-16 05:30 | 2026-05-21 05:30 | 5 | Not Started | High | M | 100% consensus on must-have vs. nice-to-have features for frontline agents | Stakeholder Interview Guide, Functional Requirement Matrix | Finalization of the internal evaluation committee members
5.2.2 | Develop Weighted Feature Importance Rubric | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-21 05:30 | 2026-05-28 05:30 | 7 | Not Started | High | M | Documented weighting system reflecting field-sales priorities and ROI potential | Feature Weighting Spreadsheet, Enterprise Business Impact Map | Completion of stakeholder requirement gathering and prioritization
5.2.3 | Build Standardized Demo Scorecard Templates | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-28 05:30 | 2026-06-01 05:30 | 4 | Not Started | Medium | S | Scorecard completion rate of 100% across all pilot evaluators during demos | Mobile-Optimized Scorecard Template, Demo Evaluation Instruction Sheet | Approval of the weighted feature importance rubric
5.2.4 | Establish Quantitative Vendor Comparison Dashboard | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-01 05:30 | 2026-06-04 05:30 | 3 | Not Started | Medium | S | 25% reduction in time spent on final vendor comparison meetings | Automated Ranking Dashboard, Executive Summary Report Template | Initial pilot of the scorecard template to ensure data usability
5.3 | Curate Interactive POC Content for Field Agent Usability Testing | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-04 05:30 | 2026-06-11 05:30 | 7 | Not Started | Medium | L | Minimum 85% usability score from the frontline agent pilot group during hands-on testing sessions. | PitchWiz sample decks, mobile-first product brochures, and sample AI-generated objection handling scripts | Depends on the vendor's ability to ingest existing brand collateral for a personalized experience.
5.3.1 | Develop Interactive Product Playbooks for Field Agent POC | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-23 05:30 | 2026-05-28 05:30 | 5 | Not Started | High | M | Agent content adoption and engagement rate during the POC period | Current product brochures, technical spec sheets, brand assets, and Sharpsell.ai playbook templates | Sales leadership must sign off on the specific high-margin product lines to be featured in the test
5.3.2 | Configure AI-Powered Objection Handling Battlecards for Field Contexts | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-28 05:30 | 2026-06-01 05:30 | 4 | Not Started | High | M | Average time spent by agents on objection handling assets during customer interactions | List of top 10 common field objections, competitive analysis data, and Sharpsell.ai Battlecard modules | Field sales managers must validate the 'winning responses' to ensure local market relevance
5.3.3 | Design AI Role-play Scenarios for Standardized Pitching Assessments | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-01 05:30 | 2026-06-08 05:30 | 7 | Not Started | Medium | L | Percentage of participating agents reaching 'Proficient' status on the AI role-play leaderboard | Ideal pitch scripts, scoring rubrics for AI evaluation, and audio-visual samples of top-tier sales behavior | Completion of the product playbooks to ensure the AI scoring aligns with the new content
5.3.4 | Implement Field Usability Feedback Surveys and Analytics Dashboard | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-08 05:30 | 2026-06-11 05:30 | 3 | Not Started | High | S | Average Agent Usability Score and Net Promoter Score (NPS) from the test group | In-app survey forms, automated feedback triggers, and Sharpsell.ai analytics configuration | User IDs for the test cohort must be mapped to specific geographic regions for granular data analysis
5.4 | Build Internal Procurement Battlecards and Implementation Roadmaps | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-11 05:30 | 2026-06-15 05:30 | 4 | Done | Medium | M | Reduction in procurement cycle time by providing proactive answers to technical and deployment objections. | Data security whitepapers, technical integration guides, and 90-day onboarding timelines | Follows the initial feedback from IT and Legal stakeholders during the demo phase.
5.4.1 | Create 'Procurement Battlecards' Comparing Sales Execution Systems vs. Legacy LMS/CRM | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-18 05:30 | 2026-05-25 05:30 | 7 | Not Started | High | M | Number of downloads by MQLs in the decision-making stage | Competitor feature matrix, Sharpsell.ai differentiator list, and internal buyer persona guide | Requires completed competitor capability audit and value proposition mapping for CROs.
5.4.2 | Develop 90-Day Implementation Roadmaps for Enterprise Consumer Verticals | Execute vendor demos with cross-functional core stakeholders |  | 2026-05-25 05:30 | 2026-06-04 05:30 | 10 | Not Started | High | L | Reduction in average procurement cycle length for enterprise deals | Industry-specific onboarding templates, field agent rollout checklists, and success milestone visuals | Completion of historical deployment analysis for Banking and Automotive clients.
5.4.3 | Draft an 'Internal Business Case' Presentation Deck for Sales Leaders | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-04 05:30 | 2026-06-09 05:30 | 5 | Not Started | Medium | S | Prospect feedback on ease of internal stakeholder alignment | Customizable PPT template, ROI calculator data, and stakeholder mapping worksheet | Needs validated ROI metrics from existing Lead Activation and PitchWiz case studies.
5.4.4 | Produce Technical Compliance and Data Security One-Pagers for Procurement Teams | Execute vendor demos with cross-functional core stakeholders |  | 2026-06-09 05:30 | 2026-06-15 05:30 | 6 | Not Started | High | M | Decrease in time spent in technical vetting/IT approval phases | Security whitepaper, data privacy FAQ for frontline lead management, and integration specifications | Input from product and engineering teams regarding 2026 data compliance standards.
6 | Conduct sandboxed technical evaluation and usability testing | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-15 05:30 | 2026-06-20 05:30 | 5 | Not Started | High | L | Usability report from sample group of frontline agents | Sample sales collateral, dummy customer data | Dependent on successful vendor demos
6.1 | Sandbox Provisioning and Frontline Persona Setup | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-24 05:30 | 2026-05-29 05:30 | 5 | Not Started | High | M | 100% of pilot user roles mapped to specific frontline sales personas | Sharpsell sandbox instance, pre-loaded interactive product illustrators, sample lead data, persona-based login credentials | Finalization of pilot user list from Automotive/BFSI business units
6.1.1 | Frontline Persona Use Case Mapping for Consumer Sectors | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-10 05:30 | 2026-05-15 05:30 | 5 | Not Started | High | M | Documented user journeys for at least 3 distinct frontline personas (e.g., Bank RM, Field Agent) | ICP Persona Templates, Field Sales Friction Point Reports, Product Catalog Data | Completion of Stakeholder Discovery Interviews
6.1.2 | Interactive Product Illustrator & Content Asset Integration | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-15 05:30 | 2026-05-22 05:30 | 7 | Not Started | High | L | Percentage of sandbox-ready visual assets vs total product catalog for the pilot group | High-fidelity product images, 3D assets, dynamic pricing sheets, technical spec sheets | Persona Use Case Mapping
6.1.3 | Playbook and Objection Handling Battlecard Configuration | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-22 05:30 | 2026-05-26 05:30 | 4 | Not Started | High | M | Successful configuration of 10+ industry-specific objection handling scenarios in the sandbox | Sharpsell.ai Battlecard Templates, Historical Sales Objection Logs, Competitor Comparison Data | Persona Use Case Mapping
6.1.4 | Sandbox Guided Walkthrough and Procurement User Guides | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-26 05:30 | 2026-05-29 05:30 | 3 | Not Started | Medium | S | Stakeholder engagement rate within the sandbox environment | Screen recording software, Sandbox Access Credentials, Persona-specific 'Day-in-the-life' scripts | Asset Integration and Battlecard Configuration
6.2 | Field-Led Usability Testing and Feedback Collection | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-29 05:30 | 2026-06-08 05:30 | 10 | Not Started | High | L | Minimum 85% Ease-of-Use score from frontline sales agents | Frontline feedback survey, screen recording of pitch sessions, usability test script for PitchWiz and Copilot | Successful completion of sandboxed user onboarding
6.2.1 | Pilot Group Asset Localization and Setup | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-09 05:30 | 2026-05-16 05:30 | 7 | Not Started | High | M | 100% of pilot users onboarded with industry-relevant sales content. | Interactive Product Illustrators, Industry-specific Battlecards, and PitchWiz templates. | Finalization of target pilot geography and specific consumer product lines for testing.
6.2.2 | In-Field Lead Activation Performance Monitoring | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-16 05:30 | 2026-05-30 05:30 | 14 | Not Started | High | S | Percentage increase in lead response time and content engagement rates. | Platform analytics dashboard, lead conversion tracking tags, and automated usage reports. | Deployment of the Lead Management System to the pilot frontline team.
6.2.3 | Frontline Agent Capability Feedback Workshops | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-30 05:30 | 2026-06-04 05:30 | 5 | Not Started | Medium | M | Average Net Promoter Score (NPS) from frontline agents regarding tool usability. | Structured feedback surveys, AI Role-play evaluation scripts, and user interview guides. | Minimum of 7 days of active field tool usage by the pilot group.
6.2.4 | Field Usability and Sales Execution Gap Analysis | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-04 05:30 | 2026-06-08 05:30 | 4 | Not Started | High | L | Finalized business case for CRBO sign-off on enterprise-wide procurement. | Capability gap heatmaps, ROI projection calculator, and qualitative feedback summary. | Aggregation of all quantitative usage data and qualitative feedback from workshops.
6.3 | Technical Integration Audit and Performance Stress Test | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-08 05:30 | 2026-06-15 05:30 | 7 | Not Started | Medium | M | Zero critical latency issues during peak simulated usage | API documentation, SOC2 compliance reports, CRM integration checklist, offline mode performance metrics | IT security clearance of the sandbox environment
6.3.1 | Develop Integration Readiness Toolkit for Enterprise CRM and LMS Ecosystems | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-12 05:30 | 2026-05-19 05:30 | 7 | Not Started | High | M | Number of downloads from IT and Sales Ops personas | Interactive Compatibility Checklist, API Documentation Summary, Data Flow Diagrams | Product engineering team to confirm current API endpoints and webhook support for 2026 standards
6.3.2 | Publish Frontline Scalability and Concurrency Stress Test Whitepaper | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-19 05:30 | 2026-05-31 05:30 | 12 | Done | High | L | Marketing Qualified Leads (MQLs) generated from Chief Technology Officer profiles | Technical Whitepaper, Performance Benchmark Charts, Infrastructure Overview | Access to backend load testing data simulating 50,000+ concurrent frontline agents
6.3.3 | Create Field-Agent Latency Case Study for Low-Bandwidth Geographies | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-31 05:30 | 2026-06-10 05:30 | 10 | Not Started | Medium | M | Engagement rate on LinkedIn among Sales Leaders in distributed industries | Video Testimonials, Comparison Infographic, Technical Briefing | Field data from existing consumer durable or pharma clients operating in rural territories
6.3.4 | Draft Enterprise AI Security and Data Sovereignty Governance Guide | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-10 05:30 | 2026-06-15 05:30 | 5 | Not Started | High | S | Reduction in average technical audit duration during the procurement cycle | One-Page Security Brief, Compliance Matrix, Data Encryption Overview | Legal and compliance department sign-off on AI model data usage policies
6.4 | Content Delivery Efficiency Benchmarking | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-15 05:30 | 2026-06-20 05:30 | 5 | Not Started | High | S | 40% reduction in time spent by agents searching for relevant sales collateral | Just-in-time content library, objection handling battlecards, legacy sales material for comparison | Live simulation of a sales meeting using the interactive illustrator
6.4.1 | Frontline Sales Content Accessibility Audit | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-08 05:30 | 2026-05-18 05:30 | 10 | Not Started | High | M | Baseline Average Time-to-Content (ATC) for regional sales reps | Content inventory list, field agent survey templates, WhatsApp/Email distribution logs | None. This serves as the baseline for the entire benchmarking phase.
6.4.2 | Competitive Personalization Speed Benchmarking | Conduct sandboxed technical evaluation and usability testing |  | 2026-05-18 05:30 | 2026-06-01 05:30 | 14 | Not Started | Medium | M | Delta between manual asset customization vs. AI-powered automated personalization | Industry reports on sales tech adoption, Interactive Product Illustrator feature comparison docs | Requires baseline data from Task 1 to identify specific comparison gaps.
6.4.3 | Consumer Segment Friction-Point Mapping | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-01 05:30 | 2026-06-13 05:30 | 12 | Not Started | High | L | Number of identified friction points in 'during-meeting' content delivery | Sales journey map templates for Automotive/Banking sectors, interview transcripts | Needs internal stakeholder access (SVPs/Frontline Agents) for qualitative data.
6.4.4 | Sales Execution System Efficiency Framework | Conduct sandboxed technical evaluation and usability testing |  | 2026-06-13 05:30 | 2026-06-20 05:30 | 7 | Not Started | High | M | Stakeholder sign-off on the procurement criteria for just-in-time enablement tools | ROI calculator model, Lead Activation scorecards, executive presentation deck | Completion of tasks 2 and 3 to define target state metrics.
7 | Review information security compliance and data governance standards | Review information security compliance and data governance standards |  | 2026-06-20 05:30 | 2026-06-23 05:30 | 3 | Not Started | High | M | Signed approval from Chief Information Security Officer | Vendor security architecture documents, SOC2 reports | Can run parallel to usability testing
7.1 | Compile Enterprise Security and Data Governance Trust Pack | Review information security compliance and data governance standards |  | 2026-05-04 05:30 | 2026-05-16 05:30 | 12 | Not Started | High | M | Availability of a standardized security collateral folder in the Sales Playbook. | SOC2/ISO 27001 summaries, PII handling documentation, Data Processing Agreement (DPA), and cloud infrastructure architecture diagrams. | Requires sign-off from Legal and IT Security teams regarding current 2026 data standards.
7.1.1 | Consolidate Technical Security Certifications and Privacy Frameworks | Review information security compliance and data governance standards |  | 2026-04-10 05:30 | 2026-04-17 05:30 | 7 | Not Started | High | S | Completion of a centralized 'Security Vault' folder for procurement readiness. | SOC2 Type II reports, ISO 27001 certificates, GDPR compliance maps, and data encryption architecture diagrams. | Requires internal audit of current DevOps and InfoSec documentation.
7.1.2 | Develop Industry-Specific Data Governance Whitepapers | Review information security compliance and data governance standards |  | 2026-04-17 05:30 | 2026-05-01 05:30 | 14 | Not Started | High | L | Document approval from the Legal and InfoSec teams for external distribution. | Technical writing resource, RBI/IRDAI compliance checklists (for BFSI/Insurance), and Pharma data privacy standards. | Depends on the finalization of the technical security audit.
7.1.3 | Create Frontline Sales Objection Handling Guide for Security | Review information security compliance and data governance standards |  | 2026-05-01 05:30 | 2026-05-06 05:30 | 5 | Not Started | Medium | M | 100% of the sales team trained on responding to initial IT/CISO security hurdles. | Battlecards for data residency, multi-tenancy architecture FAQs, and PII handling protocols. | Must align with the Enterprise Security Whitepaper technical specs.
7.1.4 | Build Pre-filled Vendor Security Assessment Questionnaire (VSAQ) Kit | Review information security compliance and data governance standards |  | 2026-05-06 05:30 | 2026-05-16 05:30 | 10 | Not Started | High | M | 50% reduction in time taken to submit security responses to Enterprise prospects. | Master response spreadsheet for standard enterprise procurement questions (SIG/CAIQ). | Requires input from the CTO or Head of Engineering for technical validation.
7.2 | Develop Sector-Specific Compliance Battlecards for Regulated Industries | Review information security compliance and data governance standards |  | 2026-05-16 05:30 | 2026-05-24 05:30 | 8 | Not Started | High | S | Usage rate of compliance-specific battlecards by sales teams during the procurement phase. | Industry-specific data sovereignty sheets for Banking, NBFC, and Pharma sectors focusing on frontline agent data access. | Needs input from Product Engineering on data masking and role-based access control (RBAC) features.
7.2.1 | Regulatory Audit & Compliance Requirement Mapping | Review information security compliance and data governance standards |  | 2026-04-27 05:30 | 2026-05-04 05:30 | 7 | Done | High | M | Documented list of 10+ critical compliance triggers per industry that influence software procurement. | Industry-specific regulatory guidelines (RBI, IRDAI), existing Sharpsell.ai product feature list, compliance gap analysis template. | Finalize list of target regulated sectors (e.g., Banking, Insurance, Pharma).
7.2.2 | Feature-to-Compliance Proof Point Development | Review information security compliance and data governance standards |  | 2026-05-04 05:30 | 2026-05-09 05:30 | 5 | Not Started | High | S | Verified set of 15+ value propositions linking Sharpsell.ai features to specific regulatory risk mitigations. | Sharpsell.ai product capability matrix, case studies on mis-selling prevention, technical documentation on data residency. | Regulatory Audit & Compliance Requirement Mapping.
7.2.3 | Drafting and Designing Sector-Specific Battlecards | Review information security compliance and data governance standards |  | 2026-05-09 05:30 | 2026-05-19 05:30 | 10 | Not Started | High | L | 3 sets of finalized high-fidelity battlecards for Banking, Insurance, and Pharma ready for distribution. | Sharpsell.ai brand design system, battlecard copy templates, interactive content previews for PitchWiz. | Feature-to-Compliance Proof Point Development.
7.2.4 | Procurement Guide Integration for Frontline Sales Teams | Review information security compliance and data governance standards |  | 2026-05-19 05:30 | 2026-05-24 05:30 | 5 | Not Started | Medium | M | Deployment of a 'Procurement Readiness' section within the Sharpsell.ai internal sales enablement portal. | Evaluation checklist for Enterprise procurement, InfoSec FAQ document, RFP response template for regulated industries. | Drafting and Designing Sector-Specific Battlecards.
7.3 | Create a Whitepaper on Mitigating PII Risks in Field Sales AI Enablement | Review information security compliance and data governance standards |  | 2026-05-24 05:30 | 2026-06-13 05:30 | 20 | Not Started | Medium | L | Number of marketing-qualified leads (MQLs) generated from CTO and Chief Risk Officer roles. | 10-page strategic guide, landing page for lead capture, and promotional email sequence for CROs. | Completion of user interviews with existing enterprise clients to document real-world data governance workflows.
7.3.1 | SME Interviews and Regulatory Mapping for Enterprise PII Compliance | Review information security compliance and data governance standards |  | 2026-05-18 05:30 | 2026-05-23 05:30 | 5 | Not Started | High | M | Comprehensive research brief detailing 2026 data privacy requirements for frontline sales teams. | Security architecture documentation, industry compliance checklists for BFSI and Pharma, and expert interview notes. | Secure commitment from internal Information Security and Legal teams for security protocol consultation.
7.3.2 | Drafting Whitepaper Content and Procurement Evaluation Framework | Review information security compliance and data governance standards |  | 2026-05-23 05:30 | 2026-06-02 05:30 | 10 | Not Started | High | L | First draft approval including a structured matrix for evaluating secure AI enablement tools. | Sharpsell.ai security specs, AI Lead Activation case studies, and a procurement scorecard template. | Completion of the research brief to ensure alignment with current sector-specific PII risks.
7.3.3 | Technical Validation and Security Checklist Creation | Review information security compliance and data governance standards |  | 2026-06-02 05:30 | 2026-06-06 05:30 | 4 | Not Started | Medium | S | Finalized one-pager security checklist for procurement teams in consumer-facing industries. | 10-point PII risk mitigation checklist and executive summary on data residency. | Review of the content draft by technical leads to verify AI security claims.
7.3.4 | Visual Design and Gated Content Funnel Deployment | Review information security compliance and data governance standards |  | 2026-06-06 05:30 | 2026-06-13 05:30 | 7 | Not Started | High | M | Live landing page with integrated lead tracking to generate MQLs from target Enterprise accounts. | Final PDF layout, branded landing page, and LinkedIn-ready social creative assets. | Final copy sign-off from the leadership team for public distribution.
7.4 | Produce an Interactive Security Checklist and Vendor Comparison Tool | Review information security compliance and data governance standards |  | 2026-06-13 05:30 | 2026-06-23 05:30 | 10 | Not Started | Medium | M | Download-to-demo conversion rate from the Security Trust landing page. | Web-based interactive PDF or microsite allowing prospects to score Sharpsell.ai against standard enterprise security requirements. | Design team availability for UI/UX elements of the checklist.
7.4.1 | Enterprise Compliance and Security Feature Mapping | Review information security compliance and data governance standards |  | 2026-05-28 05:30 | 2026-06-02 05:30 | 5 | Not Started | High | M | A finalized matrix of 25+ essential security and compliance parameters for enterprise sales software. | SOC2 documentation, GDPR compliance checklists, enterprise data privacy standards, and industry-specific regulatory benchmarks. | Initial alignment with the technical and legal teams on 2026 enterprise security standards.
7.4.1.1 | Produce the Enterprise Security and InfoSec Readiness Kit | Review information security compliance and data governance standards |  | 2026-04-26 05:30 | 2026-05-08 05:30 | 12 | Not Started | High | M | 50% reduction in time spent by sales teams during the technical due diligence phase | SOC2 Type II summary document, Penetration Testing executive summary, and Cloud Infrastructure architecture diagram | Product Engineering must provide the latest 2026 security audit reports and hosting architecture details
7.4.1.2 | Develop Sector-Specific Regulatory Compliance Fact Sheets | Review information security compliance and data governance standards |  | 2026-05-08 05:30 | 2026-05-16 05:30 | 8 | Not Started | High | S | Number of high-intent enterprise prospects downloading industry-specific compliance guides | Compliance mapping guides for RBI (Banking), IRDAI (Insurance), and Pharma-specific data handling protocols | Legal team verification of platform alignment with latest 2026 industry regulations
7.4.1.3 | Build Data Privacy and Sovereignty Sales Deck for IT Stakeholders | Review information security compliance and data governance standards |  | 2026-05-16 05:30 | 2026-05-26 05:30 | 10 | Not Started | Medium | L | Direct positive feedback from CISO or CTO personas during the procurement evaluation cycle | Technical presentation deck covering PII encryption, data residency in India, and GDPR/DPDP alignment | Finalization of the Data Processing Agreement (DPA) templates
7.4.1.4 | Create the Enterprise Integration and SSO Implementation Guide | Review information security compliance and data governance standards |  | 2026-05-26 05:30 | 2026-06-02 05:30 | 7 | Not Started | High | M | Decrease in security-related objections raised during the Pilot/POC stage | Technical whitepaper on SAML 2.0, OAuth integration, and Mobile Device Management (MDM) compatibility | Success stories from previous enterprise deployments involving complex SSO environments
7.4.2 | Vendor Comparison Scoring Engine Development | Review information security compliance and data governance standards |  | 2026-06-02 05:30 | 2026-06-09 05:30 | 7 | Not Started | High | L | Validated scoring logic that provides a 'Vendor Readiness Score' based on specific user inputs. | Comparison logic spreadsheets, vendor performance benchmarks, and weighted scoring algorithms for field-sales capabilities. | Completion of security feature mapping to ensure technical weightage is accurate.
7.4.3 | Interactive Web UI Design and Development | Review information security compliance and data governance standards |  | 2026-06-09 05:30 | 2026-06-19 05:30 | 10 | Not Started | Medium | L | A functional beta version of the interactive tool deployed on a staging environment for internal testing. | Sharpsell.ai brand style guides, primary color #b00054 assets, low-code interactive tool framework, and mobile-responsive wireframes. | Completion of the scoring engine architecture.
7.4.4 | Automated Benchmarking Report and CRM Integration | Review information security compliance and data governance standards |  | 2026-06-19 05:30 | 2026-06-23 05:30 | 4 | Not Started | High | S | 100 percent automation of custom report delivery and lead data synchronization with the CRM system. | Personalized PDF report templates, CRM API documentation, email automation copy, and lead capture form assets. | Final approval of the web UI and scoring results.
8 | Negotiate commercial terms and define service level agreements | Negotiate commercial terms and define service level agreements |  | 2026-06-23 05:30 | 2026-06-27 05:30 | 4 | Not Started | High | M | Finalized pricing structure and SLA document | Budget approvals, procurement guidelines | Dependent on usability testing and InfoSec approval
8.1 | Develop Value-Based Pricing Matrix for Distributed Sales Teams | Negotiate commercial terms and define service level agreements |  | 2026-06-01 05:30 | 2026-06-06 05:30 | 5 | Not Started | High | M | Sales cycle velocity reduction in the procurement phase | Commercial proposal template, ROI calculator, and competitive feature-price comparison | Successful completion of the product pilot and feature prioritization phase
8.1.1 | Create Industry-Specific ROI Calculators for Enterprise Frontline Teams | Negotiate commercial terms and define service level agreements |  | 2026-05-07 05:30 | 2026-05-17 05:30 | 10 | Not Started | High | L | Number of sales-qualified leads generated through the pricing tool | ROI whitepaper, sector-specific performance benchmarks, Excel-based interactive calculator | Existing case study data from Banking and Insurance deployments
8.1.2 | Map Feature Bundles to Frontline and Sales Management Personas | Negotiate commercial terms and define service level agreements |  | 2026-05-17 05:30 | 2026-05-24 05:30 | 7 | Not Started | High | M | Stakeholder approval of the tiered pricing structure | Tiered feature matrix, persona-based value proposition cards, PitchWiz usage guide | Product roadmap and feature availability for 2026
8.1.3 | Design Total Cost of Ownership (TCO) Comparison Guides | Negotiate commercial terms and define service level agreements |  | 2026-05-24 05:30 | 2026-05-29 05:30 | 5 | Done | Medium | M | Marketing collateral download rate from the website | Competitive comparison PDF, manual training vs. automation cost analysis | Market research on legacy sales enablement costs
8.1.4 | Formalize Multi-Geography Volume Discount and Licensing Models | Negotiate commercial terms and define service level agreements |  | 2026-05-29 05:30 | 2026-06-06 05:30 | 8 | Not Started | High | L | Reduction in enterprise contract negotiation cycle time | Standardized enterprise pricing sheet, discount threshold documentation | Alignment with Finance on gross margin targets for distributed teams
8.2 | Draft Industry-Specific SLA and Security Compliance Collateral | Negotiate commercial terms and define service level agreements |  | 2026-06-06 05:30 | 2026-06-13 05:30 | 7 | Not Started | High | L | Procurement and Legal approval turnaround time | Security whitepaper, SOC2 certification proof, and data residency policies for Banking/Insurance | Final technical architecture review from the IT and compliance teams
8.2.1 | Develop Vertical-Specific Compliance Briefs | Negotiate commercial terms and define service level agreements |  | 2026-05-18 05:30 | 2026-05-28 05:30 | 10 | Not Started | High | L | Completion of four distinct compliance briefs for Banking, Insurance, Pharma, and Automotive sectors. | Regulatory guidelines (RBI, IRDAI, HIPAA), technical architecture diagrams, and existing security certificates. | Requires sign-off from the technical and legal teams on data residency and encryption protocols.
8.2.2 | Draft Frontline-Centric Service Level Agreement (SLA) One-Pagers | Negotiate commercial terms and define service level agreements |  | 2026-05-28 05:30 | 2026-06-02 05:30 | 5 | Not Started | Medium | S | Standardized SLA document ready for procurement inclusion with 99.9% uptime commitment. | Support response time data, uptime statistics, and platform maintenance schedules. | Must align with the customer success team's current support capabilities and bandwidth.
8.2.3 | Create IT Security & Data Privacy FAQ for Consumer Enterprises | Negotiate commercial terms and define service level agreements |  | 2026-06-02 05:30 | 2026-06-09 05:30 | 7 | Done | High | M | Document addressing at least 20 critical security concerns common in enterprise IT evaluations. | SOC2/ISO certification details, data masking policies, and mobile device management (MDM) compatibility list. | Collate frequently asked questions from previous procurement cycles in the Consumer Durables and Construction sectors.
8.2.4 | Design Technical Procurement Evaluation Checklist | Negotiate commercial terms and define service level agreements |  | 2026-06-09 05:30 | 2026-06-13 05:30 | 4 | Not Started | Medium | S | A downloadable checklist for Chief Revenue Officers to use when vetting sales execution systems. | Product feature list, integration capabilities (CRM/LMS), and offline-mode technical specifications. | None.
8.3 | Create Execution Support and Platform Adoption Roadmap | Negotiate commercial terms and define service level agreements |  | 2026-06-13 05:30 | 2026-06-17 05:30 | 4 | Not Started | Medium | S | Stakeholder confidence score in post-purchase execution | Post-launch training schedule, AI role-play rollout plan, and customer success escalation matrix | Definition of target frontline user groups and geographical rollout phases
8.3.1 | Develop Frontline Adoption Blueprint for Enterprise Consumer Teams | Negotiate commercial terms and define service level agreements |  | 2026-05-05 05:30 | 2026-05-19 05:30 | 14 | Not Started | High | L | Number of high-intent MQLs (Marketing Qualified Leads) downloading the blueprint | Comprehensive Whitepaper, PDF Case Study on Adoption Benchmarks | Conduct interviews with Sales Leaders in the 2026 Insurance and Banking sectors to identify common friction points during digital transitions.
8.3.2 | Design PitchWiz Execution Training Modules for Sales Ops | Negotiate commercial terms and define service level agreements |  | 2026-05-19 05:30 | 2026-05-29 05:30 | 10 | Not Started | Medium | M | Completion rate of the 'First 30 Days' training module among pilot users | Interactive Training Slides, PitchWiz Setup Guide, Explainer Video | Alignment with the Sales Enablement team on core product features and the 2026 roadmap for AI Lead Activation.
8.3.3 | Launch 'Champion Program' Framework for Distributed Sales Agents | Negotiate commercial terms and define service level agreements |  | 2026-05-29 05:30 | 2026-06-05 05:30 | 7 | Not Started | High | S | Increase in Daily Active Usage (DAU) on the Sharpsell.ai platform during the pilot phase | Email Sequence Templates, Recognition Poster Graphics, Leaderboard Mockups | Validation of incentive structures with SVPs of Sales in Consumer Durables to ensure scalability across geographies.
8.3.4 | Create 2026 ROI and Adoption Projection Calculator | Negotiate commercial terms and define service level agreements |  | 2026-06-05 05:30 | 2026-06-17 05:30 | 12 | Not Started | Medium | L | Conversion rate from calculator usage to demo request | Web-based Interactive Calculator, Technical Documentation for Sales Reps | Integration of historical performance data from existing Automotive and NBFC clients to ensure projection accuracy.
8.4 | Produce Pilot ROI Case Study to Validate Commercial Terms | Negotiate commercial terms and define service level agreements |  | 2026-06-17 05:30 | 2026-06-27 05:30 | 10 | Not Started | High | M | Contract value retention versus initial quote | Data visualizations from pilot lead activation rates and frontline performance uplift | Availability of usage data and performance metrics from the pilot group
8.4.1 | Aggregate Quantitative Pilot Performance Metrics | Negotiate commercial terms and define service level agreements |  | 2026-06-01 05:30 | 2026-06-06 05:30 | 5 | Not Started | High | M | Completion of a verified data sheet showing improvements in pitch frequency and lead conversion. | Sharpsell usage dashboards, CRM lead conversion data, and field activity logs. | Access to pilot user group performance data versus historical benchmarks.
8.4.2 | Conduct Frontline Success Interviews and Qualitative Analysis | Negotiate commercial terms and define service level agreements |  | 2026-06-06 05:30 | 2026-06-16 05:30 | 10 | Not Started | Medium | L | Minimum of five recorded testimonials showcasing specific time-savings or objection-handling wins. | Interview scripts tailored for field agents, video recording software, and testimonial templates. | Coordination with Regional Sales Managers to identify 'power users' within the pilot.
8.4.3 | Draft Comparative 'Delta' Analysis Report | Negotiate commercial terms and define service level agreements |  | 2026-06-16 05:30 | 2026-06-23 05:30 | 7 | Not Started | High | M | Documented percentage lift in sales productivity between the pilot group and the control group. | Statistical visualization tools and branded case study presentation template. | Finalized quantitative data from Task 1 and qualitative feedback from Task 2.
8.4.4 | Develop Executive ROI Presentation for Commercial Sign-off | Negotiate commercial terms and define service level agreements |  | 2026-06-23 05:30 | 2026-06-27 05:30 | 4 | Not Started | High | S | Finalized presentation ready for Chief Revenue Officer and Procurement review in 2026. | ROI calculator model and high-level executive summary slide deck. | Completion of the Delta Analysis Report.
9 | Present final vendor recommendation for executive review and sign contract | Present final vendor recommendation for executive review and sign contract |  | 2026-06-27 05:30 | 2026-06-29 05:30 | 2 | Not Started | High | S | Fully executed vendor agreement for the selected enablement platform | Executive summary presentation, final contract draft | Dependent on commercial negotiation and legal review
9.1 | Develop Executive Value Business Case | Present final vendor recommendation for executive review and sign contract |  | 2026-06-04 05:30 | 2026-06-09 05:30 | 5 | Not Started | High | M | C-level approval of the business case and ROI projections | ROI Calculator, Frontline Capability Gap Analysis, Industry Success Stories | Consolidation of Pilot or POC performance data
9.1.1 | Develop Industry-Specific ROI Impact Models | Present final vendor recommendation for executive review and sign contract |  | 2026-05-18 05:30 | 2026-05-25 05:30 | 7 | Not Started | High | M | Completion of 4 vertical-specific ROI templates for CRO presentation | Benchmarking data from Banking/Insurance sectors, ROI calculator spreadsheet, financial impact templates | Requires baseline performance data from current field-testing or customer success reports
9.1.2 | Create Executive Board Deck for Sales Execution Strategy | Present final vendor recommendation for executive review and sign contract |  | 2026-05-25 05:30 | 2026-05-30 05:30 | 5 | Not Started | High | M | Approved executive deck finalized for internal stakeholder review | Sharpsell positioning framework, C-level messaging guide, high-resolution product visuals | Align with the ROI models to ensure financial projections are consistent across all assets
9.1.3 | Draft Procurement & Legacy Integration Gap Analysis | Present final vendor recommendation for executive review and sign contract |  | 2026-05-30 05:30 | 2026-06-03 05:30 | 4 | Not Started | Medium | S | Technical risk and gap assessment document for procurement review | CRM integration specs, comparison matrix of legacy LMS vs. Sales Enablement platforms | Consult product team for technical feasibility of deep integrations with legacy core banking or ERP systems
9.1.3.1 | Map Current Frontline Tech Stack and Workflow Gaps | Present final vendor recommendation for executive review and sign contract |  | 2026-05-05 05:30 | 2026-05-12 05:30 | 7 | Not Started | High | M | Documented list of manual steps in the current sales cycle that lead to productivity leakage. | Current workflow diagrams, frontline pain-point survey results, tech stack inventory. | Complete stakeholder interviews with frontline sales managers to identify real-world friction points.
9.1.3.2 | Document CRM and Lead Management System Integration Specs | Present final vendor recommendation for executive review and sign contract |  | 2026-05-12 05:30 | 2026-05-17 05:30 | 5 | Not Started | High | L | Completed technical requirement sheet for seamless lead and activity data synchronization. | Existing CRM API documentation, data flow mapping template, security compliance standards. | Technical audit of existing legacy systems to ensure Sharpsell.ai can sync data without friction.
9.1.3.3 | Create Legacy vs. AI-Powered Enablement Gap Analysis Report | Present final vendor recommendation for executive review and sign contract |  | 2026-05-17 05:30 | 2026-05-27 05:30 | 10 | Not Started | Medium | M | Stakeholder-approved report detailing missed revenue opportunities due to legacy tool limitations. | Sharpsell.ai ROI framework, competitive comparison matrix, internal performance benchmarks. | Consolidation of workflow gap data to highlight specific areas where AI automation drives uplift.
9.1.3.4 | Draft IT Security and Procurement Compliance Checklist | Present final vendor recommendation for executive review and sign contract |  | 2026-05-27 05:30 | 2026-05-31 05:30 | 4 | Not Started | Medium | S | Verified procurement-ready checklist to accelerate vendor vetting and reduce legal bottlenecks. | Standard security questionnaire, data residency requirements, procurement vendor onboarding forms. | Coordination with IT and legal departments to align on data privacy and enterprise security needs.
9.1.3.5 | Build Value-Based Procurement Scorecard for Stakeholders | Present final vendor recommendation for executive review and sign contract |  | 2026-05-31 05:30 | 2026-06-03 05:30 | 3 | Not Started | High | S | Finalized scorecard adopted by the executive committee for objective vendor selection. | ROI calculator, multi-stakeholder evaluation criteria, vendor scoring template. | Finalization of the Gap Analysis report to weight scoring toward critical business needs.
9.1.4 | Compile Frontline Field-Test Performance Benchmarks | Present final vendor recommendation for executive review and sign contract |  | 2026-06-03 05:30 | 2026-06-09 05:30 | 6 | Not Started | High | L | Documented 15% improvement in pitch consistency across pilot groups | Usage data from pilot programs, interview transcripts from frontline sales agents, 2026 performance trends | Requires raw data output from initial 30-day pilot phases to validate behavior change
9.2 | Coordinate Final Security and Data Privacy Audit | Present final vendor recommendation for executive review and sign contract |  | 2026-06-09 05:30 | 2026-06-16 05:30 | 7 | Done | High | M | Full clearance from Enterprise Security and Compliance departments | Sharpsell.ai SOC2/ISO Certifications, Data Privacy Agreement (DPA), InfoSec Questionnaire | Technical vetting by IT stakeholders
9.2.1 | Compile Enterprise-Grade Security and Compliance Documentation | Present final vendor recommendation for executive review and sign contract |  | 2026-05-24 05:30 | 2026-05-29 05:30 | 5 | Not Started | High | M | Successful submission of the security packet to the prospect's CISO and IT audit committee. | SOC2 Type II reports, ISO 27001 certifications, and DPDP compliance whitepapers specific to BFSI and Insurance data residency requirements. | Procurement of updated technical security specifications and cloud architecture diagrams from the engineering team.
9.2.2 | Develop Data Privacy Impact Assessment (DPIA) Briefing for Sales Leaders | Present final vendor recommendation for executive review and sign contract |  | 2026-05-29 05:30 | 2026-06-02 05:30 | 4 | Not Started | High | S | Sales leadership alignment on data privacy protocols before the final procurement review. | A simplified executive summary detailing how the Lead Management System anonymizes PII and ensures compliant frontline data handling. | Completion of the technical data flow mapping between the Sharpsell.ai platform and the client's existing CRM.
9.2.3 | Create Security-Focused Objection Handling Playbook for Procurement | Present final vendor recommendation for executive review and sign contract |  | 2026-06-02 05:30 | 2026-06-08 05:30 | 6 | Not Started | Medium | M | Zero unresolved security objections during the final vendor evaluation phase. | A specialized Battlecard addressing common IT concerns regarding AI model training, data leakage prevention, and secure API integrations. | Review of past audit queries from similar enterprise clients in the Consumer Durables and Automotive sectors.
9.2.4 | Design Post-Audit Trust and Data Safety Communication Kit | Present final vendor recommendation for executive review and sign contract |  | 2026-06-08 05:30 | 2026-06-16 05:30 | 8 | Not Started | Medium | L | 90% positive sentiment regarding data privacy in the pre-launch frontline agent survey. | Internal launch materials for frontline agents explaining how their performance data in AI Role-plays is secured and used ethically. | Final sign-off from the prospect's legal and data privacy officer on the end-user license agreement.
9.3 | Finalize MSA and SOW Legal Review | Present final vendor recommendation for executive review and sign contract |  | 2026-06-16 05:30 | 2026-06-26 05:30 | 10 | Not Started | High | L | Contract terms finalized and ready for signature | Master Service Agreement, Statement of Work, Pricing Schedule | Procurement team confirmation on billing cycles
9.3.1 | Security and Compliance Documentation Audit | Present final vendor recommendation for executive review and sign contract |  | 2026-06-07 05:30 | 2026-06-12 05:30 | 5 | Not Started | High | M | Zero high-risk findings in the vendor security assessment report. | SOC2 Type II reports, ISO 27001 certifications, Data Privacy Policy, and Sharpsell.ai security whitepaper. | Completion of technical pilot and initial vendor security clearance.
9.3.2 | Marketing Rights and Branding Clause Negotiation | Present final vendor recommendation for executive review and sign contract |  | 2026-06-12 05:30 | 2026-06-15 05:30 | 3 | Not Started | Medium | S | Inclusion of mutual case study and logo usage rights in the finalized MSA. | Standard MSA draft, brand usage guidelines, and mutual non-disclosure agreement (MNDA). | Internal approval of the co-marketing strategy for 2026.
9.3.3 | SOW Technical Deliverable and SLA Alignment | Present final vendor recommendation for executive review and sign contract |  | 2026-06-15 05:30 | 2026-06-22 05:30 | 7 | Not Started | High | L | Legal and Sales Ops sign-off on the specific platform uptime and support response times. | Detailed Statement of Work (SOW), implementation roadmap for Lead Activation, and custom SLA terms. | Finalization of the frontline sales team rollout schedule.
9.3.4 | Data Processing Agreement (DPA) Legal Review | Present final vendor recommendation for executive review and sign contract |  | 2026-06-22 05:30 | 2026-06-26 05:30 | 4 | Not Started | High | M | Fully executed DPA compliant with local data protection regulations. | DPA template, consumer data flow diagrams, and regional data residency requirements. | Confirmation of data storage locations for enterprise consumer data.
9.4 | Draft Post-Contract Implementation Roadmap | Present final vendor recommendation for executive review and sign contract |  | 2026-06-26 05:30 | 2026-06-29 05:30 | 3 | Not Started | Medium | S | Defined launch date for field sales teams | Rollout Timeline, Frontline Training Schedule, Resource Allocation Plan | Availability of Sales Enablement Leads for rollout
9.4.1 | Design Internal Rollout Communication Kit | Present final vendor recommendation for executive review and sign contract |  | 2026-05-31 05:30 | 2026-06-05 05:30 | 5 | Not Started | High | S | Percentage of frontline agents completing initial platform login within 48 hours | WhatsApp announcement templates, email scripts for Sales Leaders, and digital launch posters for regional offices | Finalization of the core feature set (e.g., PitchWiz or Copilot) prioritized for the specific industry rollout
9.4.2 | Produce Feature-Specific Micro-Learning Video Series | Present final vendor recommendation for executive review and sign contract |  | 2026-06-05 05:30 | 2026-06-17 05:30 | 12 | Not Started | High | M | Average completion rate of the onboarding learning journey across distributed teams | Series of 30-second screen recordings demonstrating interactive product illustrators and objection handling cards | Stable access to the customized Sharpsell.ai sandbox environment for recording
9.4.3 | Curate Industry-Specific Sales Battlecards and Playbooks | Present final vendor recommendation for executive review and sign contract |  | 2026-06-17 05:30 | 2026-06-25 05:30 | 8 | Not Started | High | M | Search frequency and content engagement scores within the platform's just-in-time library | Localized PDF playbooks and digital battlecards tailored for Banking, Automotive, or Insurance scenarios | Insights from regional sales managers regarding current frontline capability gaps
9.4.4 | Establish Gamified Adoption and Incentive Framework | Present final vendor recommendation for executive review and sign contract |  | 2026-06-25 05:30 | 2026-06-29 05:30 | 4 | Done | Medium | S | Month-on-month growth in Daily Active Users (DAU) and platform-assisted pitch closures | Leaderboard logic document, reward tier structure, and automated achievement badge designs | Alignment with the 2026 sales performance budget and incentive cycle