## Sheet1
PROJECT RAG STATUS TEMPLATE
Project Name: | < Insert Project Name > |  |  | Date: | < Insert Date Issued >
Project Number: | < Insert Project Number >
RAG Status Key
Rating | Definition / Action
Red | Immediate action required, critical issues impacting project deliverables.
Amber | Attention needed, potential risks or minor issues that may impact deliverables.
Green | On track, no immediate risks or issues.
RAG Criteria
Metric | Green |  | Amber |  | Red
Scope | Expected to deliver all base line approved scope. |  | Significant scope change requests not yet approved. |  | Significant scope creep and lack of a formal change request process.
Time | On track. Less than 1 months delay from approved schedule. |  | Delayed. |  | Significant delay.
Cost | On or under budget. |  | Over budget by 10%. |  | Significantly over budget. Greater than 10% over budget.
Risk | Risks are being managed without flow-on impacts and there are no issues. |  | Risks require attention to mitigate or there are outstanding issues that need resolution. |  | Indicates risks or issues that require immediate attention and may cause significant impacts.
Safety | Nil lost time injuries or notifiable incidents. |  | One (1) lost time injury or notifiable incident or OHS Inspection by Authority. |  | Two (2) or more lost time injuries or notifiable incidents.
Quality | No quality concerns. The scope is being delivered to relevant codes and compliance. |  | Quality concerns to resolve. There are concerns the project's scope is not being delivered to relevant codes and compliance. |  | Major quality concerns and non-conformance to relevant codes and compliance.
RAG Status Report
Metric | Rating | Comments / Actions
Scope |  | The project scope is well-defined and remains stable with no significant changes or deviations.
Time |  | The project schedule is facing some delays, and attention is required to address potential timeline risks.
Cost |  | The project is currently over budget due to unforeseen expenses, and immediate action is needed to control costs.
Risk |  | All identified project risks are being effectively managed, and no new risks have been reported.
Safety | < Insert Rating > | < Insert any comments and/or actions to occur >
Quality | < Insert Rating > | < Insert any comments and/or actions to occur >
Changes Since Last Status Report
Metric | Current Rating | Previous Rating | Trend | Comments
Scope |  |  | Improving | Project scope has been refined and is now stable.
Time |  |  | Improving | Project timeline improving from critical to manageable.
Cost |  |  | Worsening | Costs escalating, budget status worsening from manageable to critical.
Risk |  |  | Stable | Risks remain stable and under control.
Safety | < Insert Rating > | < Insert Previous Rating > | < Insert Trend > | < Insert any comments >
Quality | < Insert Rating > | < Insert Previous Rating > | < Insert Trend > | < Insert any comments >