## Cover
PROJECT INITIATION CHECKLIST
103 things a client-side team should have done before a contractor starts on site, grouped into five phases and five decision gates. Every item states the evidence that proves it is done, so the checklist survives a gate review rather than just making everyone feel organised.
HOW TO USE IT
1 | Fill in the Setup sheet | Project, sponsor, budget, jurisdiction and tier. The jurisdiction tells you which assurance framework applies - the Framework Mapping sheet has the detail.
2 | Decide what does not apply | Work down the checklist and set anything genuinely out of scope to Not applicable, with a reason in the comments. Do this once, deliberately, rather than item by item later.
3 | Give every item an owner and a date | An item with no owner and no date will not happen. The Flag column tells you what is overdue.
4 | Work by gate, not by row number | Filter on the Gate column and close out one gate at a time. The Framework Mapping sheet shows how many items and how many mandatory items sit at each gate.
5 | Record the evidence, not the tick | Column F says what 'done' looks like. Column M is where you record the document reference. A tick with no evidence is worth nothing at a gate review.
6 | Review it at every control group | The progress summary on Setup gives you percentage complete, overdue count and mandatory items outstanding - three numbers that fit on one slide.
THE FIVE PHASES AND FIVE GATES
| Phase | Gate reached | Items
| 1 Need & business case | G0 - G1 | 20
| 2 Funding & approvals | G1 | 14
| 3 Governance & team | G2 | 20
| 4 Planning & baselines | G2 - G3 | 25
| 5 Procurement & mobilisation | G3 - G4 | 24
| TOTAL |  | 103
WHAT IS IN THE WORKBOOK
| Sheet | Purpose | Update
| Setup | Project, governance and commercial details, plus the live progress summary by phase. | Once, then review
| Initiation Checklist | 103 activities across five phases, each with the evidence that proves it is done. | Weekly
| Framework Mapping | How the G0-G4 gates map to the NSW, VIC, QLD, WA, Infrastructure Australia and Commonwealth frameworks. | Reference
| Reference | Dropdown lists, status definitions and the cell conventions used across the workbook. | Review annually
WORKED EXAMPLE · WHAT A COMPLETED ROW LOOKS LIKE
| Ref | 2.04
| Phase | 2 Funding & approvals
| Gate | G1
| Activity | Confirm the delegation of authority
| How you know it is done | A written delegation naming who may approve variations, contracts and payments, and to what value.
| Type | Mandatory
| Owner | R. Alvarez, Portfolio Director
| Target date | 14 Sep 2026
| Status | Complete
| Date completed | 09 Sep 2026
| Evidence reference | DoA-2026-014 rev B, filed at 01 Governance / Delegations
| Comments | Variation limit set at $250k for the PM, above that to the sponsor.
IMPORTANT
This checklist is a working tool, not legal, financial or procurement advice. It is deliberately generic - your own delegations, procurement policy and assurance framework take precedence over anything written here, and frameworks are revised regularly.
Built for capital project teams by Mastt. Project controls, cost management and reporting · mastt.com

## Setup
PROJECT SETUP
Complete once. The checklist and the framework mapping both read from here.
Blue cells are yours. Off-white cells calculate themselves. The progress table at the foot of this sheet updates as you work through the checklist.
1 · PROJECT
Project name
Project or business case number
Client / owner organisation
Business unit or portfolio
Location
Jurisdiction |  | Sets which assurance framework is likely to apply.
Sector
One-line description of the project
2 · GOVERNANCE
Project sponsor
Project director or manager
Steering committee chair
Project tier |  | Drives how much assurance your framework requires.
Applicable assurance framework |  | See the Framework Mapping sheet for the detail.
Delegation limit for this project
3 · COMMERCIAL
Approved capital budget (excluding GST)
Contingency held within the budget
Contingency as a percentage of budget
Funding source or sources
Intended delivery model
Target contract award date
Target date for practical completion
4 · CHECKLIST CONTROL
Checklist owner
Date started
Date of this review
Next review due
Current gate
Target date for the next gate
PROGRESS BY PHASE
Phase | Progress | % complete | Complete / applicable | Overdue | Mandatory outstanding
1 Need & business case |  | 0% | 0 / 20 | 0 | 15
2 Funding & approvals |  | 0% | 0 / 14 | 0 | 12
3 Governance & team |  | 0% | 0 / 20 | 0 | 15
4 Planning & baselines |  | 0% | 0 / 25 | 0 | 15
5 Procurement & mobilisation |  | 0% | 0 / 24 | 0 | 20
ALL PHASES |  | 0% | 0 / 103 | 0 | 77
'Overdue' counts items with a target date in the past that are not complete and not marked not applicable. 'Mandatory outstanding' is the number that should stop a gate being passed. Percentage complete excludes items marked not applicable, so marking things N.A. flatters the number - use it honestly.
Built with Mastt ¦ mastt.com

## Initiation Checklist
PROJECT INITIATION CHECKLIST
Overall complete 0% Overdue 0 Mandatory outstanding 77
Ref | Phase | Gate | Activity | How you know it is done | Type | Owner | Target date | Status | Date completed | Flag | Evidence reference | Comments
1.01 | 1 Need & business case | G0 | Define the service need or problem | A written problem statement backed by evidence - demand data, condition assessment, compliance gap or service shortfall. Not a solution in disguise. | Mandatory |  |  | Not started |  | no date
1.02 | 1 Need & business case | G0 | Confirm strategic alignment | A documented line of sight from the problem to the corporate plan, asset strategy or portfolio priority. | Mandatory |  |  | Not started |  | no date
1.03 | 1 Need & business case | G0 | Complete options analysis | Base case (do nothing), do minimum and at least two investment options, each costed and assessed against the same criteria. | Mandatory |  |  | Not started |  | no date
1.04 | 1 Need & business case | G0 | Test non-asset solutions | Demand management, operational and policy alternatives considered, with reasons for rejection recorded. | Recommended |  |  | Not started |  | no date
1.05 | 1 Need & business case | G1 | Draft the preliminary scope and functional brief | A brief describing what the asset must do, the key spaces or capacities, and the performance requirements. | Mandatory |  |  | Not started |  | no date
1.06 | 1 Need & business case | G1 | Prepare an order-of-cost estimate | Estimate by a qualified cost manager stating the basis, base date, source data, exclusions and accuracy range. | Mandatory |  |  | Not started |  | no date
1.07 | 1 Need & business case | G1 | Complete the economic appraisal | Cost-benefit or cost-effectiveness analysis with a stated discount rate, appraisal period and benefit-cost ratio. | Mandatory |  |  | Not started |  | no date
1.08 | 1 Need & business case | G1 | Model whole-of-life cost | Capex, opex, lifecycle replacement and disposal costs over the asset life, agreed with the asset owner. | Mandatory |  |  | Not started |  | no date
1.09 | 1 Need & business case | G1 | Identify and quantify the benefits | Every benefit has a measure, a baseline, a target, a timeframe and a named benefit owner. | Mandatory |  |  | Not started |  | no date
1.10 | 1 Need & business case | G1 | Complete the strategic risk assessment | Risks to the investment decision identified, rated, and reflected in both the options analysis and the contingency. | Mandatory |  |  | Not started |  | no date
1.11 | 1 Need & business case | G1 | Assess site or asset condition and constraints | Survey, condition report and constraints plan covering access, services, adjoining owners and continuing operations. | Mandatory |  |  | Not started |  | no date
1.12 | 1 Need & business case | G1 | Identify the planning and approvals pathway | Consent authority, assessment type and indicative timeframes confirmed in writing by a planner. | Mandatory |  |  | Not started |  | no date
1.13 | 1 Need & business case | G1 | Screen heritage, native title and cultural heritage | Searches completed and, where triggered, a plan and budget for assessment and consultation. | If applicable |  |  | Not started |  | no date
1.14 | 1 Need & business case | G1 | Screen environmental and contamination risk | Desktop review covering contamination, flooding, bushfire, biodiversity and any EPBC Act triggers. | Mandatory |  |  | Not started |  | no date
1.15 | 1 Need & business case | G1 | Scope early geotechnical and services investigation | Scope, budget and site access arranged so that ground and services risk is priced, not assumed. | Recommended |  |  | Not started |  | no date
1.16 | 1 Need & business case | G1 | Complete market sounding | Documented engagement with the market on capacity, appetite, packaging and acceptable risk allocation. | Recommended |  |  | Not started |  | no date
1.17 | 1 Need & business case | G1 | Test affordability against the forward estimates | Estimate reconciled to the capital program envelope across each relevant financial year. | Mandatory |  |  | Not started |  | no date
1.18 | 1 Need & business case | G1 | Prepare the business case | Business case complete against the applicable jurisdiction's template and guidance - see the Framework Mapping sheet. | Mandatory |  |  | Not started |  | no date
1.19 | 1 Need & business case | G1 | Have the business case independently reviewed | Peer or gateway review completed, with recommendations closed out or formally accepted with reasons. | Recommended |  |  | Not started |  | no date
1.20 | 1 Need & business case | G1 | Complete the early assurance review | Review report received, rating recorded, and every action assigned to a person with a due date. | Mandatory |  |  | Not started |  | no date
2.01 | 2 Funding & approvals | G1 | Confirm the funding sources | Each source named, the amount confirmed, and any conditions or milestone triggers documented. | Mandatory |  |  | Not started |  | no date
2.02 | 2 Funding & approvals | G1 | Approve and phase the capital budget | Approved total split by financial year, matching the cash flow forecast and the program. | Mandatory |  |  | Not started |  | no date
2.03 | 2 Funding & approvals | G1 | Set contingency and escalation | Contingency quantified - ideally risk-based rather than a flat percentage - with escalation indices and a base date stated. | Mandatory |  |  | Not started |  | no date
2.04 | 2 Funding & approvals | G1 | Confirm the delegation of authority | A written delegation naming who may approve variations, contracts and payments, and to what value. | Mandatory |  |  | Not started |  | no date
2.05 | 2 Funding & approvals | G1 | Obtain investment approval | Minute or resolution recording the approved scope, budget, program and any conditions attached. | Mandatory |  |  | Not started |  | no date
2.06 | 2 Funding & approvals | G1 | Record funding conditions and reporting obligations | Conditions extracted into an obligations register with an owner and a due date against each one. | Mandatory |  |  | Not started |  | no date
2.07 | 2 Funding & approvals | G1 | Execute grant or co-contribution agreements | Executed agreement on file, with acquittal requirements and the milestone claim schedule extracted. | If applicable |  |  | Not started |  | no date
2.08 | 2 Funding & approvals | G1 | Set the project up in the finance system | Project number, cost centre and WBS created, access granted, and a first commitment able to be raised. | Mandatory |  |  | Not started |  | no date
2.09 | 2 Funding & approvals | G1 | Confirm the accounting treatment | Capitalisation policy, GST treatment and the asset recognition point agreed with finance in writing. | Recommended |  |  | Not started |  | no date
2.10 | 2 Funding & approvals | G1 | Confirm the insurance strategy | Decision recorded on principal-arranged versus contractor-arranged cover, with limits and excesses set. | Mandatory |  |  | Not started |  | no date
2.11 | 2 Funding & approvals | G1 | Agree the statutory approvals strategy | Approvals list, sequencing, lodgement dates and responsible party recorded - DA, CDC, EIS, EPBC, s.68 and similar. | Mandatory |  |  | Not started |  | no date
2.12 | 2 Funding & approvals | G1 | Confirm land tenure, acquisition and easements | Title searches complete; any acquisitions, leases or easements identified with their own program and budget. | Mandatory |  |  | Not started |  | no date
2.13 | 2 Funding & approvals | G1 | Identify authority and utility requirements | Service authority applications, relocations, lead times and connection agreements scoped and programmed. | Mandatory |  |  | Not started |  | no date
2.14 | 2 Funding & approvals | G1 | Approve the project mandate or charter | Charter signed by the sponsor stating objectives, scope, budget, program, governance and tolerances. | Mandatory |  |  | Not started |  | no date
3.01 | 3 Governance & team | G2 | Appoint the project sponsor in writing | A named individual with the authority and the availability to act, accountable for the benefits. | Mandatory |  |  | Not started |  | no date
3.02 | 3 Governance & team | G2 | Establish the steering committee or control group | Terms of reference approved, membership named, and quorum and decision rights defined. | Mandatory |  |  | Not started |  | no date
3.03 | 3 Governance & team | G2 | Set the meeting and reporting calendar | A published calendar for control group, project meetings and executive reporting for the next 12 months. | Mandatory |  |  | Not started |  | no date
3.04 | 3 Governance & team | G2 | Appoint the project director or manager | Appointment letter, position description and written delegation issued. | Mandatory |  |  | Not started |  | no date
3.05 | 3 Governance & team | G2 | Issue the delegations of authority matrix | A matrix of approval thresholds by role for variations, extensions of time, payments and commitments. | Mandatory |  |  | Not started |  | no date
3.06 | 3 Governance & team | G2 | Agree the responsibility assignment | A RACI or equivalent covering every major decision and deliverable, accepted by each party. | Mandatory |  |  | Not started |  | no date
3.07 | 3 Governance & team | G2 | Issue the project organisation chart | Chart showing client, consultant and contractor interfaces and the single point of contact for each. | Recommended |  |  | Not started |  | no date
3.08 | 3 Governance & team | G2 | Resource the client-side team | Cost manager, superintendent, design manager and other advisers engaged or scheduled with confirmed availability. | Mandatory |  |  | Not started |  | no date
3.09 | 3 Governance & team | G2 | Appoint the probity adviser | Engagement letter and probity plan in place before the procurement process begins. | If applicable |  |  | Not started |  | no date
3.10 | 3 Governance & team | G2 | Collect conflict of interest declarations | Declarations from every decision maker and evaluator, reviewed, with any conflict actively managed. | Mandatory |  |  | Not started |  | no date
3.11 | 3 Governance & team | G2 | Agree the reporting framework | Report format, data sources, cut-off dates, cadence and audience agreed, with a template issued. | Mandatory |  |  | Not started |  | no date
3.12 | 3 Governance & team | G2 | Configure the project management system | Project, budget, contracts, cost codes and users set up, with one agreed source of truth. | Mandatory |  |  | Not started |  | no date
3.13 | 3 Governance & team | G2 | Establish the cost breakdown structure | CBS or code of accounts agreed and mirrored in the finance system, the estimate and the reporting. | Mandatory |  |  | Not started |  | no date
3.14 | 3 Governance & team | G2 | Set document management and naming conventions | Repository live, with folder structure, naming convention and version control published to all parties. | Mandatory |  |  | Not started |  | no date
3.15 | 3 Governance & team | G2 | Agree correspondence and RFI protocols | Who may issue and respond to formal correspondence, and the required turnaround times. | Recommended |  |  | Not started |  | no date
3.16 | 3 Governance & team | G2 | Set information security and access controls | Access permissions by role, external party access rules and data handling requirements confirmed. | Recommended |  |  | Not started |  | no date
3.17 | 3 Governance & team | G2 | Confirm records retention obligations | Applicable records legislation identified and retention periods set for project records. | Recommended |  |  | Not started |  | no date
3.18 | 3 Governance & team | G2 | Approve the project execution plan | PEP covering scope, governance, program, cost, risk, quality, safety, communications and handover. | Mandatory |  |  | Not started |  | no date
3.19 | 3 Governance & team | G2 | Approve the stakeholder and communications plan | Stakeholders mapped by influence and interest, with engagement method, owner and frequency for each. | Mandatory |  |  | Not started |  | no date
3.20 | 3 Governance & team | G2 | Define the change control procedure | Thresholds, forms, approval path and register defined before any commitment is made. | Mandatory |  |  | Not started |  | no date
4.01 | 4 Planning & baselines | G2 | Sign off the scope baseline | Scope statement with explicit inclusions and exclusions, approved by the sponsor and put under change control. | Mandatory |  |  | Not started |  | no date
4.02 | 4 Planning & baselines | G2 | Finalise the design brief | Functional and technical brief issued, covering standards, authority requirements and any BIM or digital requirements. | Mandatory |  |  | Not started |  | no date
4.03 | 4 Planning & baselines | G2 | Establish the work breakdown structure | WBS to the level at which cost and progress will actually be controlled, aligned to the cost breakdown structure. | Recommended |  |  | Not started |  | no date
4.04 | 4 Planning & baselines | G2 | Baseline the master program | Logic-linked program with durations, dependencies, schedule contingency and a named, dated baseline version. | Mandatory |  |  | Not started |  | no date
4.05 | 4 Planning & baselines | G2 | Identify the critical path and float | Critical path documented, float ownership stated in the contract, and long-lead items flagged. | Mandatory |  |  | Not started |  | no date
4.06 | 4 Planning & baselines | G2 | Agree the key milestone dates | Milestones agreed with the sponsor and carried consistently into the funding profile and the contract. | Mandatory |  |  | Not started |  | no date
4.07 | 4 Planning & baselines | G2 | Baseline the budget by cost breakdown structure | Approved budget allocated across the CBS, with contingency held separately and visibly. | Mandatory |  |  | Not started |  | no date
4.08 | 4 Planning & baselines | G2 | Prepare the cash flow forecast | S-curve by month and financial year, reconciled to both the program and the funding profile. | Mandatory |  |  | Not started |  | no date
4.09 | 4 Planning & baselines | G2 | Agree the contingency drawdown protocol | Who can release contingency, on what evidence, and how each drawdown is reported. | Mandatory |  |  | Not started |  | no date
4.10 | 4 Planning & baselines | G2 | Document the escalation assumptions | Base date, index source and escalation rates stated and agreed with finance. | Recommended |  |  | Not started |  | no date
4.11 | 4 Planning & baselines | G2 | Have the cost estimate independently reviewed | Independent estimate review or benchmarking completed, with differences reconciled and explained. | Recommended |  |  | Not started |  | no date
4.12 | 4 Planning & baselines | G2 | Approve the risk management plan | Plan setting the risk process, rating scales, appetite, tolerances and escalation path. | Mandatory |  |  | Not started |  | no date
4.13 | 4 Planning & baselines | G2 | Populate and rate the risk register | Risks with cause, consequence, existing controls, ratings, treatments, owners and due dates. | Mandatory |  |  | Not started |  | no date
4.14 | 4 Planning & baselines | G2 | Complete a quantitative risk assessment | Cost and schedule risk modelled to P50 and P90, and used to set the contingency rather than a rule of thumb. | Recommended |  |  | Not started |  | no date
4.15 | 4 Planning & baselines | G2 | Establish the opportunity register | Value improvement and opportunity items captured with owners and target dates. | Recommended |  |  | Not started |  | no date
4.16 | 4 Planning & baselines | G2 | Establish the issue and decision registers | Registers live, with escalation criteria and a standing agenda item at every control group meeting. | Mandatory |  |  | Not started |  | no date
4.17 | 4 Planning & baselines | G2 | Establish the assumptions and constraints register | Every material assumption recorded with an owner and the date by which it must be confirmed or retired. | Recommended |  |  | Not started |  | no date
4.18 | 4 Planning & baselines | G2 | Establish the interface and dependency register | Interfaces with other projects, continuing operations and authorities recorded with named owners. | Recommended |  |  | Not started |  | no date
4.19 | 4 Planning & baselines | G2 | Approve the benefits realisation plan | Measures, baselines, targets, data sources, measurement dates and benefit owners all confirmed. | Mandatory |  |  | Not started |  | no date
4.20 | 4 Planning & baselines | G3 | Define the quality requirements | Standards, inspection and test requirements, hold and witness points, and the defect management process. | Mandatory |  |  | Not started |  | no date
4.21 | 4 Planning & baselines | G3 | Determine WHS principal contractor duties | Decision recorded on who is principal contractor, with the required appointment, notification and WHS management plan. | Mandatory |  |  | Not started |  | no date
4.22 | 4 Planning & baselines | G3 | Initiate the safety in design process | Risk workshops scheduled, a safety in design register established, and designer duties communicated in writing. | Mandatory |  |  | Not started |  | no date
4.23 | 4 Planning & baselines | G3 | Set the sustainability and ESG targets | Ratings or targets - Green Star, NABERS, IS, embodied carbon - written into the brief and the contract, not just the strategy. | Recommended |  |  | Not started |  | no date
4.24 | 4 Planning & baselines | G3 | Address modern slavery and supply chain requirements | Reporting obligations identified and supplier requirements written into the tender documents. | If applicable |  |  | Not started |  | no date
4.25 | 4 Planning & baselines | G3 | Set local content and participation targets | Local jobs, Indigenous participation, apprentice and SME targets set, with a reporting method that can actually be measured. | If applicable |  |  | Not started |  | no date
5.01 | 5 Procurement & mobilisation | G3 | Approve the procurement strategy | Strategy covering packaging, delivery model, risk allocation, market approach and procurement program. | Mandatory |  |  | Not started |  | no date
5.02 | 5 Procurement & mobilisation | G3 | Select and justify the delivery model | Model chosen - construct only, design and construct, ECI, construction management, alliance or PPP - with the reasoning recorded. | Mandatory |  |  | Not started |  | no date
5.03 | 5 Procurement & mobilisation | G3 | Select the contract form | Form and amendments selected, with legal review of every departure from the standard form. | Mandatory |  |  | Not started |  | no date
5.04 | 5 Procurement & mobilisation | G3 | Complete the tender documentation | Conditions of tender, contract, scope, drawings, specifications and returnable schedules reviewed and consistent with each other. | Mandatory |  |  | Not started |  | no date
5.05 | 5 Procurement & mobilisation | G3 | Approve the evaluation plan before release | Criteria, weightings, scoring method and panel approved and dated before the tender is issued - never after. | Mandatory |  |  | Not started |  | no date
5.06 | 5 Procurement & mobilisation | G3 | Put the probity plan in place | Probity plan issued, briefing held, and the probity adviser engaged for the evaluation. | If applicable |  |  | Not started |  | no date
5.07 | 5 Procurement & mobilisation | G3 | Complete prequalification or EOI | Shortlist confirmed against capability, capacity, financial standing and safety record. | Recommended |  |  | Not started |  | no date
5.08 | 5 Procurement & mobilisation | G3 | Release the tender and control addenda | Issue register maintained, questions answered to all tenderers, addenda numbered and acknowledgement obtained. | Mandatory |  |  | Not started |  | no date
5.09 | 5 Procurement & mobilisation | G4 | Complete the tender evaluation | Evaluation report with scoring, clarifications, non-conformances and a clear, supported recommendation. | Mandatory |  |  | Not started |  | no date
5.10 | 5 Procurement & mobilisation | G4 | Complete due diligence on the preferred tenderer | Financial checks, licence and insurance verification, referee checks and confirmation of available capacity. | Mandatory |  |  | Not started |  | no date
5.11 | 5 Procurement & mobilisation | G4 | Negotiate and execute the contract | Executed contract with all schedules and annexures complete, and every departure resolved and initialled. | Mandatory |  |  | Not started |  | no date
5.12 | 5 Procurement & mobilisation | G4 | Receive and verify the security | Bank guarantees or bonds received, wording checked against the contract, expiry diarised, originals held securely. | Mandatory |  |  | Not started |  | no date
5.13 | 5 Procurement & mobilisation | G4 | Verify the insurances | Certificates of currency for works, public liability, workers compensation and professional indemnity, checked against the contract. | Mandatory |  |  | Not started |  | no date
5.14 | 5 Procurement & mobilisation | G4 | Verify licences and accreditations | Contractor and key subcontractor licences, registrations and scheme accreditations confirmed current. | Mandatory |  |  | Not started |  | no date
5.15 | 5 Procurement & mobilisation | G4 | Execute the consultant agreements | All consultant appointments signed, with scope, fee, novation position and professional indemnity confirmed. | Mandatory |  |  | Not started |  | no date
5.16 | 5 Procurement & mobilisation | G4 | Formally appoint the Superintendent | Written appointment issued to both parties, stating the scope of the delegation and any limits on it. | Mandatory |  |  | Not started |  | no date
5.17 | 5 Procurement & mobilisation | G4 | Arrange site handover | Access and possession date agreed, existing services identified, site rules issued and a dilapidation survey completed. | Mandatory |  |  | Not started |  | no date
5.18 | 5 Procurement & mobilisation | G4 | Hold the pre-construction meeting | Agenda covering program, safety, quality, communications, payment process and authorities, with minutes issued. | Mandatory |  |  | Not started |  | no date
5.19 | 5 Procurement & mobilisation | G4 | Accept the contractor's program | Program checked against the contract dates and for logic, then accepted or rejected in writing within the contract timeframe. | Mandatory |  |  | Not started |  | no date
5.20 | 5 Procurement & mobilisation | G4 | Agree the payment claim and certification process | Claim dates, format, supporting information, certification timeframes and the applicable Security of Payment Act confirmed. | Mandatory |  |  | Not started |  | no date
5.21 | 5 Procurement & mobilisation | G4 | Load the baselines into the reporting system | Budget, program, contract and risk baselines live in the system, with the first report date scheduled. | Mandatory |  |  | Not started |  | no date
5.22 | 5 Procurement & mobilisation | G4 | Apply lessons learned from prior projects | Prior lessons reviewed and turned into specific actions carried into this project's plans. | Recommended |  |  | Not started |  | no date
5.23 | 5 Procurement & mobilisation | G4 | Hand project records to the delivery team | Initiation records, decisions and assumptions transferred, with a documented handover meeting. | Recommended |  |  | Not started |  | no date
5.24 | 5 Procurement & mobilisation | G4 | Complete the readiness-to-proceed review | Gate review or internal readiness check completed and approval to commence delivery formally recorded. | Mandatory |  |  | Not started |  | no date
Add your own rows inside the table rather than below it, so the progress summary on the Setup sheet keeps counting them. Every item needs an owner and a target date - an item with neither is a wish, not a task. Where an item genuinely does not apply, set the status to Not applicable and say why in the comments; it is then excluded from the percentage complete. This sheet is set to print A3 landscape - for A4, hide columns F, M and N first.
Built with Mastt ¦ mastt.com
Formulas:
Flag = IF([Activity]="","",IF(OR([Status]="Complete",[Status]="Not applicable"),"",IF([Target date]="","no date",IF([Target date]<TODAY(),"OVERDUE "&(TODAY()-[Target date])&"d","in "&([Target date]-TODAY())&"d"))))

## Framework Mapping
FRAMEWORK MAPPING
How the gates in this checklist line up with Australian assurance and gateway frameworks
The gates below are generic so the checklist works anywhere. This sheet maps them to the frameworks that actually govern assurance in each jurisdiction. Where a cell says a gate is not covered, that is the fact - do not invent a gate name to fill the gap.
THE GATES USED IN THIS CHECKLIST
Gate | What it is called here | The decision it makes |  |  | Checklist items at this gate |  | Mandatory items at this gate
G0 | Strategic need confirmed | Is there a real problem worth investigating, and should we spend money developing options? |  |  | 4 |  | 3
G1 | Business case approved and funding committed | Is this the right investment, is it affordable, and are we willing to fund it? |  |  | 30 |  | 24
G2 | Governance, planning and baselines in place | Are we set up to deliver, with scope, budget, program and risk baselined and under change control? |  |  | 39 |  | 27
G3 | Ready to go to market | Are the documents, the strategy and the evaluation approach ready to release to the market? |  |  | 14 |  | 9
G4 | Contract awarded and ready to start delivery | Do we award, and are both sides genuinely ready to commence on site? |  |  | 16 |  | 14
CROSSWALK TO AUSTRALIAN ASSURANCE FRAMEWORKS
Gate | What it is called here | NSW Infrastructure Investor Assurance Framework (IIAF) | VIC Investment Lifecycle and HVHR Gateway | QLD Project Assessment Framework (PAF) | WA Strategic Asset Management Framework (SAMF) | CTH Infrastructure Australia Assessment Framework | CTH Assurance Reviews Process (RMG 106) | Notes
G0 | Strategic need confirmed | Gate 0 Go/No-go Gate 1 Strategic Options | Gate 1 Concept and Feasibility | Stage 1 Strategic assessment of service requirement Stage 2 Preliminary evaluation | Strategic Asset Plan Application for Concept Approval | Stage 1 Defining problems and opportunities Stage 2 Identifying and analysing options | Gate 0 Business need | Two gates in NSW, one in Victoria. Queensland runs two stages here.
G1 | Business case approved and funding committed | Gate 2 Business Case | Gate 2 Business Case | Stage 3 Business case development | Business Case (required above $5 million) | Stage 3 Developing a business case | Gate 1 Business case | The investment decision. Every framework has this one, and every framework treats it as the point of no easy return.
G2 | Governance, planning and baselines in place | No separate gate - delivery readiness is tested within Gate 2 and again at Gate 3 | No separate gate - sits between Gate 2 and Gate 3 | Within Stage 3 and Stage 4 | Project Definition Plan | Not covered - IA assesses the investment proposal, not delivery readiness | Gate 2 Delivery strategy | The gap in most frameworks. Delivery readiness is assumed rather than gated - which is exactly why projects arrive at market unprepared.
G3 | Ready to go to market | Gate 3 Readiness for Market | Gate 3 Readiness for Market | Stage 4 Supply strategy development | Project Definition Plan - the pre-tender reality check | Not covered | Gate 2 Delivery strategy | Called Readiness for Market in both NSW and Victoria. WA tests it through the Project Definition Plan instead.
G4 | Contract awarded and ready to start delivery | Gate 4 Tender Evaluation | Gate 4 Tender Decision | Stage 5 Source supplier/s | Not separately gated | Not covered | Gate 3 Investment decision | The award decision. Note that the Commonwealth calls this Gate 3, not Gate 4.
Beyond G4 | After contract award | Gate 5 Readiness for Service Gate 6 Benefits Management | Gate 5 Readiness for Service Gate 6 Benefits Realisation | Stage 6 Establish service capability Stage 7 Deliver service Stage 8 Benefits realisation | Post-implementation reporting under the SAMF policy | Stage 4 Post completion review | Gate 4 Readiness for service Gate 5 Benefits realisation | Out of scope for an initiation checklist, shown so you know what comes next and can plan for it.
FRAMEWORK REGISTER · WHAT EACH ONE IS AND WHERE IT SITS
Framework |  | Owner | Current version | Stages or gates, in order |  |  | What to watch out for
NSW Gateway Policy (TPG22-12) |  | NSW Treasury | Issued 28 March 2022, in force | An umbrella policy delivered through three coordination agencies: the IIAF for infrastructure (Infrastructure NSW), the Recurrent Expenditure Assurance Framework or REAF for recurrent spend (TPG24-24), and the Digital Assurance Framework for ICT. |  |  | Replaced the former standalone NSW Gateway Review System. If someone refers to 'the NSW Gateway', ask which of the three they mean.
Infrastructure Investor Assurance Framework (IIAF) |  | Infrastructure NSW | March 2026, incorporating Addendum 8 (February 2026) | Gate 0 Go/No-go · Gate 1 Strategic Options · Gate 2 Business Case · Gate 3 Readiness for Market · Gate 4 Tender Evaluation · Gate 5 Readiness for Service · Gate 6 Benefits Management |  |  | Addendum 8 renamed 'capital project' to 'infrastructure project', added an Interdependencies and Interfaces key focus area, extended Gate 6 to Tier 2 projects of $100m or more, and introduced joint Australian and NSW government assurance reviews.
Investment Lifecycle and High Value High Risk Guidelines |  | Department of Treasury and Finance (Vic) | Guidelines updated 28 October 2024; gateway guidance updated 18 June 2026 | Lifecycle stages: Business case · Procurement · Delivery. Gates: 1 Concept and Feasibility · 2 Business Case · 3 Readiness for Market · 4 Tender Decision · 5 Readiness for Service · 6 Benefits Realisation |  |  | The older five-stage Conceive / Prove / Procure / Implement / Realise model is legacy - some older DTF pages still show it. Project Assurance Plans now sit in DTF's Online Reporting Platform.
Project Assessment Framework (PAF) |  | Queensland Treasury | Policy overview August 2024; supporting guidelines November 2025 | 1 Strategic assessment of service requirement · 2 Preliminary evaluation · 3 Business case development · 4 Supply strategy development · 5 Source supplier/s · 6 Establish service capability · 7 Deliver service · 8 Benefits realisation |  |  | PAF has stages with approval-to-proceed points, not named gates - a reference to 'PAF Gate 2' is not an official term. The November 2025 guidelines replaced Queensland's separate Value for Money Framework guidance.
Business Case Development Framework (BCDF) |  | Qld Department of State Development, Infrastructure and Planning | Release 3.1, 25 February 2025 | Stage 1 Strategic Assessment · Stage 2 Options Analysis · Stage 3 Detailed Business Case |  |  | Applies to larger Queensland infrastructure proposals and runs alongside PAF, not instead of it.
Strategic Asset Management Framework (SAMF) |  | Department of Treasury (WA) | Policy dated December 2024; document collection updated July 2026 | Strategic Asset Plan · Application for Concept Approval · Business Case (required above $5 million) · Project Definition Plan |  |  | Deliverable-gated rather than numbered - there are no 'SAMF gates'. ICT-specific tools were added in December 2025 and July 2026.
Assessment Framework |  | Infrastructure Australia | 2021 edition, still the current published edition | Stage 1 Defining problems and opportunities · Stage 2 Identifying and analysing options · Stage 3 Developing a business case · Stage 4 Post completion review |  |  | IA moved to a three-Commissioner model in September 2024 and still assesses proposals seeking more than $250 million in Commonwealth funding. A National Planning and Assessment Framework is in development to harmonise business case development across jurisdictions.
Assurance Reviews Process (Gateway), RMG 106 |  | Department of Finance (Cth) | Current | Gate 0 Business need · Gate 1 Business case · Gate 2 Delivery strategy · Gate 3 Investment decision · Gate 4 Readiness for service · Gate 5 Benefits realisation |  |  | This is the Commonwealth's own internal gateway - not Infrastructure Australia. Applies to non-corporate Commonwealth entities above threshold. Note the numbering does NOT line up with NSW's 0-6 or Victoria's 1-6; this is the commonest source of confusion in cross-jurisdiction reporting.
ISA Assurance Framework (ISAAF) |  | Infrastructure SA | Version 3.0 | Assurance gates set by project tier - refer to the framework directly |  |  | Included for completeness. South Australian projects above threshold are assured under ISAAF rather than a Treasury gateway.
ISO 21502:2020 Guidance on project management |  | ISO / TC 258 | Edition 1, December 2020; systematic review closed March 2026 | Deliberately does not prescribe phase names. Clause 4.4 states that the number and names of phases depend on the project, and that each phase should be preceded by a decision point, often called a gate. Clause 6 practices: pre-project activities · overseeing · directing · initiating · controlling · managing delivery · closing or terminating · post-project activities |  |  | Use ISO 21502 to justify running a gated life cycle - not to name the gates. Anyone quoting 'the ISO project phases' is quoting something that does not exist.
PMBOK Guide, 8th edition |  | Project Management Institute | 8th edition, November 2025 (ANSI/PMI 99-001-2025) | Performance domains: Governance · Scope · Schedule · Finance · Stakeholders · Resources · Risk |  |  | The 8th edition superseded the 7th (2021), which had eight performance domains and had dropped the five process groups. If your PMO documents still cite PMBOK 7 or the process groups, they are behind.
Built with Mastt ¦ mastt.com

## Reference
REFERENCE · DROPDOWN LISTS & CONVENTIONS
These lists drive every picklist in the workbook. Add your own values inside the ranges rather than below them, so the dropdowns pick them up.
Status | Type | Gate | Phase | Yes / No | Jurisdiction | Sector | Delivery model | Project tier | Assurance framework
Not started | Mandatory | G0 | 1 Need & business case | Yes | NSW | Commercial | Construct only | Tier 1 - high value / high risk | NSW IIAF
In progress | Recommended | G1 | 2 Funding & approvals | No | VIC | Residential | Design and construct | Tier 2 - major | VIC HVHR Gateway
Complete | If applicable | G2 | 3 Governance & team | N.A. | QLD | Health | Early contractor involvement | Tier 3 - standard | QLD PAF
Blocked |  | G3 | 4 Planning & baselines |  | WA | Education | Managing contractor | Tier 4 - minor works | QLD BCDF
Not applicable |  | G4 | 5 Procurement & mobilisation |  | SA | Transport | Construction management |  | WA SAMF
[5 empty] | TAS | Water | Alliance |  | SA ISAAF
[5 empty] | NT | Energy | Public private partnership |  | Infrastructure Australia
[5 empty] | ACT | Defence | Design, bid, build |  | Commonwealth RMG 106
[5 empty] | Commonwealth | Civil / infrastructure | Not yet determined |  | Internal / corporate only
[5 empty] | Private sector | Industrial |  |  | None
Retail
Community / recreation
Mixed use
Other
STATUS DEFINITIONS
Not started | Nothing has begun. The default state for every item in a new checklist.
In progress | Work has started but the evidence in column F does not yet exist.
Complete | The evidence exists, has been reviewed, and is filed where column M says it is.
Blocked | Cannot progress without a decision or input from someone else. Should be escalated, not parked.
Not applicable | Genuinely does not apply to this project. Record why in the comments - 'not applicable' is the most abused status on any checklist.
CELL CONVENTIONS
You complete this | Pale blue fill, blue text.
Calculated | Off-white fill. A formula - do not type over it.
Subtotal or total | Light grey with a rule above. Always a formula.
Section band | Marks the start of a section.
Assurance frameworks are revised regularly. Confirm the current position for your jurisdiction before relying on the mapping. Nothing in this workbook is legal, financial or procurement advice.
Built with Mastt ¦ mastt.com