## 3 Week Look Ahead
THREE WEEK LOOK AHEAD SCHEDULE TEMPLATE
Project Name: | <Insert Project Name>
Project Number: | <Insert Project Number>
Date Period Start: | <Insert Date Period Start>
Date Period Finish: | <Insert Date Period Finish>
[9 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
Activity ID | Activity Name | Phase Name | Start Date | End Date | Duration (Days) | Percentage Complete | Status | Owner | 15: Week 01; 22: Week 02; 29: Week 03
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
A001 | Framing Task 1 | Framing | 2024-10-30 | 2024-11-03 | 4 | 0% | Not Started | Carpenter | bar: Week 03 16 to Week 03 20
A002 | Interior Finishing Task 2 | Interior Finishing | 2024-10-31 | 2024-11-01 | 1 | 0% | Not Started | Site Manager | bar: Week 03 17 to Week 03 18
A003 | Electrical Task 3 | Electrical | 2024-10-18 | 2024-10-22 | 4 | 100% | Completed | Foreman | bar: Week 01 4 to Week 02 8
A004 | Interior Finishing Task 4 | Interior Finishing | 2024-10-19 | 2024-10-24 | 5 | 66% | In Progress | Foreman | bar: Week 01 5 to Week 02 10
A005 | Foundation Task 5 | Foundation | 2024-10-29 | 2024-11-03 | 5 | 0% | Not Started | Foreman | bar: Week 03 15 to Week 03 20
A006 | Interior Finishing Task 6 | Interior Finishing | 2024-10-30 | 2024-11-02 | 3 | 0% | Not Started | Plumber | bar: Week 03 16 to Week 03 19
A007 | Foundation Task 7 | Foundation | 2024-10-28 | 2024-11-01 | 4 | 0% | Not Started | Foreman | bar: Week 02 14 to Week 03 18
A008 | Electrical Task 8 | Electrical | 2024-11-01 | 2024-11-04 | 3 | 0% | Not Started | Foreman | bar: Week 03 18 to Week 03 21
A009 | Foundation Task 9 | Foundation | 2024-10-29 | 2024-11-01 | 3 | 0% | Not Started | Plumber | bar: Week 03 15 to Week 03 18
A010 | Framing Task 10 | Framing | 2024-10-18 | 2024-10-23 | 5 | 83% | In Progress | Foreman | bar: Week 01 4 to Week 02 9
A011 | Foundation Task 11 | Foundation | 2024-10-25 | 2024-10-26 | 1 | 0% | Not Started | Foreman | bar: Week 02 11 to Week 02 12
A012 | Electrical Task 12 | Electrical | 2024-10-25 | 2024-10-27 | 2 | 0% | Not Started | Interior Specialist | bar: Week 02 11 to Week 02 13
A013 | Site Preparation Task 13 | Site Preparation | 2024-10-27 | 2024-11-01 | 5 | 0% | Not Started | Carpenter | bar: Week 02 13 to Week 03 18
A014 | Plumbing Task 14 | Plumbing | 2024-10-23 | 2024-10-24 | 1 | 0% | Not Started | Foreman | bar: Week 02 9 to Week 02 10
A015 | Site Preparation Task 15 | Site Preparation | 2024-10-25 | 2024-10-30 | 5 | 0% | Not Started | Site Manager | bar: Week 02 11 to Week 03 16
A016 | Framing Task 16 | Framing | 2024-10-22 | 2024-10-27 | 5 | 17% | In Progress | Electrician | bar: Week 02 8 to Week 02 13
A017 | Site Preparation Task 17 | Site Preparation | 2024-10-27 | 2024-10-30 | 3 | 0% | Not Started | Electrician | bar: Week 02 13 to Week 03 16
A018 | Framing Task 18 | Framing | 2024-10-16 | 2024-10-21 | 5 | 100% | Completed | Plumber | bar: Week 01 2 to Week 01 7
A019 | Interior Finishing Task 19 | Interior Finishing | 2024-10-19 | 2024-10-20 | 1 | 100% | Completed | Carpenter | bar: Week 01 5 to Week 01 6
A020 | Foundation Task 20 | Foundation | 2024-10-25 | 2024-10-30 | 5 | 0% | Not Started | Site Manager | bar: Week 02 11 to Week 03 16
A021 | Electrical Task 21 | Electrical | 2024-10-15 | 2024-10-18 | 3 | 100% | Completed | Electrician | bar: Week 01 1 to Week 01 4
A022 | Interior Finishing Task 22 | Interior Finishing | 2024-10-17 | 2024-10-18 | 1 | 100% | Completed | Site Manager | bar: Week 01 3 to Week 01 4
A023 | Foundation Task 23 | Foundation | 2024-10-31 | 2024-11-03 | 3 | 0% | Not Started | Foreman | bar: Week 03 17 to Week 03 20
A024 | Plumbing Task 24 | Plumbing | 2024-10-23 | 2024-10-28 | 5 | 0% | Not Started | Carpenter | bar: Week 02 9 to Week 02 14
A025 | Interior Finishing Task 25 | Interior Finishing | 2024-11-02 | 2024-11-03 | 1 | 0% | Not Started | Site Manager | bar: Week 03 19 to Week 03 20
A026 | Interior Finishing Task 26 | Interior Finishing | 2024-10-16 | 2024-10-20 | 4 | 100% | Completed | Interior Specialist | bar: Week 01 2 to Week 01 6
A027 | Framing Task 27 | Framing | 2024-10-30 | 2024-11-01 | 2 | 0% | Not Started | Interior Specialist | bar: Week 03 16 to Week 03 18
A028 | Foundation Task 28 | Foundation | 2024-10-31 | 2024-11-01 | 1 | 0% | Not Started | Carpenter | bar: Week 03 17 to Week 03 18
A029 | Foundation Task 29 | Foundation | 2024-10-19 | 2024-10-24 | 5 | 66% | In Progress | Interior Specialist | bar: Week 01 5 to Week 02 10
A030 | Plumbing Task 30 | Plumbing | 2024-10-28 | 2024-11-01 | 4 | 0% | Not Started | Plumber | bar: Week 02 14 to Week 03 18
A031 | Foundation Task 31 | Foundation | 2024-10-25 | 2024-10-27 | 2 | 0% | Not Started | Site Manager | bar: Week 02 11 to Week 02 13
A032 | Interior Finishing Task 32 | Interior Finishing | 2024-10-29 | 2024-11-02 | 4 | 0% | Not Started | Plumber | bar: Week 03 15 to Week 03 19
A033 | Foundation Task 33 | Foundation | 2024-10-23 | 2024-10-25 | 2 | 0% | Not Started | Carpenter | bar: Week 02 9 to Week 02 11
A034 | Framing Task 34 | Framing | 2024-10-15 | 2024-10-19 | 4 | 100% | Completed | Electrician | bar: Week 01 1 to Week 01 5
A035 | Framing Task 35 | Framing | 2024-10-29 | 2024-10-31 | 2 | 0% | Not Started | Carpenter | bar: Week 03 15 to Week 03 17
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
… | … | … | … | … | … | … | … | …
< Insert ID > | < Insert Activity Name > | < Insert Phase > | < Insert Start Date > | < Insert Finish Date > | < Insert Duration > | < Insert % Complete > | < Insert Status > | < Insert Owner >