Statement of Work Professional services and works packages — capital projects A contract-ready scope document for engaging a project manager, superintendent, design consultant, cost consultant, specialist advisor or works contractor on a construction or capital project. It sits under, and forms part of, an executed head agreement. Jurisdiction: Global — neutral jurisdiction · Template version 1.0

| DOCUMENT CONTROL |  |
| --- | --- |
| Project | [Insert project name] |
| Project number | [Insert project / job number] |
| Client / Principal | [Insert client legal entity name and company number] |
| Service Provider | [Insert service provider legal entity name and company number] |
| SOW reference | [Insert SOW reference, e.g. SOW-001] |
| SOW version | [Insert version, e.g. 1.0] |
| Head agreement reference | [Insert head / consultancy / framework agreement reference and date] |
| Effective date | [dd-mmm-yy] |
| Governing law / jurisdiction | [Insert governing law and jurisdiction] |
| Prepared by | [Insert name, position, organisation, date] |
| Reviewed by | [Insert name, position, organisation, date] |
| Approved by | [Insert name, position, organisation, date] |
| Currency | [Insert currency code, e.g. AUD / USD / GBP / EUR] |

# Revision history and document control

This Statement of Work is a controlled document. Every issue must be recorded below. The version in the document control table on the cover must match the latest row of this table.

| Rev | Date | Prepared by | Reviewed by | Approved by | Status | Summary of change |
| --- | --- | --- | --- | --- | --- | --- |
| 0.1 | [dd-mmm-yy] | [Insert] | [Insert] | [Insert] | Draft | First draft issued for internal review |
| 0.2 | [dd-mmm-yy] | [Insert] | [Insert] | [Insert] | Draft | Updated following Client comments on scope and exclusions |
| 1.0 | [dd-mmm-yy] | [Insert] | [Insert] | [Insert] | Issued for execution | Issued for execution under the Agreement |
| [Insert] | [dd-mmm-yy] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert summary of change and the Variation reference] |
| [Insert] | [dd-mmm-yy] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert summary of change and the Variation reference] |

[ Once this SOW is executed, it may only be changed through the change control process in clause 12. Record the Variation reference in the summary of change column so the audit trail is complete. ]

## Document distribution

| Recipient | Organisation | Role | Format | Date issued |
| --- | --- | --- | --- | --- |
| [Insert] | Client | Project Sponsor | PDF | [dd-mmm-yy] |
| [Insert] | Client | Project Director | PDF + native | [dd-mmm-yy] |
| [Insert] | Service Provider | Project Director | PDF + native | [dd-mmm-yy] |
| [Insert] | Client | Commercial / Procurement | PDF | [dd-mmm-yy] |
| [Insert] | Client | Legal | PDF | [dd-mmm-yy] |

## Status of this document

This SOW is not a standalone contract. It takes effect only under, and subject to, the head agreement identified in the document control table. If this SOW is issued before that agreement is executed, no work should commence and no cost is payable until it is.

# Table of contents

The table of contents below is a Word field. It will not populate until you update it.

To populate or refresh this table of contents: click anywhere in it, then press F9 (Windows) or Command + Option + Shift + U (Mac), and choose "Update entire table". In Word you can also select the whole document with Ctrl + A and press F9 to refresh every field, including the page numbers in the footer.

…

# How to use this template

This template is written to be edited. It deliberately contains more scope, more exclusions and more commercial machinery than most single engagements need, so that you delete rather than invent. Work through it in the following order.

1	Complete the document control table on the cover and confirm the head agreement reference. If there is no head agreement, stop: this SOW is not a substitute for one.

2	Complete clauses 1 to 3 so the parties, the project and the purpose of the engagement are unambiguous. These clauses set the interpretive frame for everything below.

3	Work clause 4 hard. Delete every service you are not buying, add the ones you are, and read the exclusions list line by line. Unclear exclusions are the single largest source of scope disputes on professional services engagements.

4	Populate the deliverables table in clause 5 and the expanded register in Appendix B. Every deliverable needs a format, a trigger, a reviewer and an acceptance authority — a deliverable nobody owns is never accepted and never paid.

5	Set the review periods in clause 6 and the turnaround times in clause 8.4 to numbers your own organisation can actually meet. Deemed acceptance protects the Service Provider; unrealistic periods will be used against you.

6	Align the Milestones in clause 7 and Appendix D with the fee schedule in clause 11 and Appendix C. Every payment milestone must be objectively verifiable.

7	Choose one fee basis in clause 11.1 and delete the others. Keep the guidance note explaining why you chose it — it is useful evidence later.

8	Complete the RACI in clause 9 and Appendix E with real names and real percentages, then delete every drafting note in square brackets before issue.

## Conventions used in this document

| Convention | What it means | What you must do |
| --- | --- | --- |
| [ grey italic text in square brackets ] | A drafting note from the template author explaining a choice you must make | Read it, act on it, then delete the whole note before issue |
| [Insert ...] | A fillable placeholder for project-specific information | Replace with the actual value; search the document for "[Insert" before issue |
| Shaded callout box | A warning or an instruction that materially affects risk | Read carefully; keep or delete depending on whether it survives into the issued SOW |
| Tables with example rows | Illustrative content showing the expected level of detail | Edit, extend or delete every row — do not issue example content |
| "the Agreement" | The head agreement, consultancy agreement or framework agreement above this SOW | Confirm the correct reference in the document control table |
| "the applicable jurisdiction" | Deliberately neutral language so the template works in any country | Replace with the governing law where a specific statute or regulator is required |
| Business Days | All periods are Business Days unless stated otherwise | Confirm the place used to determine Business Days in clause 1.5 |

[ Before issuing: use Find to search for "[Insert", for "[ " and for the word "example". If any result remains, the document is not ready to issue. ]

## How this document is structured

| Part | Clauses | What it does and who uses it |
| --- | --- | --- |
| Front matter | Cover, revision history, contents | Document control. Owned by the person issuing the SOW. |
| Framing | 1 – 3 | Who the parties are, what the Project is, and why this engagement exists. Read first when interpreting anything else. |
| The bargain | 4 – 7 | Scope, exclusions, Deliverables, acceptance and Milestones. This is the operative part and the part most often litigated. |
| The conditions | 8 – 10 | Assumptions, Client obligations, people and governance. Defines what has to be true for the bargain to hold. |
| The money | 11 – 12 | Fee basis, payment, and how change is priced and authorised. |
| The controls | 13 – 15 | Performance measurement, risk and safety, and information management. |
| The protections | 16 – 20 | Intellectual property, insurance and liability, probity, termination and disputes. Must be reconciled with the head agreement. |
| Execution | 21 | The signature block. |
| Appendices | A – H | The working documents: scope matrix, deliverables register, rates, milestone and payment schedule, RACI, and the change, acceptance and reporting forms. |

This template is provided by Mastt as general good-practice guidance for capital project delivery. It is not legal advice and it is not a substitute for advice from a qualified legal practitioner in the applicable jurisdiction. Neither Mastt nor the template author accepts liability for its use. Have your legal and commercial advisors review this SOW, and the head agreement it sits under, before execution.

# 1.  Parties and Agreement Structure

## 1.1  Parties

This Statement of Work is made between the parties identified below and forms part of the Agreement.

|  | Client / Principal | Service Provider |
| --- | --- | --- |
| Legal entity name | [Insert] | [Insert] |
| Company / registration number | [Insert] | [Insert] |
| Registered address | [Insert] | [Insert] |
| Address for notices | [Insert] | [Insert] |
| Authorised representative | [Insert name and position] | [Insert name and position] |
| Representative email | [Insert] | [Insert] |
| Representative telephone | [Insert] | [Insert] |
| Single point of contact (clause 10.6) | [Insert name] | [Insert name] |

## 1.2  Relationship to the Agreement

1.2.1	This SOW is issued under and forms part of the Agreement identified in the document control table. It does not create a separate contract and has no effect independently of the Agreement.

1.2.2	The Agreement's terms — including those governing liability, insurance, indemnity, intellectual property, confidentiality, termination and dispute resolution — apply to the Services in full. Where this SOW addresses those subjects it does so to record project-specific application, not to displace the Agreement.

1.2.3	Nothing in this SOW is intended to amend the Agreement. Any amendment to the Agreement must be made by a formal deed or variation instrument executed with the same formality as the Agreement itself.

1.2.4	The Service Provider is an independent contractor. Nothing in this SOW creates a partnership, joint venture, agency or employment relationship, except to the extent the Service Provider is expressly appointed as the Client's representative under clause 4.

## 1.3  Order of precedence

If there is an inconsistency or ambiguity between documents, the following order of precedence applies, with the document listed first prevailing to the extent of the inconsistency.

| Order | Document | Notes |
| --- | --- | --- |
| 1 | Formal instrument of agreement and any executed deed of variation | Executed with the highest formality |
| 2 | Special conditions of the Agreement | Project-specific amendments |
| 3 | General conditions of the Agreement | Standard form or bespoke terms |
| 4 | This Statement of Work (clauses 1 to 21) | The operative scope document |
| 5 | Appendices A to H to this Statement of Work | Detailed scope, registers and forms |
| 6 | Schedules and annexures to the Agreement | Including any pricing schedule |
| 7 | The Client brief and functional requirements | As issued and Accepted at the date stated in clause 2 |
| 8 | Drawings, specifications and models issued for the relevant purpose | Latest revision issued through the CDE |
| 9 | The Service Provider's proposal, fee submission and clarifications | Only to the extent expressly incorporated |
| 10 | All other documents referred to in any of the above | Informative unless expressly incorporated |

[ Delete any tier that does not exist on your project rather than leaving it in the list. A precedence clause that refers to documents that do not exist creates argument. If the Service Provider's proposal is to be incorporated, list the specific document, revision and date — never incorporate a whole proposal by reference. ]

## 1.4  Definitions

In this SOW, unless the context requires otherwise, the following terms have the meanings given below. Terms defined in the Agreement and not defined here carry their Agreement meaning.

| Term | Meaning |
| --- | --- |
| Acceptance | Written confirmation by the Acceptance Authority that a Deliverable meets the Acceptance Criteria in clause 6, evidenced by a signed Deliverable Acceptance Certificate (Appendix G) or by deemed acceptance under clause 6.6. |
| Agreement | The head agreement, consultancy agreement, framework agreement or contract identified in the document control table, under which this SOW is issued and of which it forms part. |
| Background IP | Intellectual property owned or licensed by a party before the Effective Date, or created independently of the Services, which is used in performing the Services or is embedded in a Deliverable. |
| Business Day | A day other than a Saturday, Sunday or public holiday in [Insert place of the Project / principal place of business]. Unless stated otherwise, all periods in this SOW are expressed in Business Days. |
| Client | [Insert Client / Principal legal entity name and company number], being the party procuring the Services, also referred to as the Principal or Owner. Includes its authorised representatives. |
| Confidential Information | All information of a confidential nature disclosed by or on behalf of a party in connection with the Project or the Services, in any form, whether or not marked confidential, including commercial, technical, cost, programme, security and personal information. |
| Deliverable | Any report, drawing, model, register, certificate, dataset, plan, estimate, submission or other tangible output the Service Provider is required to produce under clause 5 or Appendix B, including drafts and revisions. |
| Fee | The amounts payable to the Service Provider for the Services under clause 11, exclusive of Reimbursables and applicable taxes unless expressly stated otherwise. |
| Force Majeure | An event beyond the reasonable control of the affected party which it could not have prevented or avoided by reasonable precautions, as defined in the Agreement. Where the Agreement defines this term, the Agreement definition prevails. |
| Foreground IP | Intellectual property created by or for the Service Provider in the course of performing the Services, including all Deliverables and the working papers, models and data underlying them. |
| Key Personnel | The named individuals listed in clause 9.3 whose skills, experience and availability were material to the Client's decision to engage the Service Provider. |
| Milestone | A defined point in the programme listed in clause 7.1 or Appendix D, evidenced by the Acceptance of specified Deliverables or the occurrence of a defined event. |
| Project | The capital works project described in clause 2, including all stages, packages and associated enabling and decant works, whether or not within the Service Provider's scope. |
| Reimbursable | A cost properly and necessarily incurred by the Service Provider in performing the Services which is recoverable at cost under clause 11.6, subject to the exclusions in clause 11.7. |
| Services | The services described in clause 4 and Appendix A, together with all things reasonably necessary or incidental to their proper performance, whether or not expressly stated. |
| Service Provider | [Insert Service Provider legal entity name and company number], being the party providing the Services. Includes its personnel, subconsultants and subcontractors. |
| Site | The land and structures on, under, over or through which the Works are to be executed, together with any other place made available by the Client for the purposes of the Project. |
| SOW | This Statement of Work, including its appendices, as varied from time to time under clause 12. |
| Variation | An addition to, omission from or change in the Services, Deliverables, Milestones or assumptions recorded in this SOW, instructed or agreed under clause 12. |
| Works | The physical construction, refurbishment, demolition, fit-out, commissioning and associated works comprising the Project, executed by contractors engaged by the Client or by the Service Provider where clause 4 expressly so provides. |

## 1.5  Interpretation

1.5.1	Headings are for convenience only and do not affect interpretation.

1.5.2	The singular includes the plural and vice versa, and a reference to a gender includes every gender.

1.5.3	A reference to a clause, appendix or table is a reference to a clause, appendix or table of this SOW unless stated otherwise.

1.5.4	A reference to a party includes that party's successors and permitted assigns.

1.5.5	"Including", "for example" and similar expressions are not words of limitation.

1.5.6	A reference to a standard, code or guideline is to the version current at the Effective Date, unless this SOW expressly requires the version current at the time of performance.

1.5.7	All periods are expressed in Business Days determined by reference to [Insert place]. Where a period expires on a day that is not a Business Day, it expires on the next Business Day.

1.5.8	All monetary amounts are in [Insert currency code] unless expressly stated otherwise, and are exclusive of applicable transaction taxes unless expressly stated otherwise.

1.5.9	Where this SOW requires something to be done "in writing", an email from an authorised representative to the address in clause 1.1 is sufficient, unless the Agreement requires a formal notice.

# 2.  Background and Project Description

## 2.1  Project overview

[Insert a factual description of the Project in three to six sentences: what is being built or refurbished, where, for whom, why now, and what the finished asset will be used for. Avoid marketing language — this description is used to interpret the boundaries of the Services.]

[ The project description is the primary interpretive tool when a dispute arises about whether something is in scope. Write it factually and specifically. If the Project has stages, name them and say which stages this SOW covers. ]

## 2.2  Project particulars

| PROJECT PARTICULARS |  |
| --- | --- |
| Project name | [Insert] |
| Project number | [Insert] |
| Asset type / sector | [Insert, e.g. health, education, transport, water, commercial, residential, industrial] |
| Site address and description | [Insert] |
| Site area / gross floor area | [Insert m² or ha] |
| Approximate capital value of the Works | [Insert amount and currency] (excluding client-side costs) |
| Total project cost / funding envelope | [Insert amount and currency] |
| Approved control budget at the Effective Date | [Insert amount and currency] |
| Funding source(s) | [Insert, e.g. internal capital, grant, debt facility, PPP] |
| Current project stage at the Effective Date | [Insert, e.g. business case, concept design, developed design, tender, construction] |
| Target completion date | [dd-mmm-yy] |
| Delivery model | [Insert, e.g. traditional lump sum, design and construct, construction management, managing contractor, early contractor involvement, alliance, PPP] |
| Form of construction contract | [Insert standard form and edition, or 'bespoke'] |
| Sustainability rating target | [Insert scheme and target rating, or 'not applicable'] |
| Key constraints | [Insert, e.g. live operations, heritage, staged occupation, restricted access hours] |

## 2.3  Project objectives

The Project is being delivered to achieve the following objectives. The Services are to be performed so as to support these objectives.

| Ref | Objective | Success measure | Priority |
| --- | --- | --- | --- |
| PO-1 | Deliver the asset to the approved functional brief without unapproved reduction in scope or quality | Brief compliance confirmed at each gateway | [Insert] |
| PO-2 | Deliver within the approved control budget | Anticipated final cost ≤ control budget | [Insert] |
| PO-3 | Achieve practical completion by the target completion date | Certified practical completion on or before [dd-mmm-yy] | [Insert] |
| PO-4 | Zero serious harm to any person on or affected by the Project | No notifiable incident; leading indicators met | [Insert] |
| PO-5 | Achieve the target sustainability rating and carbon outcome | [Insert scheme] rating certified | [Insert] |
| PO-6 | Deliver an asset that is operable, maintainable and fully documented | O&M documentation complete at handover; no operational rework | [Insert] |
| PO-7 | Maintain stakeholder and community confidence throughout delivery | No sustained escalation; complaint closeout within agreed periods | [Insert] |
| PO-8 | Deliver the social and local procurement commitments | [Insert target] achieved and evidenced | [Insert] |

[ Delete objectives that do not apply and add project-specific ones. Rank them: when time, cost and scope conflict on site, the priority order recorded here tells the Service Provider how to decide. An unranked objectives list is of little practical use. ]

## 2.4  Project stages and this SOW

| Stage | Description | Covered by this SOW? | Notes |
| --- | --- | --- | --- |
| Stage 0 — Strategy and business case | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 1 — Concept design | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 2 — Developed design | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 3 — Detailed design and documentation | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 4 — Procurement and tender | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 5 — Construction | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 6 — Commissioning and handover | [Insert] | [Yes / No / Partial] | [Insert] |
| Stage 7 — Defects liability and closeout | [Insert] | [Yes / No / Partial] | [Insert] |

Where a stage is marked "No", the Service Provider has no obligation in that stage and no fee is payable for it. If the Client later requires services in that stage, it is a Variation under clause 12 — not an extension of the existing Fee.

## 2.5  Delivery model and contracting environment

[Insert a short description of how the Works are being procured and contracted, the packages involved, the other consultants and contractors engaged, and the interfaces the Service Provider must manage. Identify any novation, any early contractor involvement, and any separately engaged specialist that the Service Provider must coordinate but does not direct.]

## 2.6  Other parties engaged on the Project

| Party | Role | Engaged by | Interface with the Service Provider |
| --- | --- | --- | --- |
| [Insert] | Architect / lead design consultant | Client | Coordinated by SP; SP does not direct design content |
| [Insert] | Structural and civil engineer | Client / novated | Coordinated by SP |
| [Insert] | Services (MEP) engineer | Client / novated | Coordinated by SP |
| [Insert] | Cost consultant / quantity surveyor | Client | [Insert] |
| [Insert] | Principal / head contractor | Client | Administered by SP within delegation |
| [Insert] | Independent certifier / building surveyor | Client | SP provides information only |
| [Insert] | Planning and approvals consultant | Client | Coordinated by SP |
| [Insert] | Geotechnical and environmental consultants | Client | Coordinated by SP |
| [Insert] | Probity advisor | Client | SP complies with probity plan |
| [Insert] | Legal advisor | Client | SP provides factual input only |

# 3.  Purpose and Objectives of this SOW

## 3.1  Purpose

3.1.1	The purpose of this SOW is to define, with sufficient precision to be administered and enforced, the Services the Service Provider will perform, the Deliverables it will produce, when they are due, how they will be accepted, what the Client will provide in return, and how the Service Provider will be paid.

3.1.2	This SOW is the operative scope document for the engagement. Where the Service Provider is required to determine whether an activity falls within its obligations, that question is answered by reference to clause 4 and Appendix A, read with the exclusions in clause 4.4 and the assumptions in clause 8.

3.1.3	This SOW is intended to be capable of being administered by people who did not write it. Ambiguity is to be resolved in favour of the interpretation that gives effect to the Project objectives in clause 2.3.

## 3.2  Objectives of the engagement

| Ref | Objective of the engagement | How it is measured | Linked project objective |
| --- | --- | --- | --- |
| SO-1 | Provide competent, continuous and adequately resourced management of the Project across the stages in scope | KPI 13 and KPI 14 (clause 13); resourcing report | PO-1, PO-3 |
| SO-2 | Maintain a single, reliable source of truth for cost, time and risk | Monthly report accepted without material restatement (KPI 3) | PO-2, PO-3 |
| SO-3 | Give the Client early, honest warning of any threat to cost, time, quality, safety or reputation | Early warning notices issued within 2 Business Days | PO-1 to PO-7 |
| SO-4 | Protect the Client's contractual position at all times | 100% of contractual assessments issued within the time bar (KPI 7) | PO-2 |
| SO-5 | Deliver decision-ready information so the Client can decide once and quickly | Decisions taken within the clause 8.4 turnaround times | PO-1, PO-3 |
| SO-6 | Leave the Client with a complete, usable project record | Deliverable D-26 accepted at closeout | PO-6 |

## 3.3  What success looks like

The engagement will be regarded as successful if, at the end of the Services:

The asset was delivered to the approved brief, within the approved control budget, and on or before the target completion date, or any variance was formally approved before it occurred rather than reported after it.

No person was seriously harmed, and the Service Provider's safety assurance activity is evidenced rather than asserted.

The Client was never surprised: every material cost, time or risk movement was notified in the period it first became foreseeable.

Every contractual entitlement of the Client was preserved, and no entitlement was lost through a missed time bar or an unissued notice.

Deliverables were accepted at first submission in the great majority of cases, without the Client having to rewrite the Service Provider's work.

The final account was agreed without dispute, and the project record was handed over complete, indexed and in native format.

The Client would engage the Service Provider again on a comparable project.

[ This clause is not decorative. It is used at the performance reviews in clause 13.2 and should be read aloud at the first review. Edit it so it describes success on this project, not success in general. ]

## 3.4  Alignment to project objectives

The Service Provider must, when exercising any judgement or discretion under this SOW, act consistently with the Project objectives in clause 2.3 and their recorded priority. Where two objectives conflict and the conflict cannot be resolved within the Service Provider's delegation under clause 10.5, the Service Provider must escalate under clause 10.3 rather than resolve the conflict unilaterally.

# 4.  Scope of Services

## 4.1  General obligation

4.1.1	The Service Provider must perform the Services described in this clause 4, in Appendix A and in Appendix B, together with all things reasonably necessary or incidental to their proper performance, whether or not expressly described.

4.1.2	The Services must be performed with the degree of skill, care and diligence reasonably expected of a suitably qualified and experienced provider of comparable services on a project of similar type, scale, complexity and value in the applicable jurisdiction.

4.1.3	The Service Provider must perform the Services in accordance with the Agreement, this SOW, the Client's applicable policies and standards notified to it, and all laws applicable in the jurisdiction where the Services are performed.

4.1.4	The Service Provider must allocate sufficient, suitably qualified resources to perform the Services in accordance with the programme, and must not permit the Services to be delayed by its own resourcing decisions.

4.1.5	The Service Provider acknowledges it has satisfied itself as to the nature and extent of the Services, has raised all necessary clarifications before the Effective Date, and has priced the Services on the assumptions recorded in clause 8.

## 4.2  Scope by project phase

The table below summarises the Services by phase. Appendix A contains the detailed activity-level scope matrix, which prevails over this summary.

| Ref | Phase | Core obligation of the Service Provider | Principal outputs | In scope? |
| --- | --- | --- | --- | --- |
| P1 | Initiation / business case | Establish governance, controls baseline and project execution plan | Project execution plan, governance charter, initial risk register, control budget | [Insert] |
| P2 | Planning and design | Manage design development, cost planning, approvals and stakeholder input | Design programme, cost plans, design review reports, approvals tracker | [Insert] |
| P3 | Procurement / tender | Package strategy, tender documentation, evaluation and award recommendation | Procurement strategy, tender documents, evaluation report, award recommendation | [Insert] |
| P4 | Construction delivery | Contract administration, cost and programme control, quality and safety oversight | Monthly reports, progress claim assessments, variation assessments, forecast | [Insert] |
| P5 | Commissioning and handover | Manage commissioning, completion, handover and operational readiness | Commissioning plan oversight, completion checklists, handover register, O&M audit | [Insert] |
| P6 | Post-completion / defects | Defects liability management, final account, benefits and lessons learned | Defects register, final account report, project closeout report, lessons learned | [Insert] |

[ Mark each phase 'Yes', 'No' or 'Partial — see Appendix A'. Where a phase is partially in scope, the boundary must be described in Appendix A at activity level. A phase marked 'Partial' with no activity-level detail is an invitation to a dispute. ]

## 4.3  Services by discipline

The Service Provider's role in each discipline is stated below. "Lead" means the Service Provider owns the activity and its output. "Support" means the Service Provider contributes to an activity owned by another party. "Review" and "Approve" describe the Client's role.

| Ref | Discipline | Description of the service | Service Provider | Client |
| --- | --- | --- | --- | --- |
| D1 | Programme and schedule management | Baseline, update, analyse and report the integrated project programme | Lead | Review |
| D2 | Cost management and estimating | Cost plans, estimates, cash flow, cost reports and change valuation | Lead | Review |
| D3 | Contract administration | Administer the construction contracts as the Client's representative | Lead | Approve |
| D4 | Design management | Coordinate the design team, manage design programme, reviews and change | Lead | Input |
| D5 | Procurement and tendering | Package strategy, tender process, evaluation and recommendation | Lead | Approve |
| D6 | Risk and opportunity management | Maintain the risk register, facilitate workshops, quantify exposure | Lead | Input |
| D7 | Stakeholder and communications | Stakeholder mapping, engagement plan, community and authority liaison | Support | Lead |
| D8 | Health, safety and environment oversight | Client-side assurance of contractor HSE systems and performance | Support | Lead |
| D9 | Quality and technical assurance | Assurance of the contractor's ITPs, inspections and non-conformance closeout | Lead | Review |
| D10 | Commissioning and handover management | Commissioning readiness, witness testing coordination, handover documentation | Lead | Review |
| D11 | Reporting and project controls | Monthly reporting, dashboards, earned value and forecasting | Lead | Review |
| D12 | Information and document management | CDE administration, document control, records and transmittals | Lead | Support |

## 4.4  Services included

Without limiting clause 4.1, the Services include the following. This list is cumulative with Appendix A.

4.4.1	Act as the Client's principal representative for the Project and provide day-to-day management of the delivery of the Services and, where authorised, of the Works.

4.4.2	Prepare, obtain approval of, and maintain the Project Execution Plan, including governance, controls, assurance, communication and delegation arrangements.

4.4.3	Establish and maintain the integrated master programme, including baselining, monthly status updating, critical path analysis and what-if scenario modelling.

4.4.4	Establish and maintain the project control budget and cost plan, including the anticipated final cost forecast, commitment register and contingency drawdown register.

4.4.5	Prepare and maintain the Project cash flow forecast and reconcile actual expenditure against forecast each reporting period.

4.4.6	Manage the design programme and design team interfaces, chair design coordination meetings, and track design deliverables against the design deliverables schedule.

4.4.7	Coordinate and record design reviews at each design stage, including capture, tracking and closeout of review comments in a single comment register.

4.4.8	Manage value management and value engineering workshops, and maintain the register of opportunities identified, adopted, deferred or rejected with the reasons recorded.

4.4.9	Manage statutory approvals and third-party approvals interfaces, maintaining an approvals and conditions tracker to closeout.

4.4.10	Develop the procurement and packaging strategy, including recommended contract forms, packaging boundaries, market sounding and tender programme.

4.4.11	Prepare, assemble and issue tender documentation, manage the tender period including addenda and tenderer queries, and maintain the probity record of the process.

4.4.12	Evaluate tenders against the approved evaluation plan, prepare the tender evaluation report and award recommendation, and support contract negotiation and execution.

4.4.13	Administer the construction contracts on the Client's behalf, including instructions, notices, certificates, extensions of time and determinations, within the delegated authority recorded in clause 10.5.

4.4.14	Assess and certify contractor progress claims, including verification of quantities, measurement, retention, statutory declarations and supporting evidence.

4.4.15	Assess, price and recommend disposition of contractor variations and claims, and maintain the change and claims registers.

4.4.16	Chair and minute the Project Control Group, site and coordination meetings listed in clause 10.1, and issue minutes within the periods stated.

4.4.17	Maintain the Project risk and opportunity register, facilitate risk workshops at the frequency stated in clause 14.1, and report movement in the risk exposure each month.

4.4.18	Provide client-side assurance of the contractor's health, safety and environmental systems, including review of safety management plans and attendance at safety walks.

4.4.19	Provide client-side quality assurance, including review of inspection and test plans, surveillance of hold and witness points, and tracking of non-conformances to closure.

4.4.20	Manage commissioning readiness, witness testing coordination, and the transition to operational readiness including training and spares verification.

4.4.21	Manage the completion and handover process, including completion inspections, defects identification, handover documentation and warranty collation.

4.4.22	Manage the defects liability period, including defect notification, rectification tracking and final completion certification.

4.4.23	Prepare and issue the monthly report in the format required by Appendix H, and any ad hoc briefing papers or board papers reasonably requested.

4.4.24	Administer the common data environment and project document control in accordance with clause 15, including transmittals, revision control and the handover of native files.

4.4.25	Prepare the final account, project closeout report, benefits realisation input and lessons learned record at the end of the engagement.

## 4.5  Services excluded / out of scope

Read this list line by line before issue. Ambiguous or missing exclusions are the number one cause of scope and fee disputes on professional services engagements. Anything the Client expects but which is not listed as included should be added to clause 4.4; anything the Service Provider has not priced should be listed here.

The following are expressly excluded from the Services. If the Client requires any of them, they must be instructed as a Variation under clause 12 and priced before the work is performed.

4.5.1	Design of any part of the Works. The Service Provider manages and coordinates design but does not perform, warrant or take design responsibility for the design of others.

4.5.2	Certification of design or structural adequacy, and any service requiring the Service Provider to sign a designer's or engineer's certificate.

4.5.3	Preparation of statutory approval applications, environmental impact statements, or planning submissions in the Service Provider's own name.

4.5.4	Payment of statutory fees, application fees, authority charges, headworks charges, connection fees, bonds or securities, all of which remain a Client cost.

4.5.5	Site acquisition, land assembly, easements, leasing, valuation, or negotiation of property rights with adjoining owners.

4.5.6	Legal advice of any kind, including drafting, interpretation or negotiation of contracts, and any advice on statutory obligations of the Client.

4.5.7	Financial, taxation, accounting, funding, treasury, hedging or insurance broking advice.

4.5.8	Geotechnical, contamination, hazardous materials, unexploded ordnance, heritage or archaeological investigation, and the management of any resulting condition.

4.5.9	Removal, remediation or management of asbestos, contaminated soil, per- and polyfluoroalkyl substances, or other hazardous materials.

4.5.10	Utility relocation and diversion design, negotiation of works with utility authorities, and any authority-imposed programme consequences.

4.5.11	Third-party or independent certification, including independent certifier, principal certifying authority, building surveyor and commissioning agent roles.

4.5.12	Discharge of the principal contractor's or site controller's statutory health and safety duties. The Service Provider provides oversight only, and does not direct the means, methods or sequencing of construction work.

4.5.13	Preparation of the contractor's programme, methodology, temporary works design or construction sequencing.

4.5.14	Supply, storage, security or insurance of Client-furnished equipment, loose furniture, artwork or operational assets.

4.5.15	Operational readiness activities beyond those in clause 4, including recruitment, business process re-engineering, change management and staff training delivery.

4.5.16	Relocation, decant, removalist services and the migration of the Client's operations, data or information technology systems.

4.5.17	Post-occupancy evaluation, facilities management, asset management system population and ongoing building tuning beyond the period stated in clause 4.

4.5.18	Marketing, sales, leasing, tenancy coordination or tenant fit-out management.

4.5.19	Expert witness services, litigation support, forensic delay analysis, forensic quantum analysis or attendance at any dispute proceeding, whether or not related to the Project.

4.5.20	Attendance at meetings, workshops, site visits or hearings in excess of the frequencies and durations stated in clause 10.1 and the assumptions in clause 8.

4.5.21	Preparation of documentation in a language other than [Insert contract language], and any translation, interpretation or certified translation service.

4.5.22	Travel outside [Insert defined travel zone], and any accommodation or subsistence associated with it, unless separately authorised in writing.

4.5.23	Provision of site accommodation, site establishment, plant, equipment, survey instruments, testing apparatus or information technology hardware for the Client's use.

4.5.24	Building information modelling authoring, model federation, clash detection or model auditing unless expressly included in clause 15.5.

4.5.25	Development of the Client's enterprise systems, dashboards or data integrations beyond the reporting required by clause 10.2 and Appendix H.

4.5.26	Re-performance of Services made necessary by a Client-directed change of scope, standard, brief or budget after the relevant Deliverable has been Accepted.

4.5.27	Services arising from the insolvency, default, abandonment or replacement of any contractor or consultant, including re-tendering and novation management.

4.5.28	Management of any package, stage or work not listed in Appendix A, including future stages, options, provisional sums released after the Effective Date and separable portions.

4.5.29	Any service that is expressed as an assumption in clause 8 and later proves untrue, to the extent that additional effort results.

4.5.30	Any service that is stated in this SOW to be the responsibility of the Client, another consultant, a contractor or a third party.

## 4.6  Additional services

4.6.1	The Client may instruct additional services at any time. Additional services are Variations and must be instructed, priced and authorised under clause 12 before the Service Provider commences them.

4.6.2	Where an additional service is of a type covered by the schedule of rates in Appendix C, it is priced at those rates unless the parties agree a lump sum.

4.6.3	The Service Provider must not perform additional services on the basis of an informal request, a meeting minute, a verbal instruction, or an email that does not expressly authorise a Variation. Work performed without authorisation is performed at the Service Provider's risk and is not payable.

4.6.4	The Service Provider must notify the Client in writing within [Insert] Business Days of becoming aware that an instruction, a change in circumstances, or the failure of an assumption in clause 8 constitutes or is likely to constitute a Variation.

## 4.7  Scope boundaries and interfaces

| Interface | Service Provider obligation | Boundary — where the obligation stops |
| --- | --- | --- |
| Design team | Manage the design programme, coordinate reviews, track comment closeout | Does not perform, check or warrant design; does not direct design solutions |
| Head contractor | Administer the contract, assess claims, monitor progress | Does not direct means, methods, sequence or safety of construction work |
| Statutory authorities | Track approvals, coordinate responses to conditions | Does not lodge applications or hold the applicant role |
| Client operations | Provide information for operational readiness planning | Does not deliver operational change, training or recruitment |
| Client finance | Provide cost reports, forecasts and claim certifications | Does not make payment, hold funds or provide financial advice |
| Independent certifier | Provide information and access as required | Does not certify, and does not influence the certifier's determinations |
| Other packages / stages | Coordinate interfaces identified in Appendix A | No obligation for packages or stages not listed in Appendix A |

# 5.  Deliverables

## 5.1  General

5.1.1	The Service Provider must produce and submit the Deliverables listed in clause 5.4 and Appendix B, at the frequency and by the trigger stated, in the format stated.

5.1.2	Every Deliverable must be submitted through the common data environment in accordance with clause 15, using the naming convention in clause 15.3, and must be identified by its reference, revision and date.

5.1.3	A Deliverable is not submitted until it is submitted complete. Partial submissions, submissions marked "draft for information" where a formal issue is required, and submissions missing their supporting data do not start the review period in clause 6.

5.1.4	Each Deliverable must be accompanied by the native working files unless the Client agrees otherwise in writing. A PDF alone does not satisfy a native-file requirement.

5.1.5	The Service Provider must maintain a live deliverables register recording, for each Deliverable, its status, revision, submission date, review status, acceptance date and the acceptance certificate reference.

## 5.2  Deliverable standards

Each Deliverable must be internally consistent, and consistent with every other current Deliverable. A cost report that does not reconcile to the cost plan is not fit for purpose.

Each Deliverable must state its basis, its assumptions, its exclusions, its data sources and its date of information.

Each Deliverable must be traceable: the working files, calculations, models and source data behind it must be retrievable and must be handed over under clause 15.

Numerical Deliverables must be free of unexplained restatement. Where a figure changes from the previous period, the movement must be reconciled and explained.

Each Deliverable must be prepared, checked and approved by different individuals, and must record who did each on its cover sheet.

## 5.3  Ownership and reuse

5.3.1	Title to and intellectual property in the Deliverables is dealt with in clause 16.

5.3.2	The Client may reuse a Deliverable for the purposes of the Project, including for later stages and for the operation, maintenance, alteration and disposal of the asset, without further payment.

5.3.3	The Service Provider must not restrict the Client's use of a Deliverable by embedding proprietary formats, licence keys, watermarks or access controls that the Client cannot administer after the Services end.

## 5.4  Deliverables table

The rows below are realistic examples for a client-side construction project management engagement. They are provided to show the required level of detail. Edit, delete and extend every row so the table reflects the Deliverables actually being bought. Appendix B contains the expanded register with revision, distribution and retention columns.

| Ref | Deliverable | Description | Format | Standard / template | Frequency | Due date / trigger | Reviewer | Acceptance authority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D-01 | Project Execution Plan | Governance, controls, assurance and delivery approach for the Project | DOCX + PDF | Client PEP template | Once, then 6-monthly | 15 BD from Effective Date | Client PM | Project Director |
| D-02 | Project Governance Charter | Committees, membership, quorum, delegations and decision rights | DOCX + PDF | Client governance template | Once | 15 BD from Effective Date | Client PM | Project Sponsor |
| D-03 | Baseline Master Programme | Resource-loaded, logic-linked integrated programme with critical path | XER/MPP + PDF | Client scheduling standard | Once, then re-baseline on approval | 20 BD from Effective Date | Client Scheduler | Project Director |
| D-04 | Programme Update and Analysis | Progress update, critical path narrative, slippage and recovery actions | XER/MPP + PDF | Client scheduling standard | Monthly | With monthly report | Client Scheduler | Client PM |
| D-05 | Control Budget and Cost Plan | Elemental cost plan reconciled to the approved control budget | XLSX + PDF | Elemental cost plan format | At each design stage | 5 BD after stage issue | Client Cost Manager | Project Director |
| D-06 | Cash Flow Forecast | S-curve forecast of commitments and expenditure by period | XLSX | Client finance template | Monthly | With monthly report | Client Finance | Client PM |
| D-07 | Monthly Project Report | Full report per Appendix H, including cost, time, risk, HSE and quality | PDF + native | Appendix H | Monthly | By the 5th BD of each month | Client PM | Project Sponsor |
| D-08 | Risk and Opportunity Register | Live register with ratings, owners, treatments and quantified exposure | XLSX or PMIS | Client risk template | Monthly, workshops quarterly | With monthly report | Client Risk Manager | Client PM |
| D-09 | Procurement and Packaging Strategy | Package boundaries, contract forms, market approach and tender programme | DOCX + PDF | Client procurement template | Once per stage | [Insert date] | Client Procurement | Project Director |
| D-10 | Tender Documentation Set | Complete issued-for-tender package including conditions and returnables | PDF + native | Client tender template | Per package | Per procurement programme | Client Procurement | Project Director |
| D-11 | Tender Evaluation Report | Evaluation against the approved plan with scoring, probity and recommendation | DOCX + PDF | Client evaluation template | Per package | 10 BD after tender close | Evaluation Panel | Delegated Authority |
| D-12 | Contract Award Recommendation | Recommendation, commercial summary, risk position and approval paper | DOCX + PDF | Client board paper format | Per package | With evaluation report | Client Procurement | Delegated Authority |
| D-13 | Design Review Report | Consolidated review comments, compliance check against brief and budget | PDF + comment register | Client review template | Per design stage | 10 BD after stage issue | Client Design Lead | Client PM |
| D-14 | Progress Claim Assessment and Certificate | Assessment of contractor claim, measurement, retention and certificate | PDF + XLSX | Contract form | Monthly | Per contract time bar | Client Cost Manager | Superintendent / Contract Administrator |
| D-15 | Variation Assessment and Register | Assessment of entitlement and quantum, with cumulative change position | XLSX + PDF | Client change template | Monthly, and per event | 10 BD from receipt | Client Cost Manager | Delegated Authority |
| D-16 | Extension of Time Assessment | Delay analysis, entitlement determination and programme impact | DOCX + PDF | Contract form | Per event | Per contract time bar | Client PM | Superintendent / Contract Administrator |
| D-17 | Cost Report and Anticipated Final Cost | Committed, incurred, forecast and contingency drawdown position | XLSX + PDF | Client cost report format | Monthly | With monthly report | Client Cost Manager | Project Director |
| D-18 | HSE Assurance Report | Audit and surveillance findings, incident summary and trend analysis | PDF | Client HSE template | Monthly | With monthly report | Client HSE Manager | Client PM |
| D-19 | Quality Surveillance Report | ITP surveillance, hold and witness point results, NCR status | PDF | Client quality template | Monthly | With monthly report | Client Quality Lead | Client PM |
| D-20 | Commissioning Readiness Report | Commissioning plan status, systems readiness, witness test schedule | PDF | Client commissioning template | Monthly from [Insert stage] | With monthly report | Client Engineering | Project Director |
| D-21 | Completion and Handover Register | Completion inspections, defects list, handover documents and warranties | XLSX + PDF | Client handover template | Per completion event | 5 BD before completion | Client Facilities | Project Director |
| D-22 | Operations and Maintenance Manual Audit | Verification that O&M manuals, as-builts and warranties are complete | PDF checklist | Client O&M standard | Per completion event | 10 BD before handover | Client Facilities | Client PM |
| D-23 | Defects Register and Closeout Report | Defect notification, rectification status and final completion position | XLSX + PDF | Client defects template | Monthly during DLP | Monthly, and at final completion | Client Facilities | Project Director |
| D-24 | Final Account Report | Reconciled final account for each contract with supporting evidence | XLSX + PDF | Client final account format | Per contract | 20 BD after final completion | Client Cost Manager | Delegated Authority |
| D-25 | Project Closeout and Lessons Learned Report | Outturn performance, benefits input, lessons and record handover | DOCX + PDF | Client closeout template | Once | 20 BD after final completion | Client PM | Project Sponsor |
| D-26 | Records and Native File Handover | Complete, indexed transfer of the project record in native formats | Structured file set | Clause 15 naming convention | Once, plus on termination | 10 BD after final completion | Client Records | Client PM |

# 6.  Acceptance Criteria and Review Process

## 6.1  Fit for purpose

A Deliverable is fit for purpose, and is capable of Acceptance, when it satisfies each of the following criteria.

| Ref | Acceptance criterion | Test applied by the reviewer |
| --- | --- | --- |
| AC-1 | Complete | Contains every element required by clause 5.4 or Appendix B, with no placeholder, blank field or unresolved query |
| AC-2 | Compliant | Complies with the format, template, standard and naming convention specified for it |
| AC-3 | Accurate | Free of material error; figures reconcile to their source and to the other current Deliverables |
| AC-4 | Current | Based on the latest issued information, and states its date of information |
| AC-5 | Traceable | Assumptions, exclusions, sources and methodology are stated and the working files are provided |
| AC-6 | Decision-ready | A competent reader can take the decision the Deliverable exists to support without further work |
| AC-7 | Quality assured | Records the prepare / check / approve chain, performed by different individuals |
| AC-8 | Timely | Submitted on or before the due date or trigger |

"Fit for purpose" in this clause describes the standard of the Deliverable as a document. It does not impose a fitness-for-purpose warranty on the Service Provider's professional services, which are governed by the standard of care in clause 17.6 and by the Agreement.

## 6.2  Review periods

| Deliverable category | Client review period | Resubmission review period |
| --- | --- | --- |
| Routine periodic report or register (D-04, D-06, D-08, D-18, D-19) | [Insert, e.g. 5] Business Days | [Insert, e.g. 3] Business Days |
| Monthly project report (D-07) | [Insert, e.g. 5] Business Days | [Insert, e.g. 3] Business Days |
| Plan, strategy or governance document (D-01, D-02, D-09) | [Insert, e.g. 10] Business Days | [Insert, e.g. 5] Business Days |
| Baseline programme or control budget (D-03, D-05) | [Insert, e.g. 10] Business Days | [Insert, e.g. 5] Business Days |
| Tender or evaluation documentation (D-10, D-11, D-12) | [Insert, e.g. 10] Business Days | [Insert, e.g. 5] Business Days |
| Contractual assessment or certificate (D-14, D-15, D-16) | Per the contract time bar | Per the contract time bar |
| Completion, handover and closeout documentation (D-21 to D-26) | [Insert, e.g. 15] Business Days | [Insert, e.g. 10] Business Days |

The review period starts on the first Business Day after a complete submission is received through the CDE and the reviewer is notified.

## 6.3  Review outcomes

| Outcome | Meaning | Consequence |
| --- | --- | --- |
| Accepted | Meets all applicable criteria in clause 6.1 | Acceptance Certificate issued; any linked Milestone achieved; payment may be claimed |
| Accepted with comments | Meets the criteria; minor comments to be incorporated | Accepted; comments incorporated in the next revision at no additional cost |
| Not accepted — resubmit | Fails one or more criteria | Written reasons given by criterion; Service Provider resubmits under clause 6.4 |
| Not accepted — fundamental | Fails so substantially that a further review would serve no purpose | Escalated under clause 10.3; may trigger clause 13.3 remediation |

The Client must state the outcome in writing within the review period, and where a Deliverable is not accepted must identify the criterion in clause 6.1 that is not met and the specific deficiency relied on. A rejection that does not identify a criterion and a deficiency is not effective.

## 6.4  Resubmission

6.4.1	The Service Provider must resubmit a corrected Deliverable within [Insert, e.g. 5] Business Days of receiving the reasons for non-acceptance, unless the Client agrees a longer period in writing.

6.4.2	A resubmission must be accompanied by a response schedule addressing each stated deficiency, identifying where and how it has been resolved. A resubmission without a response schedule is not a complete submission.

6.4.3	The Client's review of a resubmission is limited to the stated deficiencies and to any consequential change, unless the resubmission introduces new material.

6.4.4	Revisions must be clearly marked, with changes tracked or clouded, so the reviewer is not required to compare documents manually.

## 6.5  Rework at the Service Provider's cost

6.5.1	Where a Deliverable is not accepted because it fails a criterion in clause 6.1, all correction, resubmission and re-review effort is at the Service Provider's cost. No Variation, additional fee, time-related cost or extension of a Milestone arises.

6.5.2	Where a Deliverable requires amendment because of a Client-directed change, a change in the brief, or the failure of an assumption in clause 8, the amendment is a Variation under clause 12.

6.5.3	Where a Deliverable is rejected more than [Insert, e.g. 2] times, the Client may escalate under clause 10.3, require a remediation plan under clause 13.3, or require replacement of the responsible personnel under clause 13.5.

6.5.4	Repeated failure of the same criterion across different Deliverables is evidence of a systemic deficiency and may be treated as a performance failure rather than an isolated rejection.

## 6.6  Deemed acceptance

Deemed acceptance protects the Service Provider from an unresponsive client. It also transfers real risk to the Client, because a defective Deliverable can become Accepted by inaction. Set the review periods in clause 6.2 to periods your organisation can genuinely meet, and make sure the named reviewers know they are named.

6.6.1	If the Client does not state a review outcome within the applicable review period, and does not request an extension before that period expires, the Deliverable is deemed Accepted on the Business Day after the period expires.

6.6.2	Deemed acceptance does not apply to a Deliverable that is materially incomplete on its face, to a contractual assessment or certificate, or where the Client has notified the Service Provider before expiry that additional time is required.

6.6.3	The Client may extend a review period once by up to [Insert, e.g. 5] Business Days by notice given before the original period expires.

6.6.4	Deemed acceptance does not relieve the Service Provider of liability for an error, omission or non-compliance in the Deliverable, and does not constitute a waiver of the standard of care in clause 17.6.

## 6.7  Acceptance certificate

Acceptance is evidenced by a Deliverable Acceptance Certificate in the form of Appendix G, signed by the Acceptance Authority named in clause 5.4. Where a Milestone payment is linked to Acceptance, the signed certificate is a condition precedent to the invoice for that Milestone.

# 7.  Milestones and Programme

## 7.1  Milestone table

Every payment milestone must be objectively verifiable by a person who was not involved in achieving it. "Design substantially complete" is not verifiable; "developed design Deliverable D-13 Accepted under clause 6" is. Percentages below must total 100%.

| Ref | Milestone | Description / evidence of achievement | Planned date | Dependency | Payment linked? | Value / % |
| --- | --- | --- | --- | --- | --- | --- |
| M-01 | SOW mobilisation complete | Team mobilised, PEP and governance charter Accepted | [Insert date] | Effective Date | Yes | 5% |
| M-02 | Baseline programme and control budget Accepted | Baseline programme and control budget approved by the Client | [Insert date] | M-01; Client brief issued | Yes | 5% |
| M-03 | Concept design stage complete | Concept design review report Accepted and cost plan reconciled | [Insert date] | Design consultant appointment | Yes | 10% |
| M-04 | Developed design stage complete | Developed design Accepted, cost plan within control budget | [Insert date] | M-03 | Yes | 10% |
| M-05 | Statutory approval obtained | Principal development or building approval issued | [Insert date] | Authority determination | Yes | 5% |
| M-06 | Tender documentation issued to market | Issued-for-tender package released for the main works | [Insert date] | M-04; procurement strategy approved | Yes | 10% |
| M-07 | Main works contract awarded | Evaluation report Accepted and contract executed | [Insert date] | M-06; Client delegated approval | Yes | 10% |
| M-08 | Site possession and construction commencement | Contractor granted access and works commenced | [Insert date] | M-07; Site availability | No | — |
| M-09 | Construction 25% complete | Certified value of work done reaches 25% of contract sum | [Insert date] | M-08 | Yes | 8% |
| M-10 | Construction 50% complete | Certified value of work done reaches 50% of contract sum | [Insert date] | M-09 | Yes | 8% |
| M-11 | Construction 75% complete | Certified value of work done reaches 75% of contract sum | [Insert date] | M-10 | Yes | 8% |
| M-12 | Commissioning commenced | Commissioning readiness report Accepted and testing started | [Insert date] | M-11 | No | — |
| M-13 | Practical completion achieved | Certificate of practical completion issued for the main works | [Insert date] | M-12; contractor performance | Yes | 10% |
| M-14 | Handover and operational readiness complete | Handover register closed, O&M audit Accepted, occupation achieved | [Insert date] | M-13 | Yes | 5% |
| M-15 | Final account agreed | Final account report Accepted for all contracts | [Insert date] | M-14; contractor agreement | Yes | 4% |
| M-16 | Defects liability period expired and project closed out | Final completion certified, closeout report Accepted | [Insert date] | M-15; DLP expiry | Yes | 2% |

## 7.2  Programme obligations

7.2.1	The Service Provider must submit the baseline master programme within [Insert, e.g. 20] Business Days of the Effective Date, in the scheduling software and to the standard stated in clause 15.4.

7.2.2	The baseline programme must be logic-linked, free of open ends and constraints other than those agreed, must show the critical path, and must identify every Milestone in clause 7.1 and every Deliverable in clause 5.4.

7.2.3	The programme must be updated monthly with actual progress, remaining duration and revised logic, and must be accompanied by a written narrative explaining critical path movement, float consumption and any recovery action.

7.2.4	The Service Provider must not re-baseline the programme without the Client's written approval. An unapproved re-baseline conceals delay and is a performance failure.

7.2.5	Where the Service Provider's programme incorporates a contractor's programme, the Service Provider must review that programme for logic, resourcing and achievability and report its assessment rather than simply reproducing it.

## 7.3  Float

7.3.1	Float in the programme is a project resource. It is not owned by either party and is available to whichever party first requires it, subject to the terms of the Agreement.

7.3.2	The Service Provider must not conceal float through artificial logic, extended durations, unnecessary constraints or preferential sequencing.

7.3.3	Float consumption must be reported monthly, showing total float on the critical and near-critical paths and the movement since the previous period.

7.3.4	[Insert any project-specific float ownership provision, or delete this note if float is shared as above.]

## 7.4  Notification of delay

7.4.1	The Service Provider must notify the Client in writing within [Insert, e.g. 2] Business Days of becoming aware of any event or circumstance that is likely to delay a Milestone, a Deliverable due date, or the Project completion date.

7.4.2	The notice must state the event, the date it was first known, the Milestones and Deliverables affected, the estimated effect on the programme and cost, the mitigation available, and what the Client must decide and by when.

7.4.3	Notification does not of itself create an entitlement to time or money. Entitlement is determined under the Agreement and clause 12.

7.4.4	Failure to notify within the period stated does not extinguish an entitlement unless the Agreement expressly provides for a time bar, but the Service Provider is not entitled to recover any cost that timely notification would have avoided.

## 7.5  Consequences of late delivery

| Situation | Consequence |
| --- | --- |
| Deliverable submitted late for reasons within the Service Provider's control | No fee adjustment; the Service Provider must recover the programme at its own cost; recorded against KPI 1 |
| Milestone missed for reasons within the Service Provider's control | Milestone payment not payable until achieved; remediation plan may be required under clause 13.3 |
| Milestone missed because of Client delay or the failure of an assumption | Milestone date adjusted; time-related cost recoverable under clause 11 as a Variation |
| Milestone missed because of contractor or third-party delay | Milestone date adjusted where the Service Provider could not reasonably have prevented or mitigated the delay |
| Persistent late delivery across multiple periods | Treated as a performance failure under clause 13; may constitute a substantial breach under clause 19.6 |
| [Insert any liquidated or agreed sum for a missed Milestone, or delete] | [Insert the amount and the cap, and confirm it is a genuine pre-estimate] |

[ Only include an agreed damages amount for a missed Milestone if the Agreement permits it and the amount is a genuine pre-estimate of loss. In many jurisdictions an amount that operates as a penalty is unenforceable. Take local legal advice before using this row. ]

# 8.  Assumptions, Dependencies and Client Obligations

## 8.1  Status of assumptions

8.1.1	The Services and the Fee are based on the assumptions in clause 8.2. Each assumption is a shared statement of the basis on which the engagement is priced and programmed.

8.1.2	If an assumption proves untrue, the consequence stated against it applies, and the Service Provider may notify a Variation under clause 12. The Service Provider must notify within [Insert, e.g. 10] Business Days of becoming aware that an assumption has failed.

8.1.3	The Service Provider must not rely on an assumption that it knew, or ought reasonably to have known, was untrue at the Effective Date.

8.1.4	An assumption is not a warranty by the Client unless expressly stated to be one.

## 8.2  Assumptions register

| Ref | Subject | Assumption | If this proves untrue, then ... |
| --- | --- | --- | --- |
| A-01 | Engagement duration | The Services are performed over [Insert] months from the Effective Date without suspension. | Fee is adjusted on a time-related basis at the rates in Appendix C for each month of extension. |
| A-02 | Team resourcing | The resourcing profile in clause 9.3 reflects the effort required for the Services. | Effort beyond the stated allocations is a Variation priced under clause 12. |
| A-03 | Client decisions | The Client provides decisions within the turnaround times in clause 8.4. | Programme dates move day-for-day and time-related costs are recoverable. |
| A-04 | Client-furnished information | Information listed in clause 8.3 is provided complete, accurate and on time. | The Service Provider is entitled to rely on it; correction or re-work is a Variation. |
| A-05 | Brief stability | The Client brief, functional requirements and area schedule are fixed at [Insert stage]. | Changes after that stage are Variations, including consequential re-design management. |
| A-06 | Budget adequacy | The approved control budget is adequate for the brief at current market rates. | Re-scoping, value engineering or re-tendering effort is a Variation. |
| A-07 | Design team performance | Design consultants deliver to the agreed design deliverables schedule. | Additional coordination or recovery management effort is a Variation. |
| A-08 | Site availability | The Site is available, vacant and free of encumbrance from [Insert date]. | Standing time and re-programming costs are recoverable under clause 11. |
| A-09 | Site conditions | Ground, contamination and heritage conditions are as disclosed in the reports listed. | Management of latent conditions is a Variation and may affect Milestones. |
| A-10 | Statutory approvals | Approvals are obtained within the periods shown on the baseline programme. | Delay beyond [Insert] Business Days entitles a programme and fee adjustment. |
| A-11 | Procurement outcome | A compliant, affordable tender is received in the first tender round for each package. | Re-tendering, negotiation or re-scoping effort is a Variation. |
| A-12 | Number of packages | The Services cover [Insert number] contract packages listed in Appendix A. | Each additional package is a Variation priced at [Insert] per package or at rates. |
| A-13 | Meeting frequency | Meetings occur at the frequency and duration in clause 10.1. | Additional meetings are charged at the rates in Appendix C. |
| A-14 | Reporting scope | One monthly report in the Appendix H format satisfies all reporting obligations. | Additional report formats, board papers or funder reporting are Variations. |
| A-15 | Site attendance | Site attendance is [Insert] days per week from [Insert stage] to practical completion. | Increased attendance is charged at the rates in Appendix C. |
| A-16 | Systems and licences | The Client provides access to its CDE and PMIS at no cost to the Service Provider. | Licence and administration costs become a Reimbursable. |
| A-17 | Working hours | Services are performed during normal business hours in the applicable jurisdiction. | Out-of-hours or shift attendance is charged at the overtime rates in Appendix C. |
| A-18 | Contract form | The construction contracts use the form identified in clause 2.5 without material amendment. | Bespoke or heavily amended forms may require additional administration effort. |
| A-19 | No dispute | No contractual dispute, arbitration or litigation arises requiring the Service Provider's support. | Dispute support is excluded under clause 4.4 and is a Variation if instructed. |
| A-20 | Force majeure and market conditions | No Force Majeure event, industrial action, pandemic restriction or supply failure occurs. | Time and cost consequences are dealt with under the Agreement and clause 12. |

## 8.3  Client-furnished information

The Client must provide the following at no cost to the Service Provider. The Service Provider is entitled to rely on it as complete and accurate, and is not required to verify it independently, unless this SOW expressly requires verification.

| Ref | Information or item to be provided by the Client | Client owner | Required by |
| --- | --- | --- | --- |
| CFI-01 | Approved Client brief, functional brief and area schedule | Client Sponsor | Effective Date |
| CFI-02 | Approved control budget, funding approvals and cash flow constraints | Client Finance | Effective Date |
| CFI-03 | Title, survey, easements, encumbrances and site boundary information | Client Property | Effective Date + 10 BD |
| CFI-04 | Geotechnical, contamination, hazardous materials and services investigation reports | Client Technical | Effective Date + 10 BD |
| CFI-05 | Existing as-built documentation, asset registers and condition reports | Client Facilities | Effective Date + 15 BD |
| CFI-06 | Client standards, design guidelines, specifications and preferred products | Client Technical | Effective Date + 10 BD |
| CFI-07 | Client governance framework, delegations of authority and approval thresholds | Client Sponsor | Effective Date |
| CFI-08 | Templates and formats for reports, cost plans and registers | Client PMO | Effective Date + 5 BD |
| CFI-09 | Access to the CDE, PMIS and finance systems with appropriate permissions | Client IT / PMO | Effective Date + 5 BD |
| CFI-10 | Site access, inductions, permits, security passes and parking | Client Facilities | As required, 5 BD notice |
| CFI-11 | Details and contact points for all separately engaged consultants and contractors | Client PM | Effective Date |
| CFI-12 | Stakeholder register, engagement commitments and communications protocols | Client Communications | Effective Date + 10 BD |
| CFI-13 | Existing contracts, deeds, agreements to lease and third-party commitments | Client Legal | Effective Date + 10 BD |
| CFI-14 | Operational and decant requirements, occupancy constraints and staging needs | Client Operations | Effective Date + 15 BD |
| CFI-15 | Insurance particulars, project insurances and claims history | Client Risk | Effective Date + 10 BD |

## 8.4  Client decisions and turnaround times

The Client must provide decisions and responses within the periods below. These periods are a Client obligation, not a target.

| Decision or response required | Turnaround | Accountable |
| --- | --- | --- |
| Routine review of a Deliverable | [Insert] Business Days | Client PM |
| Approval of a design stage | [Insert] Business Days | Project Control Group |
| Approval of a Variation within delegation | [Insert] Business Days | Project Director |
| Approval of a Variation above delegation | [Insert] Business Days | Project Sponsor / Board |
| Response to a request for information | [Insert] Business Days | Client PM |
| Payment approval of an undisputed invoice | [Insert] Business Days | Client Finance |
| Provision of Client-furnished information on request | [Insert] Business Days | Relevant owner |
| Escalated decision under clause 10.3 | [Insert] Business Days | Per escalation ladder |

Late Client decisions are the most common cause of consultant time-related cost claims, and the hardest to defend, because the record is usually clear. Populate this table with realistic periods and hold both parties to them. Track adherence in the monthly report.

## 8.5  Other Client obligations

Appoint and maintain an authorised representative with the delegated authority recorded in clause 10.5, and notify any change in writing.

Give the Service Provider safe, timely and sufficient access to the Site and to Client premises, subject to induction and security requirements.

Procure that the Client's other consultants and contractors cooperate with the Service Provider and comply with the governance and reporting arrangements in clause 10.

Maintain the project insurances the Client is required to effect under the Agreement and provide evidence on request.

Pay undisputed invoices in accordance with clause 11.9.

Notify the Service Provider promptly of any change in the Client's requirements, funding, governance, approvals or operational constraints.

Not instruct the Service Provider's personnel directly outside the governance channels in clause 10, and not direct the Service Provider's subcontractors at all.

## 8.6  Dependency register

| Ref | Dependency | Depends on | Owner | Required by | Effect if not met |
| --- | --- | --- | --- | --- | --- |
| DEP-01 | Commencement of Services | Executed Agreement and purchase order | Client | Effective Date | No mobilisation; Milestone dates move day-for-day |
| DEP-02 | Baseline programme | Client brief and approved control budget | Client | Effective Date | Baseline delayed; M-02 moves |
| DEP-03 | Design management | Appointment of design consultants | Client | [dd-mmm-yy] | Design programme cannot be baselined |
| DEP-04 | Cost planning | Access to historical cost data and benchmarks | Client | Effective Date + 10 BD | Cost plan carries wider tolerance bands |
| DEP-05 | Procurement | Approved procurement strategy and delegation | Client | [dd-mmm-yy] | Tender programme slips; M-06 moves |
| DEP-06 | Tender documentation | Issued-for-tender design from the design team | Design team | [dd-mmm-yy] | Tender release delayed |
| DEP-07 | Contract award | Client board or delegate approval | Client | [dd-mmm-yy] | Award delayed; contractor pricing may lapse |
| DEP-08 | Construction commencement | Site availability and statutory approval | Client / authority | [dd-mmm-yy] | Standing time; time-related cost |
| DEP-09 | CDE and PMIS access | Client IT provisioning and licences | Client | Effective Date + 5 BD | Manual document control; Reimbursable cost |
| DEP-10 | Commissioning management | Contractor commissioning plan | Contractor | [dd-mmm-yy] | Readiness reporting cannot commence |
| DEP-11 | Handover | O&M manuals and as-builts from the contractor | Contractor | [dd-mmm-yy] | Handover delayed; occupation at risk |
| DEP-12 | Final account | Contractor final claim and substantiation | Contractor | [dd-mmm-yy] | Closeout and M-15 delayed |

# 9.  Roles, Responsibilities and Key Personnel

## 9.1  RACI convention

| Code | Meaning | Rule |
| --- | --- | --- |
| R | Responsible | Does the work. There may be more than one R. |
| A | Accountable | Owns the outcome and signs it off. There is exactly one A per activity. |
| C | Consulted | Two-way: must be given the opportunity to input before the decision. |
| I | Informed | One-way: told after the decision. |
| — | Not involved | No role in this activity. |

## 9.2  RACI matrix

The matrix below covers the principal activities, using the role abbreviations in the legend. Appendix E contains the expanded matrix with full role names. Where this matrix and Appendix E differ, Appendix E prevails.

CS = Client Sponsor   ·   CPM = Client PM   ·   SPD = SP Project Director   ·   SPM = SP Project Manager   ·   DL = Design Lead   ·   CM = Cost Manager   ·   CTR = Contractor

| Activity | CS | CPM | SPD | SPM | DL | CM | CTR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Approve the Project business case and control budget | A | C | I | I | I | R | — |
| Prepare and maintain the Project Execution Plan | A | C | A | R | C | C | I |
| Establish and maintain the master programme | I | A | A | R | C | C | C |
| Maintain the cost plan and anticipated final cost | I | A | A | C | I | R | I |
| Manage the design programme and design reviews | I | A | A | R | R | C | I |
| Approve design at each stage gate | A | R | C | C | C | C | I |
| Develop the procurement and packaging strategy | A | C | A | R | C | C | — |
| Prepare and issue tender documentation | I | A | A | R | C | C | — |
| Evaluate tenders and recommend award | A | C | A | R | C | C | — |
| Execute the construction contract | A | R | C | I | I | I | R |
| Administer the construction contract | I | A | A | R | C | C | C |
| Assess and certify progress claims | I | A | A | C | I | R | C |
| Assess variations and claims | A | A | R | R | C | R | C |
| Manage the risk register and risk workshops | I | A | A | R | C | C | C |
| Deliver HSE performance on Site | I | I | C | C | I | I | A |
| Provide client-side HSE assurance | I | A | A | R | I | I | C |
| Deliver quality and close out non-conformances | I | C | C | C | C | I | A |
| Provide quality surveillance and ITP review | I | A | A | R | C | I | C |
| Prepare and issue the monthly report | I | A | A | R | C | C | I |
| Manage commissioning and operational readiness | A | A | A | R | C | I | R |
| Manage completion, handover and warranties | I | A | A | R | C | C | R |
| Manage the defects liability period | I | A | A | R | I | I | R |
| Agree the final account | A | A | A | C | I | R | R |
| Prepare the closeout and lessons learned report | I | A | A | R | C | C | I |

## 9.3  Key Personnel

The following individuals are Key Personnel. Their identity, seniority and availability are material to this engagement.

| Name | Role | Minimum allocation | Rate (local currency / hour) | Substitution restriction |
| --- | --- | --- | --- | --- |
| [Insert name] | Project Director | [Insert]% | [Insert] | No substitution without consent |
| [Insert name] | Project Manager | [Insert]% | [Insert] | No substitution without consent |
| [Insert name] | Senior Cost Manager | [Insert]% | [Insert] | No substitution without consent |
| [Insert name] | Contract Administrator | [Insert]% | [Insert] | Consent not to be unreasonably withheld |
| [Insert name] | Planner / Scheduler | [Insert]% | [Insert] | Consent not to be unreasonably withheld |
| [Insert name] | Design Manager | [Insert]% | [Insert] | No substitution without consent |
| [Insert name] | HSE Advisor | [Insert]% | [Insert] | Equivalent competency required |
| [Insert name] | Document Controller | [Insert]% | [Insert] | Equivalent competency required |

[ Percentage allocations only mean something if they are measured. Require monthly timesheet reporting of actual hours by named individual against the committed allocation, and report it as KPI 14. A commitment nobody measures is a commitment nobody keeps. ]

## 9.4  Substitution and continuity

9.4.1	The Service Provider must not remove, replace or materially reduce the involvement of any Key Personnel without the Client's prior written consent, except where the individual resigns, is incapacitated, dies, or is removed for serious misconduct.

9.4.2	Where a substitution is unavoidable, the Service Provider must propose a replacement of equivalent or superior qualifications, experience and availability within [Insert, e.g. 10] Business Days, together with the individual's curriculum vitae and referees.

9.4.3	The Service Provider must provide a documented handover of no less than [Insert, e.g. 10] Business Days of overlap between the outgoing and incoming individual, at the Service Provider's cost.

9.4.4	No additional fee, mobilisation cost, learning-curve cost or time-related cost is payable in connection with a substitution initiated by the Service Provider.

9.4.5	The Client may, acting reasonably, require the removal of any of the Service Provider's personnel whose performance, conduct or safety behaviour is unsatisfactory. The Service Provider must replace that person within [Insert, e.g. 10] Business Days at its own cost.

9.4.6	The Service Provider must notify the Client within [Insert, e.g. 5] Business Days of becoming aware that any Key Personnel is likely to become unavailable.

## 9.5  Minimum time commitments

9.5.1	Key Personnel must devote at least the allocation stated in clause 9.3 to the Project, measured monthly and reported with the monthly report.

9.5.2	The Service Provider must attend the Site at the frequency stated in assumption A-15 and must attend every meeting listed in clause 10.1 at the seniority stated there.

9.5.3	Where actual effort falls below [Insert, e.g. 85]% of the committed allocation in any month without the Client's agreement, the Client may abate the Fee for that month proportionally, without prejudice to any other right.

## 9.6  Subcontracting and novation

9.6.1	The Service Provider must not subcontract any part of the Services without the Client's prior written consent, other than to a subcontractor identified in clause 9.7.

9.6.2	Consent to subcontract does not relieve the Service Provider of any obligation. The Service Provider remains fully responsible for the acts and omissions of its subcontractors as if they were its own.

9.6.3	Every subcontract must impose obligations equivalent to those in this SOW relating to confidentiality, intellectual property, information security, safety, conflicts, anti-bribery, modern slavery, records and audit.

9.6.4	The Service Provider must not assign or novate this SOW or the Agreement without the Client's prior written consent. The Client may novate to a related body corporate, a successor entity, a special purpose vehicle or a delivery partner on notice, and the Service Provider must execute the required documents promptly.

9.6.5	The Client may require the Service Provider to novate any third-party appointment it holds for the Project to the Client or its nominee on termination or completion.

## 9.7  Approved subcontractors

| Subcontractor | Scope subcontracted | Approved? | Conditions |
| --- | --- | --- | --- |
| [Insert] | [Insert] | [Yes / No] | [Insert] |
| [Insert] | [Insert] | [Yes / No] | [Insert] |
| [Insert] | [Insert] | [Yes / No] | [Insert] |

## 9.8  Organisation chart

[Insert the project organisation chart here. It must show: the Client's governance bodies and representatives; the Service Provider's team including every named individual in clause 9.3 with their allocation; every other consultant and contractor; and the reporting and instruction lines between them. Mark clearly which lines are instruction lines and which are coordination lines only.]

[ Insert organisation chart image or embedded object here ]

# 10.  Governance, Reporting and Communication

## 10.1  Meeting schedule

| Meeting | Purpose | Frequency | Attendees | Chair | Outputs |
| --- | --- | --- | --- | --- | --- |
| Project Control Group | Strategic direction, approvals, escalated risks and change | Monthly | Sponsor, Client PM, SP Project Director | Client Sponsor | Minutes + actions within 3 BD |
| Project Team Meeting | Delivery coordination, programme, actions and issues | Fortnightly | Client PM, SP team, discipline leads | SP Project Manager | Minutes + action register within 3 BD |
| Design Coordination Meeting | Design progress, interfaces, comment closeout | Weekly during design | Design team, SP Design Manager | SP Design Manager | Minutes + comment register update |
| Site Progress Meeting | Progress, quality, HSE, RFIs, programme and claims | Weekly during construction | Contractor, SP team, Client PM | SP Project Manager | Minutes + site instruction log |
| Cost and Commercial Review | Cost report, forecast, change and contingency | Monthly | Client Finance, Cost Manager, SP Project Director | SP Cost Manager | Cost report + change register |
| Risk Workshop | Review and re-score risks, agree treatments and owners | Quarterly | Full project team and key stakeholders | SP Project Manager | Updated risk register within 5 BD |
| HSE Walk and Review | Site safety observation and system assurance | Monthly | Client HSE, SP HSE Advisor, Contractor | Client HSE Manager | Observation report within 3 BD |
| Commissioning and Handover Meeting | Readiness, testing, documentation and training | Fortnightly from [Insert stage] | Client Facilities, Contractor, SP team | SP Project Manager | Readiness tracker update |
| Stakeholder / Community Briefing | External communications and community impacts | As required | Client Communications, SP Project Manager | Client Communications | Briefing note and issues log |

The Service Provider must prepare and circulate an agenda at least [Insert, e.g. 2] Business Days before each meeting it chairs, and issue minutes with a numbered action register within the period stated above. Minutes are taken as agreed if no written objection is received within [Insert, e.g. 3] Business Days.

[ Attendance at the frequencies above is priced into the Fee. If you increase the frequency or add meetings, that is a Variation. Conversely, if you can combine meetings, do — meeting load is one of the largest hidden costs on a client-side engagement. ]

## 10.2  Reporting requirements

| Report | Content | Frequency | Due | Recipient |
| --- | --- | --- | --- | --- |
| Monthly Project Report | Full contents per Appendix H | Monthly | By the 5th Business Day | Client PM and Project Control Group |
| Executive Dashboard | One-page RAG summary of cost, time, risk, HSE, quality | Monthly | With monthly report | Project Sponsor |
| Cost Report and Anticipated Final Cost | Budget, commitment, expenditure, forecast, contingency | Monthly | With monthly report | Client Finance |
| Programme Status Report | Progress, critical path, float erosion, recovery actions | Monthly | With monthly report | Client PM |
| Cash Flow Forecast | Rolling forecast to completion by period | Monthly | With monthly report | Client Finance |
| Risk and Opportunity Report | Top risks, movement, treatment status, quantified exposure | Monthly | With monthly report | Client Risk Manager |
| Change and Variation Register | Cumulative change position and pipeline | Monthly | With monthly report | Client PM |
| HSE Report | Incidents, near misses, audits, statutory notices | Monthly | With monthly report | Client HSE Manager |
| Quality and NCR Report | ITP status, hold points, non-conformances | Monthly | With monthly report | Client Quality Lead |
| Exception / Early Warning Notice | Any matter threatening cost, time, quality, HSE or reputation | As it arises | Within 2 BD of becoming aware | Client PM and Sponsor |
| Board / Investment Committee Paper | Approval papers for gateway decisions | Per gateway | 10 BD before the meeting | Project Sponsor |
| Weekly Flash Report | One-page progress, look-ahead and blockers | Weekly | By close of business Friday | Client PM |

The monthly report must follow the structure in Appendix H. A report that omits a required section, or that reports a section as "no change" without confirming it was reviewed, is not a complete submission for the purposes of clause 5.1.

## 10.3  Escalation ladder

| Level | Trigger | Escalate to | Response time | Forum |
| --- | --- | --- | --- | --- |
| Level 1 | Day-to-day delivery issue, RFI, minor coordination | SP Project Manager ↔ Client PM | 2 Business Days | Project team meeting |
| Level 2 | Issue affecting a Deliverable due date, or change up to [Insert] value | SP Project Director ↔ Client Project Director | 5 Business Days | Project Control Group |
| Level 3 | Issue affecting a Milestone, the control budget or a Key Personnel change | SP Regional Director ↔ Client Project Sponsor | 5 Business Days | Project Control Group |
| Level 4 | Material breach, safety event, or dispute under clause 20 | SP Executive ↔ Client Executive Sponsor | 10 Business Days | Formal dispute process |

10.3.1	An issue must be escalated to the next level if it is not resolved within the response time for the current level.

10.3.2	Escalation must be in writing, must state the issue, the resolution attempted, the decision required and the consequence of further delay.

10.3.3	Escalation is not a substitute for performance. Both parties must continue to perform their obligations while an issue is escalated.

10.3.4	A Level 4 escalation that remains unresolved may be referred to dispute resolution under clause 20.

## 10.4  Communication protocols

All formal communications must be issued through the CDE and recorded against the correct project, package and document type.

Contractual notices must be issued in the manner and to the addresses required by the Agreement. Email alone is not sufficient for a contractual notice unless the Agreement expressly permits it.

The Service Provider must not communicate directly with a statutory authority, a funder, the media or the community on the Client's behalf without the Client's prior written authorisation.

The Service Provider must copy the Client's single point of contact on all material correspondence with contractors and consultants.

Instructions to contractors must be issued only by the person holding the relevant delegation under clause 10.5 and only in the form required by the construction contract.

The Service Provider must respond to a Client request for information within [Insert, e.g. 2] Business Days, or acknowledge and state when a substantive response will follow.

## 10.5  Decision authority and tolerances

| Decision | Authority | Threshold / tolerance |
| --- | --- | --- |
| Issue routine correspondence and site instructions of no cost or time effect | SP Project Manager | Nil |
| Issue requests for information and design clarifications | SP Project Manager | Nil |
| Approve a contractor variation | SP Project Director | Up to [Insert] per event |
| Approve cumulative variations | Client Project Director | Up to [Insert] cumulative |
| Draw down project contingency | Client Project Director | Up to [Insert] per event |
| Grant an extension of time | Superintendent / Contract Administrator | Per the contract |
| Certify a progress claim | Superintendent / Contract Administrator | Per the contract |
| Approve a change to this SOW | Client Project Sponsor | Per clause 12 |
| Approve a Key Personnel substitution | Client Project Sponsor | Per clause 9.4 |
| Approve a change to the control budget | Client Board / Investment Committee | Any amount |

The delegations recorded here must match the Client's own instrument of delegation and the construction contract. A Service Provider acting outside its delegation exposes the Client to unauthorised commitments; a Service Provider with too narrow a delegation cannot administer the contract within the time bars. Check both documents before issuing this SOW.

## 10.6  Single point of contact

10.6.1	Each party must nominate a single point of contact for the engagement, named in clause 1.1. All formal instructions, submissions and notices pass through them.

10.6.2	The Service Provider is not obliged to act on, and must not act on, an instruction that does not come from the Client's single point of contact or a person holding the relevant delegation under clause 10.5.

10.6.3	Either party may change its single point of contact by written notice, effective on receipt.

10.6.4	Day-to-day technical liaison between team members is encouraged and is not a substitute for, and does not constitute, a formal instruction.

# 11.  Fees, Payment and Commercial Terms

## 11.1  Fee basis

The Fee for the Services is calculated on the basis marked below. Delete every basis that does not apply.

| Fee basis | When it is appropriate | Advantage | Watch out for |
| --- | --- | --- | --- |
| Lump sum / fixed fee | Scope is well defined, stable and time-bounded; deliverables are clearly specified. | Price certainty for the Client; the Service Provider carries efficiency risk. | Requires a rigorous exclusions list and a working change control process, or it becomes a claims vehicle. |
| Schedule of rates (time-charge) | Scope or duration is uncertain, or the engagement is advisory and reactive. | Flexible; the Client pays for effort actually expended. | No cost certainty. Always pair with a not-to-exceed cap and monthly effort reporting. |
| Time and materials with a cap | Scope is broadly known but the effort profile is uncertain. | Balances flexibility and control; the cap protects the Client. | Define clearly whether the cap is per stage or overall, and what happens on reaching it. |
| Cost plus fixed fee / percentage | Delivery-partner or integrated-team arrangements with open-book costs. | Transparency of actual cost; suits early or evolving scope. | Requires audit rights, an agreed cost build-up and a defined overhead and profit rate. |
| Target cost with pain / gain share | Collaborative delivery where both parties can influence outturn cost. | Aligns incentives to beat the target. | Needs a robust target-setting process, an agreed share ratio and a defined adjustment mechanism for scope change. |
| Percentage of construction cost | Traditional consultancy engagements where scope scales with project value. | Simple to administer and scales with project size. | Perverse incentive: fee rises with cost. Cap the fee, define the cost base, and state how it is adjusted for Variations. |

[ Choose one primary basis and, if needed, one secondary basis for a defined part of the scope (for example lump sum for the design stages and a capped time charge for construction-phase attendance). Record why you chose it — that record is useful when the engagement is audited or when the basis is challenged two years later. ]

| SELECTED FEE BASIS |  |
| --- | --- |
| Primary fee basis | [Insert the selected basis] |
| Secondary fee basis (if any) | [Insert basis and the scope it applies to] |
| Total fee (excluding taxes and Reimbursables) | [Insert amount and currency] |
| Not-to-exceed cap (if applicable) | [Insert amount and currency] |
| Reimbursables allowance | [Insert amount and currency, or 'at cost, no allowance'] |
| Fee as a percentage of construction cost (if applicable) | [Insert %] of [Insert defined cost base] |

## 11.2  Fee schedule

| Ref | Stage / component of the Services | Basis | Fee (local currency) | % of total | Payment trigger |
| --- | --- | --- | --- | --- | --- |
| F-01 | Stage 1 — Initiation and mobilisation | Lump sum | [Insert] | [Insert]% | M-01 |
| F-02 | Stage 2 — Planning and concept design | Lump sum | [Insert] | [Insert]% | M-03 |
| F-03 | Stage 3 — Developed and detailed design | Lump sum | [Insert] | [Insert]% | M-04 |
| F-04 | Stage 4 — Procurement and tender | Lump sum | [Insert] | [Insert]% | M-06 / M-07 |
| F-05 | Stage 5 — Construction delivery | Time-related, monthly | [Insert] | [Insert]% | Monthly / M-09 to M-11 |
| F-06 | Stage 6 — Commissioning and handover | Lump sum | [Insert] | [Insert]% | M-13 / M-14 |
| F-07 | Stage 7 — Post-completion and defects | Schedule of rates, capped | [Insert] | [Insert]% | M-16 |
| F-08 | Provisional sum — additional services (if instructed) | Schedule of rates | [Insert] | — | On instruction |
|  | Total fee (excluding taxes and Reimbursables) |  | [Insert] | 100% |  |

The fee percentages must total 100%. Where a stage is not in scope under clause 2.4, delete the row rather than showing a nil value.

## 11.3  Schedule of rates

The rates below apply to Variations, additional services and any time-charged component of the Fee. Rates are hourly, in [Insert currency], exclusive of applicable taxes, and inclusive of all overheads, on-costs and profit.

| Role | Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- | --- |
| Project Director / Principal | [Insert] | [Insert] | [Insert] | [Insert] |
| Senior Project Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Project Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Assistant Project Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Contract Administrator / Superintendent's Representative | [Insert] | [Insert] | [Insert] | [Insert] |
| Senior Cost Manager / Quantity Surveyor | [Insert] | [Insert] | [Insert] | [Insert] |
| Cost Manager / Quantity Surveyor | [Insert] | [Insert] | [Insert] | [Insert] |
| Planner / Scheduler | [Insert] | [Insert] | [Insert] | [Insert] |
| Design Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Site Superintendent / Clerk of Works | [Insert] | [Insert] | [Insert] | [Insert] |
| HSE Advisor | [Insert] | [Insert] | [Insert] | [Insert] |
| Risk Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Specialist Advisor / Technical Expert | [Insert] | [Insert] | [Insert] | [Insert] |
| Document Controller / Project Administrator | [Insert] | [Insert] | [Insert] | [Insert] |
| Graduate / Cadet | [Insert] | [Insert] | [Insert] | [Insert] |

Rates are fixed for the period stated and adjust only in accordance with clause 11.11.

Time is recorded and charged in increments of [Insert, e.g. 0.25] hours.

Travel time is [chargeable / not chargeable]. If chargeable, state the rate and the maximum chargeable hours per day.

Overtime, weekend and public holiday attendance is charged at [Insert multiplier] of the standard rate, and only where authorised in advance in writing.

A rate must not be charged for a role more senior than the work reasonably requires.

## 11.4  Reimbursable expenses

The following are recoverable at cost, without mark-up, on production of receipts or supplier invoices, and only where authorised in advance where this SOW requires authorisation.

11.4.1	Economy-class travel beyond [Insert] km from the Service Provider's nominated office, authorised in advance in writing.

11.4.2	Accommodation and subsistence for authorised overnight travel, at the Client's travel policy rates.

11.4.3	Printing, plotting and binding of documents expressly requested by the Client in hard copy.

11.4.4	Statutory searches, title searches and third-party data purchases requested by the Client.

11.4.5	Courier and freight charges for physical items required for the Project.

11.4.6	Specialist software licences procured specifically for the Project at the Client's written direction.

## 11.5  Expenses not recoverable

The following are deemed included in the Fee and are not recoverable as Reimbursables under any circumstances.

11.5.1	Salaries, on-costs, bonuses, overheads, profit and general administration.

11.5.2	Home-to-office travel, local travel within the nominated office region, and vehicle running costs.

11.5.3	Mobile telephony, data, internet, and standard information technology hardware and software.

11.5.4	Standard office consumables, stationery, in-house printing and general reproduction.

11.5.5	Professional indemnity, public liability and workers compensation insurance premiums.

11.5.6	Professional subscriptions, registrations, continuing professional development and training.

11.5.7	Recruitment, mobilisation, demobilisation and staff replacement costs.

11.5.8	Entertainment, hospitality, alcohol, fines, penalties and parking infringements.

11.5.9	Costs arising from the Service Provider's error, omission, rework or negligence.

11.5.10	Any expense not authorised in advance in writing where prior authorisation is required.

| Reimbursables cap | [Insert amount, or '% of Fee', or 'nil — all costs included'] |
| --- | --- |
| Mark-up on Reimbursables | Nil |
| Prior authorisation threshold | [Insert amount] per item |
| Travel policy applied | [Insert: the Client's travel policy / the Service Provider's policy] |

## 11.6  Invoicing

11.6.1	The Service Provider must invoice monthly in arrears, or on achievement of a Milestone where the Fee is milestone-based, and must submit each invoice to [Insert invoicing address or portal].

11.6.2	Every invoice must state: the SOW reference; the purchase order number; the period covered; the stage or Milestone claimed; the amount claimed this period; the amount claimed to date; the percentage of each stage complete; and the balance remaining.

11.6.3	Every invoice must be supported by: a progress narrative; the timesheet detail by named individual, role, date and activity where any component is time-charged; receipts for every Reimbursable; and the signed Acceptance Certificate where the claim is linked to a Deliverable or Milestone.

11.6.4	An invoice that is not supported as required is not a valid invoice and the payment period does not commence until the supporting documentation is provided.

11.6.5	The Service Provider must not claim for a Milestone before it is achieved, or for a Variation before it is authorised in writing under clause 12.

11.6.6	The final invoice must be marked "final" and must be submitted within [Insert, e.g. 20] Business Days of completion of the Services. Claims submitted after that period are barred.

## 11.7  Payment terms

| PAYMENT TERMS |  |
| --- | --- |
| Payment period | [Insert, e.g. 30] days from receipt of a valid invoice |
| Payment method | [Insert, e.g. electronic funds transfer to the nominated account] |
| Purchase order required before invoicing | [Yes / No] |
| Invoicing frequency | [Insert, e.g. monthly in arrears] |
| Disputed amounts | The undisputed portion must be paid within the payment period |
| Interest on late payment | [Insert rate and basis, or 'as provided in the Agreement'] |
| Statutory payment regime | The security of payment or prompt payment regime of the applicable jurisdiction applies and prevails over this clause to the extent of any inconsistency |

Many jurisdictions have mandatory security of payment, prompt payment or construction payment legislation that overrides agreed payment periods, imposes response deadlines and creates adjudication rights. Confirm what applies in the applicable jurisdiction before setting the payment period, and make sure the Client's payment process can actually meet it.

## 11.8  Retention

11.8.1	The Client may retain [Insert, e.g. 5]% of each payment, up to a maximum of [Insert, e.g. 5]% of the total Fee.

11.8.2	Half of the retention is released on [Insert trigger, e.g. Acceptance of Deliverable D-21 at practical completion], and the balance on [Insert trigger, e.g. Acceptance of Deliverable D-25 at closeout].

11.8.3	Retention is not held as trust money unless the applicable jurisdiction requires it.

11.8.4	The Service Provider may substitute an unconditional undertaking from a financial institution acceptable to the Client for cash retention, at its own cost.

11.8.5	[Delete this clause entirely if no retention is held on professional services — retention is uncommon on consultancy engagements in many markets and may be resisted.]

## 11.9  Escalation and indexation

11.9.1	The Fee and the rates in clause 11.3 are fixed until [dd-mmm-yy].

11.9.2	After that date they adjust annually on [Insert date] by the lesser of the movement in [Insert published index, e.g. the applicable jurisdiction's consumer price index or wage price index] over the preceding 12 months and [Insert, e.g. 4]%.

11.9.3	The Service Provider must give at least [Insert, e.g. 30] days written notice of an adjustment, showing the calculation and the published index figures relied on.

11.9.4	No adjustment applies to a lump sum for a stage that should have been completed before the adjustment date but was delayed by the Service Provider.

## 11.10  Taxes, currency and exchange

11.10.1	All amounts are exclusive of value added tax, goods and services tax, sales tax or equivalent transaction taxes, which are payable in addition on production of a valid tax invoice.

11.10.2	Each party is responsible for its own income, corporate, payroll and employment taxes.

11.10.3	Where withholding tax is required by law, the paying party may withhold and must provide the recipient with the certificate or receipt evidencing the payment.

11.10.4	The currency of the engagement is [Insert currency code]. All invoices and payments are in that currency.

11.10.5	Where any cost is incurred in another currency, it is converted at [Insert basis, e.g. the published mid-market rate on the date the cost is incurred]. Exchange rate risk is borne by [Insert party].

## 11.11  Suspension for non-payment and set-off

11.11.1	If the Client fails to pay an undisputed amount by its due date, the Service Provider may give written notice requiring payment within [Insert, e.g. 10] Business Days.

11.11.2	If payment is not made within that period, the Service Provider may suspend the Services on a further [Insert, e.g. 5] Business Days written notice, unless the Agreement or the applicable statutory payment regime provides otherwise.

11.11.3	Before suspending, the Service Provider must secure the Project position: issue all outstanding contractual notices and certificates, notify the Client of any approaching time bar, and confirm the status of every open matter in writing.

11.11.4	The Service Provider must resume the Services promptly on payment, and is entitled to the reasonable, evidenced costs of demobilisation and remobilisation and to a corresponding adjustment of the Milestone dates.

11.11.5	The Client may set off against any amount payable any amount due from the Service Provider under this SOW or the Agreement, provided it gives written notice of the amount, the basis and the calculation before the set-off takes effect.

# 12.  Variations and Change Control

## 12.1  What constitutes a Variation

A Variation to this SOW arises where any of the following occurs.

An addition to, omission from or change in the Services or the Deliverables.

A change in the standard, format, frequency or acceptance criteria applying to a Deliverable.

A change in a Milestone date or in the sequence or duration of the Services, other than one caused by the Service Provider.

The failure of an assumption in clause 8.2, to the extent stated against that assumption.

The failure of the Client to provide information under clause 8.3, or a decision within the turnaround in clause 8.4, where that failure causes additional effort or delay.

A change in the delivery model, contract form, packaging strategy or number of packages.

A change in law or in a mandatory standard that materially increases the cost or effort of performing the Services.

A suspension, or the resumption of the Services after a suspension.

An instruction to perform any service listed as excluded in clause 4.5.

The following do not constitute a Variation: correction of the Service Provider's own errors or omissions; rework arising from non-acceptance under clause 6.5; resourcing changes made by the Service Provider; and effort arising from the Service Provider's inefficiency, mobilisation or staff turnover.

## 12.2  Change control process

| Step | Action | Responsible | Period |
| --- | --- | --- | --- |
| 1 | Identify the change and notify the other party in writing | Either party | Within [Insert, e.g. 5] BD of becoming aware |
| 2 | Raise a Change Request using the form in Appendix F, with a unique reference | Originating party | Within [Insert, e.g. 5] BD of notification |
| 3 | Price and programme the change: effort by role, cost, Milestone effect, risk effect, and effect on other Deliverables | Service Provider | Within [Insert, e.g. 10] BD of the Change Request |
| 4 | Review, clarify and negotiate the assessment | Both parties | Within [Insert, e.g. 5] BD of the assessment |
| 5 | Approve, reject or defer within the delegation in clause 10.5 | Client delegate | Within [Insert, e.g. 5] BD |
| 6 | Record the outcome in the change log and update the affected registers | Service Provider | Within [Insert, e.g. 3] BD of the decision |
| 7 | Perform the varied Services | Service Provider | Per the approved change |
| 8 | Reflect the change in the next monthly report and the next invoice | Service Provider | Next reporting period |

## 12.3  Pricing of Variations

12.3.1	A Variation is priced, in order of preference: by a lump sum agreed before the work commences; failing that, at the rates in Appendix C applied to a reasonable and agreed assessment of effort; failing that, on a time-charge basis against an agreed not-to-exceed cap with daily records.

12.3.2	The Service Provider's assessment must show effort by named role and hours, the rate applied, any Reimbursable, the effect on Milestones, the effect on other Deliverables, and any consequential change to assumptions.

12.3.3	An omission is valued using the same basis and rates as the original pricing. The Service Provider is not entitled to retain the profit component of omitted work unless the Agreement so provides.

12.3.4	The Service Provider must not include in a Variation any element of cost already recovered in the Fee, or any cost caused by its own delay or error.

12.3.5	Cumulative Variations exceeding [Insert, e.g. 10]% of the original Fee require approval at the level stated in clause 10.5, regardless of the value of the individual Variation.

## 12.4  No work without authorisation

The Service Provider must not commence a varied service before written authorisation is issued. Work performed without authorisation is at the Service Provider's risk and is not payable, even if the Client benefits from it. The only exception is work reasonably necessary to prevent injury, protect property, or preserve a contractual entitlement of the Client that would otherwise be lost — and the Service Provider must notify the Client of that work within one Business Day.

## 12.5  Change log

The Service Provider must maintain a cumulative change log and issue it with each monthly report. The log must show the position for the engagement as a whole, not only the movement in the period.

| CR ref | Description | Date raised | Status | Fee effect | Programme effect | Approved by | Approval date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 | [Insert] | [dd-mmm-yy] | [Draft / Submitted / Approved / Rejected / Withdrawn] | [Insert] | [Insert] | [Insert] | [dd-mmm-yy] |
| CR-002 | [Insert] | [dd-mmm-yy] | [Insert] | [Insert] | [Insert] | [Insert] | [dd-mmm-yy] |
|  | Total approved to date |  |  | [Insert] | [Insert] |  |  |
|  | Total pending |  |  | [Insert] | [Insert] |  |  |
|  | Cumulative % of original Fee |  |  | [Insert]% |  |  |  |

## 12.6  Disputed Variations

12.6.1	If the parties cannot agree whether an event is a Variation, or its value, either party may escalate the matter under clause 10.3.

12.6.2	The Client may direct the Service Provider to proceed with the disputed work pending resolution. In that case the Service Provider must proceed, must keep contemporaneous records of the actual effort and cost, and must submit those records weekly.

12.6.3	Contemporaneous records submitted under this clause are without prejudice to either party's position on entitlement.

12.6.4	A disputed Variation that remains unresolved after escalation is dealt with under clause 20.

# 13.  Performance Management and KPIs

## 13.1  Principles

13.1.1	Performance is measured against the key performance indicators in clause 13.6. Each KPI must be capable of objective measurement from an identified data source that both parties can access.

13.1.2	The Service Provider must report actual performance against every KPI with the monthly report, including the underlying data, and must not self-assess a KPI without evidence.

13.1.3	A KPI that cannot be measured from an identified source must be deleted rather than estimated.

## 13.2  Performance review cadence

| Review | Scope | Frequency | Participants | Output |
| --- | --- | --- | --- | --- |
| Monthly performance snapshot | KPI dashboard reported with the monthly report | Monthly | Client PM, SP Project Manager | KPI table in the monthly report |
| Quarterly performance review | Trend analysis, root causes, corrective actions | Quarterly | Client Project Director, SP Project Director | Signed review record and action plan |
| Annual / stage-gate review | Full review of scope, resourcing, fee basis and continued fit | Annually or at each stage gate | Client Sponsor, SP Executive | Continuation decision and any SOW Variation |
| Exception review | Called when any KPI breaches its threshold | Within 10 BD of the breach | As determined by the escalation level | Remediation plan under clause 13.3 |

## 13.3  Remediation

13.3.1	Where a KPI breaches its threshold, or where performance is otherwise unsatisfactory, the Client may require the Service Provider to submit a remediation plan within [Insert, e.g. 10] Business Days.

13.3.2	The remediation plan must identify the root cause, the corrective actions, the individuals accountable, the dates for recovery and the measures that will demonstrate recovery. It must be prepared at the Service Provider's cost.

13.3.3	The Client may require the plan to be presented to the Project Control Group.

13.3.4	If performance is not restored within the period stated in the accepted remediation plan, the Client may replace personnel under clause 13.5, apply the fee mechanism in clause 13.4, or treat the failure as a substantial breach under clause 19.6.

## 13.4  Performance-linked fee

[Insert the performance-linked fee mechanism, or delete this clause if the Fee is not performance-linked. If used, complete every field below and confirm the total at-risk amount is consistent with the Agreement.]

| PERFORMANCE-LINKED FEE MECHANISM |  |
| --- | --- |
| Portion of the Fee at risk | [Insert %] of the Fee for each measurement period |
| Measurement period | [Insert, e.g. each quarter] |
| KPIs that determine the at-risk portion | [Insert KPI references] |
| Weighting between those KPIs | [Insert weightings, totalling 100%] |
| Score required to earn the full at-risk portion | [Insert] |
| Score below which none is earned | [Insert] |
| Ability to earn back a forgone amount in a later period | [Yes / No] |
| Maximum upside (if any gain share applies) | [Insert % and cap] |
| Who determines the score | [Insert role]; disputes resolved under clause 20 |

## 13.5  Right to replace personnel

In addition to clause 9.4, where an individual's performance is a material cause of a KPI breach, or where an individual has failed to comply with the Client's safety, probity or conduct requirements, the Client may require that individual to be removed from the Project immediately. Replacement is at the Service Provider's cost and does not entitle the Service Provider to any extension of a Milestone.

## 13.6  Key performance indicators

| KPI | Definition | Measurement method | Data source | Target | Threshold | Frequency | Consequence |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Deliverable timeliness | Deliverables submitted on or before the due date | Count on time ÷ count due | Deliverables register | ≥ 95% | < 85% | Monthly | Remediation plan at threshold |
| Deliverable quality at first submission | Deliverables Accepted without resubmission | Count accepted first pass ÷ count submitted | Acceptance certificates | ≥ 85% | < 70% | Monthly | Rework at SP cost |
| Report accuracy | Monthly reports free of material error or restatement | Count of material corrections | Client review record | 0 per quarter | ≥ 2 per quarter | Quarterly | Performance review |
| Cost forecast accuracy | Variance between forecast and actual outturn per period | ¦Forecast − actual¦ ÷ actual | Cost report vs finance ledger | ≤ 2% | > 5% | Monthly | Root cause analysis required |
| Programme forecast accuracy | Variance of forecast milestone dates over rolling 3 months | Mean absolute date variance | Programme updates | ≤ 5 days | > 15 days | Monthly | Re-baseline review |
| Change control discipline | Variations approved before work commenced | Count pre-approved ÷ total variations | Change register | 100% | < 95% | Monthly | Unauthorised work not payable |
| Contract administration timeliness | Contractual assessments issued within the contract time bar | Count within time bar ÷ total | Contract register | 100% | < 100% | Monthly | Escalation to Level 2 |
| RFI turnaround | RFIs closed within the agreed response period | Count closed on time ÷ total | CDE / PMIS log | ≥ 90% | < 80% | Monthly | Resourcing review |
| Meeting and minute discipline | Minutes issued within 3 Business Days | Count on time ÷ meetings held | CDE | ≥ 95% | < 85% | Monthly | Performance review |
| Risk register currency | Risks reviewed and re-scored within the review period | Count reviewed ÷ open risks | Risk register | 100% | < 90% | Monthly | Risk workshop called |
| HSE assurance participation | Planned safety walks and audits completed | Count completed ÷ planned | HSE report | 100% | < 90% | Monthly | Escalation to Level 3 |
| Reportable safety events attributable to the Service Provider | Incidents caused by SP personnel or direction | Count | Incident register | 0 | ≥ 1 | Monthly | Immediate escalation and review |
| Key Personnel continuity | Key Personnel retained without unapproved substitution | Count retained ÷ Key Personnel | Resourcing report | 100% | < 100% | Quarterly | Fee abatement per clause 13.5 |
| Resourcing compliance | Actual time delivered against committed allocation | Actual hours ÷ committed hours | Timesheets | 95–105% | < 85% | Monthly | Fee adjustment and recovery plan |
| Information management compliance | Documents filed to the CDE naming convention | Count compliant ÷ sampled | CDE audit | ≥ 98% | < 90% | Quarterly | Rectify at SP cost |
| Stakeholder satisfaction | Structured survey of nominated Client stakeholders | Mean score out of 5 | Survey | ≥ 4.0 | < 3.0 | Six-monthly | Remediation plan |

[ Six to ten KPIs that are genuinely measured beat sixteen that are not. Delete the ones you will not actually collect data for. Every KPI you keep must have a named owner of the data source. ]

# 14.  Risk, Health, Safety, Environment and Sustainability

## 14.1  Risk management

14.1.1	The Service Provider must establish and maintain the Project risk and opportunity register in the Client's format, and must review and re-score every open risk at least monthly.

14.1.2	The Service Provider must facilitate a formal risk workshop at least quarterly, and at each stage gate, and must issue the updated register within [Insert, e.g. 5] Business Days of each workshop.

14.1.3	Risks must be quantified where they can be. The register must show the expected monetary value of the retained risk exposure and reconcile it to the remaining contingency in the cost report.

14.1.4	Every risk must have a single named owner who is a person, not an organisation, and a treatment with a date.

14.1.5	The Service Provider must escalate under clause 10.3 any risk that, if realised, would exceed the tolerances in clause 10.5.

## 14.2  Risk allocation summary

The table below records the intended allocation of the principal project risks. It is a summary for the guidance of the parties and does not override the Agreement or the construction contracts.

| Risk | Allocated to | Primary management mechanism |
| --- | --- | --- |
| Adequacy and stability of the Client brief | Client | Change control under clause 12 |
| Adequacy of the control budget | Client | Value management; budget review at gateways |
| Accuracy of Client-furnished information | Client | Reliance permitted under clause 8.3 |
| Latent site conditions | Client | Contingency; investigation before commitment |
| Statutory approval timing and conditions | Client | Programme float; early lodgement |
| Design error or omission by design consultants | Design consultants | Consultant appointments and professional indemnity |
| Coordination of the design process | Service Provider | Design management under clause 4 |
| Accuracy of the Service Provider's cost estimates and forecasts | Service Provider | Standard of care under clause 17.6 |
| Timeliness and quality of Deliverables | Service Provider | Clause 6 and clause 13 |
| Availability and continuity of Key Personnel | Service Provider | Clause 9.4 |
| Construction cost escalation | Client / shared | Escalation allowance; contract mechanism |
| Construction programme performance | Contractor | Liquidated damages under the works contract |
| Site safety of construction activities | Contractor | Principal contractor duties; SP provides assurance only |
| Industrial relations and labour availability | Contractor / Client | Per the works contract |
| Force Majeure and public health restrictions | Per the Agreement | Agreement terms prevail |
| Cyber and information security of the CDE | Client / shared | Clause 15.8 |
| Failure of a contractor or consultant (insolvency) | Client | Security, bonds and step-in rights; SP support is a Variation |

## 14.3  Health and safety

14.3.1	The Service Provider must comply with all health and safety laws applicable in the jurisdiction where the Services are performed, with the Client's site rules and policies, and with the principal contractor's site safety requirements.

14.3.2	The Service Provider must ensure its personnel are inducted before entering the Site, hold the required competencies and licences, and use the personal protective equipment required for the area they enter.

14.3.3	The Service Provider must not direct, and must not purport to direct, the means, methods or sequencing of construction work. Its safety role is assurance and oversight.

14.3.4	The Service Provider must stop, and must require the immediate stopping of, any activity it observes that presents an imminent risk of serious harm, and must report it to the Client and the principal contractor immediately.

14.3.5	The Service Provider must report to the Client any incident, near miss, dangerous occurrence, statutory notice or regulator attendance within [Insert, e.g. 4] hours of becoming aware of it, and must not participate in any investigation on the Client's behalf without authorisation.

14.3.6	The Service Provider must maintain its own safety management system, certified to [Insert standard, e.g. an internationally recognised occupational health and safety management system standard] or equivalent, and must provide evidence on request.

14.3.7	The Service Provider must consult, cooperate and coordinate with every other duty holder on the Project so far as its own duties are concerned.

## 14.4  Environment

Comply with all environmental laws, approvals and conditions applicable to the Project, and with the Client's environmental management requirements.

Review the contractor's environmental management plan and monitor compliance with it, including noise, dust, vibration, sediment, water quality, waste and hours of work.

Report every environmental incident, exceedance, complaint or regulator contact to the Client within [Insert, e.g. 4] hours.

Maintain the register of environmental approval conditions and track each to closeout.

Ensure that contaminated material, hazardous material and waste are handled, tracked and disposed of in accordance with the applicable jurisdiction's requirements, and that the disposal records are collected and handed over.

## 14.5  Sustainability and ESG

| Requirement | Obligation of the Service Provider | Evidence |
| --- | --- | --- |
| Rating scheme | Manage the Project to achieve [Insert scheme and target rating], including submission coordination and credit tracking | Credit tracker; certification |
| Carbon | Track embodied and operational carbon against the Project target and report movement monthly | Carbon register in the monthly report |
| Energy and water | Verify that design and construction meet the Project performance targets | Design compliance reports; commissioning results |
| Waste and circularity | Monitor the contractor's waste diversion against the target and report | Waste reports and disposal dockets |
| Social procurement | Track and report local content, indigenous or minority business participation and apprenticeships against targets | Monthly social procurement report |
| Modern slavery | Ensure no forced, bonded or child labour in the Service Provider's operations or supply chain; conduct proportionate due diligence on its own supply chain | Annual statement; supplier declarations |
| Climate risk and resilience | Ensure identified physical climate risks are addressed in design decisions and recorded | Risk register entries; design review records |
| Accessibility and inclusion | Verify that the design and delivery meet the accessibility standards required by the brief | Design review records |

## 14.6  Quality management

14.6.1	The Service Provider must maintain a documented quality management system certified to [Insert standard, e.g. an internationally recognised quality management system standard] or equivalent, and must apply it to the Services.

14.6.2	The Service Provider must apply a documented prepare / check / approve process to every Deliverable and record it on the Deliverable.

14.6.3	The Service Provider must submit a project quality plan within [Insert, e.g. 20] Business Days of the Effective Date describing how it will assure the quality of its own work and how it will assure the quality of the Works.

14.6.4	The Client may audit the Service Provider's quality system and project records on [Insert, e.g. 10] Business Days notice, up to [Insert, e.g. twice] per year.

14.6.5	Non-conformances in the Service Provider's own work must be recorded, notified and closed out at the Service Provider's cost.

# 15.  Information Management, Systems and Data

## 15.1  Common data environment

15.1.1	The Project common data environment is [Insert system name]. It is the single source of truth for all project information. A document that is not in the CDE does not exist for the purposes of this SOW.

15.1.2	The Service Provider must issue, receive, review and store all project information through the CDE, and must not maintain a parallel record as the operative version.

15.1.3	The Service Provider must administer the CDE in accordance with the Client's information management protocol, including workflow states, access permissions and transmittals, where clause 4 makes it responsible for document control.

15.1.4	Information must be filed against the correct project, package, discipline, document type and status. Superseded revisions must be retained and clearly marked.

## 15.2  Systems

| System | Purpose | Provided by | Service Provider obligation |
| --- | --- | --- | --- |
| [Insert CDE] | Document control and transmittals | Client | Use exclusively; administer where clause 4 so provides |
| [Insert PMIS] | Cost, change, risk, reporting and dashboards | Client | Maintain project data as the source of the monthly report |
| [Insert scheduling tool] | Programme development and analysis | Service Provider | Provide native files with each update |
| [Insert cost tool] | Cost planning and estimating | Service Provider | Provide native files and the estimate build-up |
| [Insert BIM environment] | Model federation and coordination | Client / design team | Access and review only unless clause 15.5 provides otherwise |
| [Insert finance system] | Commitments, invoices and payments | Client | Reconcile the cost report to the finance ledger monthly |

## 15.3  File naming and formats

| NAMING AND FORMAT REQUIREMENTS |  |
| --- | --- |
| Naming convention | [Insert convention, e.g. PROJECT-ORIGINATOR-VOLUME-LEVEL-TYPE-ROLE-NUMBER, with revision and status suffix] |
| Revision convention | [Insert, e.g. P01, P02 for preliminary; C01, C02 for issued] |
| Status codes | [Insert, e.g. S0 work in progress, S2 for information, S4 for construction, A1 authorised] |
| Documents | PDF/A for issue, plus native (DOCX, XLSX) for every Deliverable |
| Drawings | PDF for issue, plus native (DWG / DGN / RVT) as applicable |
| Programmes | PDF for issue, plus native (XER / MPP / XML) for every update |
| Cost data | XLSX with formulae intact and unprotected — not values-only or PDF |
| Models | [Insert authoring format] plus IFC for exchange |
| Photographs | JPEG with date, location and description metadata retained |
| Maximum file size | [Insert] per file; larger files split or transferred as agreed |

## 15.4  Native file delivery

Insist on native files with every submission, not only at the end. A cost model delivered as a PDF, or with formulae stripped, is worthless for the next stage and for benchmarking. Make native delivery a condition of a complete submission under clause 5.1, so an incomplete submission does not start the review clock.

15.4.1	Every Deliverable must be accompanied by its native working files, with formulae, links, logic and layers intact and unprotected.

15.4.2	Passwords, licences and access controls must not be applied to native files. Where a proprietary format is unavoidable, the Service Provider must also provide an open-format export.

15.4.3	Native files must be provided on each submission, on request, on termination, and at the end of the Services under Deliverable D-26.

15.4.4	The Service Provider must not withhold native files on the basis of an unpaid invoice, except to the extent the Agreement or the applicable jurisdiction expressly permits a lien.

## 15.5  Building information modelling

[Insert the BIM requirements applying to the Services, or state 'not applicable'. If BIM applies, address: the information delivery standard adopted; the Client's exchange information requirements; the BIM execution plan and who owns it; the required level of information need at each stage; model federation and clash resolution responsibility; the classification system; asset data (COBie or equivalent) and who populates it; model ownership and licensing; and the format and timing of model handover.]

[ If the Service Provider is a project or cost manager rather than a designer, its BIM role is usually to specify, coordinate and audit — not to author or federate models. Say so explicitly, and cross-reference exclusion 4.5.24, otherwise model authoring gets assumed into the scope. ]

## 15.6  Data ownership and records

15.6.1	All Project data created or collected by the Service Provider in performing the Services is the Client's data. The Service Provider holds it as custodian.

15.6.2	The Service Provider must not use Project data for any purpose other than performing the Services, other than aggregated and de-identified data used for internal benchmarking, and only where the Client has consented in writing.

15.6.3	The Service Provider must maintain complete and accurate records of the Services, including timesheets, correspondence, minutes, registers, calculations and working files, for at least [Insert, e.g. 7] years after completion of the Services, or longer where the applicable jurisdiction requires it.

15.6.4	The Service Provider must hand over the complete, indexed project record in native format under Deliverable D-26, and must not delete or archive Project data before handover is accepted.

## 15.7  Cyber and information security

Maintain information security controls appropriate to the sensitivity of the Project information, aligned to a recognised information security management standard.

Apply multi-factor authentication to all systems holding Project information, and remove access within one Business Day when a person leaves the Project.

Encrypt Project information in transit and at rest, and prohibit storage on unmanaged personal devices or unapproved consumer cloud services.

Notify the Client of any actual or suspected security incident affecting Project information within [Insert, e.g. 24] hours of becoming aware, and cooperate fully with the Client's response.

Where the Project involves security-sensitive, critical or protected infrastructure, comply with the additional requirements in [Insert reference], including personnel vetting and restricted distribution.

Do not use Project information to train, fine-tune or prompt any external artificial intelligence or machine learning service without the Client's prior written consent.

## 15.8  Personal data and privacy

15.8.1	Each party must comply with the privacy and data protection law applicable in the jurisdictions where personal data is collected, processed or stored.

15.8.2	The Service Provider must collect and process personal data only to the extent necessary to perform the Services, and only in accordance with the Client's instructions where the Client is the controller.

15.8.3	The Service Provider must not transfer personal data across borders without the Client's prior written consent and the safeguards the applicable law requires.

15.8.4	The Service Provider must notify the Client of any personal data breach without undue delay and in any event within [Insert, e.g. 24] hours of becoming aware.

15.8.5	On completion or termination the Service Provider must return or securely destroy personal data, except where retention is required by law, and must certify that it has done so.

# 16.  Intellectual Property, Confidentiality and Publicity

This clause records how the intellectual property and confidentiality provisions of the Agreement apply to the Deliverables. Where the Agreement deals with the same subject, the Agreement prevails.

## 16.1  Background IP

16.1.1	Each party retains ownership of its Background IP. Nothing in this SOW transfers Background IP.

16.1.2	The Service Provider grants the Client a perpetual, irrevocable, non-exclusive, royalty-free, transferable licence to use the Service Provider's Background IP to the extent it is embedded in, or necessary to use, a Deliverable, for the purposes in clause 16.3.

16.1.3	The Service Provider must identify in writing any Background IP it embeds in a Deliverable that is subject to a third-party licence, before that Deliverable is submitted, together with the terms of that licence.

## 16.2  Foreground IP

16.2.1	[Option A — assignment] All Foreground IP vests in the Client on creation. The Service Provider assigns to the Client all present and future rights in the Foreground IP and must do all things necessary to give effect to that assignment.

16.2.2	[Option B — licence] All Foreground IP remains with the Service Provider, which grants the Client a perpetual, irrevocable, non-exclusive, royalty-free, transferable and sub-licensable licence to use it for the purposes in clause 16.3.

16.2.3	The Service Provider warrants that the Deliverables do not infringe the intellectual property rights of any third party and indemnifies the Client against any claim that they do, subject to the liability provisions of the Agreement.

[ Choose Option A or Option B and delete the other. Assignment is common on public sector and owner-side engagements; a broad licence is more common for professional consultancy and is usually easier to negotiate. Either way the practical test is the same: can the Client use, amend and give the Deliverables to a replacement consultant without asking permission? If not, the clause is not fit for purpose. ]

## 16.3  Permitted purposes

Delivering, completing, operating, maintaining, repairing, altering, extending and disposing of the Project and the asset.

Procuring and instructing replacement or additional consultants and contractors.

Meeting statutory, funding, audit, insurance and reporting obligations.

Internal benchmarking, business case development and future capital planning.

The licence in clause 16.1 and, if Option B applies, clause 16.2, survives termination for any reason and is not conditional on payment, except to the extent the Agreement expressly provides otherwise.

## 16.4  Moral rights

[Insert the moral rights position for the applicable jurisdiction. In jurisdictions recognising moral rights, the usual approach is a written consent from each individual author to specified acts or omissions — for example not being identified as author, and the Deliverable being altered — to the extent permitted by law. Moral rights cannot be assigned in most jurisdictions, so a consent, not an assignment, is required. Take local advice.]

## 16.5  Confidentiality

16.5.1	Each party must keep the other's Confidential Information confidential, use it only for the Project, and disclose it only to those of its personnel and advisors who need it and who are bound by equivalent obligations.

16.5.2	The obligation does not apply to information that is public other than through a breach, was lawfully held before disclosure, is independently developed, or must be disclosed by law, a regulator, a court or a stock exchange — and in the last case the disclosing party must notify the other first where lawful.

16.5.3	The Service Provider must return or destroy Confidential Information on request or on completion of the Services, other than one archival copy retained for record and insurance purposes.

16.5.4	Confidentiality obligations survive termination for [Insert, e.g. 5] years, and indefinitely for information that is security-sensitive or personal.

## 16.6  Publicity and media

16.6.1	The Service Provider must not issue any media release, social media post, award submission, case study, website content or marketing material referring to the Project, the Client or the Services without the Client's prior written consent.

16.6.2	The Service Provider must refer all media, community and political enquiries to the Client's nominated communications contact and must not comment.

16.6.3	The Client's name, logo and brand may not be used except as the Client approves in writing.

16.6.4	This clause survives completion and termination.

## 16.7  Project imagery

16.7.1	Photography, filming and drone operation on the Site require the Client's prior written consent and compliance with the site rules and the applicable aviation and privacy laws.

16.7.2	Imagery of identifiable individuals must not be captured or used without their consent.

16.7.3	The Client owns all imagery captured for the Project. The Service Provider may use approved imagery for its own marketing only with the Client's prior written consent, which may be given for defined images and a defined period.

# 17.  Insurance, Liability and Indemnity

The Agreement governs insurance, liability and indemnity. This clause records the project-specific requirements and must be reconciled with the Agreement before issue. Where they differ, the Agreement prevails.

## 17.1  Required insurances

| Insurance | Minimum sum insured | Period to be maintained |
| --- | --- | --- |
| Professional indemnity | [Insert sum] per claim and in the aggregate | Term plus [Insert] years after completion of the Services |
| Public and products liability | [Insert sum] per occurrence | Term of the Services |
| Workers compensation / employers liability | As required by the applicable jurisdiction, or [Insert sum] | Term of the Services |
| Motor vehicle third-party liability | [Insert sum], or statutory minimum if higher | Term of the Services |
| Cyber liability | [Insert sum] per claim | Term of the Services |
| Contract works / construction insurance (if applicable to this SOW) | [Insert sum], noting the Client's interest | As specified in the Agreement |

17.1.1	The Service Provider must effect and maintain the insurances above with insurers of acceptable standing, licensed or authorised in the applicable jurisdiction.

17.1.2	The Service Provider must provide certificates of currency before commencing the Services, on each renewal, and within [Insert, e.g. 5] Business Days of a request.

17.1.3	The Service Provider must notify the Client immediately if any policy is cancelled, materially altered, or if a claim is made that could exhaust or materially reduce the professional indemnity limit.

17.1.4	Professional indemnity insurance must be maintained on a continuous claims-made basis for the run-off period stated, and the Service Provider must not allow a gap in cover.

17.1.5	The Service Provider's insurance obligations do not limit its liability under the Agreement or this SOW.

## 17.2  Liability cap

| LIABILITY |  |
| --- | --- |
| Aggregate liability cap | [Insert amount and currency, or a multiple of the Fee, or 'as stated in the Agreement'] |
| Basis of the cap | [Per claim / in the aggregate] for all claims arising out of the Services |
| Carve-outs from the cap | [Insert, e.g. death or personal injury, fraud, wilful misconduct, breach of confidentiality, IP infringement, uninsured deliberate acts — and any liability that cannot be limited by law] |
| Period after which liability ends | [Insert, e.g. the limitation period in the applicable jurisdiction, or an agreed shorter period] |
| Proportionate liability | [Insert whether any proportionate liability regime applies or is contracted out of, where the applicable jurisdiction permits] |

A liability cap set at, or below, the fee is common but leaves the Client materially exposed on a large capital project, because the loss a management error can cause is a function of project value, not fee value. Test the cap against a realistic worst case — a missed time bar, an uncertified variation, an unnoticed defect — and against the professional indemnity limit actually held.

## 17.3  Indemnities

The Service Provider indemnifies the Client against loss, damage, cost and expense arising from: personal injury or death caused by the Service Provider; loss of or damage to property caused by the Service Provider; infringement of third-party intellectual property rights by a Deliverable; breach of confidentiality, privacy or information security obligations; and any claim by the Service Provider's personnel or subcontractors. Each indemnity is reduced proportionally to the extent the loss is caused or contributed to by the Client.

## 17.4  Consequential loss

Neither party is liable to the other for consequential or indirect loss, loss of profit, loss of revenue, loss of opportunity, loss of use or loss of goodwill, except to the extent the Agreement provides otherwise, and except for liability arising from the carve-outs recorded in clause 17.2.

[ The phrase "consequential loss" is interpreted very differently between jurisdictions and is a frequent source of litigation. Prefer an express list of excluded loss categories over the bare phrase, and make sure the categories the Client most fears — for example delay costs and the cost of re-performing the Services — are dealt with expressly rather than left to argument. ]

## 17.5  Insurance of the Works

Contract works, public liability and any principal-arranged insurance for the Works are effected as stated in the Agreement and the construction contracts. The Service Provider must verify that the required policies are in place before authorising site possession, and must report any lapse immediately. The Service Provider is not an insurance advisor and does not warrant the adequacy of any policy.

## 17.6  Standard of care

The Service Provider must exercise the standard of skill, care and diligence reasonably expected of a suitably qualified and experienced provider of comparable services on a project of similar type, scale, complexity and value in the applicable jurisdiction. Nothing in this SOW imposes a fitness-for-purpose obligation on the professional services, and any reference to a Deliverable being "fit for purpose" in clause 6 relates only to the sufficiency of the document itself.

# 18.  Compliance, Probity and Conflicts

## 18.1  Conflicts of interest

18.1.1	The Service Provider must declare, in the form in clause 18.2, every actual, potential and perceived conflict of interest affecting it, its personnel, its related entities and its subcontractors, before the Effective Date.

18.1.2	The Service Provider must continue to monitor for conflicts and must declare any new conflict within [Insert, e.g. 2] Business Days of becoming aware of it.

18.1.3	The Service Provider must not act for any tenderer, contractor, supplier or other party with an interest in the Project without the Client's prior written consent.

18.1.4	Where a conflict arises, the Service Provider must propose a management plan. The Client may accept it, require additional controls, exclude the affected individual, or terminate under clause 19 if the conflict cannot be managed.

18.1.5	A failure to declare a material conflict is a substantial breach for the purposes of clause 19.6.

## 18.2  Conflict declaration

| Ref | Nature of interest | Person or entity affected | Actual / potential / perceived | Proposed management | Client decision |
| --- | --- | --- | --- | --- | --- |
| COI-01 | [Insert, or state 'nil declared'] | [Insert] | [Insert] | [Insert] | [Accepted / Rejected / Conditions] |
| COI-02 | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| COI-03 | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |

## 18.3  Anti-bribery, corruption and fraud

18.3.1	The Service Provider must comply with all anti-bribery, anti-corruption, anti-money laundering, sanctions and fraud laws applicable in the jurisdictions in which it operates, including any law with extraterritorial effect.

18.3.2	The Service Provider must not offer, give, request or accept any bribe, secret commission, facilitation payment, kickback or other improper advantage, whether directly or through a third party.

18.3.3	The Service Provider must maintain adequate procedures to prevent bribery and corruption by its personnel and subcontractors, and must provide evidence of them on request.

18.3.4	The Service Provider must report to the Client immediately any actual or suspected fraud, corruption, collusive tendering, bid rigging or improper conduct affecting the Project, whoever is involved.

18.3.5	Breach of this clause is a substantial breach entitling the Client to terminate immediately under clause 19.6.

## 18.4  Gifts and hospitality

| Category | Rule | Recording requirement |
| --- | --- | --- |
| Cash or cash equivalent | Never permitted, given or received, any amount | — |
| Gifts from a contractor, tenderer or supplier | Not permitted during a live procurement; otherwise only nominal items | Register every offer, accepted or declined |
| Meals and refreshments | Modest, infrequent, business-related only | Register where the value exceeds [Insert] |
| Hospitality, events and travel | Requires prior written approval from the Client's probity contact | Register in all cases |
| Sponsorship and donations | Not permitted in connection with the Project | — |

The Service Provider must maintain a gifts and hospitality register for the Project and make it available to the Client on request.

## 18.5  Probity

Comply with the Project probity plan and any direction of the probity advisor.

Treat all tenderers fairly, equally and consistently, and give no tenderer an advantage in information, time or access.

Keep tender information confidential and secure, and restrict access to the evaluation panel and those with a need to know.

Maintain a complete, contemporaneous and auditable record of every procurement decision, including the reasons.

Declare any prior or current relationship with a tenderer before participating in an evaluation.

Do not enter into any arrangement with a tenderer that is contingent on the outcome of the procurement.

## 18.6  Code of conduct

The Service Provider's personnel must comply with the Client's code of conduct while on the Site or Client premises, and must at all times behave lawfully, safely and respectfully. Bullying, harassment, discrimination, intimidation and impairment by alcohol or drugs are grounds for immediate removal from the Project under clause 13.5.

## 18.7  Modern slavery and labour standards

The Service Provider must take reasonable steps to identify, assess and address modern slavery risks in its operations and supply chain, must not use forced, bonded, compulsory or child labour, must pay its personnel at least the legal minimum and on time, and must report any credible allegation of modern slavery affecting the Project to the Client immediately.

## 18.8  Audit and access

18.8.1	The Client, its auditors and its regulators may audit the Service Provider's records relating to the Services, including timesheets, invoices, Reimbursable substantiation, subcontracts, quality records and conflict declarations.

18.8.2	The Client must give [Insert, e.g. 10] Business Days notice, except where fraud or a safety matter is suspected, in which case no notice is required.

18.8.3	Audit rights continue for [Insert, e.g. 7] years after completion of the Services.

18.8.4	Where an audit identifies an overcharge exceeding [Insert, e.g. 5]% of the amount audited, the Service Provider must refund the overcharge and bear the reasonable cost of the audit.

18.8.5	The Service Provider must include equivalent audit rights in every subcontract.

# 19.  Term, Suspension and Termination

## 19.1  Commencement and term

| TERM |  |
| --- | --- |
| Effective Date | [dd-mmm-yy] |
| Commencement of the Services | [dd-mmm-yy, or 'on receipt of a purchase order'] |
| Expected completion of the Services | [dd-mmm-yy, or 'on achievement of Milestone M-16'] |
| Extension options | [Insert, e.g. 2 × 12 months, exercisable by the Client on 30 days notice] |
| Conditions precedent to commencement | [Insert, e.g. executed Agreement; evidence of insurance; purchase order; approved conflict management plan] |

The Service Provider must not commence the Services, and no cost is payable, until every condition precedent is satisfied. If the Client requires an early start, the conditions must be waived in writing by a person with authority to do so.

## 19.2  Suspension by the Client

19.2.1	The Client may suspend all or part of the Services at any time by written notice stating the scope and expected duration of the suspension.

19.2.2	On receiving a suspension notice the Service Provider must stop the affected Services, secure and protect the work in progress, mitigate cost, and provide a status report on every open matter within [Insert, e.g. 5] Business Days.

19.2.3	The Service Provider is entitled to the reasonable, evidenced and unavoidable costs of suspension and remobilisation, and to a corresponding adjustment of Milestone dates. It is not entitled to loss of profit on suspended Services.

19.2.4	If a suspension continues for more than [Insert, e.g. 6] months, either party may terminate the affected Services on [Insert, e.g. 20] Business Days written notice, and clause 19.7 applies.

## 19.3  Termination for convenience

19.3.1	The Client may terminate this SOW, in whole or in part, at any time and for any reason by giving [Insert, e.g. 20] Business Days written notice.

19.3.2	On termination for convenience the Service Provider is entitled to: the Fee for Services properly performed to the date of termination; approved Reimbursables incurred; and the reasonable, evidenced and unavoidable costs of demobilisation.

19.3.3	The Service Provider is not entitled to loss of profit on the unperformed Services, to loss of opportunity, or to any other compensation.

19.3.4	The Service Provider must mitigate its costs, including by redeploying personnel, and must substantiate every amount claimed.

## 19.4  Termination for cause — by the Client

The Client may terminate immediately by written notice if the Service Provider:

commits a substantial breach of the Agreement or this SOW that is not capable of remedy;

commits a breach capable of remedy and fails to remedy it within [Insert, e.g. 10] Business Days of a written notice requiring remedy;

fails to maintain a required insurance;

becomes insolvent, or an insolvency event under the Agreement occurs;

breaches clause 18.3 (anti-bribery), clause 18.1 (conflicts) or clause 18.7 (modern slavery);

assigns, novates or subcontracts in breach of clause 9.6;

fails to restore performance within the period of an accepted remediation plan under clause 13.3; or

does anything that in the Client's reasonable opinion brings the Project or the Client into disrepute.

## 19.5  Termination for cause — by the Service Provider

The Service Provider may terminate on [Insert, e.g. 20] Business Days written notice if the Client fails to pay an undisputed amount and does not remedy that failure within [Insert, e.g. 10] Business Days of a notice under clause 11.11, or if a suspension continues beyond the period in clause 19.2.

## 19.6  Substantial breach

Without limitation, each of the following is a substantial breach: a failure to declare a material conflict; a breach of the anti-bribery obligations; a persistent failure to meet KPI thresholds after remediation; the loss of a Key Person without an acceptable replacement; a failure to issue a contractual notice within a time bar that causes the Client to lose an entitlement; a breach of confidentiality or information security causing material harm; and the abandonment of the Services.

## 19.7  Consequences of termination

19.7.1	The Service Provider must immediately stop the Services except as directed, secure the work in progress, and take all reasonable steps to mitigate cost.

19.7.2	The Service Provider must hand over, within [Insert, e.g. 10] Business Days, all Deliverables (complete or not), working files, native files, models, data, records, correspondence, registers and Client property, in the formats required by clause 15.

19.7.3	The Service Provider must provide a written status report on every open matter, including every pending contractual deadline, time bar, claim, notice, approval and decision, and must identify anything requiring action within the following 20 Business Days.

19.7.4	The Service Provider must, if requested, novate or assign to the Client or its nominee any third-party appointment, licence or subcontract it holds for the Project.

19.7.5	The licences granted under clause 16 survive and are not conditional on payment of any disputed amount.

19.7.6	Accrued rights, and the clauses expressed to survive, are unaffected by termination.

## 19.8  Transition-out

| Transition activity | Period | Responsible | Evidence of completion |
| --- | --- | --- | --- |
| Transition-out plan submitted | Within 5 BD of the termination notice | Service Provider | Plan accepted by the Client |
| Knowledge transfer sessions with the incoming provider | [Insert, e.g. up to 5 days] | Service Provider | Attendance record and handover pack |
| Handover of all records, registers and native files | Within 10 BD | Service Provider | Signed handover register (Deliverable D-26) |
| Status report on every open matter and time bar | Within 5 BD | Service Provider | Report accepted by the Client |
| Return of Client property, passes, keys and system access | Within 5 BD | Service Provider | Asset return schedule |
| Revocation of system and CDE access | Within 1 BD of handover | Client | Access log |
| Final invoice and substantiation | Within 20 BD | Service Provider | Invoice accepted for payment |
| Final reconciliation and release | Within 30 BD | Both parties | Signed reconciliation |

Transition-out obligations are worthless unless they are priced and resourced. Make the transition-out plan a Deliverable, make final payment conditional on completing it, and confirm that the Service Provider is obliged to perform it even where it terminated for the Client's non-payment.

# 20.  Dispute Resolution

## 20.1  Application

This clause applies to any dispute arising out of or in connection with this SOW. Where the Agreement contains a dispute resolution regime, that regime prevails and this clause operates only to the extent it is consistent with it.

## 20.2  Process

| Step | Process | Who | Period |
| --- | --- | --- | --- |
| 1 | Written notice of dispute stating the issue, the relief sought and the basis | Either party | Within [Insert, e.g. 10] BD of the dispute arising |
| 2 | Good-faith negotiation between the project representatives | SP Project Director and Client Project Director | [Insert, e.g. 10] BD from the notice |
| 3 | Escalation to senior executives with authority to settle | SP Executive and Client Executive Sponsor | A further [Insert, e.g. 10] BD |
| 4 | Structured mediation or expert determination (see clause 20.3) | Independent third party | [Insert, e.g. 20] BD from appointment |
| 5 | Arbitration or litigation | As elected in clause 20.4 | Only after steps 1 to 4 are exhausted |

## 20.3  Choosing the third-party process

| Mechanism | Best suited to | Binding? | Considerations |
| --- | --- | --- | --- |
| Expert determination | Technical or valuation disputes — measurement, rates, quantum, programme analysis | [Binding / non-binding — select] | Fast and cheap; poorly suited to disputes turning on contract interpretation |
| Mediation | Relationship disputes and multi-issue commercial disagreements | Non-binding | Preserves the relationship; success depends on both parties attending with authority to settle |
| Arbitration | Cross-border engagements, or where confidentiality and enforceability matter | Binding | Specify the rules, the seat, the number of arbitrators and the language |
| Statutory adjudication | Payment disputes where the applicable jurisdiction provides a payment regime | Interim binding | Cannot be contracted out of where it applies; timeframes are very short |
| Litigation | Where a precedent, a public judgment or joinder of third parties is needed | Binding | Slow and public; consider the courts' familiarity with construction disputes |

## 20.4  Elections

| DISPUTE RESOLUTION ELECTIONS |  |
| --- | --- |
| Third-party mechanism elected | [Expert determination / Mediation / Arbitration] |
| Appointing body if the parties cannot agree | [Insert institution in the applicable jurisdiction] |
| Rules | [Insert rules, e.g. the institution's standard rules current at the date of the notice] |
| Seat / venue | [Insert city and country] |
| Language | [Insert] |
| Number of arbitrators / experts | [Insert 1 or 3] |
| Costs | [Insert, e.g. each party bears its own costs; the third party's fees shared equally pending determination] |

## 20.5  Continue to perform

The parties must continue to perform their obligations under this SOW and the Agreement while a dispute is being resolved. The Service Provider must not suspend or slow the Services because a dispute exists, except where clause 11.11 applies. The Client must continue to pay all undisputed amounts.

## 20.6  Urgent relief and governing law

20.6.1	Nothing in this clause prevents a party from seeking urgent interlocutory or injunctive relief from a court of competent jurisdiction.

20.6.2	This SOW is governed by the law of [Insert governing law], and the parties submit to the [exclusive / non-exclusive] jurisdiction of the courts of [Insert jurisdiction].

20.6.3	Where the Agreement specifies a different governing law or jurisdiction, the Agreement prevails and this clause must be amended to match it before issue.

[ The governing law of the SOW must match the Agreement. A SOW governed by a different law from the contract it sits under creates a conflict that is expensive to resolve and serves no commercial purpose. Confirm this with legal before issue. ]

# 21.  Signatures

By signing below, each party agrees that this Statement of Work forms part of the Agreement identified in the document control table, and that the Services will be performed and paid for in accordance with it.

| EXECUTION SUMMARY |  |
| --- | --- |
| SOW reference | [Insert] |
| SOW version | [Insert] |
| Head agreement reference | [Insert] |
| Effective Date | [dd-mmm-yy] |
| Total Fee (excluding taxes and Reimbursables) | [Insert amount and currency] |

### 21.1  Executed for the Client / Principal

| Signed for and on behalf of | the Client / Principal — [Insert legal entity name] |
| --- | --- |
| Name (print) | [Insert full name] |
| Position / title | [Insert position] |
| Authority to bind | [Insert basis of authority, e.g. director / delegate under instrument] |
| Signature |  |
| Date | [dd-mmm-yy] |
| Witness name (print) | [Insert full name] |
| Witness signature |  |

### 21.2  Executed for the Service Provider

| Signed for and on behalf of | the Service Provider — [Insert legal entity name] |
| --- | --- |
| Name (print) | [Insert full name] |
| Position / title | [Insert position] |
| Authority to bind | [Insert basis of authority, e.g. director / delegate under instrument] |
| Signature |  |
| Date | [dd-mmm-yy] |
| Witness name (print) | [Insert full name] |
| Witness signature |  |

Confirm before execution that each signatory holds authority to bind their entity, that the execution formality matches the requirements of the applicable jurisdiction and the Agreement (including any requirement for a deed, a common seal, two officers or a witness), and that the version being signed is the version recorded in the revision history.

# Appendix A — Detailed Scope Matrix by Phase

This matrix is the activity-level definition of the Services and prevails over the summary in clause 4.2. "Lead" means the party owns the activity and its output; "Support" means it contributes; "Approve" means it authorises; "—" means no role. Add, delete and amend rows so the matrix reflects the engagement actually being bought.

[ Complete a row for every activity that either party could reasonably expect to be someone's job. An activity that appears on no row is an activity nobody has been paid to do, and it will surface as a dispute at the worst possible moment. ]

| Activity | Phase | Service Provider | Client | Others | Notes |
| --- | --- | --- | --- | --- | --- |
| Confirm business case, benefits and success measures | Initiation | Support | Lead | — | Client owns the benefits case |
| Establish governance structure and delegations | Initiation | Lead | Approve | — | Recorded in the PEP |
| Prepare the Project Execution Plan | Initiation | Lead | Approve | — | Deliverable D-01 |
| Establish the control budget and cost plan | Initiation | Lead | Approve | — | Deliverable D-05 |
| Establish the baseline master programme | Initiation | Lead | Approve | — | Deliverable D-03 |
| Establish risk management framework and register | Initiation | Lead | Approve | — | Deliverable D-08 |
| Establish the CDE and document control protocols | Initiation | Lead | Support | — | Clause 15 |
| Confirm the Client brief and functional requirements | Initiation | Support | Lead | Client user groups | Assumption A-05 |
| Procure and appoint design consultants | Planning | Lead | Approve | — | Client executes the appointments |
| Manage concept design development | Planning | Lead | Approve | Design team | Design team performs the design |
| Manage developed and detailed design | Planning | Lead | Approve | Design team | Design team performs the design |
| Coordinate design reviews and comment closeout | Planning | Lead | Input | Design team | Deliverable D-13 |
| Prepare and update cost plans at each stage | Planning | Lead | Approve | — | Deliverable D-05 |
| Run value management workshops | Planning | Lead | Participate | Design team | — |
| Prepare and lodge statutory approval applications | Planning | Coordinate | Approve | Planning consultant | Excluded from SP scope |
| Conduct site investigations and surveys | Planning | Coordinate | Procure | Specialist consultants | Client cost |
| Develop the procurement and packaging strategy | Procurement | Lead | Approve | — | Deliverable D-09 |
| Prepare tender documentation | Procurement | Lead | Approve | Design team | Deliverable D-10 |
| Manage the tender process and addenda | Procurement | Lead | Support | Probity advisor | Probity record maintained |
| Evaluate tenders and prepare recommendation | Procurement | Lead | Approve | Evaluation panel | Deliverable D-11 |
| Negotiate and execute construction contracts | Procurement | Support | Lead | Legal advisor | Client executes |
| Administer the construction contract | Construction | Lead | Oversee | Contractor | Within delegation, clause 10.5 |
| Assess and certify progress claims | Construction | Lead | Approve payment | Contractor | Deliverable D-14 |
| Assess variations, claims and extensions of time | Construction | Lead | Approve | Contractor | Deliverables D-15, D-16 |
| Maintain cost report and anticipated final cost | Construction | Lead | Approve | — | Deliverable D-17 |
| Update and analyse the programme | Construction | Lead | Review | Contractor | Deliverable D-04 |
| Provide HSE assurance and attend safety walks | Construction | Lead | Oversee | Contractor | Contractor holds statutory duties |
| Provide quality surveillance and ITP review | Construction | Lead | Review | Contractor | Deliverable D-19 |
| Chair site and progress meetings | Construction | Lead | Attend | Contractor | Clause 10.1 |
| Manage stakeholder and community communications | Construction | Support | Lead | Communications advisor | — |
| Manage commissioning readiness and witness testing | Commissioning | Lead | Review | Contractor | Deliverable D-20 |
| Verify O&M manuals, as-builts and warranties | Commissioning | Lead | Approve | Contractor | Deliverable D-22 |
| Manage completion inspections and defects identification | Commissioning | Lead | Attend | Contractor | Deliverable D-21 |
| Manage operational readiness and training coordination | Commissioning | Support | Lead | Contractor | Client owns operational change |
| Manage handover, keys, access and asset data transfer | Handover | Lead | Approve | Contractor | Deliverable D-21 |
| Manage the defects liability period | Post-completion | Lead | Support | Contractor | Deliverable D-23 |
| Agree and certify the final account | Post-completion | Lead | Approve | Contractor | Deliverable D-24 |
| Prepare closeout report and lessons learned | Post-completion | Lead | Approve | — | Deliverable D-25 |
| Hand over the complete project record in native format | Post-completion | Lead | Receive | — | Deliverable D-26 |
| Post-occupancy evaluation and benefits realisation | Post-completion | — | Lead | — | Excluded from SP scope |

# Appendix B — Deliverables Register (expanded)

The expanded register adds the revision, distribution, retention and status columns required to administer the Deliverables in clause 5.4. Maintain it live in the CDE or the PMIS and issue it with each monthly report.

Status codes:  NS = not started  ·  DR = drafting  ·  SU = submitted  ·  RS = resubmission required  ·  AC = accepted.

| Ref | Deliverable | Format | Standard / template | Frequency | Due date / trigger | Owner (SP) | Reviewer | Acceptance | Rev | Status | Distribution | Retention |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D-01 | Project Execution Plan | DOCX + PDF | Client PEP template | Once, then 6-monthly | 15 BD from Effective Date | [Insert] | Client PM | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-02 | Project Governance Charter | DOCX + PDF | Client governance template | Once | 15 BD from Effective Date | [Insert] | Client PM | Project Sponsor | [Insert] | [NS] | [Insert] | [Insert] |
| D-03 | Baseline Master Programme | XER/MPP + PDF | Client scheduling standard | Once, then re-baseline on approval | 20 BD from Effective Date | [Insert] | Client Scheduler | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-04 | Programme Update and Analysis | XER/MPP + PDF | Client scheduling standard | Monthly | With monthly report | [Insert] | Client Scheduler | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-05 | Control Budget and Cost Plan | XLSX + PDF | Elemental cost plan format | At each design stage | 5 BD after stage issue | [Insert] | Client Cost Manager | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-06 | Cash Flow Forecast | XLSX | Client finance template | Monthly | With monthly report | [Insert] | Client Finance | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-07 | Monthly Project Report | PDF + native | Appendix H | Monthly | By the 5th BD of each month | [Insert] | Client PM | Project Sponsor | [Insert] | [NS] | [Insert] | [Insert] |
| D-08 | Risk and Opportunity Register | XLSX or PMIS | Client risk template | Monthly, workshops quarterly | With monthly report | [Insert] | Client Risk Manager | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-09 | Procurement and Packaging Strategy | DOCX + PDF | Client procurement template | Once per stage | [Insert date] | [Insert] | Client Procurement | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-10 | Tender Documentation Set | PDF + native | Client tender template | Per package | Per procurement programme | [Insert] | Client Procurement | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-11 | Tender Evaluation Report | DOCX + PDF | Client evaluation template | Per package | 10 BD after tender close | [Insert] | Evaluation Panel | Delegated Authority | [Insert] | [NS] | [Insert] | [Insert] |
| D-12 | Contract Award Recommendation | DOCX + PDF | Client board paper format | Per package | With evaluation report | [Insert] | Client Procurement | Delegated Authority | [Insert] | [NS] | [Insert] | [Insert] |
| D-13 | Design Review Report | PDF + comment register | Client review template | Per design stage | 10 BD after stage issue | [Insert] | Client Design Lead | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-14 | Progress Claim Assessment and Certificate | PDF + XLSX | Contract form | Monthly | Per contract time bar | [Insert] | Client Cost Manager | Superintendent / CA | [Insert] | [NS] | [Insert] | [Insert] |
| D-15 | Variation Assessment and Register | XLSX + PDF | Client change template | Monthly, and per event | 10 BD from receipt | [Insert] | Client Cost Manager | Delegated Authority | [Insert] | [NS] | [Insert] | [Insert] |
| D-16 | Extension of Time Assessment | DOCX + PDF | Contract form | Per event | Per contract time bar | [Insert] | Client PM | Superintendent / CA | [Insert] | [NS] | [Insert] | [Insert] |
| D-17 | Cost Report and Anticipated Final Cost | XLSX + PDF | Client cost report format | Monthly | With monthly report | [Insert] | Client Cost Manager | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-18 | HSE Assurance Report | PDF | Client HSE template | Monthly | With monthly report | [Insert] | Client HSE Manager | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-19 | Quality Surveillance Report | PDF | Client quality template | Monthly | With monthly report | [Insert] | Client Quality Lead | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-20 | Commissioning Readiness Report | PDF | Client commissioning template | Monthly from [Insert stage] | With monthly report | [Insert] | Client Engineering | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-21 | Completion and Handover Register | XLSX + PDF | Client handover template | Per completion event | 5 BD before completion | [Insert] | Client Facilities | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-22 | Operations and Maintenance Manual Audit | PDF checklist | Client O&M standard | Per completion event | 10 BD before handover | [Insert] | Client Facilities | Client PM | [Insert] | [NS] | [Insert] | [Insert] |
| D-23 | Defects Register and Closeout Report | XLSX + PDF | Client defects template | Monthly during DLP | Monthly, and at final completion | [Insert] | Client Facilities | Project Director | [Insert] | [NS] | [Insert] | [Insert] |
| D-24 | Final Account Report | XLSX + PDF | Client final account format | Per contract | 20 BD after final completion | [Insert] | Client Cost Manager | Delegated Authority | [Insert] | [NS] | [Insert] | [Insert] |
| D-25 | Project Closeout and Lessons Learned Report | DOCX + PDF | Client closeout template | Once | 20 BD after final completion | [Insert] | Client PM | Project Sponsor | [Insert] | [NS] | [Insert] | [Insert] |
| D-26 | Records and Native File Handover | Structured file set | Clause 15 naming convention | Once, plus on termination | 10 BD after final completion | [Insert] | Client Records | Client PM | [Insert] | [NS] | [Insert] | [Insert] |

[ Keep the Ref column stable for the life of the engagement. Deliverable references are cited in invoices, acceptance certificates, milestone claims and the change log — renumbering them mid-engagement breaks the audit trail. ]

# Appendix C — Schedule of Rates

All rates are in [Insert currency code], exclusive of applicable transaction taxes, and inclusive of all overheads, on-costs, profit, standard information technology, communications, insurance and local travel. Rates apply to Variations, additional services and any time-charged component of the Fee.

| Role | Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- | --- |
| Project Director / Principal | [Insert] | [Insert] | [Insert] | [Insert] |
| Senior Project Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Project Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Assistant Project Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Contract Administrator / Superintendent's Representative | [Insert] | [Insert] | [Insert] | [Insert] |
| Senior Cost Manager / Quantity Surveyor | [Insert] | [Insert] | [Insert] | [Insert] |
| Cost Manager / Quantity Surveyor | [Insert] | [Insert] | [Insert] | [Insert] |
| Planner / Scheduler | [Insert] | [Insert] | [Insert] | [Insert] |
| Design Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Site Superintendent / Clerk of Works | [Insert] | [Insert] | [Insert] | [Insert] |
| HSE Advisor | [Insert] | [Insert] | [Insert] | [Insert] |
| Risk Manager | [Insert] | [Insert] | [Insert] | [Insert] |
| Specialist Advisor / Technical Expert | [Insert] | [Insert] | [Insert] | [Insert] |
| Document Controller / Project Administrator | [Insert] | [Insert] | [Insert] | [Insert] |
| Graduate / Cadet | [Insert] | [Insert] | [Insert] | [Insert] |

## C.1  Rate conditions

| RATE CONDITIONS |  |
| --- | --- |
| Currency | [Insert currency code] |
| Rate validity period | Fixed to [dd-mmm-yy], then adjusted under clause 11.9 |
| Escalation mechanism | [Insert index] capped at [Insert]% per annum |
| Minimum charging increment | [Insert, e.g. 0.25] hours |
| Standard working day | [Insert, e.g. 7.6] hours |
| Overtime multiplier | [Insert, e.g. 1.5] — prior written authorisation required |
| Weekend / public holiday multiplier | [Insert, e.g. 2.0] — prior written authorisation required |
| Travel time | [Chargeable at Insert% of rate / not chargeable] |
| Daily rate | [Insert basis, e.g. hourly rate × standard working day] |
| Mark-up on subcontracted specialists | [Insert %, or 'nil'] |
| Mark-up on Reimbursables | Nil |

## C.2  Resource allocation forecast

| Role | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Stage 6 | Stage 7 | Total hours |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Director / Principal | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Senior Project Manager | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Project Manager | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Assistant Project Manager | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Contract Administrator / Superintendent's Representative | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Senior Cost Manager / Quantity Surveyor | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Cost Manager / Quantity Surveyor | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Planner / Scheduler | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Design Manager | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Site Superintendent / Clerk of Works | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |
| Total hours | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] | [Insert] |

[ A resource forecast turns a fee proposal into something that can be tested. Compare the hours here against the allocations in clause 9.3 — if the percentages and the hours do not reconcile, one of them is wrong. ]

# Appendix D — Milestone and Payment Schedule

This schedule links the Milestones in clause 7.1 to the fee schedule in clause 11.2. Every payment milestone must be objectively verifiable by reference to an Accepted Deliverable or a defined event. Percentages must total 100%.

| Ref | Milestone | Evidence of achievement | Planned date | Payment linked? | % of Fee | Amount | Cumulative % |
| --- | --- | --- | --- | --- | --- | --- | --- |
| M-01 | SOW mobilisation complete | Team mobilised, PEP and governance charter Accepted | [Insert date] | Yes | 5% | [Insert] | [Insert] |
| M-02 | Baseline programme and control budget Accepted | Baseline programme and control budget approved by the Client | [Insert date] | Yes | 5% | [Insert] | [Insert] |
| M-03 | Concept design stage complete | Concept design review report Accepted and cost plan reconciled | [Insert date] | Yes | 10% | [Insert] | [Insert] |
| M-04 | Developed design stage complete | Developed design Accepted, cost plan within control budget | [Insert date] | Yes | 10% | [Insert] | [Insert] |
| M-05 | Statutory approval obtained | Principal development or building approval issued | [Insert date] | Yes | 5% | [Insert] | [Insert] |
| M-06 | Tender documentation issued to market | Issued-for-tender package released for the main works | [Insert date] | Yes | 10% | [Insert] | [Insert] |
| M-07 | Main works contract awarded | Evaluation report Accepted and contract executed | [Insert date] | Yes | 10% | [Insert] | [Insert] |
| M-08 | Site possession and construction commencement | Contractor granted access and works commenced | [Insert date] | No | — | [Insert] | [Insert] |
| M-09 | Construction 25% complete | Certified value of work done reaches 25% of contract sum | [Insert date] | Yes | 8% | [Insert] | [Insert] |
| M-10 | Construction 50% complete | Certified value of work done reaches 50% of contract sum | [Insert date] | Yes | 8% | [Insert] | [Insert] |
| M-11 | Construction 75% complete | Certified value of work done reaches 75% of contract sum | [Insert date] | Yes | 8% | [Insert] | [Insert] |
| M-12 | Commissioning commenced | Commissioning readiness report Accepted and testing started | [Insert date] | No | — | [Insert] | [Insert] |
| M-13 | Practical completion achieved | Certificate of practical completion issued for the main works | [Insert date] | Yes | 10% | [Insert] | [Insert] |
| M-14 | Handover and operational readiness complete | Handover register closed, O&M audit Accepted, occupation achieved | [Insert date] | Yes | 5% | [Insert] | [Insert] |
| M-15 | Final account agreed | Final account report Accepted for all contracts | [Insert date] | Yes | 4% | [Insert] | [Insert] |
| M-16 | Defects liability period expired and project closed out | Final completion certified, closeout report Accepted | [Insert date] | Yes | 2% | [Insert] | [Insert] |
|  | TOTAL |  |  |  | 100% | [Insert] | 100% |

Front-loaded milestone payments transfer risk to the Client and remove the Service Provider's incentive to finish. Test the profile: at any point in the engagement, the cumulative percentage paid should not materially exceed the percentage of the Services actually performed.

## D.1  Payment conditions

A Milestone payment may be claimed only after the Acceptance Certificate for every linked Deliverable has been signed under clause 6.7.

Where a Milestone is partially achieved, no payment is due unless the Client agrees a partial payment in writing.

Milestone dates adjust automatically where the Milestone is delayed by a cause for which the Client is responsible under clause 7.5.

The final Milestone must represent at least [Insert, e.g. 5]% of the Fee and must not be claimable until Deliverable D-26 is Accepted.

# Appendix E — RACI Matrix

R = Responsible (does the work) · A = Accountable (owns the outcome, exactly one per activity) · C = Consulted (two-way input before the decision) · I = Informed (told afterwards) · — = no role. Where this matrix differs from clause 9.2, this matrix prevails.

| Activity | Client Sponsor | Client PM | SP Project Director | SP Project Manager | Design Lead | Cost Manager | Contractor | Contract Admin | HSE Advisor | Stakeholder Lead |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approve the Project business case and control budget | A | C | I | I | I | R | — | [Insert] | [Insert] | [Insert] |
| Prepare and maintain the Project Execution Plan | A | C | A | R | C | C | I | [Insert] | [Insert] | [Insert] |
| Establish and maintain the master programme | I | A | A | R | C | C | C | [Insert] | [Insert] | [Insert] |
| Maintain the cost plan and anticipated final cost | I | A | A | C | I | R | I | [Insert] | [Insert] | [Insert] |
| Manage the design programme and design reviews | I | A | A | R | R | C | I | [Insert] | [Insert] | [Insert] |
| Approve design at each stage gate | A | R | C | C | C | C | I | [Insert] | [Insert] | [Insert] |
| Develop the procurement and packaging strategy | A | C | A | R | C | C | — | [Insert] | [Insert] | [Insert] |
| Prepare and issue tender documentation | I | A | A | R | C | C | — | [Insert] | [Insert] | [Insert] |
| Evaluate tenders and recommend award | A | C | A | R | C | C | — | [Insert] | [Insert] | [Insert] |
| Execute the construction contract | A | R | C | I | I | I | R | [Insert] | [Insert] | [Insert] |
| Administer the construction contract | I | A | A | R | C | C | C | [Insert] | [Insert] | [Insert] |
| Assess and certify progress claims | I | A | A | C | I | R | C | [Insert] | [Insert] | [Insert] |
| Assess variations and claims | A | A | R | R | C | R | C | [Insert] | [Insert] | [Insert] |
| Manage the risk register and risk workshops | I | A | A | R | C | C | C | [Insert] | [Insert] | [Insert] |
| Deliver HSE performance on Site | I | I | C | C | I | I | A | [Insert] | [Insert] | [Insert] |
| Provide client-side HSE assurance | I | A | A | R | I | I | C | [Insert] | [Insert] | [Insert] |
| Deliver quality and close out non-conformances | I | C | C | C | C | I | A | [Insert] | [Insert] | [Insert] |
| Provide quality surveillance and ITP review | I | A | A | R | C | I | C | [Insert] | [Insert] | [Insert] |
| Prepare and issue the monthly report | I | A | A | R | C | C | I | [Insert] | [Insert] | [Insert] |
| Manage commissioning and operational readiness | A | A | A | R | C | I | R | [Insert] | [Insert] | [Insert] |
| Manage completion, handover and warranties | I | A | A | R | C | C | R | [Insert] | [Insert] | [Insert] |
| Manage the defects liability period | I | A | A | R | I | I | R | [Insert] | [Insert] | [Insert] |
| Agree the final account | A | A | A | C | I | R | R | [Insert] | [Insert] | [Insert] |
| Prepare the closeout and lessons learned report | I | A | A | R | C | C | I | [Insert] | [Insert] | [Insert] |

[ Check three things before you issue this: exactly one A per row; no row where the same party is both A and the only R for an approval activity; and no activity in Appendix A that is missing from this matrix. ]

# Appendix F — Change Request Form

Use one form per change. Raise it under clause 12.2 and record the outcome in the change log at clause 12.5. Do not commence varied work before Part 4 is signed.

| Change request number | CR-[Insert] |
| --- | --- |
| Project / SOW reference | [Insert] |
| Date raised | [dd-mmm-yy] |
| Raised by | [Insert name, organisation, role] |
| Change title | [Insert a short descriptive title] |

### Part 1 — Description of the change

| Description of the change | [Describe what is changing, in enough detail that a person who was not present can price it] |
| --- | --- |
| Reason for the change | [Client instruction / failed assumption (state ref) / statutory change / design development / other] |
| Origin | [Client / Service Provider / Contractor / Authority / Other] |
| Clauses, Deliverables and Milestones affected | [Insert references] |
| Urgency and the consequence of not deciding | [Insert, with the date a decision is required] |

### Part 2 — Service Provider assessment

| Role | Hours | Rate | Amount | Notes |
| --- | --- | --- | --- | --- |
| [Insert role] | [Insert] | [Insert] | [Insert] | [Insert] |
| [Insert role] | [Insert] | [Insert] | [Insert] | [Insert] |
| [Insert role] | [Insert] | [Insert] | [Insert] | [Insert] |
| Reimbursables | — | — | [Insert] | [Insert] |
| Total (excluding taxes) |  |  | [Insert] |  |

| Effect on Milestones | [State each Milestone affected and the revised date] |
| --- | --- |
| Effect on other Deliverables | [Insert] |
| Effect on assumptions and risks | [Insert] |
| Validity period of this assessment | [Insert, e.g. 20 Business Days from the date below] |
| Assessed by / date | [Insert name, role, date] |

### Part 3 — Client review

| Reviewed by / date | [Insert name, role, date] |
| --- | --- |
| Budget source and availability | [Contingency / additional funding / reallocation — state the source] |
| Within delegation? (clause 10.5) | [Yes — approver: Insert / No — escalate to: Insert] |
| Comments | [Insert] |

### Part 4 — Decision

| Decision | [Approved / Approved with conditions / Rejected / Deferred to: Insert date] |
| --- | --- |
| Conditions (if any) | [Insert] |
| Approved value | [Insert amount and currency] |
| Revised total Fee after this change | [Insert amount and currency] |
| Cumulative change as a % of the original Fee | [Insert]% |
| Approved by (name and position) | [Insert] |
| Signature |  |
| Date | [dd-mmm-yy] |

No work on this change may commence until Part 4 is completed and signed by a person holding the relevant delegation under clause 10.5. Work performed before that is at the Service Provider's risk and is not payable (clause 12.4).

# Appendix G — Deliverable Acceptance Certificate

Issue one certificate per Deliverable submission. A signed certificate is a condition precedent to any Milestone payment linked to the Deliverable (clause 6.7).

| Certificate number | AC-[Insert] |
| --- | --- |
| Project / SOW reference | [Insert] |
| Deliverable reference and title | [Insert, e.g. D-07 Monthly Project Report] |
| Revision submitted | [Insert] |
| Date submitted | [dd-mmm-yy] |
| Date review period expires | [dd-mmm-yy] |
| Submitted by | [Insert name, role] |

### Assessment against the acceptance criteria (clause 6.1)

| Ref | Criterion | Met? | Comment / deficiency relied on |
| --- | --- | --- | --- |
| AC-1 | Complete | [Yes / No] | [Insert] |
| AC-2 | Compliant with format, template and naming | [Yes / No] | [Insert] |
| AC-3 | Accurate and reconciled | [Yes / No] | [Insert] |
| AC-4 | Current and dated | [Yes / No] | [Insert] |
| AC-5 | Traceable, with working files provided | [Yes / No] | [Insert] |
| AC-6 | Decision-ready | [Yes / No] | [Insert] |
| AC-7 | Quality assured (prepare / check / approve) | [Yes / No] | [Insert] |
| AC-8 | Timely | [Yes / No] | [Insert] |

| Outcome | [Accepted / Accepted with comments / Not accepted — resubmit / Not accepted — fundamental] |
| --- | --- |
| If not accepted, resubmission due by | [dd-mmm-yy] |
| Milestone linked to this Deliverable | [Insert Milestone ref, or 'none'] |
| Payment released by this certificate | [Insert amount, or 'nil'] |
| Acceptance authority (name and position) | [Insert] |
| Signature |  |
| Date | [dd-mmm-yy] |

Acceptance does not relieve the Service Provider of liability for any error, omission or non-compliance in the Deliverable, and is not a waiver of the standard of care in clause 17.6.

# Appendix H — Monthly Report Structure

The monthly report required by Deliverable D-07 must contain the following sections, in this order. A section that has no movement in the period must still be reported, confirming that it was reviewed. "No change" without confirmation of review is not acceptable.

| § | Section | Minimum content |
| --- | --- | --- |
| 1 | Executive summary and RAG dashboard | One page: overall status, top three issues, top three decisions required |
| 2 | Health, safety and environment | Incidents, near misses, lost time injury frequency rate, audits, statutory notices, environmental events |
| 3 | Progress this period | Narrative of work completed by discipline and package, with photographs |
| 4 | Look-ahead | Planned activities for the next period and the next quarter, with constraints |
| 5 | Programme status | Percent complete, critical path narrative, float position, milestone tracker, delay events and recovery actions |
| 6 | Cost status | Control budget, approved changes, commitments, expenditure to date, anticipated final cost, contingency drawdown and remaining |
| 7 | Cash flow | Actual versus forecast expenditure, revised forecast to completion |
| 8 | Change and variation | Approved, pending and potential variations with values and programme effect |
| 9 | Claims and contractual notices | Notices issued and received, extension of time positions, time bars pending |
| 10 | Risk and opportunity | Movement in the top risks, new risks, closed risks, quantified exposure versus contingency |
| 11 | Design status | Design deliverables tracker, outstanding comments, unresolved coordination issues |
| 12 | Procurement status | Package tracker, tenders in market, awards, long-lead item status |
| 13 | Quality | ITP surveillance, hold and witness points, open non-conformances and ageing |
| 14 | Approvals and conditions | Statutory approval status and outstanding conditions with owners and dates |
| 15 | Stakeholder and communications | Engagement undertaken, complaints and issues, media and community matters |
| 16 | Sustainability and ESG | Rating scheme progress, waste diversion, energy and carbon, social procurement outcomes |
| 17 | Resourcing | Actual versus committed effort by Key Personnel, changes proposed |
| 18 | Decisions and actions required | Specific decisions sought this period, with owner, date required and consequence of delay |
| 19 | Action register | Open actions, owners, due dates and overdue items |
| 20 | Appendices | Programme extract, cost report, risk register, change register, photographs, minutes |

## H.1  Report standards

The report must be issued by the 5th Business Day of each month, with a data cut-off no earlier than the last day of the preceding month.

Every figure must reconcile to its source system, and any movement from the previous period must be explained.

The report must be self-contained: a reader who has attended no meetings must be able to understand the position from the report alone.

Every issue raised must have a named owner, a date and a requested decision. A report that describes problems without asking for decisions is a record, not a management tool.

The executive summary must not contradict the detail. Where the detail shows a problem, the summary must say so.

The report must be issued through the CDE, in PDF for distribution and in native format for the Client's records.

[ Agree the report template with the Client in the first month and lock it. Changing the structure between periods destroys comparability and is the most common complaint clients make about consultant reporting. ]