## LL Register Template
LESSONS LEARNED REGISTER TEMPLATE
Project Name: |  | <Insert Project Name>
Project Number: |  | <Insert Project Number>
Date: |  | <Insert Date Issued>
LL No. | Date Raised |  | Phase | Issue Description | Issue Impact | Issue Cause | Issue Resolution | Resolution Date | Status | Responsible Party | Lessons Learned | Additional Notes
1 | 2024-02-29 |  | Construction | Inadequate site assessment led to unforeseen soil conditions. | Increased project costs due to additional resources needed. | Initial oversight or inadequate assessment for inadequate. | Not Applicable | - | Open | Contractor | Not Applicable | Additional action needed for similar cases.
2 | 2024-05-15 |  | Design | Design changes delayed due to late approvals. | Increased project costs due to additional resources needed. | Initial oversight or inadequate assessment for design. | Not Applicable | - | Open | Engineer | Not Applicable | Not Applicable
3 | 2024-02-21 |  | Handover | Permitting issues caused delays in start date. | Increased project costs due to additional resources needed. | Initial oversight or inadequate assessment for permitting. | Resolved by implementing a solution for permitting. | 2024-04-14 | Closed | Owner | Ensure permitting assessment to prevent recurrence. | Additional action needed for similar cases.
4 | 2024-01-11 |  | Construction | Coordination issue between trades on electrical and plumbing installations. | Caused delay of 7 days. | Initial oversight or inadequate assessment for coordination. | Not Applicable | - | Open | Project Manager | Not Applicable | Additional action needed for similar cases.
5 | 2024-04-08 |  | Handover | Unexpected weather conditions caused disruptions. | Increased project costs due to additional resources needed. | Initial oversight or inadequate assessment for unexpected. | Resolved by implementing a solution for unexpected. | 2024-05-16 | Under Review | Project Manager | Ensure unexpected assessment to prevent recurrence. | Not Applicable
6 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
7 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
8 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
9 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
10 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
11 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
12 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
13 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
14 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
15 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
16 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
17 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
18 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
19 | … |  | ... | ... | ... | ... | ... | ... | ... | ... | ... | …
20 | < Insert > |  | < Insert > | < Insert > | < Insert > | < Insert > | < Insert > | < Insert > | < Insert > | < Insert > | < Insert > | < Insert >