## Critical Path Template
CRITICAL PATH TEMPLATE
Project Name: | < Insert Project Name >
Project Number: | < Insert Project Number >
Date: | < Insert Date Issued >
|  |  |  | ES | EF |  |  |  | ES | EF |  |  |  | ES | EF |  |  |  | ES | EF
|  | Activity ID No. | 1 | 0 | 7 | Activity ID No. |  | 3 | 7 | 21 |  | Activity ID No. | 5 | 21 | 31 |  | Activity ID No. | 7 | 31 | 38
|  | Duration | 7 | 36 | 43 | Duration |  | 14 | 43 | 57 |  | Duration | 10 | 57 | 67 |  | Duration | 7 | 67 | 74
|  |  |  | LS | LF |  |  |  | LS | LF |  |  |  | LS | LF |  |  |  | LS | LF
|  |  |  | Slack | 36 |  |  |  | Slack | 36 |  |  |  | Slack | 36 |  |  |  | Slack | 36
Start | [20 empty] | Finish | 74
|  |  |  | ES | EF |  |  |  | ES | EF |  |  |  | ES | EF |  |  |  | ES | EF
|  | Activity ID No. | 2 | 0 | 15 | Activity ID No. |  | 4 | 15 | 45 |  | Activity ID No. | 6 | 45 | 60 |  | Activity ID No. | 8 | 60 | 74
|  | Duration | 15 | 0 | 15 | Duration |  | 30 | 15 | 45 |  | Duration | 15 | 45 | 60 |  | Duration | 14 | 60 | 74
|  |  |  | LS | LF |  |  |  | LS | LF |  |  |  | LS | LF |  |  |  | LS | LF
|  |  |  | Slack | 0 |  |  |  | Slack | 0 |  |  |  | Slack | 0 |  |  |  | Slack | 0
ID No. | Activity Name |  |  |  | Preceding Activity |  | Phases |  |  |  | Duration | Completion Date |  | Status |  | Assignee |  |  | Notes / Comments
1 | Activity 01 |  |  |  | - |  | Initiation |  |  |  | 7 | 2024-06-30 |  | Completed |  | Clark Kent |  |  | < Insert Notes / Comments >
2 | Activity 02 |  |  |  | - |  | Initiation |  |  |  | 15 | 2024-07-31 |  | Completed |  | Peter Parker |  |  | < Insert Notes / Comments >
3 | Activity 03 |  |  |  | 1 |  | Initiation |  |  |  | 14 | 2024-08-30 |  | Completed |  | Bruce Wayne |  |  | < Insert Notes / Comments >
4 | Activity 04 |  |  |  | 2 |  | Planning |  |  |  | 30 | 2024-09-30 |  | Completed |  | Diana Prince |  |  | < Insert Notes / Comments >
5 | Activity 05 |  |  |  | 3 |  | Planning |  |  |  | 10 | 2024-10-31 |  | Completed |  | Tony Stark |  |  | < Insert Notes / Comments >
6 | Activity 06 |  |  |  | 4 |  | Planning |  |  |  | 15 | 2024-11-30 |  | In Progress |  | Clark Kent |  |  | < Insert Notes / Comments >
7 | Activity 07 |  |  |  | 5 |  | Design |  |  |  | 7 | 2024-12-31 |  | Not Started |  | Peter Parker |  |  | < Insert Notes / Comments >
8 | Activity 08 |  |  |  | 6 |  | Design |  |  |  | 14 | 2025-01-01 |  | Not Started |  | Bruce Wayne |  |  | < Insert Notes / Comments >
9 | Activity 09 |  |  |  | 7 |  | Design |  |  |  | 14 | 2025-02-28 |  | Not Started |  | Diana Prince |  |  | < Insert Notes / Comments >
10 | Activity 10 |  |  |  | 8 |  | Delivery |  |  |  | 10 | 2025-03-31 |  | Not Started |  | Tony Stark |  |  | < Insert Notes / Comments >
11 | Activity 11 |  |  |  | 9 |  | Delivery |  |  |  | 5 | 2025-04-30 |  | Not Started |  | Clark Kent |  |  | < Insert Notes / Comments >
12 | Activity 12 |  |  |  | 10 |  | Delivery |  |  |  | 15 | 2025-05-31 |  | Not Started |  | Peter Parker |  |  | < Insert Notes / Comments >
13 | Activity 13 |  |  |  | 11 |  | Close |  |  |  | 20 | 2025-06-30 |  | Not Started |  | Bruce Wayne |  |  | < Insert Notes / Comments >
14 | Activity 14 |  |  |  | 12 |  | Close |  |  |  | 14 | 2025-07-31 |  | Not Started |  | Diana Prince |  |  | < Insert Notes / Comments >
15 | Activity 15 |  |  |  | 13 |  | Close |  |  |  | 8 | 2025-08-31 |  | Not Started |  | Tony Stark |  |  | < Insert Notes / Comments >
16 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
17 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
18 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
19 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
20 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
21 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
22 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
23 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
24 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
25 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
26 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
27 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
28 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
29 | … |  |  |  | … |  | … |  |  |  | … | … |  | … |  | … |  |  | …
30 | < Insert Activity Name> |  |  |  | < Insert Preceding Activity ID > |  | < Insert Phase > |  |  |  | < Insert > | < Insert > |  | < Insert > |  | < Insert Assignee > |  |  | < Insert Notes / Comments >