## Submittal Register
SUBMITTAL REGISTER TEMPLATE
Project Name: |  | <Insert Project Name>
Project Number: |  | <Insert Project Number>
Date: |  | <Insert Date Issued>
Item No. | Submittal Title |  | Specification Section | Submittal Description | Submittal Type | Responsible Party | Required Submission Date | Required Approval Date | Review Duration (Days) | Notes / Remarks
A | B |  | C | D | E | F | G | H | I | J
1 | Concrete Mix Design |  | 03 30 00 | Concrete Mix Design for review and approval. | Shop Drawing | Steel Fabricator | 2025-05-01 | 2025-05-08 | 7 | < Insert Notes / Remarks >
2 | Reinforcement Shop Drawings |  | 03 20 00 | Reinforcement Shop Drawings for review and approval. | Test Report | General Contractor | 2025-05-04 | 2025-05-14 | 10 | < Insert Notes / Remarks >
3 | Structural Steel Submittal |  | 05 12 00 | Structural Steel Submittal for review and approval. | Product Data | MEP Contractor | 2025-05-07 | 2025-05-14 | 7 | < Insert Notes / Remarks >
4 | Masonry Sample |  | 04 20 00 | Masonry Sample for review and approval. | Test Report | Concrete Subcontractor | 2025-05-10 | 2025-05-24 | 14 | < Insert Notes / Remarks >
5 | Waterproofing System Data |  | 07 10 00 | Waterproofing System Data for review and approval. | Product Data | MEP Contractor | 2025-05-13 | 2025-05-23 | 10 | < Insert Notes / Remarks >
6 | Window Shop Drawings |  | 08 50 00 | Window Shop Drawings for review and approval. | Shop Drawing | Architect | 2025-05-16 | 2025-05-26 | 10 | < Insert Notes / Remarks >
7 | Roofing Material Data |  | 07 50 00 | Roofing Material Data for review and approval. | Product Data | Concrete Subcontractor | 2025-05-19 | 2025-05-29 | 10 | < Insert Notes / Remarks >
8 | HVAC Equipment Submittal |  | 23 00 00 | HVAC Equipment Submittal for review and approval. | Test Report | General Contractor | 2025-05-22 | 2025-06-01 | 10 | < Insert Notes / Remarks >
9 | Fire Alarm System Specs |  | 28 31 00 | Fire Alarm System Specs for review and approval. | Test Report | MEP Contractor | 2025-05-25 | 2025-06-01 | 7 | < Insert Notes / Remarks >
10 | Electrical Panel Details |  | 26 24 00 | Electrical Panel Details for review and approval. | Sample | MEP Contractor | 2025-05-28 | 2025-06-07 | 10 | < Insert Notes / Remarks >
11 | Plumbing Fixture Cutsheets |  | 22 40 00 | Plumbing Fixture Cutsheets for review and approval. | Sample | MEP Contractor | 2025-05-31 | 2025-06-10 | 10 | < Insert Notes / Remarks >
12 | Interior Door Hardware |  | 08 71 00 | Interior Door Hardware for review and approval. | Sample | General Contractor | 2025-06-03 | 2025-06-13 | 10 | < Insert Notes / Remarks >
13 | Elevator Shop Drawings |  | 14 20 00 | Elevator Shop Drawings for review and approval. | Test Report | MEP Contractor | 2025-06-06 | 2025-06-13 | 7 | < Insert Notes / Remarks >
14 | Painting Color Samples |  | 09 91 00 | Painting Color Samples for review and approval. | Certificate | Architect | 2025-06-09 | 2025-06-19 | 10 | < Insert Notes / Remarks >
15 | Flooring Material Data |  | 09 60 00 | Flooring Material Data for review and approval. | Product Data | MEP Contractor | 2025-06-12 | 2025-06-22 | 10 | < Insert Notes / Remarks >
16 | Ceiling Tile Samples |  | 09 51 00 | Ceiling Tile Samples for review and approval. | Sample | Steel Fabricator | 2025-06-15 | 2025-06-29 | 14 | < Insert Notes / Remarks >
17 | Security System Submittal |  | 28 20 00 | Security System Submittal for review and approval. | Certificate | Concrete Subcontractor | 2025-06-18 | 2025-07-02 | 14 | < Insert Notes / Remarks >
18 | Lighting Fixture Submittal |  | 26 50 00 | Lighting Fixture Submittal for review and approval. | Shop Drawing | Architect | 2025-06-21 | 2025-07-01 | 10 | < Insert Notes / Remarks >
19 | Site Utilities Drawings |  | 33 00 00 | Site Utilities Drawings for review and approval. | Product Data | Concrete Subcontractor | 2025-06-24 | 2025-07-04 | 10 | < Insert Notes / Remarks >
20 | Landscape Material Samples |  | 32 90 00 | Landscape Material Samples for review and approval. | Product Data | Steel Fabricator | 2025-06-27 | 2025-07-07 | 10 | < Insert Notes / Remarks >
21 | … | bar: C to J
22 | … | bar: C to J
23 | … | bar: C to J
24 | … | bar: C to J
25 | … | bar: C to J
26 | … | bar: C to J
27 | … | bar: C to J
28 | … | bar: C to J
29 | … | bar: C to J
30 | … | bar: C to J
31 | … | bar: C to J
32 | … | bar: C to J
33 | … | bar: C to J
34 | … | bar: C to J
35 | … | bar: C to J
36 | … | bar: C to J
37 | … | bar: C to J
38 | … | bar: C to J
39 | … | bar: C to J
40 | … | bar: C to J
41 | … | bar: C to J
42 | … | bar: C to J
43 | … | bar: C to J
44 | … | bar: C to J
45 | … | bar: C to J
46 | … | bar: C to J
47 | … | bar: C to J
48 | … | bar: C to J
49 | … | bar: C to J
50 | < Insert Submittal Title > |  | < Insert Spec Section Ref > | < Insert Submittal Description > | < Insert Submittal Type > | < Insert Responsible Party > | < Insert Date > | < Insert Date > | < Insert Days > | < Insert Notes / Remarks >