## Cover
Capital Improvement Plan
A rolling five-year program of capital projects - cost, phasing, funding and priority in one model.
This workbook holds the whole capital program in one place: every candidate project, what it costs, which year the money is needed, where that money comes from, and where each project ranks when there is not enough to do all of it. Enter the plan period once and every year column re-labels itself, so the plan rolls forward each cycle instead of being rebuilt. Costs are held both in today's money and in the money of the year they are spent, because the second is what has to be appropriated.
HOW TO USE IT
1 | Set the plan up. On Setup enter the organisation, the first year of the plan, the escalation rate and the funding envelope for each year. Every year heading derives from that first year.
2 | Agree the weightings first. Set the eight criteria weightings so they total 100 per cent before anyone scores anything. The check cell tells you when they do.
3 | List every candidate project. One row each on the Project Register. Enter the total cost, anything already spent, then phase the remaining cost across the years until the check column reads OK.
4 | Say where the money comes from. Give each project up to two funding sources and the share each one carries. Anything left over is reported as unfunded - a finding, not an error.
5 | Write the case before you score it. Project Brief holds a page for every project on the register - the problem, the options, the scope, the estimate basis, the risks, the benefits, the cost of deferring it and how ready it is. Write those ten fields before the scoring panel meets. Scoring a project nobody can describe is how bad projects get funded. Print the tab and each project comes out as its own A4 page for the committee pack.
6 | Score each project 1 to 5. On Prioritisation, score against the eight criteria. The rubric on Reference says what a 1 and a 5 mean, so two assessors land in the same place.
7 | Read the affordability position. Funding Summary sets the requirement for each year against the envelope for that year. A shortfall in red is a year to re-phase, fund or defer.
8 | Take Plan Summary to the board. Every figure on it is a formula reading the sheets behind it. Nothing on that page is typed.
9 | Delete the examples. The 15 example projects are marked EX on the Project Register. Delete those rows and every example banner in the workbook clears.
WHAT IS IN THE WORKBOOK
| Sheet | What it does | Who fills it in
| Setup | Organisation, plan period, escalation, funding envelope, criteria weightings and priority bands. | Plan owner, once a cycle
| Project Register | One row per candidate project: cost, phasing by year, escalation and funding split. | Sponsors, then the plan owner
| Prioritisation | Scores each project 1 to 5 against the weighted criteria. Rank and band are calculated. | Assessment panel
| Project Brief | One printable page per project - cost, funding, priority and the ten narrative fields that say why it is in the plan. | Project sponsor, before scoring
| Funding Summary | Funding by source and year against the envelope, and the unfunded gap. | Calculated - read only
| Plan Summary | The board page. Plan value, funded against unfunded, spend by year, category and driver, top ten. | Calculated - read only
| Reference | Every dropdown list, the scoring rubric, definitions and cell conventions. | Plan owner, when lists change
IMPORTANT
This template is a planning tool, not advice. The cost, escalation, funding and scoring assumptions in it are examples. Check every figure against your own estimates, your own financial strategy and the terms of the Contract and any funding agreement before you rely on it or publish it. Mastt accepts no liability for decisions taken from this workbook.
Terminology: this set is written for a global audience. Owner (Client) is the organisation that pays for the work - called the Principal or the Employer in some contracts. Where a term differs by region, both are given on Reference. Amounts are in the organisation's own currency, shown with a neutral $.
Built with Mastt ¦ mastt.com

## Setup
CAPITAL IMPROVEMENT PLAN · SETUP
EXAMPLE DATA - the 15 rows marked EX on the Project Register are worked examples. Delete or overwrite them, and this banner clears.
Enter these once. Every other sheet reads from here by formula. Pale blue cells are yours to type in - everything else is calculated. Change the first year of the plan and every year heading in the workbook moves with it.
1 · ORGANISATION AND PLAN
Organisation | Northgate City
Plan title | Capital Improvement Plan
Plan period | FY2027 to FY2031 (5 years, plus what falls beyond)
Plan owner - who maintains this workbook | Head of Asset Planning
Approving body | Finance and Infrastructure Committee
Plan status | Draft
Date prepared | 2026-08-12
Currency | Contract currency, shown as $ |  |  |  | Use one currency across the whole plan.
The plan owner is the single point of truth for this workbook. Sponsors propose projects; the plan owner decides what enters the register.
2 · PLAN PERIOD, ESCALATION AND DISCOUNTING
First year of the plan (Year 1) | 2027 | The plan rolls: change this and every year heading in the workbook moves.
Year label prefix | FY | Use FY, or leave it blank for calendar years.
Cost escalation rate a year | 3.5% | Applied from Year 2 onwards. Year 1 is already in today's money.
Discount rate a year | 5% | Used for the present value figure on Plan Summary only.
Plan year | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | Beyond FY2031 | Total
Escalation factor applied to that year | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877
Discount factor applied to that year | 1 | 0.95238 | 0.90703 | 0.86384 | 0.8227 | 0.78353
Year 1 is unescalated - it is already in today's money. Year n is escalated by (1 + rate) ^ (n - 1). Cost that falls beyond the plan is escalated at the Year 6 factor, which is deliberately conservative for a bucket that has no dates in it yet. Discounting brings future cash back to the start of Year 1; it drives the present value figure on Plan Summary and nothing else.
3 · ANNUAL FUNDING ENVELOPE
Funding envelope for the year (cash) | 30000000 | 46000000 | 50000000 | 48000000 | 40000000 | 45000000 | 259000000
Envelope available inside the plan period (Year 1 to Year 5) | [6 empty] | 214000000
The envelope is what the organisation can afford to commit in each year under its financial strategy - rates or revenue capacity, borrowing headroom, reserve balances and grants already agreed. It is not the sum of what projects have asked for. Enter it in cash terms, the same basis as the escalated cost.
4 · PRIORITISATION CRITERIA WEIGHTINGS
Criterion | Weighting | What it measures
Asset condition and failure risk | 15% | Physical condition, remaining life and failure history of the asset being replaced or renewed.
Health, safety and compliance | 20% | Risk to life safety, and any written direction or standard the Owner has to meet.
Service demand and growth | 12% | Capacity against current and committed demand across the plan period.
Strategic alignment | 12% | Whether the project is a named commitment in an adopted strategy or asset management plan.
Economic or community benefit | 12% | Measurable benefit to users, the wider economy or the community, evidenced by a business case.
Deliverability and readiness | 10% | Scope maturity, design, approvals, land and delivery resource. Can it actually start.
Funding certainty | 9% | How committed the funding is, from nothing identified to executed agreement.
Consequence of doing nothing | 10% | What happens to service, cost and risk if the project is deferred out of the plan.
Total weighting | 100%
Weighting check |  | RECONCILED - the eight criteria total 100%
Weight the criteria to your own strategy, then leave them alone for the cycle. Changing a weighting after the scores are in re-ranks the plan, and everyone can see it.
5 · PRIORITY BANDS
Band | Weighted score from | What it means
Critical | 4.2 | Fund it. Deferring it carries a risk the Owner has to accept in writing.
High | 3.5 | Fund it inside the plan period unless the envelope makes that impossible.
Medium | 2.5 | Fund it if the envelope allows, otherwise carry it to the next cycle.
Low | below 2.50 | Below the Medium threshold. Do not fund it from this plan without a written case.
Bands are cut from the weighted score, not from cost. A cheap project can be Critical and an expensive one Low - that is the point of scoring before you fund.
Built with Mastt ¦ mastt.com

## Project Register
CAPITAL IMPROVEMENT PLAN · PROJECT REGISTER
EXAMPLE DATA - the 15 rows marked EX on the Project Register are worked examples. Delete or overwrite them, and this banner clears.
One row per candidate project. Type in the pale blue cells only. Phase the REMAINING cost (estimated total less spend already incurred) across the years - the check column reads OK when it ties back. Filter this sheet, do not sort it. Prints A3 landscape, two pages wide.
IDENTIFICATION | [9 empty] | COST |  |  | PHASING - NOMINAL (today's money) | [8 empty] | PHASING - ESCALATED (cash of the year) | [7 empty] | FUNDING SPLIT
Who, what and why | [9 empty] | Whole of project |  |  | Only the remaining cost is phased | [8 empty] | Nominal uplifted by the Setup escalation factors | [7 empty] | Share of the escalated in-plan cost
EX | Project ID | Project name | Description | Category | Asset class | Department / owner | Driver | Status | Delivery lead | Estimated total cost | Spend already incurred | Remaining cost | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | Beyond FY2031 | Phased total | Phasing variance | Check | FY2027 esc | FY2028 esc | FY2029 esc | FY2030 esc | FY2031 esc | Beyond FY2031 esc | Escalated in plan (Y1-Y5) | Escalated total | Funding source 1 | Share | Funding source 2 | Share | Unfunded | Funded (escalated, in plan) | Unfunded (escalated, in plan)
EX | CIP-001 | Riverside Bridge deck renewal | Replace the deck, bearings and barriers on the 1968 river crossing. Load limit lifts on completion. | Roads and bridges | Bridge and structure | Infrastructure and delivery | Renewal | Approved | A. Whitfield | 12400000 | 400000 | 12000000 | 2000000 | 6000000 | 4000000 | 0 | 0 | 0 | 12000000 | 0 | OK | 2000000 | 6210000 | 4284900 | 0 | 0 | 0 | 12494900 | 12494900 | Grants - government | 60% | Own revenue | 40% | 0% | 12494900 | 0
EX | CIP-002 | Central water treatment plant upgrade | Membrane replacement and a second clarifier to meet the drinking water standard the Owner operates to. | Water and wastewater | Water network | Water services | Compliance and safety | Approved | M. Okonkwo | 38000000 | 1500000 | 36500000 | 4500000 | 12000000 | 12000000 | 8000000 | 0 | 0 | 36500000 | 0 | OK | 4500000 | 12420000 | 12854700 | 8869743 | 0 | 0 | 38644443 | 38644443 | Borrowings | 70% | Own revenue | 30% | 0% | 38644443 | 0
EX | CIP-003 | Northgate aquatic centre replacement | Replace the 1974 pool hall. Concept design only. The largest single call on the plan. | Buildings | Building - community | Community services | Service improvement | Proposed | S. Duarte | 46000000 | 750000 | 45250000 | 1250000 | 6000000 | 14000000 | 16000000 | 8000000 | 0 | 45250000 | 0 | OK | 1250000 | 6210000 | 14997150 | 17739486 | 9180184.005 | 0 | 49376820.005 | 49376820.005 | Borrowings | 50% | Grants - government | 20% | 30% | 34563774.0035 | 14813046.0015
EX | CIP-004 | Depot Road reconstruction - stage 2 | Full pavement reconstruction, kerb and drainage over 2.4 km. Stage 1 is complete. | Roads and bridges | Road pavement | Infrastructure and delivery | Renewal | In delivery | A. Whitfield | 8600000 | 2600000 | 6000000 | 3500000 | 2500000 | 0 | 0 | 0 | 0 | 6000000 | 0 | OK | 3500000 | 2587500 | 0 | 0 | 0 | 0 | 6087500 | 6087500 | Own revenue | 100% |  |  | 0% | 6087500 | 0
EX | CIP-005 | Wastewater pump station renewals | Rolling renewal of 14 stations by condition rank. Two stations a year, funded from the water reserve. | Water and wastewater | Wastewater network | Water services | Renewal | Approved | M. Okonkwo | 9000000 | 0 | 9000000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 9000000 | 0 | OK | 1500000 | 1552500 | 1606837.5 | 1663076.8125 | 1721284.5009 | 1781529.4585 | 8043698.8134 | 9825228.2719 | Reserves | 60% | Own revenue | 40% | 0% | 8043698.8134 | 0
EX | CIP-006 | Kingsway Park sports precinct | Two new playing fields, lighting and a pavilion to serve the eastern growth area. | Parks and recreation | Open space | Parks and open space | Growth | Proposed | L. Fenwick | 14500000 | 250000 | 14250000 | 0 | 2250000 | 6000000 | 6000000 | 0 | 0 | 14250000 | 0 | OK | 0 | 2328750 | 6427350 | 6652307.25 | 0 | 0 | 15408407.25 | 15408407.25 | Developer contributions | 55% | Grants - government | 25% | 20% | 12326725.8 | 3081681.45
EX | CIP-007 | Fleet replacement program - heavy plant | Replace graders, trucks and loaders at the end of economic life, on the fleet replacement schedule. | Fleet and plant | Vehicle and plant | Fleet operations | Renewal | Approved | R. Castillo | 11000000 | 0 | 11000000 | 2000000 | 2000000 | 2000000 | 2500000 | 2500000 | 0 | 11000000 | 0 | OK | 2000000 | 2070000 | 2142450 | 2771794.6875 | 2868807.5016 | 0 | 11853052.1891 | 11853052.1891 | Reserves | 100% |  |  | 0% | 11853052.1891 | 0
EX | CIP-008 | Core network and cyber security uplift | Segment the operational technology network and replace end-of-support edge hardware. | Technology | ICT system | Technology | Compliance and safety | Approved | P. Nkemdirim | 6200000 | 200000 | 6000000 | 2400000 | 2100000 | 1500000 | 0 | 0 | 0 | 6000000 | 0 | OK | 2400000 | 2173500 | 1606837.5 | 0 | 0 | 0 | 6180337.5 | 6180337.5 | Own revenue | 100% |  |  | 0% | 6180337.5 | 0
EX | CIP-009 | Civic administration building - structural and fire upgrade | Structural strengthening and fire system replacement. The building stays occupied through the works. | Buildings | Building - operational | Property and facilities | Compliance and safety | Approved | S. Duarte | 10800000 | 300000 | 10500000 | 1500000 | 4500000 | 4500000 | 0 | 0 | 0 | 10500000 | 0 | OK | 1500000 | 4657500 | 4820512.5 | 0 | 0 | 0 | 10978012.5 | 10978012.5 | Own revenue | 60% | Reserves | 40% | 0% | 10978012.5 | 0
EX | CIP-010 | Harbour catchment flood mitigation | Trunk drainage, detention basins and overland flow works across the harbour catchment. | Water and wastewater | Stormwater | Infrastructure and delivery | Compliance and safety | Proposed | M. Okonkwo | 22000000 | 0 | 22000000 | 0 | 1000000 | 4000000 | 7000000 | 7000000 | 3000000 | 22000000 | 0 | OK | 0 | 1035000 | 4284900 | 7761025.125 | 8032661.0044 | 3563058.9169 | 21113586.1294 | 24676645.0463 | Grants - government | 45% | Borrowings | 25% | 30% | 14779510.2906 | 6334075.8388
EX | CIP-011 | Land acquisition - eastern growth corridor | Acquire four parcels for the future arterial and drainage reserve ahead of development. | Land | Land holding | Corporate services | Growth | Approved | L. Fenwick | 7500000 | 0 | 7500000 | 3000000 | 4500000 | 0 | 0 | 0 | 0 | 7500000 | 0 | OK | 3000000 | 4657500 | 0 | 0 | 0 | 0 | 7657500 | 7657500 | Developer contributions | 60% | Asset sales | 40% | 0% | 7657500 | 0
EX | CIP-012 | Library and learning hub fit-out | Fit-out of leased floor space as a branch library. Deferred pending a decision on the lease. | Buildings | Building - community | Community services | Service improvement | Deferred | S. Duarte | 5400000 | 0 | 5400000 | 0 | 0 | 0 | 1400000 | 4000000 | 0 | 5400000 | 0 | OK | 0 | 0 | 0 | 1552205.025 | 4590092.0025 | 0 | 6142297.0275 | 6142297.0275 | Own revenue | 50% |  |  | 50% | 3071148.5137 | 3071148.5137
EX | CIP-013 | Asset renewal program - minor buildings and structures | Annual allowance for roof, cladding and plant renewals identified by condition survey. | Renewals | Building - operational | Property and facilities | Renewal | Approved | R. Castillo | 6000000 | 0 | 6000000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 0 | 6000000 | 0 | OK | 1200000 | 1242000 | 1285470 | 1330461.45 | 1377027.6007 | 0 | 6434959.0508 | 6434959.0508 | Own revenue | 100% |  |  | 0% | 6434959.0508 | 0
EX | CIP-014 | Transit interchange upgrade | Rebuild the interchange with the transport agency. Joint funding is agreed in principle only. | Roads and bridges | Other | Infrastructure and delivery | Growth | Proposed | A. Whitfield | 18000000 | 0 | 18000000 | 0 | 0 | 2000000 | 5000000 | 6000000 | 5000000 | 18000000 | 0 | OK | 0 | 0 | 2142450 | 5543589.375 | 6885138.0038 | 5938431.5282 | 14571177.3788 | 20509608.907 | Partner contributions | 40% | Grants - government | 30% | 30% | 10199824.1651 | 4371353.2136
EX | CIP-015 | Solar and battery installation - operational sites | Rooftop solar and storage at the depot, library and civic building. Payback inside 9 years. | Buildings | Building - operational | Property and facilities | Service improvement | Proposed | P. Nkemdirim | 4200000 | 0 | 4200000 | 0 | 1200000 | 3000000 | 0 | 0 | 0 | 4200000 | 0 | OK | 0 | 1242000 | 3213675 | 0 | 0 | 0 | 4455675 | 4455675 | Own revenue | 50% | Asset sales | 50% | 0% | 4455675 | 0
| 15 projects | TOTAL - all projects in the register | [7 empty] | 219600000 | 6000000 | 213600000 | 22850000 | 46750000 | 55700000 | 48600000 | 30200000 | 9500000 | 213600000 | 0 | 0 | 22850000 | 48386250 | 59667232.5 | 53883688.725 | 34655194.6189 | 11283019.9036 | 219442365.8439 | 230725385.7475 |  |  |  |  | 14.43% | 187771060.8262 | 31671305.0177
CHECKS - these must read RECONCILED before the plan goes anywhere
Phasing ties to remaining cost |  |  | RECONCILED - every project phases exactly to its remaining cost
Funding shares within 100% |  |  | RECONCILED - no project is allocated more than 100% funding
A share is entered without a source |  |  | RECONCILED - every funding share names a source
Source 1 and source 2 differ |  |  | RECONCILED - no project names the same funding source twice
Escalated total rebuilt from the nominal row |  |  | RECONCILED - the escalated total equals the nominal total times the Setup factors
Built with Mastt ¦ mastt.com

## Prioritisation
CAPITAL IMPROVEMENT PLAN · PRIORITISATION SCORING
EXAMPLE DATA - the 15 rows marked EX on the Project Register are worked examples. Delete or overwrite them, and this banner clears.
Score every project 1 to 5 against each criterion. Reference holds the rubric - what a 1 and a 5 actually mean - so two assessors land in the same place. Project details mirror the Project Register row for row, so do not sort either sheet. Prints A3 landscape.
PROJECT - mirrored from the register |  |  |  |  | SCORE 1 (low) TO 5 (high) AGAINST EACH WEIGHTED CRITERION | [7 empty] | RESULT
Weighting from Setup |  |  |  |  | 15% | 20% | 12% | 12% | 12% | 10% | 9% | 10% | 100% |  | Set on Setup
EX | Project ID | Project name | Category | Escalated cost in plan | Asset condition and failure risk | Health, safety and compliance | Service demand and growth | Strategic alignment | Economic or community benefit | Deliverability and readiness | Funding certainty | Consequence of doing nothing | Weighted score | Rank | Priority band | Driver | Status | Cumulative cost at this rank | Against the envelope
EX | CIP-001 | Riverside Bridge deck renewal | Roads and bridges | 12494900 | 5 | 5 | 3 | 4 | 3 | 4 | 4 | 5 | 4.21 | 2 | Critical | Renewal | Approved | 51139343 | Above the line
EX | CIP-002 | Central water treatment plant upgrade | Water and wastewater | 38644443 | 4 | 5 | 4 | 5 | 4 | 3 | 4 | 5 | 4.32 | 1 | Critical | Compliance and safety | Approved | 38644443 | Above the line
EX | CIP-003 | Northgate aquatic centre replacement | Buildings | 49376820.005 | 3 | 3 | 4 | 4 | 5 | 2 | 2 | 3 | 3.29 | 10 | Medium | Service improvement | Proposed | 172429850.1369 | Above the line
EX | CIP-004 | Depot Road reconstruction - stage 2 | Roads and bridges | 6087500 | 4 | 4 | 3 | 3 | 3 | 5 | 5 | 4 | 3.83 | 6 | High | Renewal | In delivery | 92564465.4428 | Above the line
EX | CIP-005 | Wastewater pump station renewals | Water and wastewater | 8043698.8134 | 5 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 3.91 | 5 | High | Renewal | Approved | 86476965.4428 | Above the line
EX | CIP-006 | Kingsway Park sports precinct | Parks and recreation | 15408407.25 | 2 | 2 | 4 | 4 | 4 | 3 | 3 | 2 | 2.91 | 13 | Medium | Growth | Proposed | 208844393.8164 | Above the line
EX | CIP-007 | Fleet replacement program - heavy plant | Fleet and plant | 11853052.1891 | 4 | 4 | 2 | 3 | 2 | 5 | 5 | 4 | 3.59 | 8 | High | Renewal | Approved | 115395530.1319 | Above the line
EX | CIP-008 | Core network and cyber security uplift | Technology | 6180337.5 | 3 | 5 | 3 | 4 | 3 | 4 | 5 | 5 | 4 | 4 | High | Compliance and safety | Approved | 78433266.6294 | Above the line
EX | CIP-009 | Civic administration building - structural and fire upgrade | Buildings | 10978012.5 | 4 | 5 | 2 | 3 | 2 | 4 | 4 | 5 | 3.7 | 7 | High | Compliance and safety | Approved | 103542477.9428 | Above the line
EX | CIP-010 | Harbour catchment flood mitigation | Water and wastewater | 21113586.1294 | 4 | 5 | 4 | 5 | 4 | 2 | 2 | 5 | 4.04 | 3 | High | Compliance and safety | Proposed | 72252929.1294 | Above the line
EX | CIP-011 | Land acquisition - eastern growth corridor | Land | 7657500 | 2 | 2 | 5 | 5 | 4 | 4 | 4 | 4 | 3.54 | 9 | High | Growth | Approved | 123053030.1319 | Above the line
EX | CIP-012 | Library and learning hub fit-out | Buildings | 6142297.0275 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 2 | 1.98 | 15 | Low | Service improvement | Deferred | 219442365.8439 | Below the line
EX | CIP-013 | Asset renewal program - minor buildings and structures | Renewals | 6434959.0508 | 4 | 3 | 2 | 3 | 2 | 5 | 5 | 3 | 3.29 | 11 | Medium | Renewal | Approved | 178864809.1876 | Above the line
EX | CIP-014 | Transit interchange upgrade | Roads and bridges | 14571177.3788 | 2 | 3 | 5 | 4 | 4 | 2 | 2 | 3 | 3.14 | 12 | Medium | Growth | Proposed | 193435986.5664 | Above the line
EX | CIP-015 | Solar and battery installation - operational sites | Buildings | 4455675 | 2 | 2 | 2 | 4 | 3 | 4 | 3 | 2 | 2.65 | 14 | Medium | Service improvement | Proposed | 213300068.8164 | Above the line
CHECKS
Weightings total 100% |  |  | RECONCILED - the criteria weightings total 100%
Every project is fully scored |  |  | RECONCILED - every project in the register carries all eight scores
Ranks are unique |  |  | RECONCILED - every project holds a unique rank, ties broken by register order
Project list matches the register |  |  | RECONCILED - the same projects appear here as on the Project Register
Above the line means the project fits inside the funding envelope for the plan period when projects are funded in rank order. It is a planning signal, not a decision - the envelope is spread across years and a project below the line may still be affordable if it can be re-phased.
Built with Mastt ¦ mastt.com

## Project Brief
CAPITAL IMPROVEMENT PLAN · PROJECT BRIEF
EXAMPLE DATA - the 15 rows marked EX on the Project Register are worked examples. Delete or overwrite them, and this banner clears.
One block per project, keyed row for row to the Project Register. Type the ten narrative fields - every figure is a formula. Print the tab: one A4 page per project.
[11 empty] | Block ID | Fields written | Workings. These two columns sit outside the printed page and feed the narrative checks on Plan Summary.
PROJECT BRIEF |  |  | CIP-001 | Riverside Bridge deck renewal | [6 empty] | CIP-001 | 10
Replace the deck, bearings and barriers on the 1968 river crossing. Load limit lifts on completion.
Category |  | Roads and bridges |  |  | Asset class |  |  | Bridge and structure
Department / owner |  | Infrastructure and delivery |  |  | Delivery lead |  |  | A. Whitfield
Primary driver |  | Renewal |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 12400000 |  | Spend already incurred |  |  |  | 400000
Remaining cost to spend |  |  | 12000000 |  | Escalated total in the plan |  |  |  | 12494900
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 12494900
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 2000000 |  | 6000000 | 4000000 |  | 0 |  | 0 |  | 0
Escalated | 2000000 |  | 6210000 | 4284900 |  | 0 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Grants - government |  |  |  | 60% |  |  | 7496940
Own revenue |  |  |  | 40% |  |  | 4997960
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 4.21 |  | Rank in the plan |  | 2 of 15 |  | Priority band |  | Critical
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The 1968 deck is delaminated across 40 per cent of its soffit and carries a 22 tonne load limit. Heavy vehicles detour 11 km through the town centre. The next inspection is expected to drop the limit again.
Options considered and why this one |  | Do nothing holds the limit and the detour. Patch and monitor was costed at $4.1M over ten years and still ends in replacement. Deck and bearing replacement resets the asset life and lifts the limit.
Scope summary |  | Replace the deck slab, bearings, joints and barriers across all four spans, with cathodic protection to the piers. The substructure is sound and stays. One lane runs under signals throughout.
Basis of the cost estimate |  | Class 3 estimate from the detailed design, priced at Year 1 rates, accuracy minus 10 to plus 20 per cent. Includes traffic management and 12 per cent contingency. Excludes utility relocation.
Key delivery risks |  | Pier condition is unknown until the deck is off, which could add strengthening. In-stream work is limited to the dry season, so a wet start pushes the whole program a year.
Dependencies and interfaces |  | Needs the water authority approval for in-stream works and a road occupancy licence from the transport agency. Interfaces with Depot Road, which carries the detour traffic.
Benefits and how they will be measured |  | Load limit removed at opening, against the current 22 tonne posting. Heavy vehicle detour down from 11 km to nil. The asset engineer owns both measures.
Consequence of deferral |  | A year of delay adds an inspection cycle and a likely further load restriction. The detour cost to freight operators continues and the patching budget is spent with nothing to show.
Readiness |  | Detailed design complete, in-stream approval lodged, no land required. Procurement is a single lump sum contract with tender documents drafted. Ready to go to market in Year 1.
Recommended action |  | Fund as phased and award early enough to catch the first dry season. Report pier condition to the committee before the strengthening provision is drawn.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-002 | Central water treatment plant upgrade | [6 empty] | CIP-002 | 10
Membrane replacement and a second clarifier to meet the drinking water standard the Owner operates to.
Category |  | Water and wastewater |  |  | Asset class |  |  | Water network
Department / owner |  | Water services |  |  | Delivery lead |  |  | M. Okonkwo
Primary driver |  | Compliance and safety |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 38000000 |  | Spend already incurred |  |  |  | 1500000
Remaining cost to spend |  |  | 36500000 |  | Escalated total in the plan |  |  |  | 38644443
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 38644443
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 4500000 |  | 12000000 | 12000000 |  | 8000000 |  | 0 |  | 0
Escalated | 4500000 |  | 12420000 | 12854700 |  | 8869743 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Borrowings |  |  |  | 70% |  |  | 27051110.1
Own revenue |  |  |  | 30% |  |  | 11593332.9
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 4.32 |  | Rank in the plan |  | 1 of 15 |  | Priority band |  | Critical
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The membrane trains are at the end of their service life and the plant has no redundancy when one is offline. Two turbidity exceedances were recorded last year and the regulator has been notified.
Options considered and why this one |  | Do nothing risks a boil water notice for 62,000 connections. Replacing membranes alone defers the capacity problem three years. Membranes plus a second clarifier fixes compliance and redundancy in one shutdown.
Scope summary |  | Replace four membrane trains, build a second clarifier, upgrade dosing and the plant control system, and add a 4 ML balance tank. The intake and the trunk pipework stay.
Basis of the cost estimate |  | Concept estimate from the reference design, priced at Year 1 rates, accuracy plus or minus 25 per cent. Includes 15 per cent contingency and commissioning. Excludes any change to the raw water source.
Key delivery risks |  | The plant cannot be taken fully offline, so the work runs in stages behind temporary treatment. Membranes and control hardware sit on a 40 week order book.
Dependencies and interfaces |  | Depends on the borrowing approval in Year 1 and on the pump station renewals for network pressure. The regulator has to accept the staging plan before construction starts.
Benefits and how they will be measured |  | Turbidity exceedances at nil against two last year, and full treatment capacity held with one train offline. The water services manager reports monthly.
Consequence of deferral |  | A year of delay carries the redundancy gap through another summer peak. A boil water notice costs far more, in response and in standing, than the escalation saved.
Readiness |  | Reference design complete, detailed design starting, the site is owned. Approvals identified but not held. Procurement is design and construct with early contractor involvement.
Recommended action |  | Fund and start in Year 1. Do not split the clarifier from the membrane works - they share the shutdown windows and splitting them doubles the temporary treatment cost.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-003 | Northgate aquatic centre replacement | [6 empty] | CIP-003 | 10
Replace the 1974 pool hall. Concept design only. The largest single call on the plan.
Category |  | Buildings |  |  | Asset class |  |  | Building - community
Department / owner |  | Community services |  |  | Delivery lead |  |  | S. Duarte
Primary driver |  | Service improvement |  |  | Status |  |  | Proposed
COST
Estimated total cost |  |  | 46000000 |  | Spend already incurred |  |  |  | 750000
Remaining cost to spend |  |  | 45250000 |  | Escalated total in the plan |  |  |  | 49376820.005
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 49376820.005
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 1250000 |  | 6000000 | 14000000 |  | 16000000 |  | 8000000 |  | 0
Escalated | 1250000 |  | 6210000 | 14997150 |  | 17739486 |  | 9180184.005 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Borrowings |  |  |  | 50% |  |  | 24688410.0025
Grants - government |  |  |  | 20% |  |  | 9875364.001
Unfunded residual - no source named |  |  |  | 30% |  |  | 14813046.0015
PRIORITY
Weighted score | 3.29 |  | Rank in the plan |  | 10 of 15 |  | Priority band |  | Medium
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The 1974 pool hall leaks, the plant is beyond economic repair and the hall closes about four weeks a year for unplanned repairs. Attendance has fallen 18 per cent in three years.
Options considered and why this one |  | Do nothing means closure inside five years on plant failure. Refurbishment was costed at $19M and buys perhaps twelve years in a building with the wrong pool mix. Replacement costs more but carries a 50 year life.
Scope summary |  | New eight lane 25 metre pool, learn to swim pool, water play area, gym and change rooms on the existing site. The old hall is demolished after the new centre opens.
Basis of the cost estimate |  | Order of magnitude estimate from benchmark rates for three comparable centres, accuracy plus or minus 30 per cent. Includes demolition. Excludes contaminated soil disposal and any car park works.
Key delivery risks |  | The estimate is benchmark only and will move once concept design lands. Building on an operating site restricts the working area, and the market for aquatic centres is thin.
Dependencies and interfaces |  | Depends on the land swap with the sports club for temporary parking and on a decision about the existing hall. Shares a parking strategy with the Kingsway Park precinct.
Benefits and how they will be measured |  | Attendance back above 240,000 visits a year from 197,000 now, and unplanned closure days at nil against 28 last year. The community services manager reports quarterly.
Consequence of deferral |  | A year of delay raises the chance that plant failure closes the centre before the new one opens, which would leave the city without a public pool for two summers.
Readiness |  | Concept design only. No approvals, the land is owned but the temporary car park is not secured, no procurement route settled. The least ready project of this size in the plan.
Recommended action |  | Fund design and the business case in Year 1 only. Do not commit construction money until the design lands and the estimate is rebuilt from a priced bill of quantities.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-004 | Depot Road reconstruction - stage 2 | [6 empty] | CIP-004 | 10
Full pavement reconstruction, kerb and drainage over 2.4 km. Stage 1 is complete.
Category |  | Roads and bridges |  |  | Asset class |  |  | Road pavement
Department / owner |  | Infrastructure and delivery |  |  | Delivery lead |  |  | A. Whitfield
Primary driver |  | Renewal |  |  | Status |  |  | In delivery
COST
Estimated total cost |  |  | 8600000 |  | Spend already incurred |  |  |  | 2600000
Remaining cost to spend |  |  | 6000000 |  | Escalated total in the plan |  |  |  | 6087500
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 6087500
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 3500000 |  | 2500000 | 0 |  | 0 |  | 0 |  | 0
Escalated | 3500000 |  | 2587500 | 0 |  | 0 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Own revenue |  |  |  | 100% |  |  | 6087500
- |  |  |  | 0% |  |  | 0
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 3.83 |  | Rank in the plan |  | 6 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The pavement has failed over 2.4 km with rutting beyond 40 mm and 61 defect reports last year. Stage 1 proved the subgrade is the cause, so resurfacing alone will not hold.
Options considered and why this one |  | Do nothing means patching at about $380,000 a year with ride quality still falling. A thin overlay was rejected after stage 1 showed subgrade failure. Full reconstruction repeats what worked on stage 1.
Scope summary |  | Full depth reconstruction of 2.4 km with new subbase, kerb and channel, drainage pits and line marking, including the two intersections at either end.
Basis of the cost estimate |  | Priced from the stage 1 tendered rates with a 5 per cent uplift, accuracy plus or minus 10 per cent. Includes traffic management. Excludes the shared path, which is funded separately.
Key delivery risks |  | Wet weather is the main exposure - stage 1 lost six weeks to it. Service relocations found in stage 1 may repeat and the utility has not committed to dates.
Dependencies and interfaces |  | Runs after the water main renewal in the same trench line, which has to finish first. This road carries the Riverside Bridge detour, so the two programs cannot overlap.
Benefits and how they will be measured |  | Roughness back to the network standard, from 4.1 to below 2.5 IRI on the annual survey. Defect reports below 10 a year against 61. The asset engineer owns it.
Consequence of deferral |  | A year of delay leaves the detour route in failed condition while the bridge works run, and forfeits the stage 1 rates, which are held for six months only.
Readiness |  | Design complete, approvals held, contractor already engaged under the stage 1 contract, work is inside the road reserve. The most ready project in the plan.
Recommended action |  | Continue as phased. Confirm the utility relocation dates before the Year 1 works order is issued.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-005 | Wastewater pump station renewals | [6 empty] | CIP-005 | 10
Rolling renewal of 14 stations by condition rank. Two stations a year, funded from the water reserve.
Category |  | Water and wastewater |  |  | Asset class |  |  | Wastewater network
Department / owner |  | Water services |  |  | Delivery lead |  |  | M. Okonkwo
Primary driver |  | Renewal |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 9000000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 9000000 |  | Escalated total in the plan |  |  |  | 8043698.8134
Beyond the plan (escalated) |  |  | 1781529.4585 |  | Whole of project, escalated |  |  |  | 9825228.2719
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 1500000 |  | 1500000 | 1500000 |  | 1500000 |  | 1500000 |  | 1500000
Escalated | 1500000 |  | 1552500 | 1606837.5 |  | 1663076.8125 |  | 1721284.5009 |  | 1781529.4585
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Reserves |  |  |  | 60% |  |  | 4826219.2881
Own revenue |  |  |  | 40% |  |  | 3217479.5254
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 3.91 |  | Rank in the plan |  | 5 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | Fourteen stations carry pumps and switchboards past economic life. Six overflow events in two years traced back to pump failure, each one reportable to the environmental regulator.
Options considered and why this one |  | Do nothing means run to failure with hire pumps at roughly four times the planned cost. Upgrading only the worst three was rejected because it leaves eleven stations ageing at the same rate.
Scope summary |  | Rolling replacement of pumps, switchboards, telemetry and wet well linings at two stations a year, taken in condition rank order from the most recent assessment.
Basis of the cost estimate |  | Unit rate estimate from the last three station renewals, priced at Year 1 rates, accuracy plus or minus 15 per cent. Includes telemetry. Excludes any rising main replacement.
Key delivery risks |  | The condition rank changes if a station fails early, which reorders the program. Switchboard lead times run to 30 weeks and are lengthening.
Dependencies and interfaces |  | Depends on the water reserve holding the balance set in the financial strategy. The telemetry scope interfaces with the network and cyber security uplift.
Benefits and how they will be measured |  | Overflow events from pump failure at nil against six in two years, and emergency hire spend below $50,000 a year. The water services manager reports quarterly.
Consequence of deferral |  | A year of delay pushes two more stations into run to failure. Each emergency response costs about $180,000 and carries a reportable environmental event with it.
Readiness |  | Standard designs held, no approvals needed beyond the standing environmental authorisation, all sites owned. Procurement is off a panel arrangement already in place.
Recommended action |  | Fund the full six years and hold the annual allocation flat, so the condition ranking drives the order of work rather than the budget.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-006 | Kingsway Park sports precinct | [6 empty] | CIP-006 | 10
Two new playing fields, lighting and a pavilion to serve the eastern growth area.
Category |  | Parks and recreation |  |  | Asset class |  |  | Open space
Department / owner |  | Parks and open space |  |  | Delivery lead |  |  | L. Fenwick
Primary driver |  | Growth |  |  | Status |  |  | Proposed
COST
Estimated total cost |  |  | 14500000 |  | Spend already incurred |  |  |  | 250000
Remaining cost to spend |  |  | 14250000 |  | Escalated total in the plan |  |  |  | 15408407.25
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 15408407.25
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 0 |  | 2250000 | 6000000 |  | 6000000 |  | 0 |  | 0
Escalated | 0 |  | 2328750 | 6427350 |  | 6652307.25 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Developer contributions |  |  |  | 55% |  |  | 8474623.9875
Grants - government |  |  |  | 25% |  |  | 3852101.8125
Unfunded residual - no source named |  |  |  | 20% |  |  | 3081681.45
PRIORITY
Weighted score | 2.91 |  | Rank in the plan |  | 13 of 15 |  | Priority band |  | Medium
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The eastern growth area adds 6,400 dwellings across the plan period with no district sports provision. Existing fields run at 34 hours a week against a 25 hour capacity and are closing for turf recovery.
Options considered and why this one |  | Do nothing pushes demand onto fields already over capacity. Lighting the existing fields adds four hours a week and does not meet the growth. A new precinct is the only option that meets the adopted provision standard.
Scope summary |  | Two full size playing fields with sports lighting, a four court pavilion, parking for 120 cars and connecting paths. Irrigation comes off the existing bore.
Basis of the cost estimate |  | Concept estimate from comparable precincts on a cost per field basis, priced at Year 1 rates, accuracy plus or minus 25 per cent. Includes 10 per cent contingency. Excludes land, already in reserve.
Key delivery risks |  | The site is low lying and the geotechnical work is not done, so earthworks could move the estimate. Contribution income depends on a settlement rate the plan does not control.
Dependencies and interfaces |  | Depends on the developer contribution plan being adopted and on the drainage outfall built under the harbour catchment project. Shares parking with the aquatic centre.
Benefits and how they will be measured |  | Field hours available up from 25 to 75 a week on the booking system, and closure days for turf recovery at nil against 22 last year. The parks manager reports each season.
Consequence of deferral |  | A year of delay lands the first 2,000 dwellings with no provision and moves the shortfall into the next plan at a higher price, with contribution income sitting unspent.
Readiness |  | Concept design only. Planning approval not lodged, land is in public reserve, no procurement route settled. The geotechnical investigation is the next step.
Recommended action |  | Fund design and investigation in Year 2. Hold the construction money until the contribution income is banked and the geotechnical result is in.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-007 | Fleet replacement program - heavy plant | [6 empty] | CIP-007 | 10
Replace graders, trucks and loaders at the end of economic life, on the fleet replacement schedule.
Category |  | Fleet and plant |  |  | Asset class |  |  | Vehicle and plant
Department / owner |  | Fleet operations |  |  | Delivery lead |  |  | R. Castillo
Primary driver |  | Renewal |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 11000000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 11000000 |  | Escalated total in the plan |  |  |  | 11853052.1891
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 11853052.1891
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 2000000 |  | 2000000 | 2000000 |  | 2500000 |  | 2500000 |  | 0
Escalated | 2000000 |  | 2070000 | 2142450 |  | 2771794.6875 |  | 2868807.5016 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Reserves |  |  |  | 100% |  |  | 11853052.1891
- |  |  |  | 0% |  |  | 0
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 3.59 |  | Rank in the plan |  | 8 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | Twenty two items of heavy plant are past economic life. Maintenance cost per hour is up 41 per cent in three years and availability has fallen to 78 per cent against a 92 per cent target.
Options considered and why this one |  | Do nothing carries rising maintenance and hire costs. Extending life by two years was tested and costs more in hire and downtime than it saves in capital. Replacing on the fleet schedule is the lowest whole of life option.
Scope summary |  | Replace six graders, nine trucks and seven loaders at their optimum replacement point, with trade-in of the units they replace. Telematics is fitted to every new unit.
Basis of the cost estimate |  | Priced from current supplier schedules net of trade-in, accuracy plus or minus 5 per cent. Includes delivery and fit-out. Excludes light fleet, which runs on a separate lease.
Key delivery risks |  | Order lead times have moved from 26 to 48 weeks, so a late order slips a full year. Trade-in values are assumed at today's market and could fall.
Dependencies and interfaces |  | Depends on the fleet reserve balance and on workshop capacity for fit-out. No approvals, no land and no interface with any other project in the plan.
Benefits and how they will be measured |  | Availability back to 92 per cent from 78, and maintenance cost per hour back to the schedule rate. The fleet manager reports monthly from the maintenance system.
Consequence of deferral |  | A year of delay adds about $640,000 in maintenance and hire on the units held over, and the trade-in value falls with every year of age.
Readiness |  | Fully specified, procurement is off an existing supply panel, no approvals or land needed. Orders can be placed as soon as the year is funded.
Recommended action |  | Fund at the flat annual rate. Place the Year 1 orders in the first quarter to hold the delivery slots.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-008 | Core network and cyber security uplift | [6 empty] | CIP-008 | 10
Segment the operational technology network and replace end-of-support edge hardware.
Category |  | Technology |  |  | Asset class |  |  | ICT system
Department / owner |  | Technology |  |  | Delivery lead |  |  | P. Nkemdirim
Primary driver |  | Compliance and safety |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 6200000 |  | Spend already incurred |  |  |  | 200000
Remaining cost to spend |  |  | 6000000 |  | Escalated total in the plan |  |  |  | 6180337.5
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 6180337.5
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 2400000 |  | 2100000 | 1500000 |  | 0 |  | 0 |  | 0
Escalated | 2400000 |  | 2173500 | 1606837.5 |  | 0 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Own revenue |  |  |  | 100% |  |  | 6180337.5
- |  |  |  | 0% |  |  | 0
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 4 |  | Rank in the plan |  | 4 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The operational technology network is flat, so a compromise anywhere reaches the water and traffic control systems. Edge hardware at 14 sites is out of support and no longer receives patches.
Options considered and why this one |  | Do nothing leaves a known unpatched path into the control systems. Patching alone was rejected because the vendor no longer issues patches for this hardware. Segmentation plus replacement closes the path and restores support.
Scope summary |  | Segment the operational technology network from the corporate network, replace end of support switches and firewalls at 14 sites, and add monitoring with a 24 hour response arrangement.
Basis of the cost estimate |  | Vendor quotation plus an implementation estimate from the last uplift, accuracy plus or minus 10 per cent. Includes three years of licensing. Excludes the SCADA application upgrade.
Key delivery risks |  | Cutover at the water plant and the traffic control room needs a maintenance window and both are hard to book. Specialist implementation resource is scarce and priced accordingly.
Dependencies and interfaces |  | Interfaces with the water treatment plant control system, which has to land on the segmented network. The internal audit finding stays open until it is closed by evidence.
Benefits and how they will be measured |  | Devices out of support at nil against 14, and mean time to detect below 15 minutes on the monitoring platform. The technology manager reports monthly.
Consequence of deferral |  | A year of delay carries an accepted high risk on the register for another year with no mitigation, and the audit finding stays open into the next reporting cycle.
Readiness |  | Design complete, hardware specified, procurement off a standing technology panel. No land, no planning approvals. Work can start as soon as it is funded.
Recommended action |  | Fund in full and start in Year 1. Sequence the segmentation ahead of the water plant control upgrade so the new plant lands on the new network.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-009 | Civic administration building - structural and fire upgrade | [6 empty] | CIP-009 | 10
Structural strengthening and fire system replacement. The building stays occupied through the works.
Category |  | Buildings |  |  | Asset class |  |  | Building - operational
Department / owner |  | Property and facilities |  |  | Delivery lead |  |  | S. Duarte
Primary driver |  | Compliance and safety |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 10800000 |  | Spend already incurred |  |  |  | 300000
Remaining cost to spend |  |  | 10500000 |  | Escalated total in the plan |  |  |  | 10978012.5
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 10978012.5
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 1500000 |  | 4500000 | 4500000 |  | 0 |  | 0 |  | 0
Escalated | 1500000 |  | 4657500 | 4820512.5 |  | 0 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Own revenue |  |  |  | 60% |  |  | 6586807.5
Reserves |  |  |  | 40% |  |  | 4391205
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 3.7 |  | Rank in the plan |  | 7 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The 1971 frame does not meet the current structural and fire standards, and the fire system has failed two consecutive certifications. The building holds 340 staff and the public records archive.
Options considered and why this one |  | Do nothing leaves 340 staff in a building that cannot be certified. Relocating everyone and selling the building was tested at $23M and loses the archive. Upgrading in place costs less and keeps the site.
Scope summary |  | Strengthen the frame at four core locations, replace fire detection and suppression, upgrade both stairs and rebuild the archive fire compartment. The building stays occupied, floor by floor.
Basis of the cost estimate |  | Class 3 estimate from the structural and fire design, priced at Year 1 rates, accuracy plus or minus 15 per cent. Includes staged decanting and after hours work. Excludes asbestos in the core walls.
Key delivery risks |  | Working around occupied floors is the main cost exposure and the decant space is not confirmed past Year 2. Opening up the core walls could find asbestos.
Dependencies and interfaces |  | Depends on decant space, which is the same leased floor as the library fit-out. The certifying body has to accept the staged approach before work starts.
Benefits and how they will be measured |  | Fire certification achieved at the first inspection after completion, against two failures. Structural assessment moved to compliant. The property manager holds both.
Consequence of deferral |  | A year of delay carries a third failed certification and the risk of a direction to vacate. Vacating this building costs about $2.1M a year in leased space.
Readiness |  | Structural design complete, fire design at 80 per cent, building approval lodged, site owned. Procurement is a managing contractor because of the staging.
Recommended action |  | Fund as phased and start in Year 1. Resolve the decant space before the Year 2 works are committed.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-010 | Harbour catchment flood mitigation | [6 empty] | CIP-010 | 10
Trunk drainage, detention basins and overland flow works across the harbour catchment.
Category |  | Water and wastewater |  |  | Asset class |  |  | Stormwater
Department / owner |  | Infrastructure and delivery |  |  | Delivery lead |  |  | M. Okonkwo
Primary driver |  | Compliance and safety |  |  | Status |  |  | Proposed
COST
Estimated total cost |  |  | 22000000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 22000000 |  | Escalated total in the plan |  |  |  | 21113586.1294
Beyond the plan (escalated) |  |  | 3563058.9169 |  | Whole of project, escalated |  |  |  | 24676645.0463
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 0 |  | 1000000 | 4000000 |  | 7000000 |  | 7000000 |  | 3000000
Escalated | 0 |  | 1035000 | 4284900 |  | 7761025.125 |  | 8032661.0044 |  | 3563058.9169
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Grants - government |  |  |  | 45% |  |  | 9501113.7582
Borrowings |  |  |  | 25% |  |  | 5278396.5323
Unfunded residual - no source named |  |  |  | 30% |  |  | 6334075.8388
PRIORITY
Weighted score | 4.04 |  | Rank in the plan |  | 3 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | Four hundred and twenty properties sit in the one in twenty year flood extent and eleven flooded above floor level in the last event. The trunk drainage was built for a catchment half this size.
Options considered and why this one |  | Do nothing leaves the properties exposed and the claims rising. Buying back the worst 90 properties was costed at $61M. Catchment works reduce the extent for every property at about a third of that cost.
Scope summary |  | Upgrade 3.1 km of trunk drainage, build two detention basins holding 46 ML between them, and formalise the overland flow path through the reserve.
Basis of the cost estimate |  | Concept estimate from the catchment flood study, priced at Year 1 rates, accuracy plus or minus 30 per cent. Includes land compensation for the basin sites. Excludes property level protection.
Key delivery risks |  | Two basin sites are privately held and acquisition could be contested. The modelling is at concept level, so detailed design may change the basin sizing and the cost with it.
Dependencies and interfaces |  | Depends on the grant application for the mitigation program and on acquiring the two basin sites. The Kingsway Park precinct drains to the same outfall.
Benefits and how they will be measured |  | Properties in the one in twenty year extent down from 420 to below 70 on the updated flood model, and above floor flooding at nil. Asset planning owns the measure.
Consequence of deferral |  | A year of delay carries another wet season at the current exposure. The grant round this funding assumes closes in Year 2 and will not repeat on the same terms.
Readiness |  | Flood study complete, concept design only, land not secured and no approvals held. The grant application is drafted but not lodged.
Recommended action |  | Fund design and land acquisition in Year 2. Do not commit construction until the grant is executed and both basin sites are under agreement.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-011 | Land acquisition - eastern growth corridor | [6 empty] | CIP-011 | 10
Acquire four parcels for the future arterial and drainage reserve ahead of development.
Category |  | Land |  |  | Asset class |  |  | Land holding
Department / owner |  | Corporate services |  |  | Delivery lead |  |  | L. Fenwick
Primary driver |  | Growth |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 7500000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 7500000 |  | Escalated total in the plan |  |  |  | 7657500
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 7657500
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 3000000 |  | 4500000 | 0 |  | 0 |  | 0 |  | 0
Escalated | 3000000 |  | 4657500 | 0 |  | 0 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Developer contributions |  |  |  | 60% |  |  | 4594500
Asset sales |  |  |  | 40% |  |  | 3063000
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 3.54 |  | Rank in the plan |  | 9 of 15 |  | Priority band |  | High
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The arterial and drainage reserve crosses four parcels that are all under development application. Once they are built out the corridor cannot be delivered at any reasonable price.
Options considered and why this one |  | Do nothing means buying improved land later or realigning the arterial on a longer route. Acquiring ahead of development was chosen because values in this corridor are rising about 12 per cent a year.
Scope summary |  | Acquire four parcels totalling 9.4 hectares for the future arterial alignment and the drainage reserve, by negotiation where the owner will deal.
Basis of the cost estimate |  | Independent valuation of all four parcels held at the valuation date, accuracy plus or minus 10 per cent. Includes acquisition and legal costs. Excludes the cost of a formal process if negotiation fails.
Key delivery risks |  | One owner has refused to negotiate, which puts that parcel into a formal process and adds about twelve months. Valuations move with every approval granted around them.
Dependencies and interfaces |  | Depends on the corridor alignment being confirmed in the transport strategy. The drainage reserve interfaces with the harbour catchment overland flow route.
Benefits and how they will be measured |  | Four parcels in ownership against nil, and acquisition cost within 10 per cent of the valuation. Corporate services reports on each settlement.
Consequence of deferral |  | A year of delay adds about $900,000 at the current growth in land value, and two of the four parcels may be built out and effectively unavailable.
Readiness |  | Valuations complete, alignment confirmed, negotiations open on three parcels. No design or approvals needed. Ready to settle as soon as it is funded.
Recommended action |  | Fund Year 1 and Year 2 in full. Start the formal process on the parcel that will not negotiate now, so the twelve months runs in parallel.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-012 | Library and learning hub fit-out | [6 empty] | CIP-012 | 10
Fit-out of leased floor space as a branch library. Deferred pending a decision on the lease.
Category |  | Buildings |  |  | Asset class |  |  | Building - community
Department / owner |  | Community services |  |  | Delivery lead |  |  | S. Duarte
Primary driver |  | Service improvement |  |  | Status |  |  | Deferred
COST
Estimated total cost |  |  | 5400000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 5400000 |  | Escalated total in the plan |  |  |  | 6142297.0275
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 6142297.0275
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 0 |  | 0 | 0 |  | 1400000 |  | 4000000 |  | 0
Escalated | 0 |  | 0 | 0 |  | 1552205.025 |  | 4590092.0025 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Own revenue |  |  |  | 50% |  |  | 3071148.5137
- |  |  |  | 0% |  |  | 0
Unfunded residual - no source named |  |  |  | 50% |  |  | 3071148.5137
PRIORITY
Weighted score | 1.98 |  | Rank in the plan |  | 15 of 15 |  | Priority band |  | Low
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The branch library closed when the lease ended and the northern suburbs now have no service point within 9 km. Membership in that catchment has fallen 24 per cent since the closure.
Options considered and why this one |  | Do nothing leaves the catchment without a branch. A mobile service was costed at $310,000 a year and reaches a third of the users. Fitting out leased floor space restores the service without a new building.
Scope summary |  | Fit out 1,100 square metres of leased floor space as a branch library and learning hub, with public computing, meeting rooms and a children's area.
Basis of the cost estimate |  | Fit-out rate per square metre from two recent projects, priced at Year 1 rates, accuracy plus or minus 20 per cent. Includes furniture and technology. Excludes base building works, carried by the landlord.
Key delivery risks |  | The lease is not signed and the make good obligation at the end of the term is not settled. If the landlord will not do the base building works the scope grows.
Dependencies and interfaces |  | Depends entirely on the lease decision, which sits with the property committee. The same floor is being considered as decant space for the civic building upgrade.
Benefits and how they will be measured |  | Membership in the northern catchment back to 8,400 from 6,400, and 45,000 visits a year. The community services manager reports quarterly.
Consequence of deferral |  | A year of delay is tolerable in service terms. The real exposure is that the floor is leased to someone else and the option is lost for the whole plan period.
Readiness |  | Concept layout only. No lease, no approvals and no procurement route. Deferred until the lease decision is made.
Recommended action |  | Hold in the plan as deferred, funded in Year 4 and Year 5. Bring it forward only if the lease is signed.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-013 | Asset renewal program - minor buildings and structures | [6 empty] | CIP-013 | 10
Annual allowance for roof, cladding and plant renewals identified by condition survey.
Category |  | Renewals |  |  | Asset class |  |  | Building - operational
Department / owner |  | Property and facilities |  |  | Delivery lead |  |  | R. Castillo
Primary driver |  | Renewal |  |  | Status |  |  | Approved
COST
Estimated total cost |  |  | 6000000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 6000000 |  | Escalated total in the plan |  |  |  | 6434959.0508
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 6434959.0508
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 1200000 |  | 1200000 | 1200000 |  | 1200000 |  | 1200000 |  | 0
Escalated | 1200000 |  | 1242000 | 1285470 |  | 1330461.45 |  | 1377027.6007 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Own revenue |  |  |  | 100% |  |  | 6434959.0508
- |  |  |  | 0% |  |  | 0
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 3.29 |  | Rank in the plan |  | 11 of 15 |  | Priority band |  | Medium
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The condition survey found 74 building elements at condition 4 or 5, mostly roofs, cladding and mechanical plant. Reactive repairs on those elements cost $840,000 last year.
Options considered and why this one |  | Do nothing raises reactive spend and eventually closes community buildings. Renewing only on failure was tested at about 1.7 times the planned rate. An annual allowance renews by condition rank instead.
Scope summary |  | An annual allowance for roof, cladding, mechanical and compliance renewals across 38 buildings, drawn against the condition survey and a works program agreed each year.
Basis of the cost estimate |  | Allowance set from the condition survey quantities at current rates, accuracy plus or minus 20 per cent. Includes design and superintendence. Excludes any single item above $500,000, which comes to the register on its own.
Key delivery risks |  | One large failure can consume the allowance and push planned work out. Roofing trade availability is the binding constraint in most years.
Dependencies and interfaces |  | Depends on the condition survey being refreshed every three years. Interfaces with the solar installation, where roof renewal and panels should be done in one visit.
Benefits and how they will be measured |  | Elements at condition 4 or 5 down from 74 to below 30 across five years, and reactive spend below $400,000 a year. The property manager reports on the annual works program.
Consequence of deferral |  | A year of delay adds about 15 elements to the condition 4 and 5 list and raises reactive spend. On current condition, two community buildings would close for roof failure.
Readiness |  | A standing program with an agreed method, panel contractors in place and no approvals or land needed. The Year 1 works program is drafted.
Recommended action |  | Fund the flat annual allowance. Publish the works program each year so the committee can see what the allowance actually bought.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-014 | Transit interchange upgrade | [6 empty] | CIP-014 | 10
Rebuild the interchange with the transport agency. Joint funding is agreed in principle only.
Category |  | Roads and bridges |  |  | Asset class |  |  | Other
Department / owner |  | Infrastructure and delivery |  |  | Delivery lead |  |  | A. Whitfield
Primary driver |  | Growth |  |  | Status |  |  | Proposed
COST
Estimated total cost |  |  | 18000000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 18000000 |  | Escalated total in the plan |  |  |  | 14571177.3788
Beyond the plan (escalated) |  |  | 5938431.5282 |  | Whole of project, escalated |  |  |  | 20509608.907
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 0 |  | 0 | 2000000 |  | 5000000 |  | 6000000 |  | 5000000
Escalated | 0 |  | 0 | 2142450 |  | 5543589.375 |  | 6885138.0038 |  | 5938431.5282
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Partner contributions |  |  |  | 40% |  |  | 5828470.9515
Grants - government |  |  |  | 30% |  |  | 4371353.2136
Unfunded residual - no source named |  |  |  | 30% |  |  | 4371353.2136
PRIORITY
Weighted score | 3.14 |  | Rank in the plan |  | 12 of 15 |  | Priority band |  | Medium
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The interchange handles 4,200 boardings a day on a layout built for 1,500. Buses queue in the through lane and there is no accessible path between the two stops.
Options considered and why this one |  | Do nothing leaves an interchange that fails accessibility requirements and delays services. Upgrading the existing stops was tested and does not fix the queuing. A rebuild is the only option the transport agency will co-fund.
Scope summary |  | Rebuild the interchange with six bus bays, an accessible concourse, shelters, real time information and a signalised crossing to the rail platform.
Basis of the cost estimate |  | Concept estimate prepared jointly with the transport agency, priced at Year 1 rates, accuracy plus or minus 25 per cent. Includes the signalised crossing. Excludes rail platform works.
Key delivery risks |  | The joint funding is agreed in principle only, with no executed agreement. The agency controls the rail interface and its own program is not confirmed.
Dependencies and interfaces |  | Depends on an executed funding agreement with the transport agency and on the agency's platform works. Interfaces with the road reconstruction on the approach.
Benefits and how they will be measured |  | Boarding time per service down from 95 to 60 seconds, and an accessible path of travel provided where there is none today. Transport planning reports with the agency.
Consequence of deferral |  | A year of delay is low risk to service, but the agency contribution is tied to its own program. If that program moves, the contribution may not be available at all.
Readiness |  | Concept design agreed in principle, no approvals, land is within the road reserve and the rail corridor. The procurement route depends on which party leads delivery.
Recommended action |  | Hold at concept until the funding agreement is executed. Do not phase construction money into the plan on an in principle agreement alone.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF |  |  | CIP-015 | Solar and battery installation - operational sites | [6 empty] | CIP-015 | 10
Rooftop solar and storage at the depot, library and civic building. Payback inside 9 years.
Category |  | Buildings |  |  | Asset class |  |  | Building - operational
Department / owner |  | Property and facilities |  |  | Delivery lead |  |  | P. Nkemdirim
Primary driver |  | Service improvement |  |  | Status |  |  | Proposed
COST
Estimated total cost |  |  | 4200000 |  | Spend already incurred |  |  |  | 0
Remaining cost to spend |  |  | 4200000 |  | Escalated total in the plan |  |  |  | 4455675
Beyond the plan (escalated) |  |  | 0 |  | Whole of project, escalated |  |  |  | 4455675
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal | 0 |  | 1200000 | 3000000 |  | 0 |  | 0 |  | 0
Escalated | 0 |  | 1242000 | 3213675 |  | 0 |  | 0 |  | 0
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Own revenue |  |  |  | 50% |  |  | 2227837.5
Asset sales |  |  |  | 50% |  |  | 2227837.5
Unfunded residual - no source named |  |  |  | 0% |  |  | 0
PRIORITY
Weighted score | 2.65 |  | Rank in the plan |  | 14 of 15 |  | Priority band |  | Medium
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity |  | The three largest operational sites spend $1.14M a year on electricity, up 34 per cent in two years. Roof area at all three sites is available and unused.
Options considered and why this one |  | Do nothing carries the full electricity cost and the exposure to further rises. A power purchase agreement was tested and returns less over 20 years than owning the assets. Solar with storage gives the better return.
Scope summary |  | Install 1.9 MW of rooftop solar and 2.4 MWh of battery storage at the depot, the library and the civic building, with metering and a monitoring platform.
Basis of the cost estimate |  | Supplier quotations for all three sites, accuracy plus or minus 10 per cent. Includes grid connection studies and metering. Excludes roof strengthening, which sits in the minor buildings program.
Key delivery risks |  | Grid connection approval at the depot is not certain and could limit export capacity. Roof condition at the civic building has to be resolved before panels go on.
Dependencies and interfaces |  | Depends on the roof renewals at the civic building and the depot in the minor buildings program. The connection approval sits with the network operator.
Benefits and how they will be measured |  | Electricity cost down $310,000 a year against a $1.14M baseline, and payback inside nine years measured from metered generation. The property manager reports annually.
Consequence of deferral |  | A year of delay costs about $310,000 in electricity that would have been avoided and pushes the payback out a year. Nothing fails and no service is affected.
Readiness |  | Quotations held, connection applications drafted, sites owned and no planning approval needed. Procurement is a single supply and install contract.
Recommended action |  | Fund in Year 2 and Year 3, after the roof renewals. Confirm the depot connection limit before the Year 3 order is placed.
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 16. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 17. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 18. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 19. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 20. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 21. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 22. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 23. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 24. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 25. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 26. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 27. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 28. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 29. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com
PROJECT BRIEF | [11 empty] | 0
No project on register row 30. Fill that row in on the Project Register and this block writes its own heading.
Category |  |  |  |  | Asset class
Department / owner |  |  |  |  | Delivery lead
Primary driver |  |  |  |  | Status
COST
Estimated total cost |  |  |  |  | Spend already incurred
Remaining cost to spend |  |  |  |  | Escalated total in the plan
Beyond the plan (escalated) |  |  |  |  | Whole of project, escalated
Phasing | FY2027 |  | FY2028 | FY2029 |  | FY2030 |  | FY2031 |  | Beyond FY2031
Nominal
Escalated
FUNDING
Funding source |  |  |  | Share |  |  | Amount (escalated, in plan)
Unfunded residual - no source named
PRIORITY
Weighted score |  |  | Rank in the plan |  |  |  | Priority band
THE CASE FOR THE PROJECT - written by the sponsor, before the panel scores it
Problem or opportunity
Options considered and why this one
Scope summary
Basis of the cost estimate
Key delivery risks
Dependencies and interfaces
Benefits and how they will be measured
Consequence of deferral
Readiness
Recommended action
Every figure on this page is drawn live from the Project Register. | [7 empty] | Built with Mastt ¦ mastt.com

## Funding Summary
CAPITAL IMPROVEMENT PLAN · FUNDING SUMMARY
EXAMPLE DATA - the 15 rows marked EX on the Project Register are worked examples. Delete or overwrite them, and this banner clears.
Every figure here is calculated from the Project Register and the envelope on Setup. Nothing on this sheet is typed. Funding is allocated on the escalated (cash) basis - that is the money that actually has to be appropriated in each year.
1 · WHAT THE PLAN NEEDS
Requirement | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | Beyond FY2031 | Total
Plan requirement - nominal (today's money) | 22850000 | 46750000 | 55700000 | 48600000 | 30200000 | 9500000 | 213600000
Plan requirement - escalated (cash) | 22850000 | 48386250 | 59667232.5 | 53883688.725 | 34655194.6189 | 11283019.9036 | 230725385.7475
Escalation carried in the plan | 0 | 1636250 | 3967232.5 | 5283688.725 | 4455194.6189 | 1783019.9036 | 17125385.7475
The escalated row is the cash the plan needs in each year. It is the nominal phasing on the register uplifted by the Setup escalation factors. Fund against this row, not the nominal one.
2 · WHERE THE MONEY COMES FROM (escalated cash)
Funding source | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | Beyond FY2031 | Total | % of plan
Own revenue | 10750000 | 16249500 | 13604557.5 | 5432717.5875 | 4360587.4024 | 712611.7834 | 51109974.2733 | 22.15%
Reserves | 3500000 | 4864500 | 5034757.5 | 3769640.775 | 3901578.2021 | 1068917.6751 | 22139394.1522 | 9.596%
Grants - government | 1450000 | 6015937.5 | 9748147.5 | 10366512.1312 | 7516275.6541 | 3384905.9711 | 38481778.7564 | 16.68%
Borrowings | 3775000 | 12057750 | 17568090 | 17018819.3813 | 6598257.2536 | 890764.7292 | 57908681.3641 | 25.1%
Developer contributions | 1800000 | 4075312.5 | 3535042.5 | 3658768.9875 | 0 | 0 | 13069123.9875 | 5.664%
Partner contributions | 0 | 0 | 856980 | 2217435.75 | 2754055.2015 | 2375372.6113 | 8203843.5628 | 3.556%
Asset sales | 1200000 | 2484000 | 1606837.5 | 0 | 0 | 0 | 5290837.5 | 2.293%
Unfunded - no source identified | 375000 | 2639250 | 7712820 | 11419794.1125 | 9524440.9052 | 2850447.1336 | 34521752.1512 | 14.96%
TOTAL FUNDING REQUIREMENT | 22850000 | 48386250 | 59667232.5 | 53883688.725 | 34655194.6189 | 11283019.9036 | 230725385.7475 | 100%
Unfunded is the share of a project's cost with no source named against it on the register. It is a finding, not an error - it is the number to take to the funding conversation.
3 · AFFORDABILITY
Position | FY2027 | FY2028 | FY2029 | FY2030 | FY2031 | Beyond FY2031 | Plan period
Funding envelope available (from Setup) | 30000000 | 46000000 | 50000000 | 48000000 | 40000000 | 45000000 | 214000000
Requirement - escalated (cash) | 22850000 | 48386250 | 59667232.5 | 53883688.725 | 34655194.6189 | 11283019.9036 | 219442365.8439
Surplus / (shortfall) in the year | 7150000 | -2386250 | -9667232.5 | -5883688.725 | 5344805.3811 | 33716980.0964 | -5442365.8439
Cumulative envelope | 30000000 | 76000000 | 126000000 | 174000000 | 214000000 | 259000000 | 214000000
Cumulative requirement | 22850000 | 71236250 | 130903482.5 | 184787171.225 | 219442365.8439 | 230725385.7475 | 219442365.8439
Cumulative surplus / (shortfall) | 7150000 | 4763750 | -4903482.5 | -10787171.225 | -5442365.8439 | 28274614.2525 | -5442365.8439
Of the requirement, the part with no source | 375000 | 2639250 | 7712820 | 11419794.1125 | 9524440.9052 | 2850447.1336 | 31671305.0177
Of the requirement, the part with a source | 22475000 | 45747000 | 51954412.5 | 42463894.6125 | 25130753.7137 | 8432572.7701 | 187771060.8262
Envelope less the funded requirement | 7525000 | 253000 | -1954412.5 | 5536105.3875 | 14869246.2863 | 36567427.2299 | 26228939.1738
The Plan period column adds Year 1 to Year 5 only - what falls beyond the plan is shown in its own column but is not part of the affordability test, because the envelope for those years is not yet set. The cumulative lines carry a surplus forward, which most organisations can do inside a plan period but not across one. A year that is red on its own line and black cumulatively is a re-phasing problem; red on both lines is a funding problem.
4 · CHECKS
Funding sources tie to the requirement | RECONCILED - the funding sources add back to the escalated plan requirement of $230,725,386
Every year ties, not just the total | RECONCILED - the funding split ties to the requirement in every year
Escalated rebuilt from the nominal row | RECONCILED - the escalated requirement equals the nominal requirement times the Setup factors
Register phasing is clean | RECONCILED - every project on the register phases to its remaining cost
Unfunded ties to the register | RECONCILED - the unfunded gap of $31,671,305 equals the unfunded column on the register
An envelope has been entered | RECONCILED - a funding envelope is set for the plan period
Built with Mastt ¦ mastt.com

## Plan Summary
CAPITAL IMPROVEMENT PLAN · PLAN SUMMARY
EXAMPLE DATA - the 15 rows marked EX on the Project Register are worked examples. Delete or overwrite them, and this banner clears.
The board page. Every figure is a formula reading Setup, the Project Register, Prioritisation and Funding Summary. Nothing here is typed. Prints A4 landscape over two pages.
PLAN AT A GLANCE
Projects in the plan |  | Plan value - nominal |  | Plan value - escalated |  | Beyond the plan |  | Funding envelope |  | Surplus / (shortfall) |  | Unfunded requirement
15 |  | 204100000 |  | 219442365.8439 |  | 11283019.9036 |  | 214000000 |  | -5442365.8439 |  | 31671305.0177
rows on the register |  | today's money, Y1 to Y5 |  | cash, Year 1 to Year 5 |  | escalated, after Year 5 |  | Year 1 to Year 5 |  | envelope less requirement |  | no source identified
SPEND BY YEAR | [6 empty] | SPEND BY CATEGORY
Year |  | Nominal | Escalated | % of plan | Profile |  | Category |  | Escalated | % of plan | Share
FY2027 |  | 22850000 | 22850000 | 10.41% | ████████ |  | Buildings |  | 70952804.5325 | 32.33% | ██████████████████████████
FY2028 |  | 46750000 | 48386250 | 22.05% | ████████████████ |  | Roads and bridges |  | 33153577.3788 | 15.11% | ████████████
FY2029 |  | 55700000 | 59667232.5 | 27.19% | ████████████████████ |  | Water and wastewater |  | 67801727.9428 | 30.9% | █████████████████████████
FY2030 |  | 48600000 | 53883688.725 | 24.55% | ██████████████████ |  | Parks and recreation |  | 15408407.25 | 7.022% | ██████
FY2031 |  | 30200000 | 34655194.6189 | 15.79% | ████████████ |  | Fleet and plant |  | 11853052.1891 | 5.401% | ████
Total - plan period |  | 204100000 | 219442365.8439 | 100% |  |  | Technology |  | 6180337.5 | 2.816% | ██
Beyond FY2031 (memo) |  | 9500000 | 11283019.9036 |  |  |  | Land |  | 7657500 | 3.49% | ███
[7 empty] | Renewals |  | 6434959.0508 | 2.932% | ██
[7 empty] | Other |  | 0 | 0%
[7 empty] | Total |  | 219442365.8439 | 100%
SPEND BY DRIVER | [6 empty] | PROJECTS BY PRIORITY BAND
Driver |  | Escalated | % of plan | Projects | Share |  | Band |  | Projects | Escalated | Share of value
Renewal |  | 44914110.0532 | 20.47% | 5 | ████████████ |  | Critical |  | 2 | 51139343 | 23.3%
Growth |  | 37637084.6287 | 17.15% | 3 | ██████████ |  | High |  | 7 | 71913687.1319 | 32.77%
Compliance and safety |  | 76916379.1294 | 35.05% | 4 | ████████████████████ |  | Medium |  | 5 | 90247038.6845 | 41.13%
Service improvement |  | 59974792.0325 | 27.33% | 3 | ████████████████ |  | Low |  | 1 | 6142297.0275 | 2.799%
Statutory |  | 0 | 0% | 0 |  |  | Total |  | 15 | 219442365.8439 | 100%
Total |  | 219442365.8439 | 100% | 15
TOP TEN PROJECTS BY WEIGHTED SCORE
Rank | Project |  |  | Category |  | Driver |  | Escalated cost in plan | Score | Band | Funding source 1 |  | Unfunded
1 | Central water treatment plant upgrade |  |  | Water and wastewater |  | Compliance and safety |  | 38644443 | 4.32 | Critical | Borrowings |  | 0%
2 | Riverside Bridge deck renewal |  |  | Roads and bridges |  | Renewal |  | 12494900 | 4.21 | Critical | Grants - government |  | 0%
3 | Harbour catchment flood mitigation |  |  | Water and wastewater |  | Compliance and safety |  | 21113586.1294 | 4.04 | High | Grants - government |  | 30%
4 | Core network and cyber security uplift |  |  | Technology |  | Compliance and safety |  | 6180337.5 | 4 | High | Own revenue |  | 0%
5 | Wastewater pump station renewals |  |  | Water and wastewater |  | Renewal |  | 8043698.8134 | 3.91 | High | Reserves |  | 0%
6 | Depot Road reconstruction - stage 2 |  |  | Roads and bridges |  | Renewal |  | 6087500 | 3.83 | High | Own revenue |  | 0%
7 | Civic administration building - structural and fire upgrade |  |  | Buildings |  | Compliance and safety |  | 10978012.5 | 3.7 | High | Own revenue |  | 0%
8 | Fleet replacement program - heavy plant |  |  | Fleet and plant |  | Renewal |  | 11853052.1891 | 3.59 | High | Reserves |  | 0%
9 | Land acquisition - eastern growth corridor |  |  | Land |  | Growth |  | 7657500 | 3.54 | High | Developer contributions |  | 0%
10 | Northgate aquatic centre replacement |  |  | Buildings |  | Service improvement |  | 49376820.005 | 3.29 | Medium | Borrowings |  | 30%
AFFORDABILITY POSITION
What the plan needs in the plan period (escalated cash) | [6 empty] | 219442365.8439
What the organisation can afford in the plan period | [6 empty] | 214000000
Surplus / (shortfall) against the envelope | [6 empty] | -5442365.8439
Of the requirement, the share with a funding source named | [6 empty] | 187771060.8262
Of the requirement, the share with no funding source | [6 empty] | 31671305.0177
Value of the plan in present-value terms (discounted to the start of Year 1) | [6 empty] | 206950293.6095
The plan is over the envelope by $5,442,366 across the plan period. 1 project(s) fall below the line and have to be re-phased, funded from elsewhere or deferred.
CHECKS
Category analysis ties to the register |  |  |  | RECONCILED - spend by category equals the register total
Driver analysis ties to the register |  |  |  | RECONCILED - spend by driver equals the register total
Funded and unfunded add back to the plan |  |  |  | RECONCILED - funded plus unfunded equals the escalated plan value
Priority bands cover every project |  |  |  | RECONCILED - every project on the register carries a priority band
Every project carries a written case |  |  |  | RECONCILED - all ten narrative fields are written on the Project Brief for every project on the register
A brief block for every project |  |  |  | RECONCILED - the Project Brief carries a block for every project on the register, keyed to its register row
Spend by year ties to the funding summary |  |  |  | RECONCILED - spend by year equals the escalated requirement on Funding Summary, plan period and beyond
Built with Mastt ¦ mastt.com

## Reference
CAPITAL IMPROVEMENT PLAN · REFERENCE
Every dropdown in this workbook reads from the lists below. Rename or add entries in place - if you insert a row inside a coloured block the dropdown range follows it. The rubric is what keeps two assessors scoring the same project the same way. Prints A3 landscape.
1 · DROPDOWN LISTS
Category | Asset class | Department / owner | Driver | Status | Funding source | Score | Plan status | Priority band
Buildings | Building - community | Infrastructure and delivery | Renewal | Proposed | Own revenue | 1 | Draft | Critical
Roads and bridges | Building - operational | Community services | Growth | Approved | Reserves | 2 | For review | High
Water and wastewater | Road pavement | Water services | Compliance and safety | In delivery | Grants - government | 3 | Endorsed | Medium
Parks and recreation | Bridge and structure | Parks and open space | Service improvement | Deferred | Borrowings | 4 | Adopted | Low
Fleet and plant | Water network | Corporate services | Statutory | Not funded | Developer contributions | 5
Technology | Wastewater network | Technology |  |  | Partner contributions
Land | Stormwater | Property and facilities |  |  | Asset sales
Renewals | Open space | Fleet operations
Other | Vehicle and plant
ICT system
Land holding
Other
Priority band and Score are shown for reference. Band is calculated from the weighted score and the thresholds on Setup - it is never typed.
2 · SCORING RUBRIC - what a 1 and a 5 actually mean
Criterion |  | Weighting | Score 1 |  | Score 3 |  | Score 5
Asset condition and failure risk |  | 15% | Sound condition. Remaining life extends beyond the plan period and there is no failure history. |  | Condition is fair and deteriorating. Reactive maintenance is rising but the asset still performs. |  | At or past the end of its life, or it has already failed. A condition assessment or failure record proves it.
Health, safety and compliance |  | 20% | No safety or compliance issue. The asset meets the standards that apply to it. |  | A known non-conformance with an interim control in place, recorded on the risk register. |  | A direct risk to life safety, or a written direction the Owner is required to act on.
Service demand and growth |  | 12% | Demand is flat or falling. Existing capacity is adequate for the whole plan period. |  | Demand is growing steadily. Capacity constraints appear late in the plan period. |  | Capacity is exceeded now, or committed growth lands inside the plan period.
Strategic alignment |  | 12% | Not named in any adopted strategy, asset management plan or funding agreement. |  | Supports an adopted strategy but is not a named commitment in it. |  | A named commitment in an adopted strategy, asset management plan or executed funding agreement.
Economic or community benefit |  | 12% | Benefit is limited to one site or a small user group and has not been quantified. |  | Benefit is measurable for a defined catchment. A concept-level business case exists. |  | Benefit is quantified in a business case with a benefit-cost ratio above 1, or it unlocks wider investment.
Deliverability and readiness |  | 10% | Scope is an idea. No estimate basis, no design, no approvals, no delivery resource named. |  | Concept design and an order-of-magnitude estimate exist. Approvals are identified but not obtained. |  | Design complete or near complete, approvals in hand, land secured, delivery team available. Ready to procure.
Funding certainty |  | 9% | No funding source identified. Nothing committed by anyone. |  | A source is identified and likely but not committed - a grant applied for, a reserve not yet resolved. |  | Funding is committed in writing for the full amount - adopted budget, executed grant agreement or contribution deed.
Consequence of doing nothing |  | 10% | Deferral has little effect. The service continues and costs do not rise materially. |  | Deferral raises operating cost or risk, or pushes the problem into the next plan at a higher price. |  | Deferral means service failure, closure, a compliance breach or a materially higher cost later.
A 2 or a 4 sits between the descriptions. Score against evidence you can point to - a condition report, a direction, a business case, an executed agreement. If you cannot point to it, the score is not a 5.
3 · DEFINITIONS
Term |  | What it means
Capital Improvement Plan (CIP) |  | A rolling program of capital projects across the plan period, each with a cost, a phasing, a funding source and a priority. It is the pipeline. The annual budget adopts Year 1 of it.
Owner (Client) |  | The organisation that commissions and pays for the work - a council, city or county, agency, university, health service, utility or corporate portfolio. Called the Principal or the Employer in some contracts.
Contract Administrator / Owner's Representative |  | The party named in the Contract to administer it once a project is in delivery. Not a role this plan assigns - it appears in the delivery documents, not here.
Estimated total cost |  | The whole-of-project capital cost, including what has already been spent. Say what the estimate is based on in the description - an idea, a concept estimate and a tendered price carry very different confidence.
Remaining cost |  | Estimated total cost less spend already incurred. Only the remaining cost is phased across the plan - the money already spent cannot be planned.
Nominal cost (today's money) |  | Cost stated in current-year money with no escalation applied. Use it to compare projects.
Escalated cost (cash) |  | Nominal cost uplifted to the money of the year it is spent. This is the amount that has to be appropriated, and the basis the funding and affordability pages work on.
Escalation rate |  | The expected annual increase in construction cost. Set it once on Setup from your own market data. Year 1 is not escalated; Year n carries (1 + rate) ^ (n - 1).
Discount rate |  | The rate used to bring future cash back to today's value. It drives the present value figure on Plan Summary and nothing else in this model.
Funding envelope |  | What the organisation can afford to commit in a year under its financial strategy - revenue capacity, borrowing headroom, reserves and grants already agreed. Not the sum of what has been asked for.
Unfunded |  | The share of a project's cost with no funding source named against it. Unfunded is not the same as unaffordable - it means no one has yet said where the money comes from.
Driver |  | Why the project exists: Renewal, Growth, Compliance and safety, Service improvement or Statutory. The mix of drivers across a plan says more about an organisation than any single project does.
Beyond the plan |  | Cost that falls after the last year of the plan period. Carried so the full commitment is visible, and escalated at the Year 6 factor.
Above / below the line |  | Whether a project fits inside the cumulative funding envelope for the plan period when projects are funded in strict rank order.
Program / Schedule |  | The time plan for delivery. This workbook holds only the year a cost lands in; the delivery program sits with the project.
Variation / Change Order |  | An authorised change to the scope or price of a contract in delivery. A variation that moves a project's total cost is a change to this plan and belongs back on the register.
Substantial Completion (Practical Completion) |  | The point at which the works are complete enough for the Owner to use them for their intended purpose. Capital spend on a project largely stops here.
Defects Liability Period (Warranty Period) |  | The period after Substantial Completion in which the contractor has to make good defects. Retention or security is usually held against it.
4 · TERMINOLOGY - reading this workbook in your own jurisdiction
Used in this workbook |  | Also called
Owner / Client |  | Principal (AU) · Employer (UK, FIDIC)
Contract Administrator / Owner's Representative |  | Superintendent (AU) · Architect or Engineer to the Contract (UK) · Owner's Rep (US)
Substantial Completion / Practical Completion |  | Both terms mean the same milestone here
Defects Liability Period / Warranty Period |  | Both terms mean the same period here
Variation / Change Order |  | Both terms mean the same instrument here
Program / Schedule |  | Both terms mean the delivery time plan here
Capital Improvement Plan |  | Capital Works Program (AU) · Capital Programme (UK) · Capital Improvement Program or Plan (US)
5 · CELL CONVENTIONS
You type here | Pale blue with a cobalt figure. Every other cell is calculated.
Calculated | Off-white. Do not overwrite it - you will break the reconciliation checks.
Total | Grey with a rule above. Always a formula.
Critical | A coloured chip set by formula from the score or the status list.
Exception | Red means the model has found something that does not add up. Fix it before you publish.
EX | Marks an example row. Delete the EX rows and every example banner clears.
Built with Mastt ¦ mastt.com