## Cover
Submittal Log
A submittal register for construction projects - what has to be submitted, what it is waiting on, and what is about to be late. It numbers submittals off the specification section, separates the items that need a decision from the ones that only need filing, and works back from the required-on-site date to tell you the last day each one can be submitted.
HOW TO USE IT
1 | Set the project up once | Setup holds the project, the parties, the review periods your specification actually states, and which review action set the reviewer stamps with. Every other sheet reads from it.
2 | Choose the action set first | Four sets are in real use and they are not interchangeable. Reference explains each one. Pick the one your specification uses, because the log's logic follows it.
3 | Load the register from the specification | One row per submittal, numbered off its specification section. Set the class - Action, Informational or Closeout. Only Action items get a disposition and block fabrication.
4 | Enter the lead time and the required-on-site date | These two fields drive the whole warning system. Without them the log records history; with them it tells you what is about to be late.
5 | Read the float column, not the status column | Float is the days between the latest date a submittal can be made and the day it actually was. Negative float means the item is already late even if nobody has noticed.
6 | Log received and submitted separately | The review clock runs from receipt. The gap between the two is the Contractor's, not the reviewer's, and it is the first thing challenged in a delay claim.
7 | Never delete a row | Set the Void column to Yes, or raise the revision so the old row shows as Superseded. A submittal log is a contemporaneous record - gaps in the numbering are the fastest way to lose its evidential value.
WHAT IS IN THE WORKBOOK
| Sheet | What it is for
| Setup | Project, parties, the review periods your specification states, and the review action set in use. Everything else reads from it.
| Submittal Log | The register. One row per submittal, with the review clock, the ball in court and the float against the required-on-site date.
| Summary | Counts by status, class, ball in court, package and division, the ageing of items with the reviewer, and the first-time approval rate.
| Reference | Every dropdown, the MasterFormat divisions, all four review action sets with what each one means, the ISO 19650 mapping and the definitions.
THE TWO THINGS MOST SUBMITTAL LOGS GET WRONG
| They record history instead of warning you | A log that only holds submitted and returned dates tells you what already happened. This one works back from the required-on-site date - less lead time, less review time, less one resubmittal - to the last day the submittal can be made, and shows the float against it. Negative float is an item that is already late whether or not anyone has noticed.
| They treat every submittal as the same kind of thing | Items that need a decision and items that only need filing are not the same. Action submittals get a disposition and block fabrication. Informational submittals are received and acknowledged - measuring a reviewer's turnaround on those makes the numbers meaningless. Closeout submittals belong on the log from day one, because they are what holds up the final certificate.
IMPORTANT
This log is a management and record-keeping tool, not advice. Review periods, action codes and the consequences of late or rejected submittals are set by the Contract and the specification - read them and set this workbook to match. A reviewer's action on a submittal does not relieve the Contractor of responsibility for dimensions, quantities, fabrication processes, coordination, or construction means and methods.
Built for capital project teams by Mastt. Project controls, cost management and reporting · mastt.com

## Setup
SUBMITTAL LOG · SETUP
Fill this in once. The register, the summary and every calculated date read from here.
1 · PROJECT AND CONTRACT
Project name
Project number
Site address
Contract title
Contract number
Owner / Client
Contractor
Contract Administrator / Owner's Representative
Document controller
2 · REVIEW PERIODS AND THE ACTION SET
Review action set in use | A - EJCDC (recommended) | Four sets are in real use and they are not interchangeable. Reference explains each.
Initial review period - concurrent review (calendar days) | 15 | The most common figure in US master specifications. Read your own - AIA A201 states no number at all, leaving it to the submittal schedule.
Initial review period - sequential review (calendar days) | 21 | Used where the submittal passes through consultants one after another rather than at once.
Resubmittal review period (calendar days) | 15 | Applies to revision 01 and later.
Contractor internal review allowance (calendar days) | 5 | The Contractor's own check before it goes out. Included in the back-calculated submit-by date.
Long lead threshold (weeks) | 12 | Anything at or above this is flagged as long lead on the register.
3 · WHERE THE LOG STANDS
Submittals on the log | 26
Action submittals | 22
Open - not yet closed | 12
Overdue with the reviewer | 3
Awaiting resubmittal | 2
Negative float - already late | 4
AIA A201-2017 states no review period - the number comes from the specification, usually section 01 33 00. It also says that if the Contractor fails to submit in accordance with the approved submittal schedule, it is not entitled to more time or money for the review period. That is why this log is a contractual record, not an administrative convenience.
Built with Mastt ¦ mastt.com

## Submittal Log
SUBMITTAL LOG · REGISTER
EXAMPLE DATA - 26 rows are worked examples. Delete them and this banner clears.
One row per submittal. Blue cells are yours; grey columns calculate. Float is the number that matters - it is the days between the latest date this could be submitted and the day it actually was. Prints A3 landscape, two pages wide.
Ref | Submittal no. | Spec section | Seq | Rev | Spec section title | Division | Package | Description of the submittal | Submittal type | Class | Responsible party | Submitted | Received for review | Reviewer | Review route | Review due | Returned | Review action | Days in review | Status | Ball in court | Lead time (weeks) | Required on site | Latest submit by | Float (days) | Long lead | Delegated design | Void | Notes
1 | 03 30 00-001 | 03 30 00 | 1 | 0 | Cast-in-place concrete | 03 Concrete | Structure | Concrete mix designs - 32 MPa and 40 MPa structural mixes | Design mix | Action | Northgate Readymix | 2026-06-08 | 2026-06-08 | Structural engineer | Concurrent | 2026-06-23 | 2026-06-19 | Approved as Noted | 11 | Closed | Closed | 2 | 2026-07-10 | 2026-06-06 | -2 |  | No |  | EXAMPLE - delete before use
2 | 05 12 00-002 | 05 12 00 | 2 | 0 | Structural steel framing | 05 Metals | Structure | Shop drawings - primary frame, grids A to F | SD-02 Shop drawings | Action | Kembla Steel Fabrication | 2026-06-11 | 2026-06-12 | Structural engineer | Sequential | 2026-07-03 | 2026-07-06 | Revise and Resubmit | 24 | Superseded | Closed | 14 | 2026-11-06 |  |  |  | No |  | EXAMPLE
3 | 05 12 00-002.01 | 05 12 00 | 2 | 1 | Structural steel framing | 05 Metals | Structure | Shop drawings - primary frame, grids A to F, revision 1 | SD-02 Shop drawings | Action | Kembla Steel Fabrication | 2026-07-20 | 2026-07-21 | Structural engineer | Sequential | 2026-08-05 | 2026-08-04 | Approved | 14 | Closed | Closed | 14 | 2026-11-06 | 2026-07-05 | -15 | Long lead | No |  | EXAMPLE
4 | 07 42 13-003 | 07 42 13 | 3 | 0 | Metal wall panels | 07 Thermal and Moisture Protection | Envelope | Product data and finish samples - rainscreen cladding | SD-03 Product data | Action | Vitrex Facades | 2026-06-22 | 2026-06-23 | Architect | Concurrent | 2026-07-08 | 2026-07-07 | Approved | 14 | Closed | Closed | 10 | 2026-10-02 | 2026-07-04 | 12 |  | No |  | EXAMPLE
5 | 08 44 13-004 | 08 44 13 | 4 | 0 | Glazed aluminium curtain wall | 08 Openings | Envelope | Delegated design - curtain wall structural calculations, signed and sealed | Delegated design | Action | Vitrex Facades | 2026-06-29 | 2026-06-30 | Structural engineer | Sequential | 2026-07-21 |  |  | 43 | Overdue with reviewer | Reviewer | 16 | 2026-10-16 | 2026-05-31 | -29 | Long lead | Yes |  | EXAMPLE - open, overdue
6 | 09 51 13-005 | 09 51 13 | 5 | 0 | Acoustical panel ceilings | 09 Finishes | Fit-out | Product data and samples - ceiling tile and grid | SD-04 Samples | Action | Interior Linings Co | 2026-07-27 | 2026-07-28 | Architect | Concurrent | 2026-08-12 |  |  | 15 | In review | Reviewer | 6 | 2026-10-30 | 2026-08-29 | 33 |  | No |  | EXAMPLE - in review
7 | 09 91 00-006 | 09 91 00 | 6 | 0 | Painting | 09 Finishes | Fit-out | Product data and colour schedule | SD-03 Product data | Action | Coastal Painting | 2026-07-30 | 2026-07-31 | Architect | Concurrent | 2026-08-15 |  |  | 12 | In review | Reviewer | 3 | 2026-11-20 | 2026-10-10 | 72 |  | No |  | EXAMPLE - in review
8 | 14 21 00-007 | 14 21 00 | 7 | 0 | Electric traction elevators | 14 Conveying Equipment | Vertical transport | Shop drawings, capacity calculations and finishes - two passenger cars | SD-02 Shop drawings | Action | Ascent Lifts | 2026-05-18 | 2026-05-19 | Architect | Sequential | 2026-06-09 | 2026-06-10 | Approved as Noted | 22 | Closed | Closed | 26 | 2026-12-04 | 2026-05-10 | -8 | Long lead | No |  | EXAMPLE - long lead
9 | 21 13 13-008 | 21 13 13 | 8 | 0 | Wet-pipe sprinkler systems | 21 Fire Suppression | Fire | Hydraulic calculations and layout drawings | SD-05 Design data and calculations | Action | Sentinel Fire | 2026-07-06 | 2026-07-07 | Fire engineer | Sequential | 2026-07-28 | 2026-07-24 | Revise and Resubmit | 17 | Resubmittal required | Contractor | 8 | 2026-10-09 | 2026-07-19 | 13 |  | Yes |  | EXAMPLE
10 | 22 40 00-009 | 22 40 00 | 9 | 0 | Plumbing fixtures | 22 Plumbing | Hydraulic | Product data - sanitaryware and tapware schedule | SD-03 Product data | Action | Metro Plumbing Group | 2026-07-13 | 2026-07-14 | Architect | Concurrent | 2026-07-29 | 2026-07-27 | Approved | 13 | Closed | Closed | 9 | 2026-11-13 | 2026-08-22 | 40 |  | No |  | EXAMPLE
11 | 23 73 13-010 | 23 73 13 | 10 | 0 | Air handling units | 23 Heating, Ventilating and Air Conditioning | Mechanical | Shop drawings and selection data - AHU-01 to AHU-04 | SD-02 Shop drawings | Action | Apex Mechanical | 2026-05-26 | 2026-05-27 | Services engineer | Sequential | 2026-06-17 | 2026-06-16 | Approved as Noted | 20 | Closed | Closed | 22 | 2026-11-27 | 2026-05-31 | 5 | Long lead | No |  | EXAMPLE - long lead
12 | 23 09 00-011 | 23 09 00 | 11 | 0 | Instrumentation and control for HVAC | 23 Heating, Ventilating and Air Conditioning | Mechanical | Controls architecture and points schedule | SD-05 Design data and calculations | Action | Apex Mechanical |  |  | Services engineer | Concurrent |  |  |  |  | Not submitted | Contractor | 12 | 2026-10-23 | 2026-07-11 | -32 | Long lead | No |  | EXAMPLE - not submitted, negative float
13 | 26 24 16-012 | 26 24 16 | 12 | 0 | Panelboards | 26 Electrical | Electrical | Shop drawings - main switchboard and distribution boards | SD-02 Shop drawings | Action | Arcline Electrical | 2026-06-15 | 2026-06-16 | Services engineer | Sequential | 2026-07-07 | 2026-07-08 | Approved | 22 | Closed | Closed | 18 | 2026-11-20 | 2026-06-21 | 6 | Long lead | No |  | EXAMPLE
14 | 26 51 00-013 | 26 51 00 | 13 | 0 | Interior lighting | 26 Electrical | Electrical | Product data and photometric calculations | SD-05 Design data and calculations | Action | Arcline Electrical | 2026-07-20 | 2026-07-21 | Services engineer | Concurrent | 2026-08-05 |  |  | 22 | Overdue with reviewer | Reviewer | 11 | 2026-10-16 | 2026-07-11 | -9 |  | No |  | EXAMPLE - in review
15 | 26 05 00-014 | 26 05 00 | 14 | 0 | Common work results for electrical | 26 Electrical | Electrical | Installer qualifications and licences | SD-07 Certificates | Informational | Arcline Electrical | 2026-06-01 | 2026-06-02 | Contract Administrator | Concurrent | 2026-06-17 | 2026-06-08 | Accepted | 6 | Closed | Closed | 0 |  |  |  |  | No |  | EXAMPLE - informational
16 | 28 13 00-015 | 28 13 00 | 15 | 0 | Access control | 28 Electronic Safety and Security | Electrical | Product data and system architecture | SD-03 Product data | Action | Sentry Systems | 2026-07-23 | 2026-07-24 | Services engineer | Concurrent | 2026-08-08 |  |  | 19 | Overdue with reviewer | Reviewer | 10 | 2026-10-30 | 2026-08-01 | 9 |  | No |  | EXAMPLE - in review
17 | 31 20 00-016 | 31 20 00 | 16 | 0 | Earth moving | 31 Earthwork | Civil and external | Compaction test reports - bulk earthworks | SD-06 Test reports | Informational | Groundline Civil | 2026-05-11 | 2026-05-12 | Geotechnical engineer | Concurrent | 2026-05-27 | 2026-05-20 | Accepted | 8 | Closed | Closed | 0 |  |  |  |  | No |  | EXAMPLE - informational
18 | 32 12 16-017 | 32 12 16 | 17 | 0 | Asphalt paving | 32 Exterior Improvements | Civil and external | Asphalt mix design and compaction method | Design mix | Action | Groundline Civil | 2026-07-17 | 2026-07-20 | Civil engineer | Concurrent | 2026-08-04 | 2026-08-03 | Approved as Noted | 14 | Closed | Closed | 3 | 2026-10-09 | 2026-08-29 | 43 |  | No |  | EXAMPLE
19 | 32 90 00-018 | 32 90 00 | 18 | 0 | Planting | 32 Exterior Improvements | Landscape | Plant schedule and nursery certification | SD-03 Product data | Action | Greenline Landscapes |  |  | Landscape architect | Concurrent |  |  |  |  | Not submitted | Contractor | 20 | 2026-11-27 | 2026-06-20 | -53 | Long lead | No |  | EXAMPLE - not submitted, long lead
20 | 33 11 00-019 | 33 11 00 | 19 | 0 | Water utility distribution piping | 33 Utilities | Civil and external | Product data - pipe, fittings and valves | SD-03 Product data | Action | Groundline Civil | 2026-06-24 | 2026-06-25 | Civil engineer | Concurrent | 2026-07-10 | 2026-07-08 | Approved | 13 | Closed | Closed | 6 | 2026-09-25 | 2026-07-25 | 31 |  | No |  | EXAMPLE
21 | 08 71 00-020 | 08 71 00 | 20 | 0 | Door hardware | 08 Openings | Fit-out | Hardware schedule and product data | SD-03 Product data | Action | Sentry Systems | 2026-07-06 | 2026-07-07 | Architect | Sequential | 2026-07-28 | 2026-08-03 | Approved as Noted, Resubmit | 27 | Resubmittal required | Contractor | 12 | 2026-11-06 | 2026-07-19 | 13 | Long lead | No |  | EXAMPLE - hybrid action
22 | 09 30 00-021 | 09 30 00 | 21 | 0 | Tiling | 09 Finishes | Fit-out | Samples and setting-out drawings - wet areas | SD-04 Samples | Action | Surface Floors | 2026-08-03 | 2026-08-04 | Architect | Concurrent | 2026-08-19 |  |  | 8 | In review | Reviewer | 5 | 2026-11-13 | 2026-09-19 | 47 |  | No |  | EXAMPLE - in review
23 | 10 28 00-022 | 10 28 00 | 22 | 0 | Toilet and bath accessories | 10 Specialties | Fit-out | Product data and schedule | SD-03 Product data | Action | Interior Linings Co | 2026-07-27 | 2026-07-28 | Architect | Concurrent | 2026-08-12 | 2026-08-06 | Approved | 9 | Closed | Closed | 4 | 2026-11-20 | 2026-10-03 | 68 |  | No |  | EXAMPLE
24 | 01 78 23-023 | 01 78 23 | 23 | 0 | Operation and maintenance data | 01 General Requirements | Other | Draft O&M manual structure and contents list | SD-10 Operation and maintenance data | Closeout | Meridian Construction |  |  | Contract Administrator | Concurrent |  |  |  |  | Not submitted | Contractor | 0 |  |  |  |  | No |  | EXAMPLE - closeout, not submitted
25 | 01 78 36-024 | 01 78 36 | 24 | 0 | Warranties | 01 General Requirements | Other | Warranty schedule - all packages | SD-11 Closeout submittals | Closeout | Meridian Construction |  |  | Contract Administrator | Concurrent |  |  |  |  | Not submitted | Contractor | 0 |  |  |  |  | No |  | EXAMPLE - closeout, not submitted
26 | 11 53 00-025 | 11 53 00 | 25 | 0 | Laboratory fume cupboards | 11 Equipment | Specialist | Product data and shop drawings - fume cupboards | SD-03 Product data | Action | Lab Systems Group |  |  | Architect | Concurrent |  |  |  |  | Void | Closed | 16 | 2026-11-20 |  |  |  | No | Yes | EXAMPLE - scope deleted by variation, voided not deleted
Number each submittal off its specification section - the submittal number builds itself from the section, the sequence and the revision. Log the date RECEIVED separately from the date SUBMITTED: the review clock runs from receipt, and the gap between the two belongs to the Contractor. Raise the revision number rather than overwriting a row - the superseded row greys itself out and stays as the record. For A4, hide columns G, P, S, AC, AD and AE. The print area is set to the first 60 rows - extend it under Page Layout if your log runs longer.
Built with Mastt ¦ mastt.com
Formulas:
Review due = IF([Received for review]="","",[Received for review]+IF(N([Rev])>0,Setup!$D21,IF([Review route]="Sequential",Setup!$D20,Setup!$D19)))
Days in review = IF([Received for review]="","",IF([Returned]<>"",[Returned]-[Received for review],TODAY()-[Received for review]))
Latest submit by = IF(OR([Description of the submittal]="",[Required on site]="",[Lead time (weeks)]="",[Status]="Void",[Status]="Superseded"),"",[Required on site]-N([Lead time (weeks)])*7-IF([Review route]="Sequential",Setup!$D20,Setup!$D19)-Setup!$D22)
Float (days) = IF([Latest submit by]="","",IF([Submitted]<>"",[Latest submit by]-[Submitted],[Latest submit by]-TODAY()))

## Summary
SUBMITTAL LOG · SUMMARY
EXAMPLE DATA - 26 rows are worked examples. Delete them and this banner clears.
Every figure is a formula over the register. Open means anything not Closed, not Superseded and not Void.
WHERE THE LOG STANDS
Submittals on the log |  | 26 |  | Overdue with the reviewer |  | 3
Action submittals |  | 22 |  | Awaiting resubmittal |  | 2
Closed |  | 12 |  | Negative float - already late |  | 4
Open |  | 12 |  | Approved first time |  | 78.57%
Approved first time counts revision 00 items whose action let the work proceed without a resubmittal. Below about 60 per cent, the specification or the briefing of subcontractors is the problem, not the reviewer.
Package and division counts show OPEN items only.
BY STATUS |  |  |  | BY PACKAGE
Status | Items | Share |  | Package | Items | Share
Not submitted | 4 | 15.38% | ¦¦ | Structure | 0 | 0%
In review | 3 | 11.54% | ¦ | Envelope | 1 | 3.846%
Overdue with reviewer | 3 | 11.54% | ¦ | Fit-out | 4 | 15.38% | ¦¦
Resubmittal required | 2 | 7.692% | ¦ | Mechanical | 1 | 3.846%
Closed | 12 | 46.15% | ¦¦¦¦¦¦ | Electrical | 2 | 7.692% | ¦
Superseded | 1 | 3.846% |  | Hydraulic | 0 | 0%
Void | 1 | 3.846% |  | Fire | 1 | 3.846%
|  |  |  | Vertical transport | 0 | 0%
BY CLASS |  |  |  | Civil and external | 0 | 0%
Class | Items | Share |  | Landscape | 1 | 3.846%
Action | 22 | 84.62% | ¦¦¦¦¦¦¦¦¦¦ | Specialist | 0 | 0%
Informational | 2 | 7.692% | ¦ | Other | 2 | 7.692% | ¦
Closeout | 2 | 7.692% | ¦
BY DIVISION
BY BALL IN COURT |  |  |  | Division | Items | Share
Ball In Court | Items | Share |  | 00 Procurement and Contracting Requirements | 0 | 0%
Contractor | 6 | 23.08% | ¦¦¦ | 01 General Requirements | 2 | 7.692% | ¦
Reviewer | 6 | 23.08% | ¦¦¦ | 02 Existing Conditions | 0 | 0%
Closed | 14 | 53.85% | ¦¦¦¦¦¦ | 03 Concrete | 0 | 0%
|  |  |  | 04 Masonry | 0 | 0%
AGEING OF ITEMS WITH THE REVIEWER |  |  |  | 05 Metals | 0 | 0%
Days in review | Items | Share |  | 06 Wood, Plastics and Composites | 0 | 0%
0 - 7 days | 0 | 0% |  | 07 Thermal and Moisture Protection | 0 | 0%
8 - 14 days | 2 | 33.33% | ¦¦¦¦¦¦¦¦¦ | 08 Openings | 2 | 7.692% | ¦
15 - 21 days | 2 | 33.33% | ¦¦¦¦¦¦¦¦¦ | 09 Finishes | 3 | 11.54% | ¦
22 - 30 days | 1 | 16.67% | ¦¦¦¦ | 10 Specialties | 0 | 0%
Over 30 days | 1 | 16.67% | ¦¦¦¦ | 11 Equipment | 0 | 0%
|  |  |  | 12 Furnishings | 0 | 0%
|  |  |  | 13 Special Construction | 0 | 0%
Days in review runs from the date received, and keeps running until the item is returned. Anything past the review period in your specification is a reviewer delay you can evidence; anything sitting unsubmitted with negative float is a Contractor delay you can evidence. The log is only worth what its dates are worth. |  |  |  | 14 Conveying Equipment | 0 | 0%
|  |  |  | 21 Fire Suppression | 1 | 3.846%
|  |  |  | 22 Plumbing | 0 | 0%
|  |  |  | 23 Heating, Ventilating and Air Conditioning | 1 | 3.846%
|  |  |  | 25 Integrated Automation | 0 | 0%
|  |  |  | 26 Electrical | 1 | 3.846%
|  |  |  | 27 Communications | 0 | 0%
|  |  |  | 28 Electronic Safety and Security | 1 | 3.846%
|  |  |  | 31 Earthwork | 0 | 0%
|  |  |  | 32 Exterior Improvements | 1 | 3.846%
|  |  |  | 33 Utilities | 0 | 0%
|  |  |  | 34 Transportation | 0 | 0%
|  |  |  | 35 Waterway and Marine Construction | 0 | 0%
|  |  |  | 40 Process Interconnections | 0 | 0%
|  |  |  | 41 Material Processing and Handling Equipment | 0 | 0%
|  |  |  | 42 Process Heating, Cooling and Drying Equipment | 0 | 0%
|  |  |  | 43 Process Gas and Liquid Handling and Storage | 0 | 0%
|  |  |  | 44 Pollution and Waste Control Equipment | 0 | 0%
|  |  |  | 45 Industry-Specific Manufacturing Equipment | 0 | 0%
|  |  |  | 46 Water and Wastewater Equipment | 0 | 0%
|  |  |  | 48 Electrical Power Generation | 0 | 0%
Built with Mastt ¦ mastt.com

## Reference
SUBMITTAL LOG · REFERENCE
Every dropdown in the workbook is sourced from this sheet. Add your own values inside the ranges, not below them.
Division |  | Submittal type | Review action - all sets | Package
00 Procurement and Contracting Requirements |  | SD-01 Preconstruction submittals | A1 Authorised and accepted | Structure
01 General Requirements |  | SD-02 Shop drawings | A2 Authorised with minor comments | Envelope
02 Existing Conditions |  | SD-03 Product data | Accepted | Fit-out
03 Concrete |  | SD-04 Samples | Approved | Mechanical
04 Masonry |  | SD-05 Design data and calculations | Approved as Noted | Electrical
05 Metals |  | SD-06 Test reports | Approved as Noted, Resubmit | Hydraulic
06 Wood, Plastics and Composites |  | SD-07 Certificates | Approved as Submitted | Fire
07 Thermal and Moisture Protection |  | SD-08 Manufacturer's instructions | B1 Accepted with comments | Vertical transport
08 Openings |  | SD-09 Manufacturer's field reports | B2 Rejected - resubmit | Civil and external
09 Finishes |  | SD-10 Operation and maintenance data | Information Only | Landscape
10 Specialties |  | SD-11 Closeout submittals | Make Corrections Noted | Specialist
11 Equipment |  | Mock-up or field sample | No Exceptions Taken | Other
12 Furnishings |  | Design mix | Not Acceptable
13 Special Construction |  | Delegated design | Not Approved
14 Conveying Equipment |  | Schedule or register | Receipt Acknowledged
21 Fire Suppression |  |  | Rejected
22 Plumbing |  |  | Reviewed for Record Only
23 Heating, Ventilating and Air Conditioning |  |  | Revise and Resubmit
25 Integrated Automation |  |  | S4 Issued for stage approval
26 Electrical |  |  | S6 Issued for PIM authorisation
27 Communications |  |  | Submit Specified Item
28 Electronic Safety and Security
31 Earthwork
32 Exterior Improvements
33 Utilities
34 Transportation
35 Waterway and Marine Construction
40 Process Interconnections
41 Material Processing and Handling Equipment
42 Process Heating, Cooling and Drying Equipment
43 Process Gas and Liquid Handling and Storage
44 Pollution and Waste Control Equipment
45 Industry-Specific Manufacturing Equipment
46 Water and Wastewater Equipment
48 Electrical Power Generation
Status |  | Action set in use | Class | Review route
Not submitted |  | A - EJCDC (recommended) | Action | Concurrent
In review |  | B - Conventional architectural | Informational | Sequential
Overdue with reviewer |  | C - UFGS federal | Closeout
Resubmittal required |  | D - ISO 19650 suitability |  | Yes / No
Closed |  |  |  | Yes
Superseded |  |  |  | No
Void
TYPE TO CLASS - the register reads this
SD-01 Preconstruction submittals |  | Action
SD-02 Shop drawings |  | Action
SD-03 Product data |  | Action
SD-04 Samples |  | Action
SD-05 Design data and calculations |  | Action
SD-06 Test reports |  | Informational
SD-07 Certificates |  | Informational
SD-08 Manufacturer's instructions |  | Informational
SD-09 Manufacturer's field reports |  | Informational
SD-10 Operation and maintenance data |  | Closeout
SD-11 Closeout submittals |  | Closeout
Mock-up or field sample |  | Action
Design mix |  | Action
Delegated design |  | Action
Schedule or register |  | Informational
ACTIONS THAT CLOSE AN ITEM - the register reads this |  | ACTIONS THAT COUNT AS APPROVED FIRST TIME
Approved |  | Approved
Approved as Noted |  | Approved as Noted
Approved as Submitted |  | Approved as Submitted
Accepted |  | Accepted
No Exceptions Taken |  | No Exceptions Taken
Make Corrections Noted |  | Make Corrections Noted
Receipt Acknowledged |  | A1 Authorised and accepted
Information Only |  | A2 Authorised with minor comments
Reviewed for Record Only
A1 Authorised and accepted
A2 Authorised with minor comments
THE FOUR REVIEW ACTION SETS - pick one on Setup and stay with it
A - EJCDC (recommended) | Approved · Approved as Noted · Revise and Resubmit · Rejected, plus Accepted / Not Acceptable for informational and closeout items. EJCDC argues against 'No Exceptions Taken', 'Reviewed' and 'Furnish as Submitted' - it calls them weasel words that give no good answer under cross-examination, and cites the Hyatt Regency walkway collapse where the court treated 'Reviewed' and 'Approved' as the same thing. Both AIA A201 and EJCDC C-700 use 'approve'.
B - Conventional architectural | No Exceptions Taken · Make Corrections Noted · Approved as Noted, Resubmit · Revise and Resubmit · Rejected · Submit Specified Item · Reviewed for Record Only. Widely used in US architectural practice, but the wording is not standardised and every office varies it. Note that 'Make Corrections Noted' and 'Approved as Noted, Resubmit' are different actions - one lets work proceed, the other does not.
C - UFGS federal | Used on USACE, NAVFAC and AFCEC work. Approved · Approved as Noted · Approved as Submitted · Not Approved, with Receipt Acknowledged and Information Only for items needing no action.
D - ISO 19650 suitability | For projects running a BIM Execution Plan under ISO 19650. Information is exchanged with a suitability code rather than a review stamp - A codes are authorised, B codes are shared with comment, S codes are work in progress or shared for a defined purpose. Use this set where the common data environment governs, not a submittal stamp.
MAPPING TO ISO 19650 SUITABILITY CODES
US review action |  | ISO 19650 suitability | What it means
Approved / No Exceptions Taken |  | A1 Authorised and accepted | Status A - approved, no comments. Work may proceed.
Approved as Noted / Make Corrections Noted |  | A2 Authorised with minor comments | Status B - approved subject to the comments marked. Work may proceed, corrections mandatory.
Approved as Noted, Resubmit |  | B1 Accepted with comments | Status B with a resubmittal required before the work proceeds.
Revise and Resubmit |  | B2 Rejected - resubmit | Status C - not approved. Correct and resubmit.
Rejected / Submit Specified Item |  | B2 Rejected - resubmit | Status C. Rejected outright, or the specified item was not offered.
Reviewed for Record Only / Information Only |  | S4 or S6 issued for information | Status D - for information. No responsive action, no approval implied.
SUBMITTAL CLASS - what it changes
Action | Requires the reviewer to take a responsive action. Gets a disposition code, blocks fabrication until returned, and counts in the turnaround metrics. Shop drawings, product data, samples, design data, design mixes, delegated design.
Informational | Written information that needs no responsive action - it is received and acknowledged. Qualifications, certificates, test reports, field reports, manufacturer's instructions. Do not measure a reviewer's turnaround on these.
Closeout | Specified separately and delivered at the end - O&M data, warranties, record drawings, spare parts, training. Put them on the log from day one; they are the items that hold up the final certificate.
STATUS DEFINITIONS
Not submitted | On the log, not yet issued by the Contractor. Its float is already running down.
In review | With the reviewer, inside the review period.
Overdue with reviewer | Past the review due date. This is the column that supports - or defeats - a delay claim founded on slow review.
Resubmittal required | Returned with an action that requires it to come back. The revision number goes up and the clock starts again.
Closed | Returned with an action that lets the work proceed. No further submittal due.
Superseded | A later revision of the same specification section and sequence number is on the log. Set automatically - the row greys out and stays as the record of what was issued and when.
Void | Withdrawn, cancelled or no longer required - set the Void column to Yes. The row stays on the log and drops out of every open count.
CELL CONVENTIONS
You complete this | Pale blue fill, blue text.
Calculated | Grey fill. A formula - do not type over it.
Subtotal or total | Light grey with a rule above.
Section band | Marks the start of a section.
TERMINOLOGY - this log is written for a global audience
Contract Administrator / Owner's Representative | The party who reviews and returns submittals. Called the Architect, the Engineer, the Superintendent or the Contract Administrator depending on your contract.
Submittal | Called a technical submission, a design submission or simply a submission outside the United States. Same thing.
Specification section | The six-digit MasterFormat number, e.g. 03 30 00. Outside the US, use your own specification reference - the log does not care, it only concatenates it into the submittal number.
Program / Schedule | Both mean the dated plan of works.
Built with Mastt ¦ mastt.com