Project Controls · Monthly Reporting

MONTHLY REPORT

# Monthly Project Report

Prepared for the Client by the Project Manager

| PROJECT NAME | [Insert project name] |
| --- | --- |
| PROJECT NUMBER | [Insert project / job number] |
| CLIENT | [Insert client / principal entity name] |
| REPORT NUMBER | [e.g. MPR-014] |
| REPORTING PERIOD | [e.g. 1 – 31 Month YYYY] |
| DATA CUT-OFF DATE | [DD Month YYYY] |
| PROJECT MANAGER | [Name, company] |
| PREPARED BY | [Name, role] |
| ISSUE DATE | [DD Month YYYY] |
| REVISION | [e.g. A / 1.0] |

DISTRIBUTION

[List recipients — name, organisation, role. e.g. Client Project Director; Client Representative; Superintendent; Head Contractor Project Manager; Design Manager; Financier's Technical Adviser]

Commercial-in-confidence. This report is prepared for the addressees named above and must not be relied upon by any other party without the written consent of the issuing party. All monetary values are shown in ¤ (replace with the project currency) and are exclusive of applicable taxes unless stated otherwise.

# Document Control

This page records the revision history, distribution and confidentiality status of the report. Complete it before every issue.

## Revision history

| Rev | Date | Prepared | Reviewed | Approved | Description of change |
| --- | --- | --- | --- | --- | --- |
| A | [DD/MM/YY] | [Initials] | [Initials] | [Initials] | First issue — draft for internal review |

Example row shown in grey italic — delete before use.

## Distribution

| # | Name | Organisation | Role | Format | Date issued |
| --- | --- | --- | --- | --- | --- |
| 1 | [Name] | [Client entity] | Project Director | PDF | [DD/MM/YY] |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

## Confidentiality and reliance

This report is commercial-in-confidence and is issued solely for the internal management of the project by the parties listed in the distribution table. It contains forecasts and estimates that are based on information available at the data cut-off date; those forecasts are subject to change as the works progress. No warranty is given that forecast outcomes will be achieved. The report is not a certificate, a determination, a direction, or a notice under the contract, and nothing in it varies the rights or obligations of any party under the contract. Reproduction or distribution beyond the named recipients requires the prior written consent of the issuing party.

STATUS OF THIS ISSUE

| Data cut-off | Basis of cost data | Basis of programme data | Next report due |
| --- | --- | --- | --- |
| [DD/MM/YY] | [e.g. Payment claim / certificate no. XX] | [e.g. Contractor programme rev. XX dated DD/MM/YY] | [DD/MM/YY] |

# Contents

The contents list below is a live Word field. Click in it and press F9 (or right-click → Update Field → Update entire table) to refresh page numbers after editing.

Right-click and choose Update Field (or press F9) to build the table of contents.

# 1. Executive Summary

A one-page summary written for the Client's decision-makers. State where the project stands against time, cost and quality, what changed this month, and what is needed from the Client.

[Insert commentary — describe the overall status of the project in three to five sentences: the headline programme position (ahead/behind and by how many days), the headline cost position (forecast final cost versus approved budget), the most significant event of the month, and the single greatest threat to the objectives.]

## 1.1 Project health dashboard

| Area | Status | Trend | Commentary |
| --- | --- | --- | --- |
| Safety | GREEN | ► | [One line — e.g. no recordable injuries this period; LTIFR steady.] |
| Programme | AMBER | ▼ | [One line — e.g. 9 days behind on the façade path; recovery plan requested.] |
| Cost | AMBER | ► | [One line — e.g. forecast final cost within contingency; 62% of contingency drawn.] |
| Quality | GREEN | ▲ | [One line — e.g. NCRs closed out ahead of the 21-day target.] |
| Risk | AMBER | ► | [One line — e.g. two extreme risks remain open; both have owners and dates.] |
| Stakeholder | GREEN | ► | [One line — e.g. no complaints received; authority approvals on track.] |

Key:  Green = on target, no action required.   Amber = at risk, mitigation in place and being tracked.   Red = off target, Client action or decision required.   Trend ▲ improving · ► stable · ▼ deteriorating (movement since last report).

## 1.2 Top three issues requiring Client decision this month

| # | Issue | Impact if not resolved | Decision required | By when |
| --- | --- | --- | --- | --- |
| 1 | [Issue title] | [Cost / time / quality impact, quantified] | [The specific decision or instruction sought] | [DD/MM/YY] |
| 2 |  |  |  |  |
| 3 |  |  |  |  |

## 1.3 Changes since last report

[Insert commentary — list only what materially changed: new approvals, new variations, milestone movement, risk escalations or closures, and any change to the forecast final cost or completion date. Keep to five bullet points.]

# 2. Key Project Data

Snapshot of the contractual, cost and time position at the data cut-off date. Every figure in this table must be traceable to a source document.

| Metric | Value | Source |
| --- | --- | --- |
| Contract sum (original, excl. taxes) | ¤ [0.00] | [Contract execution] |
| Approved variations to date | ¤ [0.00] | [Variation register] |
| Current contract sum | ¤ [0.00] | [Auto: original + approved variations] |
| Pending / assessed variations | ¤ [0.00] | [Variation register] |
| Forecast final cost (out-turn) | ¤ [0.00] | [Cost report] |
| Approved project budget | ¤ [0.00] | [Client budget approval] |
| Variance to budget (over / under) | ¤ [0.00] ([0.0]%) | [Auto: budget − forecast] |
| Contingency — original allowance | ¤ [0.00] | [Budget] |
| Contingency — drawn to date | ¤ [0.00] ([0.0]%) | [Contingency register] |
| Contingency — remaining | ¤ [0.00] | [Auto] |
| Certified to date (works) | ¤ [0.00] | [Payment certificate no. [XX]] |
| Paid to date | ¤ [0.00] | [Client finance] |
| Retention / security held | ¤ [0.00] | [Contract cl. [XX]] |
| Progress — planned % complete | [0.0]% | [Baseline programme] |
| Progress — actual % complete | [0.0]% | [Contractor progress claim] |
| Date for practical completion — contract | [DD/MM/YY] | [Contract, as extended] |
| Date for practical completion — forecast | [DD/MM/YY] | [Current programme rev. [XX]] |
| Extension of time granted to date | [0] days | [EOT register] |
| Extension of time claimed, not determined | [0] days | [EOT register] |
| Days ahead (+) / behind (−) programme | [0] days | [Auto: contract − forecast PC] |

Replace [ ] placeholders with project values. Rows marked "Auto" are calculated from other rows — keep them consistent. All values in ¤ (project currency) excluding taxes unless noted.

## 2.1 Commentary on the key data

[Insert commentary — explain any movement greater than the reporting threshold (e.g. ±1% of contract sum or ±5 days) since the last report, and state the recovery or corrective action.]

# 3. Health, Safety & Environment

Safety performance is reported first because it takes precedence over time and cost. Report leading indicators (inductions, toolbox talks, inspections) alongside lagging indicators (injuries, incidents).

## 3.1 HSE statistics

| Indicator | This period | Project to date | Comment |
| --- | --- | --- | --- |
| Hours worked on site | [0] | [0] |  |
| Personnel inducted | [0] | [0] |  |
| Toolbox talks / pre-start briefings | [0] | [0] |  |
| Safety inspections / audits completed | [0] | [0] |  |
| Lost time injuries (LTI) | [0] | [0] |  |
| Medical treatment injuries (MTI) | [0] | [0] |  |
| First aid injuries (FAI) | [0] | [0] |  |
| Near misses reported | [0] | [0] |  |
| Hazards / unsafe acts reported | [0] | [0] |  |
| Days lost to injury | [0] | [0] |  |
| LTIFR (per 1,000,000 hours worked) | [0.0] | [0.0] |  |
| TRIFR (per 1,000,000 hours worked) | [0.0] | [0.0] |  |
| Environmental incidents (reportable) | [0] | [0] |  |
| Environmental non-conformances (internal) | [0] | [0] |  |
| Noise / dust / water quality exceedances | [0] | [0] |  |
| Stop-work events | [0] | [0] |  |
| Regulator / authority site visits | [0] | [0] |  |

LTIFR = lost time injuries × 1,000,000 ÷ hours worked. TRIFR = (LTI + MTI + restricted work cases) × 1,000,000 ÷ hours worked. State the denominator convention used if it differs. Report against the project's own HSE targets.

## 3.2 Incident narrative

[Insert commentary — for each recordable incident this period: date, location, brief factual description, immediate cause, corrective action taken, and whether the investigation is open or closed. Do not include personal or identifying information.]

## 3.3 Environmental performance

[Insert commentary — condition of environmental controls, waste diverted from landfill, water and energy use, and any complaint or exceedance and how it was closed out.]

## 3.4 HSE focus for the next period

| Focus area | Why | Action / owner | Target date |
| --- | --- | --- | --- |
| Working at height — façade installation | New high-risk activity commencing | Verify SWMS and edge protection prior to start — [Owner] | [DD/MM/YY] |

# 4. Programme & Progress

## 4.1 Works completed this period

[Insert commentary — list the work physically completed this period by area or trade package. Be specific and measurable (e.g. "Level 3 slab poured 12/MM; 78 of 96 façade panels installed").]

## 4.2 Works planned next period

[Insert commentary — the work planned for the next reporting period, the resources committed to it, and the pre-conditions that must be met (approvals, information, access, long-lead deliveries).]

## 4.3 Milestone status

| Milestone | Contract date | Forecast / actual | Variance (days) | Status |
| --- | --- | --- | --- | --- |
| Site possession | [DD/MM/YY] | [DD/MM/YY] | 0 | Achieved |
| Design documentation complete | [DD/MM/YY] | [DD/MM/YY] | [0] | [On track] |
| Structure complete | [DD/MM/YY] | [DD/MM/YY] | [0] | [At risk] |
| Building watertight | [DD/MM/YY] | [DD/MM/YY] | [0] | [On track] |
| Services energised | [DD/MM/YY] | [DD/MM/YY] | [0] | [On track] |
| Commissioning complete | [DD/MM/YY] | [DD/MM/YY] | [0] | [On track] |
| Practical completion | [DD/MM/YY] | [DD/MM/YY] | [0] | [On track] |
| Defects liability period ends | [DD/MM/YY] | [DD/MM/YY] | [0] | [Not started] |

Variance: negative = late against the contract date (as extended). Status: Achieved / On track / At risk / Delayed / Not started.

## 4.4 Critical path commentary

[Insert commentary — identify the current critical path and the total float on the near-critical paths. State whether the critical path has changed since last report and why. Name the activities driving practical completion and the recovery measures being applied (re-sequencing, additional resources, extended hours) with their expected effect in days.]

## 4.5 Delay events and extension of time claims

| Ref | Delay event | Date notified | Days claimed | Days granted | Cost claimed | Status |
| --- | --- | --- | --- | --- | --- | --- |
| EOT-01 | Inclement weather — [month] | [DD/MM/YY] | [0] | [0] | ¤ [0.00] | Assessed |

Status: Notified / Under assessment / Assessed / Granted / Rejected / Withdrawn. Record the contractual basis of each claim and the date by which a determination is required under the contract.

## 4.6 Programme snapshot

[Insert programme snapshot — paste the summary bar chart or S-curve here. Recommended: level-2 summary programme showing baseline versus actual, with the data date marked. Size to the full text width.]

Figure 4.1 — Summary programme / S-curve, planned versus actual progress at [data cut-off date].

# 5. Cost & Commercial

## 5.1 Cost summary by cost centre

| # | Cost centre | Budget | Committed | Expended | Forecast final | Variance |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Land and acquisition costs | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 2 | Consultant and design fees | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 3 | Authority and approval fees | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 4 | Site preparation and early works | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 5 | Construction — head contract | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 6 | Construction — direct / client packages | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 7 | Client-supplied items (FF&E, ICT) | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 8 | Client-side management costs | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 9 | Contingency | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| 10 | Escalation allowance | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
|  | TOTAL | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |

Committed = value of executed contracts and purchase orders. Expended = certified and invoiced to date. Forecast final = committed + estimated cost to complete + assessed risk allowance. Variance = budget − forecast final; a negative figure is an overrun.

## 5.2 Variations summary

| Status | This period (no.) | This period (value) | To date (no.) | To date (value) |
| --- | --- | --- | --- | --- |
| Approved | [0] | ¤ [0.00] | [0] | ¤ [0.00] |
| Pending assessment | [0] | ¤ [0.00] | [0] | ¤ [0.00] |
| Submitted, awaiting Client decision | [0] | ¤ [0.00] | [0] | ¤ [0.00] |
| Rejected / withdrawn | [0] | ¤ [0.00] | [0] | ¤ [0.00] |
| Anticipated (not yet submitted) | [0] | ¤ [0.00] | [0] | ¤ [0.00] |

## 5.3 Significant variations this period

| Ref | Description | Originator | Value | Time impact | Status |
| --- | --- | --- | --- | --- | --- |
| VAR-018 | Additional ground improvement — grid C4–F7 | Client-initiated | ¤ [0.00] | [0] days | Approved |

## 5.4 Provisional sums and prime cost items

| Item | Allowance | Expended / adjusted | Balance | Status | Date required |
| --- | --- | --- | --- | --- | --- |
| PS-03 — External landscaping | ¤ [0.00] | ¤ [0.00] | ¤ [0.00] | Open | [DD/MM/YY] |

Status: Open / Instructed / Expended / Closed out. Note the date by which the Client must instruct the item so as not to affect the programme.

## 5.5 Cash flow

| Period | Planned | Actual / certified | Variance | Cumulative planned | Cumulative actual |
| --- | --- | --- | --- | --- | --- |
| [Month −2] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| [Month −1] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| [This month] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] | ¤ [0] |
| [Month +1] (forecast) | ¤ [0] | — | — | ¤ [0] | — |
| [Month +2] (forecast) | ¤ [0] | — | — | ¤ [0] | — |

[Insert cash flow chart — planned versus actual expenditure, cumulative S-curve with the current month marked.]

Figure 5.1 — Cash flow, planned versus actual to [data cut-off date].

## 5.6 Contingency register summary

| Ref | Draw description | Date approved | Amount | Contingency remaining |
| --- | --- | --- | --- | --- |
| CON-05 | Latent condition — rock excavation grid B2 | [DD/MM/YY] | ¤ [0.00] | ¤ [0.00] |
|  | TOTAL DRAWN TO DATE |  | ¤ [0.00] | ¤ [0.00] |

## 5.7 Commercial commentary

[Insert commentary — explain the movement in forecast final cost since the last report, the drivers of any overrun, the adequacy of the remaining contingency against the residual risk exposure, the status of payment claims and certificates, and any notices, claims or disputes on foot.]

# 6. Design & Documentation

## 6.1 Design status by discipline

| Discipline | Current stage | % complete | Issued for construction | Status | Comment |
| --- | --- | --- | --- | --- | --- |
| Architectural | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Structural | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Civil | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Mechanical | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Electrical | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Hydraulic | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Fire | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Façade | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Landscape | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |
| Specialist / other | [e.g. IFC] | [0]% | [DD/MM/YY] | [On track] |  |

Stage: Concept / Schematic / Developed / Detailed / IFC (issued for construction) / As-built. Status: On track / At risk / Late.

## 6.2 Outstanding information — RFI register summary

| Measure | This period | Project to date | Comment |
| --- | --- | --- | --- |
| RFIs raised | [0] | [0] |  |
| RFIs answered | [0] | [0] |  |
| RFIs open at period end | [0] | — |  |
| Open > 14 days | [0] | — | [Escalate — impacting the critical path?] |
| Average response time (days) | [0] | [0] | [Target: [X] days] |

## 6.3 Critical outstanding information

| RFI / ref | Subject | Raised | Responsible | Date required | Programme impact |
| --- | --- | --- | --- | --- | --- |
| RFI-112 | Confirmation of slab set-down at wet areas | [DD/MM/YY] | Architect | [DD/MM/YY] | Critical path — 4 days |

## 6.4 Consultant deliverables due

| Deliverable | Consultant | Due date | Status |
| --- | --- | --- | --- |
| Façade shop drawing review — package 3 | Façade engineer | [DD/MM/YY] | In progress |

## 6.5 Design changes and their impact

| Ref | Design change | Reason | Cost impact | Time impact | Approval status |
| --- | --- | --- | --- | --- | --- |
| DC-07 | Substitution of ceiling system in public areas | Availability / lead time | ¤ [0.00] | [0] days | Client approved |

# 7. Procurement & Contracts

## 7.1 Packages awarded this period

| Package | Contractor / supplier | Award date | Award value | Budget | Variance |
| --- | --- | --- | --- | --- | --- |
| Structural steel | [Company] | [DD/MM/YY] | ¤ [0.00] | ¤ [0.00] | ¤ [0.00] |

## 7.2 Packages to be awarded

| Package | Budget | Tender issue | Tender close | Award required by | Status |
| --- | --- | --- | --- | --- | --- |
| Vertical transportation | ¤ [0.00] | [DD/MM/YY] | [DD/MM/YY] | [DD/MM/YY] | Tendering |

"Award required by" is the latest date the package can be awarded without delaying the critical path, allowing for shop drawings, fabrication and delivery.

## 7.3 Long-lead items

| Item | Lead time | Order placed | Required on site | Forecast delivery | Float |
| --- | --- | --- | --- | --- | --- |
| Main switchboard | [00] weeks | [DD/MM/YY] | [DD/MM/YY] | [DD/MM/YY] | [0] days |

## 7.4 Contract status

| Contract / party | Type | Contract sum | Executed | Security held | Insurances current | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Head contract — [Company] | Lump sum D&C | ¤ [0.00] | [DD/MM/YY] | ¤ [0.00] | Yes — expires [DD/MM/YY] | Active |

Confirm each month that contract security and insurances remain current and that any expiring instrument has been renewed or replaced.

# 8. Quality

## 8.1 Quality statistics

| Measure | This period | Project to date | Open at period end | Comment |
| --- | --- | --- | --- | --- |
| ITPs issued / approved | [0] | [0] | [0] |  |
| ITP hold points released | [0] | [0] | [0] |  |
| Witness points attended | [0] | [0] | — |  |
| Non-conformance reports raised | [0] | [0] | [0] |  |
| Non-conformance reports closed | [0] | [0] | — |  |
| NCRs open > 30 days | — | — | [0] | [Escalate to the Client] |
| Defects identified | [0] | [0] | [0] |  |
| Defects rectified | [0] | [0] | — |  |
| Surveillance inspections | [0] | [0] | — |  |
| Test results received / passed | [0]/[0] | [0]/[0] | — |  |

## 8.2 Non-conformances — ageing and status

| NCR ref | Description | Raised | Days open | Severity | Responsible | Status |
| --- | --- | --- | --- | --- | --- | --- |
| NCR-021 | Cover to reinforcement below specification — level 2 slab band | [DD/MM/YY] | [00] | Major | Head contractor | Open — engineered solution submitted |

Severity: Minor / Major / Critical. Ageing bands to report: 0–14, 15–30, > 30 days.

## 8.3 Key inspections, hold and witness points next period

| Activity | Type | Scheduled date | Attendees required | Notice given |
| --- | --- | --- | --- | --- |
| Level 4 slab pre-pour | Hold point | [DD/MM/YY] | Superintendent, structural engineer | Yes |

## 8.4 Testing and commissioning status

| System | Pre-commissioning | Commissioning | Witnessing | Documentation | Status |
| --- | --- | --- | --- | --- | --- |
| [Mechanical] | [0]% | [0]% | [Not started] | [0]% | [On track] |
| [Electrical] | [0]% | [0]% | [Not started] | [0]% | [On track] |
| [Hydraulic] | [0]% | [0]% | [Not started] | [0]% | [On track] |
| [Fire and life safety] | [0]% | [0]% | [Not started] | [0]% | [On track] |
| [Vertical transportation] | [0]% | [0]% | [Not started] | [0]% | [On track] |
| [Controls / BMS] | [0]% | [0]% | [Not started] | [0]% | [On track] |

## 8.5 Quality commentary

[Insert commentary — quality trends, repeat non-conformances and their root cause, adequacy of the contractor's quality system, and any workmanship issue that may affect handover or the defects liability period.]

# 9. Risks & Opportunities

This section is set landscape so that the risk register reads across a single page. Ratings follow the project risk matrix.

## 9.1 Top risks

| ID | Risk description | Cause | Consequence | L | C | Rating | Owner | Mitigation / treatment | Move |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-014 | Late delivery of the main switchboard delays energisation | Global supply constraint on switchgear | Delay to practical completion; extended preliminaries | 3 | 4 | High | [PM] | Weekly expediting with the supplier; interim supply option priced; re-sequence commissioning | ► |

L = likelihood (1 rare – 5 almost certain). C = consequence (1 insignificant – 5 severe). Rating = the project risk matrix result (Low / Medium / High / Extreme). Move = movement since the last report: ▲ increased · ► unchanged · ▼ reduced.

## 9.2 New risks this period

| ID | Risk description | Rating | Owner | Initial treatment |
| --- | --- | --- | --- | --- |

## 9.3 Risks closed this period

| ID | Risk description | Reason for closure | Date closed |
| --- | --- | --- | --- |

## 9.4 Opportunities

| ID | Opportunity | Potential benefit | Owner | Action to realise | Decision by |
| --- | --- | --- | --- | --- | --- |
| O-03 | Early release of the car park for temporary use | ¤ [0.00] revenue / earlier partial occupancy | [PM] | Confirm separable portion and certification path | [DD/MM/YY] |

## 9.5 Risk commentary

[Insert commentary — state whether the overall risk profile has improved or deteriorated, whether the remaining contingency adequately covers the residual quantified risk exposure, and which risks require a Client decision to treat.]

# 10. Stakeholder & Communications

## 10.1 Engagement activity this period

| Date | Stakeholder | Method | Subject | Outcome / follow-up |
| --- | --- | --- | --- | --- |
| [DD/MM/YY] | Adjoining occupiers | Letterbox notice | Night works — service connection | No objections received |

## 10.2 Complaints and enquiries

| Ref | Date | Nature | Source | Response / resolution | Status |
| --- | --- | --- | --- | --- | --- |

Record every complaint, the time to first response and the time to resolution. Report the running total for the project to date.

## 10.3 Authority and third-party approvals

[Insert commentary — status of engagement with authorities, utility providers and adjoining owners; any conditions of approval that remain outstanding; and the consequence of late approval on the programme.]

## 10.4 Media and public relations

[Insert commentary — media enquiries received, statements issued and by whom, publications, site signage and community notices. Confirm that all external communication has been approved by the Client's communications representative.]

# 11. Approvals & Permits

Track every approval, permit, licence and consent required to construct, occupy and operate the asset — including its expiry and any conditions that must be discharged.

| Ref | Approval / permit | Authority / issuer | Required by | Applied | Granted | Expires | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AP-01 | Development / planning consent | [Authority] | [Date] | [Date] | [Date] | [Date] | Granted |
| AP-02 | Construction / building permit | [Authority] | [Date] | [Date] | [Date] | [Date] | [Status] |
| AP-03 | Environmental / works approval | [Authority] | [Date] | [Date] | [Date] | [Date] | [Status] |
| AP-04 | Road / footpath occupation permit | [Authority] | [Date] | [Date] | [Date] | [Date] | [Status] |
| AP-05 | Utility connection agreements | [Provider] | [Date] | [Date] | [Date] | [Date] | [Status] |
| AP-06 | Crane / hoarding / scaffold licence | [Authority] | [Date] | [Date] | [Date] | [Date] | [Status] |
| AP-07 | Occupancy / completion certificate | [Authority] | [Date] | [Date] | [Date] | [Date] | [Status] |
| AP-08 |  |  |  |  |  |  |  |

## 11.1 Outstanding conditions of approval

[Insert commentary — list conditions that must be discharged before a milestone can be achieved (for example prior to occupation), who is responsible, and the date by which each must be satisfied.]

# 12. Photographs

Progress photographs taken during the reporting period. Take them from the same vantage points each month so that progress can be compared directly.

| [Insert photograph 1] |  | [Insert photograph 2] |
| --- | --- | --- |
| Photograph 1 — [Location / view — e.g. north elevation from Smith Street, looking south-west. Date DD/MM/YY.] |  | Photograph 2 — [Location / view. Date DD/MM/YY.] |
| [Insert photograph 3] |  | [Insert photograph 4] |
| Photograph 3 — [Location / view. Date DD/MM/YY.] |  | Photograph 4 — [Location / view. Date DD/MM/YY.] |

Add further photograph pages as required. Keep file sizes reasonable — compress images before inserting.

# 13. Actions & Decisions Required

## 13.1 Action register

| ID | Action | Owner | Raised | Due | Status |
| --- | --- | --- | --- | --- | --- |
| A-042 | Issue instruction for the ground improvement variation | [Client rep] | [DD/MM/YY] | [DD/MM/YY] | Open |

Status: Open / In progress / Closed / Overdue. Carry every open action forward to the next report until it is closed.

## 13.2 Decisions required from the Client this period

| ID | Decision required | Options / recommendation | Cost impact | Time impact | Required by |
| --- | --- | --- | --- | --- | --- |
| D-009 | Approve the ceiling system substitution in public areas | Recommend option B — meets specification, 3-week shorter lead time | ¤ [0.00] | [0] days saved | [DD/MM/YY] |

State clearly the consequence of a decision not being made by the required date — this is the single most useful column in the report.

# Appendices

Attach the supporting documents listed below. Delete any appendix that does not apply and renumber the remainder.

| Appendix | Document | Attached | Reference / revision |
| --- | --- | --- | --- |
| A | Current programme (level 2 or 3) with the data date marked | [Yes / No] | [Rev / date] |
| B | Detailed cost report and cost plan reconciliation | [Yes / No] | [Rev / date] |
| C | Variation register (full) | [Yes / No] | [Rev / date] |
| D | Risk register (full) | [Yes / No] | [Rev / date] |
| E | RFI register (full) | [Yes / No] | [Rev / date] |
| F | Non-conformance and defects register | [Yes / No] | [Rev / date] |
| G | HSE monthly report / statistics pack | [Yes / No] | [Rev / date] |
| H | Payment claim and payment certificate | [Yes / No] | [Rev / date] |
| I | Photographic record (full set) | [Yes / No] | [Rev / date] |
| J | Minutes of project control group / site meetings | [Yes / No] | [Rev / date] |
| K | [Other — specify] | [Yes / No] | [Rev / date] |

PREPARED BY

| Prepared by | Reviewed by | Approved for issue by |
| --- | --- | --- |
| [Name] [Role] [Date] | [Name] [Role] [Date] | [Name] [Role] [Date] |

End of report.