## Cover
Construction Material List / Material Schedule
Global template · jurisdiction-neutral · built for construction procurement & delivery control
PROJECT DETAILS
| PROJECT NAME | e.g. Northbank Health Precinct — Stage 2 |  | ROLE
| PROJECT NUMBER |  |  | DATE
| CLIENT |  |  | REVISION | A
| CONTRACTOR |  |  | CURRENCY | USD
| PACKAGE / TRADE |  |  | UNITS SYSTEM
PREPARED BY
HOW TO USE THIS TEMPLATE
1. Complete the Project Details above, including Currency and Units System — these labels flow through to the Dashboard and the Material Register headers.
2. Open the Lists sheet and tune the settings: long-lead threshold (days), default wastage %, and tax %. Extend the dropdown lists to suit your package.
3. Build the schedule on Material Register. Fill only the shaded input cells; the tinted columns (Qty to Order, Estimated Value, Expected Delivery, Float, Qty Delivered, Qty Outstanding, Balance to Order) calculate themselves.
4. Delete the twelve EXAMPLE rows (flagged in the Notes column) once you have entered real data — they are there to show the intended level of detail.
5. Record every receipt on the Delivery Log. Qty Delivered on the register is a SUMIF over that log, so never type over it — the log is the single source of truth for what has landed on site.
6. Review the Dashboard before each procurement or site meeting: long-lead exposure, items not yet ordered, overdue deliveries and shortfall quantities all update automatically.
7. Read Notes & Assumptions and adapt the template to your contract, procurement procedure and inspection & test plan (ITP) regime before issuing it.
REVISION HISTORY
| Rev | Date | Description of Change |  | Prepared By | Approved By
| A |  | Initial issue for project use
Mastt template · mastt.com · © 2026 Mastt

## Dashboard
Construction Material List / Material Schedule
Dashboard · every figure below is calculated from the Material Register
| Project: e.g. Northbank Health Precinct — Stage 2 | [5 empty] | Values in USD · read-only
HOW THESE FIGURES ARE CALCULATED
| Total Line Items |  | Total Estimated Value (USD) |  | Total Committed Value (USD) |  | • Estimated value = Qty to Order x Unit Rate • Committed value = Qty Ordered x Unit Rate — the value placed on order, not the value certified • Delivered value = Qty Delivered x Unit Rate, and Qty Delivered is a SUMIF over the Delivery Log • Qty to Order = Qty Required x (1 + Wastage %), rounded to 2 dp • Long-lead and overdue counts use the threshold on the Lists sheet and the dates on the register • Currency and tax rate come from the Cover and Lists sheets • Nothing here is typed in — to change a number, edit the Material Register
| 12 |  | 5384695.25 |  | 5015341.5
| Register rows with an Item No. |  | Qty to Order x Unit Rate, all rows |  | Qty Ordered x Unit Rate — placed on order
| Total Delivered Value (USD) |  | % Delivered by Value |  | Items Not Yet Ordered
| 439250 |  | 8.157% |  | 3
| Qty Delivered x Unit Rate, from Delivery Log |  | Delivered value / estimated value |  | Status = Not Started or To Be Ordered
| Long-Lead Items (>= 42 days) |  | Items Overdue vs Required On Site |  | Total Shortfall Qty
| 5 |  | 1 |  | 21819.2
| Lead time at or above the Lists threshold |  | Expected delivery later than required date |  | Sum of positive Qty Outstanding
| Estimated Value excl. Tax (USD) |  | Tax @ 10.0% (indicative) |  | Estimated Value incl. Tax (USD)
| 5384695.25 |  | 538469.53 |  | 5923164.78
| VALUE & QUANTITY BY CATEGORY | [5 empty] | COUNT BY STATUS
| Category | Qty Required | Qty Ordered | Qty Delivered | Qty Outstanding | Estimated Value (USD) | Status | Items | % of Items
| Civil & Earthworks | 0 | 0 | 0 | 0 | 0 | Not Started | 1 | 8.333%
| Concrete | 1250 | 1250 | 1030 | 257.5 | 238187.5 | To Be Ordered | 2 | 16.67%
| Reinforcement | 706 | 90 | 52 | 704.8 | 183255.25 | Ordered | 5 | 41.67%
| Structural Steel | 145 | 145 | 0 | 147.9 | 480675 | Part Delivered | 4 | 33.33%
| Masonry & Blockwork | 18500 | 19610 | 14000 | 5610 | 81381.5 | Delivered | 0 | 0%
| Timber & Carpentry | 0 | 0 | 0 | 0 | 0 | On Hold | 0 | 0%
| Roofing & Waterproofing | 4800 | 0 | 0 | 5184 | 196992 | Cancelled | 0 | 0%
| Façade & Cladding | 2650 | 2650 | 0 | 2703 | 3108450 | Total | 12 | 100%
| Doors, Windows & Hardware | 0 | 0 | 0 | 0 | 0
| Mechanical (HVAC) | 4 | 4 | 0 | 4 | 314000
| Electrical | 3801 | 3991 | 1200 | 2791 | 528040
| Hydraulic / Plumbing | 950 | 0 | 0 | 1007 | 42294
| Fire Services | 0 | 0 | 0 | 0 | 0
| Internal Finishes | 3100 | 3410 | 0 | 3410 | 211420
| Landscaping & External Works | 0 | 0 | 0 | 0 | 0
| Total | — | — | — | — | 5384695.25
Category and status rows follow the lists on the Lists sheet — add an option there and it appears here automatically. Quantities are summed within a category and will mix units of measure where a category uses more than one unit, so read them as indicative; only value is totalled.
| ESTIMATED VALUE BY CATEGORY | [5 empty] | ITEMS BY STATUS
Mastt template · mastt.com · © 2026 Mastt

## Material Register
Construction Material List / Material Schedule
Material Register · quantities, procurement status and delivery control
Project: e.g. Northbank Health Precinct — Stage 2 | [11 empty] | Shaded cells = your input. Tinted cells = auto-calculated, do not type over them. Qty Delivered is a SUMIF over the Delivery Log sheet.
Item No. | Category | Sub-category | Material / Product Description | Specification / Standard Ref | Manufacturer / Supplier | Supplier Part No. | Unit | Qty Required | Wastage % | Qty to Order | Unit Rate (USD) | Estimated Value (USD) | Qty Ordered | PO / Order Ref | Order Date | Lead Time (days) | Expected Delivery | Required On Site | Float (days) | Qty Delivered | Delivered Value (USD) | Qty Outstanding | Balance to Order | Status | Inspection / ITP Required (Y/N) | Approval Status | Storage Location | Responsible | Notes
MAT-001 | Concrete | Ready-mix | Ready-mix concrete, 40 MPa, 100 mm slump, 20 mm aggregate | Spec 03 30 00 / ISO 22965-2 | Regional Ready-Mix Co. | RMC-40-20-100 | m³ | 1250 | 3% | 1287.5 | 185 | 238187.5 | 1250 | PO-0142 | 2026-03-02 | 7 | 2026-03-09 | 2026-03-20 | 11 | 1030 | 190550 | 257.5 | 37.5 | Part Delivered | Yes | Approved | Direct to pour | Site Engineer | EXAMPLE — delete before use
MAT-002 | Reinforcement | Bar reinforcement | Deformed reinforcing bar, 500 MPa, 16 mm dia., bent & bundled to schedule | Spec 03 20 00 / ISO 6935-2 | Steel Reinforcing Supplies | RB-D500-16 | t | 86 | 5% | 90.3 | 1450 | 130935 | 90 | PO-0151 | 2026-03-09 | 14 | 2026-03-23 | 2026-04-03 | 11 | 52 | 75400 | 38.3 | 0.3 | Part Delivered | Yes | Approved | Laydown Area B | Site Engineer | EXAMPLE — delete before use
MAT-003 | Reinforcement | Mesh | Welded wire fabric mesh, 200 x 200 x 8 mm, 6.0 x 2.4 m sheets | Spec 03 20 00 / ISO 6935-3 | Steel Reinforcing Supplies | WWF-8-200 | Sheet | 620 | 7.5% | 666.5 | 78.5 | 52320.25 | 0 |  |  | 10 |  | 2026-04-24 |  | 0 | 0 | 666.5 | 666.5 | To Be Ordered | No | Submitted | Laydown Area B | Site Engineer | EXAMPLE — delete before use
MAT-004 | Structural Steel | Beams & columns | Hot-rolled structural sections, grade S355 / 350, shop-primed | Spec 05 12 00 / ISO 630 | Metro Structural Fabricators | SS-S355-UB | t | 145 | 2% | 147.9 | 3250 | 480675 | 145 | PO-0163 | 2026-03-16 | 63 | 2026-05-18 | 2026-06-01 | 14 | 0 | 0 | 147.9 | 2.9 | Ordered | Yes | Approved | Fabricator works | Structural Lead | EXAMPLE — delete before use
MAT-005 | Masonry & Blockwork | Blockwork | Hollow concrete masonry units, 390 x 190 x 190 mm, 15 MPa | Spec 04 22 00 / Manufacturer TDS | Cityblock Masonry | CMU-190-15 | No. | 18500 | 6% | 19610 | 4.15 | 81381.5 | 19610 | PO-0170 | 2026-04-06 | 21 | 2026-04-27 | 2026-05-15 | 18 | 14000 | 58100 | 5610 | 0 | Part Delivered | No | Approved | Laydown Area C | Blockwork Foreman | EXAMPLE — delete before use
MAT-006 | Roofing & Waterproofing | Membrane | Single-ply TPO roof membrane, 1.5 mm, mechanically fastened | Spec 07 54 23 / Manufacturer TDS | Apex Waterproofing Systems | TPO-15-MF | m² | 4800 | 8% | 5184 | 38 | 196992 | 0 |  |  | 35 |  | 2026-07-10 |  | 0 | 0 | 5184 | 5184 | To Be Ordered | Yes | Submitted | Level 8 store | Facade Lead | EXAMPLE — delete before use
MAT-007 | Façade & Cladding | Curtain wall | Unitised curtain wall panels, 1.5 x 3.6 m, double-glazed low-E | Spec 08 44 13 / Manufacturer TDS | Vertex Façade Systems | UCW-1536-LE | m² | 2650 | 2% | 2703 | 1150 | 3108450 | 2650 | PO-0158 | 2026-03-11 | 98 | 2026-06-17 | 2026-07-06 | 19 | 0 | 0 | 2703 | 53 | Ordered | Yes | Approved | Direct to hoist | Facade Lead | EXAMPLE — delete before use
MAT-008 | Mechanical (HVAC) | Air handling | Air handling unit, 6,000 L/s, DX coil, EC fans with VSD | Spec 23 73 00 / Manufacturer TDS | Thermaflow Mechanical | AHU-6000-DX | No. | 4 | 0% | 4 | 78500 | 314000 | 4 | PO-0166 | 2026-04-10 | 120 | 2026-08-08 | 2026-07-20 | -19 | 0 | 0 | 4 | 0 | Ordered | Yes | Approved | Plant room L10 | Mechanical Lead | EXAMPLE — delete before use
MAT-009 | Electrical | Cable | LV power cable, 4C + E, 185 mm², XLPE / PVC, 0.6/1 kV | Spec 26 05 19 / IEC 60502-1 | Circuitline Electrical Supply | CBL-4C185-XLPE | m | 3800 | 5% | 3990 | 96 | 383040 | 3990 | PO-0172 | 2026-04-20 | 28 | 2026-05-18 | 2026-06-15 | 28 | 1200 | 115200 | 2790 | 0 | Part Delivered | No | Approved | Container 3 | Electrical Lead | EXAMPLE — delete before use
MAT-010 | Electrical | Switchboard | Main switchboard, 2500 A, Form 3b, type-tested assembly | Spec 26 24 13 / IEC 61439-2 | Circuitline Electrical Supply | MSB-2500-F3B | No. | 1 | 0% | 1 | 145000 | 145000 | 1 | PO-0149 | 2026-03-05 | 140 | 2026-07-23 | 2026-08-14 | 22 | 0 | 0 | 1 | 0 | Ordered | Yes | Approved | Main switch room | Electrical Lead | EXAMPLE — delete before use
MAT-011 | Hydraulic / Plumbing | Pipework | Copper tube, DN50, Type B, hard drawn, with press fittings | Spec 22 11 16 / ISO 274 | Aquaflow Plumbing Supplies | CU-DN50-B | m | 950 | 6% | 1007 | 42 | 42294 | 0 |  |  | 12 |  | 2026-06-05 |  | 0 | 0 | 1007 | 1007 | Not Started | No | Not Required | Container 2 | Hydraulic Lead | EXAMPLE — delete before use
MAT-012 | Internal Finishes | Flooring | Porcelain floor tile, 600 x 600 mm, rectified, R10 slip rating | Spec 09 30 13 / ISO 13006 | Lumina Surfaces | PT-600-R10 | m² | 3100 | 10% | 3410 | 62 | 211420 | 3410 | PO-0181 | 2026-05-11 | 45 | 2026-06-25 | 2026-08-28 | 64 | 0 | 0 | 3410 | 0 | Ordered | Yes | Submitted | Level 3 store | Finishes Lead | EXAMPLE — delete before use
Mastt template · mastt.com · © 2026 Mastt
Note on K8: Qty to Order = ROUND(Qty Required x (1 + Wastage %), 2). Where Wastage % is blank the Default Wastage % on the Lists sheet is applied.
Note on U8: Qty Delivered is calculated as SUMIF over the Delivery Log sheet (matching on Item No.). Record receipts on the Delivery Log — do not type into this column.

## Delivery Log
Construction Material List / Material Schedule
Delivery Log · dated receiving record — the single source of truth for Qty Delivered
Project: e.g. Northbank Health Precinct — Stage 2 |  |  |  | One row per delivery. Qty Delivered on the Material Register is a SUMIF over column D of this sheet — record part deliveries as separate rows.
Date | Item No. | Description (auto) | Qty Received | Delivery Docket No. | Carrier | Received By | Condition on Arrival | Damage / Shortage Notes | ITP / Test Cert Received (Y/N) | Photo Ref
2026-03-18 | MAT-001 | Ready-mix concrete, 40 MPa, 100 mm slump, 20 mm aggregate | 420 | DKT-88112 | Regional Ready-Mix Co. | S. Okafor | Good |  | Yes | IMG-0311
2026-03-24 | MAT-001 | Ready-mix concrete, 40 MPa, 100 mm slump, 20 mm aggregate | 610 | DKT-88240 | Regional Ready-Mix Co. | S. Okafor | Good |  | Yes | IMG-0327
2026-03-30 | MAT-002 | Deformed reinforcing bar, 500 MPa, 16 mm dia., bent & bundled to schedule | 52 | DKT-41007 | Steel Reinforcing Supplies | L. Marchetti | Good |  | Yes | IMG-0402
2026-04-28 | MAT-005 | Hollow concrete masonry units, 390 x 190 x 190 mm, 15 MPa | 9800 | DKT-55214 | Cityblock Masonry | T. Nguyen | Minor Damage | Approx. 120 units chipped on one pallet — set aside for cutting, no credit sought. | No | IMG-0431
2026-05-12 | MAT-005 | Hollow concrete masonry units, 390 x 190 x 190 mm, 15 MPa | 4200 | DKT-55390 | Cityblock Masonry | T. Nguyen | Short Delivered | Docket 4,600 / counted 4,200 — 400 units short, supplier notified, credit note pending. | No | IMG-0468
2026-05-19 | MAT-009 | LV power cable, 4C + E, 185 mm², XLPE / PVC, 0.6/1 kV | 1200 | DKT-70155 | Circuitline Electrical Supply | P. Ramirez | Good | Drum test certificates received with delivery. | Yes | IMG-0502
Mastt template · mastt.com · © 2026 Mastt
Note on C8: Auto-filled by INDEX/MATCH from the Material Register once a valid Item No. is entered in column B.

## Lists
Construction Material List / Material Schedule
Lists · dropdown sources and calculation settings
SETTINGS — REFERENCED BY THE DASHBOARD AND THE MATERIAL REGISTER
| Long-Lead Threshold (days) | 42 | Any item whose Lead Time (days) is greater than or equal to this value is reported as long-lead on the Dashboard.
| Default Wastage % | 5% | Applied by the Qty to Order formula when the Wastage % cell on a register row is left blank. Enter 0% on the row to override.
| Tax % | 10% | Generic, jurisdiction-neutral tax rate used only for the indicative tax line on the Dashboard. Set to 0% where materials are quoted tax-inclusive or tax does not apply.
DROPDOWN SOURCE LISTS
To add an option, insert a row INSIDE a list (not at the end) so the validation range grows with it. Unit column C is the combined list used by the register.
| Category | Unit — All | Unit — Metric | Unit — Imperial | Status | Approval Status | Condition on Arrival | Currency | Yes / No | Units System
| Civil & Earthworks | m | m | ft | Not Started | Not Required | Good | AUD | Yes | Metric
| Concrete | m² | m² | ft² | To Be Ordered | Submitted | Minor Damage | NZD | No | Imperial
| Reinforcement | m³ | m³ | ft³ | Ordered | Approved | Major Damage | USD
| Structural Steel | mm | mm | in | Part Delivered | Rejected | Short Delivered | GBP
| Masonry & Blockwork | km | km | yd | Delivered | Resubmit | Rejected | EUR
| Timber & Carpentry | kg | kg | yd² | On Hold |  |  | CAD
| Roofing & Waterproofing | t | t | yd³ | Cancelled |  |  | SGD
| Façade & Cladding | L | L | lb |  |  |  | AED
| Doors, Windows & Hardware | kL | kL | ton (US) |  |  |  | ZAR
| Mechanical (HVAC) | LM | LM | gal
| Electrical | No. | No. | LF
| Hydraulic / Plumbing | Ea | Ea | No.
| Fire Services | Set | Set | Ea
| Internal Finishes | Lot | Lot | Set
| Landscaping & External Works | Pair | Pair | Lot
|  | Pack | Pack | Pair
|  | Bag | Bag | Pack
|  | Roll | Roll | Bag
|  | Sheet | Sheet | Roll
|  | Pallet | Pallet | Sheet
|  | Drum | Drum | Pallet
|  | Hr | Hr | Drum
|  | Day | Day | Hr
|  | ft |  | Day
ft²
ft³
in
yd
yd²
yd³
lb
ton (US)
gal
LF
Mastt template · mastt.com · © 2026 Mastt

## Notes & Assumptions
Construction Material List / Material Schedule
Notes & Assumptions · how this schedule is intended to be used
QUANTITIES, WASTAGE AND THE QUANTITY TO ORDER
| • | Qty Required is the net installed (measured) quantity taken from the drawings, models or bill of quantities. It is a user input and is never overwritten by this workbook.
| • | Wastage % covers cutting, breakage, over-order minimums and off-cuts. Qty to Order = ROUND(Qty Required x (1 + Wastage %), 2). Where the Wastage % cell on a row is left blank the Default Wastage % on the Lists sheet is applied, so set that default to the value your estimator has allowed and override it only on rows that behave differently.
| • | Supplier minimum order quantities, pack sizes and standard lengths are NOT applied automatically. Where a supplier sells in packs or full lengths, round Qty Required up yourself, or set the row's Wastage % so that Qty to Order lands on a whole pack.
| • | Units are selected from a combined metric and imperial list. Set the project Units System on the Cover sheet and keep every row consistent with it — the workbook does not convert between systems.
WHAT 'COMMITTED' MEANS
| • | Committed (ordered) value on the Dashboard is Qty Ordered x Unit Rate. It is the value the project has placed on order with suppliers, not the value certified for payment and not the value delivered to site.
| • | Estimated value is Qty to Order x Unit Rate — the expected total cost of the material at the current rate, before tax and before any delivery, storage or handling costs that are not in the rate.
| • | Balance to Order = Qty to Order − Qty Ordered. Any positive figure is unplaced procurement exposure and is highlighted. Qty Outstanding = Qty to Order − Qty Delivered, which is the physical shortfall still to arrive on site.
| • | Unit Rate is the delivered-to-site material rate in the project currency selected on the Cover sheet, exclusive of tax unless you state otherwise. Keep rates consistent — mixing ex-works and delivered rates makes the committed value meaningless.
| • | The Tax % on the Lists sheet is a single generic rate used only for the indicative tax line on the Dashboard. It is not a tax calculation, it does not handle mixed or exempt rates, and it should not be used for any tax return or claim.
LEAD TIME, FLOAT AND DELIVERY CONTROL
| • | Expected Delivery = Order Date + Lead Time (days), in calendar days. It does not allow for non-working days, shutdowns, customs clearance or shipping consolidation — extend the Lead Time to cover those.
| • | Required On Site is the date driven by the construction programme, ideally with the programme activity's own float already consumed. Float (days) = Required On Site − Expected Delivery. A negative float is shown in red and means the material will land late against the programme unless the order or the sequence changes.
| • | Long-lead items are those whose Lead Time is greater than or equal to the Long-Lead Threshold on the Lists sheet (42 days by default). Review this list at every procurement meeting — long-lead items are the usual root cause of programme delay.
| • | Qty Delivered on the Material Register is a SUMIF over the Delivery Log and must not be typed over. Every receipt, including part deliveries, is one dated row on the log. This keeps the register reconcilable against delivery dockets.
INSPECTION, TEST AND APPROVAL WORKFLOW
| • | Inspection / ITP Required (Y/N) flags materials that carry a hold or witness point in the project inspection and test plan, or that require test certificates, mill certificates or conformance documentation on delivery.
| • | Approval Status tracks the material submittal: Not Required, Submitted, Approved, Rejected or Resubmit. As a rule, no order should be placed on a row whose submittal is not Approved unless the contract expressly allows ordering at risk — record any such decision in the Notes column.
| • | On the Delivery Log, record whether the ITP or test certificate was received with the delivery. Material received without its documentation should be quarantined and the Condition on Arrival noted, not silently accepted.
| • | Condition on Arrival of Major Damage, Rejected or Short Delivered is highlighted. Raise the shortage or damage with the supplier the same day and record the docket number, the counted quantity and the credit or replacement action in the notes.
DATA INTEGRITY AND HOUSEKEEPING
| • | Only the pale shaded cells are inputs. The tinted columns are formulas and the sheets are protected (no password) so they cannot be overwritten by accident. Filtering, sorting, selecting and resizing all remain available; to change a formula, unprotect the sheet from Review > Unprotect Sheet.
| • | Item No. must be unique — it is the key used by the Delivery Log lookup and by the SUMIF that returns Qty Delivered. Duplicated item numbers will double-count deliveries.
| • | Formulas are pre-filled for 200 register rows and 200 delivery log rows. If you need more, copy the last formula row down; if you insert rows inside the range, Excel extends the formulas and ranges for you.
| • | Categories and every dropdown option live on the Lists sheet. Insert new options inside an existing list rather than below it so the validation range and the Dashboard tables pick them up.
| • | The twelve EXAMPLE rows on the Material Register and the six on the Delivery Log are illustrative only. Delete them before the schedule is issued.
DISCLAIMER
This template is a starting point, not a contract document. It must be adapted to the project's contract, procurement procedure, quality management system and inspection and test plan before use. It is jurisdiction-neutral: it contains no country-specific tax, customs or legal treatment, and any statutory, tax or customs requirement remains the user's responsibility. Mastt accepts no liability for procurement, cost or programme decisions made on the basis of this workbook.
Mastt template · mastt.com · © 2026 Mastt