## Claim Cover
Progress Claim / Payment Claim
Australia · security of payment aware · built for head contract and subcontract progress claims
EXAMPLE DATA — overwrite every shaded cell below, and delete the rows flagged EXAMPLE on the schedule sheets, before issuing this claim.
| PROJECT & PARTIES |  |  | CONTRACT
| PROJECT NAME | Northbank Community Health Precinct |  | CONTRACT NO. | NB-HC-2026-001
| PROJECT NO. | MST-2601 |  | CONTRACT TITLE | D&C — Northbank Health Precinct
| SITE ADDRESS | 142 Riverside Drive, Brisbane QLD |  | CONTRACT TYPE | AS 4902-2000 (Design & Construct)
| PRINCIPAL / CLIENT | Northbank Health Services Pty Ltd |  | CONTRACT SUM (EXCL GST) | 13769750
| CONTRACTOR | Ridgeline Constructions Pty Ltd |  | RETENTION BASIS | Cash retention
| CONTRACTOR ABN | 38 642 917 205 |  | PAYMENT TERMS (DAYS FROM CONTRACT) | 15
| SUPERINTENDENT / PRINCIPAL'S REP | Mastt Project Advisory — A. Chen |  | PAYMENT DUE DATE (CALCULATED) | 2026-08-18
| CLAIM DETAILS |  |  | SECURITY OF PAYMENT
| CLAIM NO. | 4 |  | JURISDICTION OF THE WORKS | QLD
| CLAIM PERIOD FROM | 2026-07-01 |  | APPLICABLE ACT (CALCULATED) | Building Industry Fairness (Security of Payment) Act 2017 (Qld)
| CLAIM PERIOD TO | 2026-07-31 |  | RESPONSE DOCUMENT (CALCULATED) | Payment schedule
| CLAIM DATE | 2026-08-03 |  | RESPONSE DUE (DAYS — PER ACT/CONTRACT) | 15
| REFERENCE DATE / ENTITLEMENT DATE | 2026-07-31 |  | DAYS COUNTED AS | business days
| DATE RECEIVED BY SUPERINTENDENT | 2026-08-03 |  | CLAIM SERVED BY | Email to Superintendent
STATUTORY STATEMENT
This is a payment claim made under the Building Industry Fairness (Security of Payment) Act 2017 (Qld), being the Security of Payment Act applicable in the State/Territory of the Works (Queensland).
Check the Act before you rely on this statement: some Acts require particular words, a prescribed form, or a supporting statement about payment of subcontractors, and the timeframes for a response and for payment differ by jurisdiction. This template is not legal advice.
| AMOUNT CLAIMED THIS CLAIM (INCL GST) |  |  | AMOUNT CLAIMED (EXCL GST) / GST
| 1643080.73 |  |  | 1493709.75 | 149370.98
CONTRACTOR'S DECLARATION
I certify that I am authorised to make this payment claim on behalf of the Contractor; that the construction work and related goods and services described in this claim have been carried out or supplied under the contract; that the amounts claimed are calculated in accordance with the contract; and that, to the best of my knowledge, all subcontractors and suppliers have been paid all amounts that have become due and payable to them in relation to the construction work the subject of this claim.
| NAME OF AUTHORISED REPRESENTATIVE |  | POSITION |  | DATE
SIGNATURE
DISCLAIMER — This is a commercial contract-administration template, not legal advice. Security of payment legislation differs in every Australian State and Territory, and the timeframes for making a payment claim, serving a payment schedule or payment response, and paying a scheduled amount are NOT the same across jurisdictions and change over time. Some Acts also require particular words, forms or supporting statements on a payment claim. Before issuing or responding to a claim, check the Act in force in the State or Territory where the construction work is carried out, together with the contract, and obtain your own legal advice. Mastt accepts no liability for reliance on this template.
Mastt template · mastt.com · © 2026 Mastt
Note on F17: Date received by the Superintendent/Principal plus the contract payment terms. Counted in calendar days unless the contract says otherwise — and the applicable Security of Payment Act may impose a shorter maximum. Check both.
Note on F23: Timeframes differ by State/Territory and by contract — take them from the contract and the Act in force. See Lists & Settings.
Note on F24: Timeframes differ by State/Territory and by contract — take them from the contract and the Act in force. See Lists & Settings.

## Claim Summary
Claim Summary
The money page — every figure below is calculated from the schedule sheets
| PROJECT: Northbank Community Health Precinct CONTRACT: NB-HC-2026-001 CONTRACTOR: Ridgeline Constructions Pty Ltd |  |  |  | CLAIM No. 4 PERIOD ENDING 31/07/2026
PROGRESS CLAIM SUMMARY — ALL AMOUNTS EXCLUDE GST UNLESS STATED
| Ref | Description |  |  | Claimed by Contractor ($) | Superintendent's Assessment ($) | Variance ($)
| A | Original Contract Sum (excl GST) |  |  | 13769750
| B | Approved Variations to date |  |  | 234550
| C | Adjusted Contract Sum |  |  | 14004300
| D | Value of Work Completed to Date |  |  | 6892467.5
| E | Approved Variations Completed to Date |  |  | 156037.5
| F | Materials / Unfixed Goods on Site |  |  | 335650
| G | Provisional Sums / PC Items — value to date |  |  | 9000
| H | Total Value of Works to Date (D+E+F+G) |  |  | 7393155
| I | Less Retention held to date (incl. retention this claim) |  |  | 352875.25
| J | Less Liquidated Damages / set-offs / back-charges applied this claim |  |  | 32090
| K | Total Due to Date (H−I−J) |  |  | 7008189.75
| L | Less Amounts Previously Certified / Paid |  |  | 5514480
| M | AMOUNT CLAIMED THIS CLAIM (excl GST) (K−L) |  |  | 1493709.75
| N | GST |  |  | 149370.98
| O | TOTAL CLAIMED THIS CLAIM (incl GST) |  |  | 1643080.73
|  | Percentage complete (H ÷ C) |  |  | 52.79%
|  | Retention held to date |  |  | 352875.25
|  | Retention deducted this claim |  |  | 72455.25
|  | Retention remaining to cap |  |  | 347339.75
| TOTAL CLAIMED THIS CLAIM (INCL GST) |  |  |  | SCHEDULED AMOUNT (INCL GST)
1643080.73
PAYMENT SCHEDULE / SUPERINTENDENT'S ASSESSMENT
| DATE OF PAYMENT SCHEDULE / CERTIFICATE |  |  |  | SCHEDULED AMOUNT (EXCL GST)
REASONS FOR WITHHOLDING PAYMENT — where the scheduled amount is less than the claimed amount, state why, and if it is being withheld, the reasons for withholding
| ASSESSED BY (NAME & POSITION) |  |  | SIGNATURE |  | DATE
The response document, its content requirements and the time allowed to serve it differ by jurisdiction — see the Act named on the Claim Cover and the reference table on Lists & Settings. This template is not legal advice.
MOVEMENT ANALYSIS — HOW THIS CLAIM RECONCILES
|  | Value of work completed this claim (Works Breakdown) |  |  | 1408017.5
|  | Approved variations claimed this claim (Variations) |  |  | 41087.5
|  | Materials on site claimed this claim |  |  | 149150
|  | Less retention deducted this claim (Retention) |  |  | -72455.25
|  | Less deductions applied this claim (Deductions) |  |  | -32090
|  | Adjustment for prior claims — entitlement per this schedule less amounts certified |  |  | 0
|  | Amount claimed this claim (excl GST) — reconciled |  |  | 1493709.75 | RECONCILED
Mastt template · mastt.com · © 2026 Mastt

## Works Breakdown
Works Breakdown — Schedule of Works
One row per trade or work item · enter Qty and Rate, or leave Qty blank and enter a lump sum · only the % complete columns change each month
Shaded cells are inputs. Tinted columns calculate. Rows in grey italic are EXAMPLES — delete them before use. Contract Value = Qty × Rate where both are entered, otherwise the Rate / Lump Sum figure is taken as the lump sum.
Item No. | Description | Type | Unit | Qty | Rate / Lump Sum ($) | Contract Value ($) | Previous % Complete | This Claim % Complete | Total % Complete | Previous Value Claimed ($) | Value This Claim ($) | Value to Date ($) | Balance to Complete ($) | Comments
GRAND TOTAL — Schedule of Works | [5 empty] | 13769750 | 39.9% | 10.23% | 50.12% | 5493450 | 1408017.5 | 6901467.5 | 6868282.5
Subtotal — works excluding Provisional Sums & PC Items | [5 empty] | 13094750 | 41.95% | 10.68% | 52.64% | 5493450 | 1399017.5 | 6892467.5 | 6202282.5
Subtotal — Provisional Sums & PC Items | [5 empty] | 675000 | 0% | 1.333% | 1.333% | 0 | 9000 | 9000 | 666000
1 | Preliminaries & general — site management, cranage, temp services | Prelims | sum |  | 1150000 | 1150000 | 55% | 8% | 63% | 632500 | 92000 | 724500 | 425500 | EXAMPLE — time-related, claimed pro rata
2 | Site establishment — hoarding, fencing, sheds & amenities | Lump Sum | sum |  | 320000 | 320000 | 90% | 5% | 95% | 288000 | 16000 | 304000 | 16000 | EXAMPLE
3 | Bulk excavation, shoring & offsite disposal | Rate/Qty | m³ | 14500 | 38.5 | 558250 | 95% | 5% | 100% | 530337.5 | 27912.5 | 558250 | 0 | EXAMPLE — qty re-measured to survey
4 | Piling — 600mm dia. CFA piles incl. pile caps | Rate/Qty | m | 1850 | 340 | 629000 | 100% | 0% | 100% | 629000 | 0 | 629000 | 0 | EXAMPLE — complete, nil this period
5 | In-situ concrete — substructure & superstructure | Rate/Qty | m³ | 4200 | 685 | 2877000 | 62% | 11% | 73% | 1783740 | 316470 | 2100210 | 776790 | EXAMPLE — L4 slab poured 22/07
6 | Structural steel — supply, fabricate & erect | Rate/Qty | t | 285 | 6450 | 1838250 | 40% | 15% | 55% | 735300 | 275737.5 | 1011037.5 | 827212.5 | EXAMPLE — see Materials on Site
7 | Roofing — metal deck, insulation, flashings & rainwater goods | Rate/Qty | m² | 3150 | 168 | 529200 | 10% | 20% | 30% | 52920 | 105840 | 158760 | 370440 | EXAMPLE
8 | Façade — unitised curtain wall & metal cladding | Lump Sum | sum |  | 2150000 | 2150000 | 15% | 12% | 27% | 322500 | 258000 | 580500 | 1569500 | EXAMPLE — panels installed to L3
9 | Services rough-in — mechanical, electrical, hydraulic & fire | Lump Sum | sum |  | 1620000 | 1620000 | 30% | 10% | 40% | 486000 | 162000 | 648000 | 972000 | EXAMPLE
10 | Internal linings — partitions, ceilings & plasterboard | Rate/Qty | m² | 8900 | 74.5 | 663050 | 5% | 15% | 20% | 33152.5 | 99457.5 | 132610 | 530440 | EXAMPLE
11 | Internal finishes — painting, tiling & fixed joinery | Lump Sum | sum |  | 760000 | 760000 | 0% | 6% | 6% | 0 | 45600 | 45600 | 714400 | EXAMPLE — commenced L1
12 | Floor coverings & feature joinery | PC Item | sum |  | 225000 | 225000 | 0% | 0% | 0% | 0 | 0 | 0 | 225000 | EXAMPLE — supplier not yet engaged
13 | Landscaping & external works | Provisional Sum | sum |  | 450000 | 450000 | 0% | 2% | 2% | 0 | 9000 | 9000 | 441000 | EXAMPLE — subject to S/I direction
GRAND TOTAL — Schedule of Works | [5 empty] | 13769750 | 39.9% | 10.23% | 50.12% | 5493450 | 1408017.5 | 6901467.5 | 6868282.5
SUBTOTAL — visible (filtered) rows only | [5 empty] | 13769750 |  |  |  | 5493450 | 1408017.5 | 6901467.5 | 6868282.5
Mastt template · mastt.com · © 2026 Mastt

## Variations
Variations
Only APPROVED variations are picked up by the Claim Summary · pending and rejected variations are tracked but claimed at nil
% Complete is the cumulative percentage of the approved variation value completed as at this claim. Value Claimed to Date calculates at nil unless Status = Approved.
VO No. | Description | Date Approved | Status | Approved Value ($) | % Complete This Claim | Value Claimed to Date ($) | Previously Claimed ($) | Value This Claim ($) | Notes
TOTAL — APPROVED VARIATIONS |  |  |  | 234550 | 66.53% | 156037.5 | 114950 | 41087.5
VO-01 | Additional ground anchors to Grid 5–8 (latent condition) | 2026-04-12 | Approved | 86400 | 100% | 86400 | 86400 | 0 | EXAMPLE — Directed under cl.25; SI-014
VO-02 | Upgrade to lift lobby wall & floor finishes | 2026-05-28 | Approved | 142750 | 45% | 64237.5 | 28550 | 35687.5 | EXAMPLE — Principal-initiated; priced 18/05
VO-03 | Relocate hydrant booster to Riverside Drive frontage | 2026-07-16 | Approved | 23900 | 100% | 23900 | 0 | 23900 | EXAMPLE — Fire authority requirement
VO-04 | Additional acoustic treatment to Level 3 consulting suites |  | Pending | 61200 | 0% | 0 | 0 | 0 | EXAMPLE — Priced 24/07 — awaiting direction
VO-05 | Deletion of external planter beds to south elevation | 2026-06-30 | Approved | -18500 | 100% | -18500 | 0 | -18500 | EXAMPLE — Omission — credit to Principal
Mastt template · mastt.com · © 2026 Mastt

## Materials on Site
Materials on Site — Unfixed Plant & Materials
Unfixed goods and materials claimed under the contract · check the conditions before claiming
Most Australian standard forms (e.g. AS 4000 cl.42, AS 4902) only allow unfixed plant and materials to be claimed once specified conditions are met — typically that the goods are on site (or, if stored off site, stored and labelled as directed), that title is vested in the Principal free of encumbrance, that they are adequately insured, and that the Contractor has provided proof of ownership and payment. Some contracts also require a separate security or bond. Check the contract before claiming, and record the evidence below.
Item | Supplier | Invoice / Docket Ref | Date Delivered | Value ($) | Insured (Y/N) | Vested in Principal (Y/N) | Stored Off-site (Y/N) | % Allowed | Amount Claimed ($) | Previously Claimed ($) | This Claim ($) | Compliance check
TOTAL — UNFIXED PLANT & MATERIALS |  |  |  | 335650 |  |  |  | 100% | 335650 | 186500 | 149150
Structural steel — fabricated members, batch 3 | Sterling Steel Fabrication | INV-88421 / DKT-2207 | 2026-07-22 | 148000 | Yes | Yes | No | 100% | 148000 | 90000 | 58000 | OK
Façade — unitised curtain wall panels (types P1–P4) | Alumex Façade Systems | INV-10553 / DKT-1188 | 2026-07-18 | 96500 | Yes | Yes | Yes | 100% | 96500 | 96500 | 0 | Off-site — confirm storage/labelling directed
Main switchboard MSB-01 & distribution boards | Volta Switchboards Pty Ltd | INV-4417 | 2026-07-29 | 62400 | Yes | Yes | No | 100% | 62400 | 0 | 62400 | OK
Roof sheeting & insulation — site compound | Metroll QLD | DKT-77310 | 2026-07-31 | 28750 | Yes | No | No | 100% | 28750 | 0 | 28750 | Check — not insured and/or not vested
Mastt template · mastt.com · © 2026 Mastt

## Retention
Retention
Cash retention calculation, cap check and release schedule · switch to a bank guarantee to zero the cash retention
| RETENTION BASIS — INPUTS |  | RELEASE SCHEDULE
| Retention rate on works (% of value of work completed) | 5% | Date of Practical Completion (actual or forecast) | 2027-03-31
| Retention rate on variations (% of variation value completed) | 5% | Proportion of retention released at Practical Completion | 50%
| Maximum retention (% of adjusted contract sum) | 5% | Defects Liability Period (months from PC) | 12
| Security provided as bank guarantee / undertaking instead of cash? (Y/N) | No | Final release date (end of Defects Liability Period) | 2028-03-31
| Retention held per the last payment certificate ($) | 280420
| Retention released to date, if any ($) | 0 | Retention held to date | 352875.25
|  |  | Release at Practical Completion | 176437.625
| RETENTION CALCULATED THIS CLAIM |  | Balance retained through the Defects Liability Period | 176437.625
| Value of work completed to date (Works Breakdown) | 6901467.5 | Released at end of Defects Liability Period | 176437.625
| Value of approved variations completed to date (Variations) | 156037.5
| Retention on works | 345073.375
| Retention on variations | 7801.875
| Gross retention calculated (before cap) | 352875.25
| Maximum retention permitted (cap) | 700215
| Retention held to date (after cap, after security election) | 352875.25
| Retention deducted this claim (held to date less held previously) | 72455.25
| Retention remaining to cap | 347339.75
| Indicative retention on previous values (cross-check only) | 280420
Retention is within the cap and reconciles to the previous certificate.
Retention is calculated on the value of work and approved variations completed to date. Unfixed plant and materials on site are excluded from the retention base in this template — check the contract, as some forms apply retention to materials on site as well. Where the applicable Act or the contract requires retention to be held in a retention trust account, record the account details with the contract file.
Mastt template · mastt.com · © 2026 Mastt
Note on C12: Set to Yes where the contract security is an unconditional undertaking rather than cash retention. Cash retention is then calculated at nil and the claim is not reduced.
Note on C13: Take this from the last payment certificate, not from this workbook. The indicative figure opposite is calculated from the Previous columns as a cross-check.
Note on C14: Enter retention already released (e.g. at Practical Completion) so the held-to-date figure stays correct.
Note on F10: Most Australian standard forms release half the retention at Practical Completion and the balance at the end of the Defects Liability Period. Confirm against the contract.

## Deductions
Deductions, Set-offs & Back-charges
Liquidated damages, back-charges, set-offs and recoveries · only rows marked Applied This Claim = Yes reduce the claim
Amount = Days/Qty × Rate where both are entered, otherwise the Rate figure is taken as the amount. Liquidated damages and set-offs usually require a written notice under the contract before they can be applied — record the notice reference in Notes.
Ref | Description | Basis | Days / Qty | Rate ($) | Amount ($) | Applied This Claim (Y/N) | Notes
TOTAL — APPLIED THIS CLAIM |  |  |  |  | 32090 |  | 8600
D-01 | Liquidated damages — delay to Separable Portion 1 | Liquidated damages | 6 | 4500 | 27000 | Yes | EXAMPLE — 6 days @ $4,500/day; EOT 07 granted 4 of 10 days
D-02 | Back-charge — clean-down of Level 2 slab after concrete pour | Back-charge — cleaning / waste removal |  | 3850 | 3850 | Yes | EXAMPLE — Principal's cleaner, invoice PC-2231
D-03 | Temporary power & water consumption recovery — July | Utilities / consumables recovery |  | 1240 | 1240 | Yes | EXAMPLE — Per cl.12 of Annexure Part A
D-04 | Rectification of damaged wall linings — Level 1 corridor | Back-charge — rectification |  | 8600 | 8600 | No | EXAMPLE — Contractor rectifying under warranty — not applied this claim
Mastt template · mastt.com · © 2026 Mastt

## Claim History
Claim History
One row per previous claim · the Amount Certified column drives 'less previously certified' on the Claim Summary
Enter every claim already certified — do NOT enter the current claim here. Add it next month, once it has been certified.
Claim No. | Period | Claim Date | Amount Claimed (excl GST) ($) | Amount Certified (excl GST) ($) | GST ($) | Total Certified (incl GST) ($) | Date Paid | Amount Paid ($) | Balance Outstanding ($) | Cumulative Claimed ($) | Cumulative Certified ($)
TOTAL — PREVIOUS CLAIMS |  |  | 5675000 | 5514480 | 551448 | 6065928 |  | 3664100 | 2401828
1 | 01/04/2026 – 30/04/2026 | 2026-05-04 | 1285000 | 1242600 | 124260 | 1366860 | 2026-05-19 | 1366860 | 0 | 1285000 | 1242600
2 | 01/05/2026 – 31/05/2026 | 2026-06-03 | 2150000 | 2088400 | 208840 | 2297240 | 2026-06-18 | 2297240 | 0 | 3435000 | 3331000
3 | 01/06/2026 – 30/06/2026 | 2026-07-02 | 2240000 | 2183480 | 218348 | 2401828 |  | 0 | 2401828 | 5675000 | 5514480
CUMULATIVE CLAIMED VS CERTIFIED (EXCL GST)
Mastt template · mastt.com · © 2026 Mastt

## Lists & Settings
Lists & Settings
Reference data, dropdown sources, statutory reference table and disclaimer
SETTINGS
| GST rate | 10% | Australian GST is 10%. Confirm the rate and whether the supply is taxable before issuing.
| Currency | AUD | Label only — all money formats in this workbook are Australian dollars.
SECURITY OF PAYMENT — ACT BY STATE / TERRITORY
Select the jurisdiction of the Works on the Claim Cover. The Act name below is pulled into the statutory statement automatically.
| Code | State / Territory | Security of Payment Act (as at the date of this template) |  | Respondent's response document | Legislation source
| NSW | New South Wales | Building and Construction Industry Security of Payment Act 1999 (NSW) |  | Payment schedule | legislation.nsw.gov.au
| VIC | Victoria | Building and Construction Industry Security of Payment Act 2002 (Vic) |  | Payment schedule | www.legislation.vic.gov.au
| QLD | Queensland | Building Industry Fairness (Security of Payment) Act 2017 (Qld) |  | Payment schedule | www.legislation.qld.gov.au
| WA | Western Australia | Building and Construction Industry (Security of Payment) Act 2021 (WA) |  | Payment schedule | www.legislation.wa.gov.au
| SA | South Australia | Building and Construction Industry Security of Payment Act 2009 (SA) |  | Payment schedule | www.legislation.sa.gov.au
| TAS | Tasmania | Building and Construction Industry Security of Payment Act 2009 (Tas) |  | Payment schedule | www.legislation.tas.gov.au
| ACT | Australian Capital Territory | Building and Construction Industry (Security of Payment) Act 2009 (ACT) |  | Payment schedule | www.legislation.act.gov.au
| NT | Northern Territory | Construction Contracts (Security of Payments) Act 2004 (NT) |  | No statutory payment schedule — a 'payment dispute' arises under the Act; the contract governs the response | legislation.nt.gov.au
TIMEFRAMES ARE NOT THE SAME IN EVERY JURISDICTION. The time to serve a payment schedule / payment response, the time to pay a scheduled amount, and the time to apply for adjudication differ by Act (and some are counted in business days, others in calendar days). Enter the timeframes that apply to YOUR contract on the Claim Cover, taken from the contract and the Act in force at the time — do not assume a national figure.
DROPDOWN SOURCE LISTS
To add an option, type it in the first empty cell INSIDE a list block (not below it) so the named range keeps covering it.
| Jurisdiction | Contract type | Work item type | Variation status | Unit | Yes / No | Retention basis | Deduction basis
| NSW | AS 4000-1997 (General Conditions) | Lump Sum | Approved | sum | Yes | Cash retention | Liquidated damages
| VIC | AS 4902-2000 (Design & Construct) | Provisional Sum | Pending | item | No | Bank guarantee / unconditional undertaking | Back-charge — rectification
| QLD | AS 2124-1992 (General Conditions) | PC Item | Rejected | No. |  | Cash retention converting to bank guarantee | Back-charge — cleaning / waste removal
| WA | AS 4901-1998 (Subcontract Conditions) | Rate/Qty | Withdrawn | m |  | Retention trust account (if required by Act) | Set-off under the contract
| SA | AS 4903-2000 (D&C Subcontract) | Prelims |  | m² |  | No security held | Insurance excess recovery
| TAS | AS 4300-1995 (Design & Construct) |  |  | m³ |  |  | Utilities / consumables recovery
| ACT | GC21 (Edition 2) |  |  | t |  |  | Other
| NT | ABIC MW-2018 |  |  | kg
|  | Bespoke / amended standard form |  |  | L
|  | Other |  |  | LM
hr
day
wk
lot
| Day count basis | business days
calendar days
DISCLAIMER
DISCLAIMER — This is a commercial contract-administration template, not legal advice. Security of payment legislation differs in every Australian State and Territory, and the timeframes for making a payment claim, serving a payment schedule or payment response, and paying a scheduled amount are NOT the same across jurisdictions and change over time. Some Acts also require particular words, forms or supporting statements on a payment claim. Before issuing or responding to a claim, check the Act in force in the State or Territory where the construction work is carried out, together with the contract, and obtain your own legal advice. Mastt accepts no liability for reliance on this template.
HOW TO USE THIS TEMPLATE
1. Complete the shaded cells on Claim Cover — project, contract, claim period and the jurisdiction of the Works. Everything else in the workbook reads from there.
2. Price the work on Works Breakdown. Enter Qty and Rate for re-measured items, or leave Qty blank and put the lump sum in the Rate / Lump Sum column. Only the % complete columns change each month.
3. Record approved variations on Variations, unfixed goods on Materials on Site, and any liquidated damages or back-charges on Deductions.
4. Set the retention rates and the cap on Retention, and enter retention held per the last payment certificate. Everything else there calculates.
5. Enter each prior claim on Claim History. The Amount Certified column drives 'less previously certified' on the Claim Summary.
6. Read the answer off Claim Summary, print it with Claim Cover, sign the declaration and issue. The Superintendent completes the assessment column and the payment schedule block.
7. Delete every row flagged EXAMPLE and overwrite the example cover details before you use this on a live project.
Mastt template · mastt.com · © 2026 Mastt