## Cover & Instructions
Variation Template — Australia
Variation request · assessment · register · aligned to AS 4000-1997 · amounts in AUD, excl GST unless stated
| PROJECT & CONTRACT DETAILS |  | Shaded cells are inputs. These values flow to every other sheet by named range.
| PROJECT NAME | Riverside Aquatic Centre Redevelopment | CONTRACT TYPE | AS 4000-1997
| PROJECT No. | P-2451 | SUPERINTENDENT | K. Rahman — Mastt Advisory
| PRINCIPAL | Marra Shire Council | SUPERINTENDENT'S REP. | D. Whelan
| CONTRACTOR | Hallmark Constructions Pty Ltd | CONTRACT SUM (EXCL GST) | 28450000
| CONTRACTOR ABN | 51 824 753 556 | DATE OF CONTRACT | 2025-11-03
| CONTRACT No. | C-2451-02 | PREPARED BY / DATE | M. Osei — Project Manager
HOW TO USE THIS TEMPLATE — THE VARIATION WORKFLOW
| 1. Set up | Complete the project and contract details below. They feed the Variation Request, Variation Pricing and Assessment sheets by named range, so you only type them once. Then open Lists & Settings and confirm the GST rate, the notice period and the dropdown lists (especially Cost Centre).
| 2. Variation Request | The Contractor or the Superintendent completes the Variation Request pro forma for ONE variation: what is being varied, why, which clause is relied on, which drawings and revisions are affected, and the time impact. It prints on a single A4 page for issue and signature.
| 3. Assessment / pricing | The cost is built up on Variation Pricing — labour, materials, plant, subcontractors and omissions, then the percentage add-ons. The Contractor's claim builds up in the CLAIMED column; the Superintendent enters the ASSESSED figure at section level and adjusts the add-on percentages. Variance is calculated automatically.
| 4. Recommendation | The Superintendent records entitlement, the notice / time-bar check, the valuation basis relied on under cl 36.4, the time entitlement and the recommendation on Assessment & Recommendation, then signs off.
| 5. Approval | The Principal (or delegate) approves, approves in part or rejects. Record the decision, the approved amount and the date on the Variation Register.
| 6. Variation Order issued | A formal Variation Order is issued to the Contractor under cl 36.1 (separate document). Record its reference in the VO Ref column of the register — that is the audit link between the commercial workbook and the executed instruction.
| 7. Register updated | Update the Status, Approved Amount, EOT Days Granted and Date Approved on the Variation Register. The Variation Dashboard and the contingency tracker recalculate automatically.
| 8. Flows to progress claim | Approved variations are certified in the next progress claim under cl 37 and adjust the Contract Sum. Reconcile the register's Approved total to the variations schedule in the payment certificate every month.
| 9. Housekeeping | Delete the ten EXAMPLE rows on the Variation Register and the worked example figures on Variation Pricing before you issue the template on a live project. Copy the Variation Request, Variation Pricing and Assessment sheets once per variation, or save one workbook per variation.
VARIATION REQUEST → ASSESSMENT / PRICING → RECOMMENDATION → APPROVAL → VARIATION ORDER ISSUED → REGISTER UPDATED → PROGRESS CLAIM
CELL CONVENTIONS
| input | Input cell — you type here. Unlocked when the sheet is protected.
| calculated | Calculated cell — formula driven and locked. Do not type over it.
| result | Key result / KPI tile — navy fill, white figure.
IMPORTANT — SCOPE OF THIS TEMPLATE & DISCLAIMER
COMMERCIAL TEMPLATE — NOT LEGAL ADVICE. This workbook is a commercial administration tool. It is not legal advice and does not create, vary or waive any contractual right or obligation.
Clause references in this workbook are to the unamended AS 4000-1997 General Conditions of Contract and are provided as a starting point only. Standard-form contracts are almost always amended by the Annexure or a schedule of amendments, and other forms (AS 4902-2000, AS 2124-1992, AS 4300-1995, GC21, bespoke) number their clauses differently. ALWAYS check every clause reference against the actual executed contract before issuing this document.
Time bars are strict. Notices of delay, extension of time claims and notifications of claims must be given within the periods stated in the executed contract, and failure to do so can extinguish an otherwise valid entitlement.
Amounts in this workbook are in Australian dollars and are stated EXCLUSIVE of GST unless a line is expressly labelled 'incl GST'. The GST rate is held on the Lists & Settings sheet (10% at the date of this template).
Obtain advice from a suitably qualified construction lawyer or contract specialist before relying on this workbook for any contentious variation, latent condition, delay or prolongation claim.
Mastt template · mastt.com · © 2026 Mastt

## Variation Register
Variation Template — Australia
Variation Register — the master log. All amounts EXCLUDE GST. Enter credits / omissions as negative amounts.
Project: Riverside Aquatic Centre Redevelopment ¦ Contract: C-2451-02 ¦ AS 4000-1997 | [7 empty] | One row per variation. Variance, and the whole Dashboard, calculate themselves — only the shaded cells are inputs.
TOTALS — reflect the current filter · 10 variations listed | [7 empty] | 413381 | 267653.5 | 188953.5 | -80427.5 | 26 | 13
VAR No. | Date Raised | Raised By | Origin | Description | Related Instruction / RFI / SI Ref | Contract Clause | Status | Contractor Claimed Amount | Assessed Amount | Approved Amount | Variance (Assessed − Claimed) | Time Impact (days claimed) | EOT Days Granted | Date Approved | VO Ref | Cost Centre | Funding Source | Comments
VAR-001 | 2026-02-12 | Superintendent | Design Change | Upgrade of pool hall ceiling lining to perforated acoustic panel system to achieve the revised reverberation time required by the acoustic report Rev C | SI-014 | 36.1 | Approved | 144781 | 125803.5 | 125803.5 | -18977.5 | 5 | 3 | 2026-03-06 | VO-001 | Fitout & Finishes | Contingency | EXAMPLE — delete before use. Priced in full on the Variation Pricing sheet of this workbook — the worked example. Assessed down on prelims, risk allowance and scaffold; agreed with Contractor 4/3/26.
VAR-002 | 2026-02-20 | Contractor | Latent Condition | Undocumented mass concrete obstruction encountered at grid C4–E6 during bulk excavation; break-out, removal and disposal, and additional rock anchors | RFI-062 | 25 / 36.1 | Approved | 96300 | 78450 | 78450 | -17850 | 12 | 8 | 2026-03-18 | VO-002 | Substructure | Contingency | EXAMPLE — delete before use. Latent condition notice given 20/2/26, within time. Assessed on daywork records verified on site; disposal rate reduced to the contract schedule rate.
VAR-003 | 2026-03-03 | Principal | Client Request | Additional 24 rooftop photovoltaic panels and inverter capacity upgrade to lift the array from 40 kW to 58 kW | PCN-003 | 36.2 | Approved | 63900 | 61200 | 61200 | -2700 | 0 | 0 | 2026-03-27 | VO-003 | Services – Electrical | Client Budget | EXAMPLE — delete before use. Priced as a proposed variation under cl 36.2 before direction. No programme impact — installed within the existing roof works window.
VAR-004 | 2026-03-11 | Superintendent | Scope Omission | Omission of the external shade structure and associated footings to Car Park B, deferred to a future stage | SI-021 | 36.1 | Approved | -84000 | -76500 | -76500 | 7500 | 0 | 0 | 2026-04-02 | VO-004 | External Works & Landscape | Contingency | EXAMPLE — delete before use. Credit — entered as a negative amount. Deduction valued under cl 36.4 on the contract schedule of rates; Contractor's offered credit increased after review of the footing quantities.
VAR-005 | 2026-03-24 | Consultant | Error/Omission in Documents | Coordination clash between the hydraulic and structural documentation at the level 1 slab; additional penetrations, trimmer reinforcement and fire collars | RFI-088 | 8 / 36.1 | Under Assessment | 41250 | 28900 |  | -12350 | 3 |  |  |  | Structure | Contingency | EXAMPLE — delete before use. Assessment provisional pending the structural engineer's confirmation of the trimmer detail. Contribution from the consultant's PI cover under review by the Principal separately.
VAR-006 | 2026-04-02 | Contractor | Site Instruction | Out-of-hours works to complete the tie-in to the existing 300 mm sewer main under the Council road occupancy permit | SI-030 | 36.1 | Recommended | 37800 | 34600 |  | -3200 | 2 | 2 |  |  | Services – Hydraulic | Contingency | EXAMPLE — delete before use. Recommended for approval. Penalty rates verified against the enterprise agreement; traffic management assessed at the subcontract quoted rate.
VAR-007 | 2026-04-09 | Principal | Authority Requirement | Additional fire hydrant booster assembly, signage and hardstand required by the fire authority referral response dated 1/4/26 | AUTH-005 | 11 / 36.1 | Submitted | 52400 |  |  |  | 4 |  |  |  | Services – Fire | Client Budget | EXAMPLE — delete before use. Awaiting the Contractor's supporting quotations. Legislative requirement change after the tender date — check cl 11 entitlement before assessing.
VAR-008 | 2026-04-15 | Contractor | Provisional Sum Adjustment | Adjustment of the external landscape softworks provisional sum following award of the subcontract on 10/4/26 | PS-002 | 3 / 36.4 | Under Assessment | 18650 | 15200 |  | -3450 | 0 |  |  |  | External Works & Landscape | Provisional Sum | EXAMPLE — delete before use. Provisional sum allowance $145,000; subcontract awarded at $160,200. Attendance and profit percentages to be applied per the Annexure, not the Contractor's claimed 12%.
VAR-009 | 2026-04-22 | Contractor | Scope Increase | Additional 180 m² of tactile ground surface indicators and handrail extensions arising from the access consultant's DDA review | SI-035 | 36.1 | Rejected | 29400 | 0 |  | -29400 | 0 |  |  |  | External Works & Landscape | Client Budget | EXAMPLE — delete before use. Rejected — the work is required for compliance with the performance specification and forms part of the Contractor's existing obligations. Refer Superintendent's assessment dated 30/4/26. Contractor has reserved its position.
VAR-010 | 2026-04-30 | Superintendent | Design Change | Substitution of the specified pool filtration media following advice of supply unavailability within the programme | SI-038 | 36.1 | On Hold | 12900 |  |  |  | 0 |  |  |  | Services – Hydraulic | Contingency | EXAMPLE — delete before use. On hold pending the Principal's decision on the alternative product and the effect on the maintenance contract. Contractor advised 6/5/26 that the price holds until 30/6/26.
Mastt template · mastt.com · © 2026 Mastt
Note on J9: Superintendent's assessed value, excl GST. For the variation priced on the Variation Pricing sheet you can link this cell directly by typing =VP_Assessed_ExGST — see the 'Push to register' panel at the bottom of that sheet.
Note on L9: Calculated: Assessed − Claimed. Blank until an assessed amount is entered. Negative (red) means the Superintendent has assessed the variation below the Contractor's claim — a saving to the Principal.

## Variation Dashboard
Variation Template — Australia
Variation Dashboard — every figure below is driven by formula off the Variation Register
| Project: Riverside Aquatic Centre Redevelopment ¦ Contract sum (excl GST): $28,450,000.00 | [5 empty] | Amounts exclude GST. Only the contingency allowance is an input on this sheet.
KEY INDICATORS
| TOTAL VARIATIONS RAISED |  | APPROVED — VALUE |  |  | PENDING / UNDER ASSESSMENT |  | REJECTED / WITHDRAWN
| 10 |  | 188953.5 |  |  | 144000 |  | 29400
| Approved 4 · Pending 5 · Rejected/withdrawn 1 |  | 4 variation(s) approved and instructed |  |  | 5 variation(s) open · assessed value where assessed, else claimed |  | 1 variation(s) · value as claimed by the Contractor
| TOTAL CLAIMED BY CONTRACTOR |  | NET ASSESSMENT SAVING |  |  | APPROVED AS % OF CONTRACT SUM |  | TOTAL EOT DAYS GRANTED
| 413381 |  | 80427.5 |  |  | 0.6642% |  | 13
| Total approved $188,953.50 |  | Claimed less assessed, on variations assessed to date |  |  | Contract sum (excl GST) $28,450,000.00 |  | Days claimed to date 26
| CONTINGENCY TRACKER |  |  |  |  | Allowance is the only input on this sheet.
| Contingency allowance (excl GST) |  | 1250000 |  |  | How the tracker works • Set Funding Source = 'Contingency' on the Variation Register for every variation that draws on the project contingency. • Omissions and credits entered as negative amounts return value to the contingency automatically. • Committed is your forward exposure: it uses the Superintendent's assessed figure once one exists, and the Contractor's claim until then. • Report Drawn + Committed against the allowance in the monthly project report — not Drawn alone.
| Drawn — approved variations (contingency) |  | 127753.5
| Committed — open variations (contingency) |  | 76400
| Remaining contingency |  | 1045846.5
| Remaining as % of allowance |  | 83.67%
Within allowance — $1,045,846.50 remaining
| VARIATIONS BY STATUS |  |  |  |  | VARIATIONS BY ORIGIN
| Status | No. | Claimed $ | Assessed $ | Approved $ | Origin |  | No. | Claimed $ | Approved $
| Draft | 0 | 0 | 0 | 0 | Design Change |  | 2 | 157681 | 125803.5
| Submitted | 1 | 52400 | 0 | 0 | Scope Increase |  | 1 | 29400 | 0
| Under Assessment | 2 | 59900 | 44100 | 0 | Scope Omission |  | 1 | -84000 | -76500
| Recommended | 1 | 37800 | 34600 | 0 | Latent Condition |  | 1 | 96300 | 78450
| Approved | 4 | 220981 | 188953.5 | 188953.5 | Client Request |  | 1 | 63900 | 61200
| Rejected | 1 | 29400 | 0 | 0 | Authority Requirement |  | 1 | 52400 | 0
| Withdrawn | 0 | 0 | 0 | 0 | Error/Omission in Documents |  | 1 | 41250 | 0
| On Hold | 1 | 12900 | 0 | 0 | Site Instruction |  | 1 | 37800 | 0
| Total | 10 | 413381 | 267653.5 | 188953.5 | Provisional Sum Adjustment |  | 1 | 18650 | 0
[6 empty] | Other |  | 0 | 0 | 0
[6 empty] | Total |  | 10 | 413381 | 188953.5
| VARIATIONS BY COST CENTRE |  |  |  |  | APPROVED VALUE BY ORIGIN
| Cost centre |  | No. | Approved $ | Open $
| Site Establishment & Preliminaries |  | 0 | 0 | 0
| Substructure |  | 1 | 78450 | 0
| Structure |  | 1 | 0 | 28900
| Façade & External Walls |  | 0 | 0 | 0
| Roofing |  | 0 | 0 | 0
| Fitout & Finishes |  | 1 | 125803.5 | 0
| Services – Mechanical |  | 0 | 0 | 0
| Services – Electrical |  | 1 | 61200 | 0
| Services – Hydraulic |  | 2 | 0 | 47500
| Services – Fire |  | 1 | 0 | 52400
| External Works & Landscape |  | 3 | -76500 | 15200
| Design & Consultants |  | 0 | 0 | 0
| Authority & Statutory |  | 0 | 0 | 0
| Other |  | 0 | 0 | 0
| Total |  | 10 | 188953.5 | 144000
CONTRACTOR CLAIMED VS PRINCIPAL APPROVED, BY STATUS
Mastt template · mastt.com · © 2026 Mastt

## Variation Request
Variation Template — Australia
Variation Request — one variation, one page. Complete, print and issue for signature.
VARIATION REQUEST
PROJECT & CONTRACT
| PROJECT | Riverside Aquatic Centre Redevelopment |  |  | VARIATION No. | VAR-001
| PROJECT No. | P-2451 ¦ Contract C-2451-02 |  |  | DATE RAISED | 2026-02-12
| PRINCIPAL | Marra Shire Council |  |  | RAISED BY | Superintendent
| CONTRACTOR | Hallmark Constructions Pty Ltd ABN 51 824 753 556 |  |  | ORIGIN | Design Change
| SUPERINTENDENT | K. Rahman — Mastt Advisory ¦ AS 4000-1997 |  |  | CONTRACT CLAUSE | 36.1
| REQUEST TYPE | Directed variation (instruction already issued) |  |  | INSTRUCTION / RFI REF | SI-014
DESCRIPTION OF THE VARIED WORK
Remove the specified painted plasterboard ceiling lining to the pool hall (approx. 420 m²) and install a suspended perforated aluminium acoustic panel ceiling on a marine-grade exposed tee grid with 75 mm acoustic insulation blanket over, including perimeter trims, stainless steel fixings and hangers, relocation of 22 existing luminaires to suit the new grid, and post-installation acoustic verification testing.
REASON FOR THE VARIATION / BASIS OF ENTITLEMENT
Acoustic report Rev C (issued 28/1/26 after the Contract was executed) increases the required reverberation time performance for the pool hall. The specified plasterboard lining cannot achieve it. Directed by the Superintendent under SI-014 dated 12/2/26. Entitlement claimed under cl 36.1 as a change to the character and quality of the work under the Contract.
DOCUMENTS & DRAWINGS AFFECTED
| Document / drawing no. |  | Title |  | Rev | Date
| A-2104 |  | Pool hall reflected ceiling plan |  | C | 2026-01-28
| A-5502 |  | Ceiling details and perimeter trims |  | B | 2026-01-28
| ACO-RPT-003 |  | Acoustic performance report |  | C | 2026-01-28
TIME IMPACT
| EOT CLAIMED (WORKING DAYS) |  | 5 | PROGRAMME EFFECT | Critical path affected
Justification: the acoustic panel is a 6-week lead item. Ceiling installation sits on the critical path between services rough-in and pool commissioning; no float remains on activity C-2280. Notice of delay given 12/2/26 and EOT claim submitted 18/2/26, within 28 days under cl 34.3.
COST SUMMARY — FROM THE VARIATION PRICING SHEET
| Value of the variation |  |  | Contractor claimed | Superintendent assessed | Variance
| Subtotal excl GST |  |  | 144781 | 125803.5 | -18977.5
| GST @ 10.0% |  |  | 14478.1 | 12580.35 | -1897.75
| TOTAL VARIATION VALUE (INCL GST) |  |  | 159259.1 | 138383.85 | -20875.25
ATTACHMENTS
1. Superintendent's Instruction SI-014 dated 12/2/26
2. Contractor's detailed price build-up (Variation Pricing sheet) and supplier quotations QT-2291, QT-2310, QT-2318
3. Acoustic report Rev C and marked-up drawings A-2104 Rev C, A-5502 Rev B
SIGNATURES
| Prepared by |  | Contractor's Representative |  | Received by (Superintendent)
Rows above, top to bottom: Name · Signature · Date
Commercial template — not legal advice. Clause references are to the unamended AS 4000-1997 and must be checked against the executed contract. Amounts exclude GST unless labelled otherwise.
Mastt template · mastt.com · © 2026 Mastt

## Variation Pricing
Variation Template — Australia
Variation Pricing — detailed cost build-up for ONE variation. Worked EXAMPLE figures — replace with your own.
VARIATION PRICING — COST BUILD-UP
| VARIATION No. | VAR-001 | TITLE | Pool hall acoustic ceiling upgrade — SI-014
Column F builds up the CONTRACTOR'S CLAIM line by line. Column G is the SUPERINTENDENT'S ASSESSMENT, entered once per section (and as its own percentage for each add-on). Column H is the variance, assessed less claimed. All figures exclude GST until the GST line.
SECTION A — DIRECT LABOUR
| Trade / classification | Hours |  | Rate ($/hr) | Claimed $ | Assessed $ | Variance $
| Carpenter — ceiling grid installation | 180 | hr | 92 | 16560
| Plasterer / ceiling fixer | 120 | hr | 88 | 10560
| Construction labourer | 96 | hr | 68 | 6528
| Rigger / EWP operator | 40 | hr | 95 | 3800
| Leading hand — supervision | 56 | hr | 105 | 5880
| Subtotal — Section A Direct labour |  |  |  | 43328 | 39850 | -3478
SECTION B — MATERIALS
| Item / material | Qty | Unit | Rate $ | Claimed $ | Assessed $ | Variance $
| Perforated aluminium acoustic panel, 600×600 | 420 | m² | 84.5 | 35490
| Exposed tee suspension grid, marine grade | 420 | m² | 18.2 | 7644
| Acoustic insulation blanket, 75 mm | 420 | m² | 9.4 | 3948
| Stainless steel hangers, fixings & seismic bracing | 1 | item | 2850 | 2850
| Powder-coated perimeter shadowline trim | 96 | m | 22 | 2112
| Freight, offloading & site distribution | 1 | item | 1450 | 1450
| Subtotal — Section B Materials |  |  |  | 53494 | 51200 | -2294
SECTION C — PLANT & EQUIPMENT
| Item | Hours / days | Unit | Rate $ | Claimed $ | Assessed $ | Variance $
| Scissor lift 12 m, incl. transport on/off | 15 | day | 285 | 4275
| Knuckle-boom EWP | 8 | day | 420 | 3360
| Waste skip bins & offsite disposal | 6 | ea | 480 | 2880
| Small tools, consumables & laser levels | 1 | item | 950 | 950
| Subtotal — Section C Plant & equipment |  |  |  | 11465 | 9800 | -1665
SECTION D — SUBCONTRACTORS
| Subcontractor | Scope of work |  | Quote ref | Quoted amount $ | Assessed $ | Variance $
| Sonus Acoustic Services | Acoustic verification tests |  | QT-2291 | 6800
| Apex Access Systems | Scaffold & edge protection |  | QT-2310 | 9450
| Circuitline Electrical | Relocate 22 luminaires |  | QT-2318 | 7300
| Subtotal — Section D Subcontractors |  |  |  | 23550 | 22100 | -1450
SECTION E — OMISSIONS / CREDITS (ENTER AS POSITIVE AMOUNTS — DEDUCTED BELOW)
| Omission / credit | Qty | Unit | Rate $ | Credit $ | Assessed $ | Variance $
| Credit — omitted painted plasterboard ceiling lining | 420 | m² | 34.5 | 14490
| Credit — omitted ceiling access panels | 12 | No. | 112.25 | 1347
| Subtotal — Section E Omissions / credits |  |  |  | 15837 | 16950 | 1113
| DIRECT COST SUBTOTAL (A + B + C + D − E) |  |  |  | 116000 | 106000 | -10000
SECTION F — PERCENTAGE ADD-ONS, FEES & MARGIN
| Item | Applied to | Claimed % | Assessed % | Claimed $ | Assessed $ | Variance $
| Subcontractor margin / attendance | Section D | 10% | 7.5% | 2355 | 1657.5 | -697.5
| Preliminaries / time-related costs | Direct cost | 6.5% | 5% | 7540 | 5300 | -2240
| Overhead (off-site) | Direct cost | 4% | 3% | 4640 | 3180 | -1460
| Profit | Direct cost | 5% | 5% | 5800 | 5300 | -500
| Design / consultant fees | Lump sum |  |  | 4850 | 3200 | -1650
| Insurance & bonds | Direct cost | 1.1% | 1.1% | 1276 | 1166 | -110
| Contingency / risk allowance | Direct cost | 2% | 0% | 2320 | 0 | -2320
| Subtotal — Section F Add-ons, fees & margin |  |  |  | 28781 | 19803.5 | -8977.5
| SUBTOTAL — VARIATION VALUE EXCL GST |  |  |  | 144781 | 125803.5 | -18977.5
| GST @ 10.0% (rate held on the Lists & Settings sheet) |  |  |  | 14478.1 | 12580.35 | -1897.75
| TOTAL VARIATION VALUE |  |  |  | Claimed | Assessed | Variance
| INCLUDING GST |  |  |  | 159259.1 | 138383.85 | -20875.25
PUSH TO THE VARIATION REGISTER
Enter on the Variation Register row for VAR-001 : Contractor Claimed Amount $144,781.00 · Assessed Amount $125,803.50 (both excl GST). To link them live instead, type =VP_Claimed_ExGST and =VP_Assessed_ExGST into those two cells.
Worked EXAMPLE figures — delete before use. Value the variation under cl 36.4 in order of precedence: prior agreement, then applicable Contract rates, then rates in a priced bill or schedule of rates, then reasonable rates. Commercial template, not legal advice.
Mastt template · mastt.com · © 2026 Mastt

## Assessment & Recommendation
Variation Template — Australia
Superintendent's assessment & recommendation — the contemporaneous record behind the Variation Order
ASSESSMENT & RECOMMENDATION
| VARIATION No. | VAR-001 | TITLE | Pool hall acoustic ceiling upgrade — SI-014
| PROJECT / CONTRACT | Riverside Aquatic Centre Redevelopment ¦ C-2451-02 |  |  | ASSESSED ON | 2026-03-02
1. ENTITLEMENT CHECK — IS THIS A VARIATION UNDER THE CONTRACT?
| Question | Response | Date | Comment / clause relied on
| Is the work a change to the work under the Contract (i.e. capable of being a variation)? | Yes |  | Change to the character and quality of the ceiling system — cl 36.1.
| Was the variation directed in writing by the Superintendent before the work started? | Yes | 2026-02-12 | SI-014 issued 12/2/26 under cl 36.1.
| If Contractor-initiated, has the Superintendent approved it under cl 36.3? | N/A |  | Not applicable — Superintendent-directed.
| Is the work already included in the scope, the Contract Sum or a provisional sum? | No |  | Not included — acoustic report Rev C post-dates the Contract.
| Was written notice of the claim given within the time required by the Contract? | Yes | 2026-02-18 | Notice 18/2/26, within 28 days — cl 41 and cl 34.3.
| Has the Contractor provided adequate supporting records, quotations and rates? | Yes |  | Three subcontract quotations and priced build-up provided.
| Is any part of the claimed work rectification of defective or non-conforming work? | No |  | No defect component — cl 35 not engaged.
| Is the work covered by insurance, a provisional sum, or another party's liability? | No |  | Consultant PI contribution being pursued separately by the Principal.
2. NOTICE & TIME-BAR CHECK
| Date of the Superintendent's direction / the event | 2026-02-12 |  |  | Time bars are strict. Under the unamended AS 4000-1997 an EOT claim must be given within 28 days of the Contractor becoming aware of the cause (cl 34.3) and a claim for money within the period in cl 41. Check the executed contract — these periods are frequently amended.
| Date the Contractor's written notice / claim was received | 2026-02-18
| Notice period allowed by the Contract (calendar days) | 28
| Days elapsed between the event and the notice | 6
| Notice given within time? | YES — within time
3. BASIS OF VALUATION (AS 4000-1997 CL 36.4 ORDER OF PRECEDENCE)
| Rates basis relied on | Quotation |  |  | cl 36.4 order of precedence (a)→(d)
Justification: no applicable rate exists in the Contract for a perforated acoustic panel ceiling, so the variation is valued on quotation supported by first principles. Labour hours checked against the Contractor's productivity rates on comparable ceilings; supervision moved to preliminaries to avoid a double recovery; scaffold assessed against the measured access area rather than the lump sum offered.
4. ASSESSMENT COMMENTARY
Direct labour reduced from 492 to approximately 440 hours: the 56 supervision hours claimed are recovered through the preliminaries percentage. Materials assessed on the quoted panel rate with the freight allowance reduced to a single delivery. Plant reduced by one week of scissor lift hire, which overlaps the ceiling grid and panel install sequence. Scaffold assessed at $6,100 against $9,450 claimed on measured area. The omission credit is increased to reflect the full plasterboard system, including set and paint. Preliminaries assessed at 5.0% and off-site overhead at 3.0%, both consistent with the tendered preliminaries build-up; profit accepted at 5.0%. The 2.0% risk allowance is disallowed — the scope is fully defined and priced on firm quotations.
5. COST ASSESSMENT (FROM THE VARIATION PRICING SHEET)
|  |  |  | Contractor claimed | Superintendent assessed | Variance
| Direct cost (Sections A–E) |  |  | 116000 | 106000 | -10000
| Add-ons, fees & margin (Section F) |  |  | 28781 | 19803.5 | -8977.5
| Variation value excl GST |  |  | 144781 | 125803.5 | -18977.5
| Assessed as % of the amount claimed |  |  |  | 86.89%
6. TIME ENTITLEMENT ASSESSMENT
| Extension of time claimed by the Contractor (working days) |  |  | 5 | Claimed with the Variation Request 18/2/26
| Is the cause a qualifying cause of delay under the Contract? |  |  | Yes | Principal-initiated design change — cl 34.3
| Is the critical path affected (no float available)? |  |  | Yes | Ceiling on the critical path — activity C-2280
| Float available on the affected activity (days) |  |  | 0
| Extension of time RECOMMENDED (working days) |  |  | 3 | 2 days absorbed by resequencing tiling
| Are delay damages / prolongation costs payable (cl 34.9)? |  |  | No | No prolongation claimed or assessed
7. RECOMMENDATION
| RECOMMENDATION | Approve in Part |  | AMOUNT (EXCL GST) | 125803.5 | 3
Reasons: entitlement is established under cl 36.1 — the work is a directed change to the character and quality of the ceiling system, arising from acoustic report Rev C issued after the Contract was executed. Notice was given within time. The claim is recommended for approval in part in the assessed amount, on the basis set out above. A three working day extension of time is recommended under cl 34.4; no delay damages are payable. Recommend the Principal instruct a Variation Order under cl 36.1 and that the register, the contingency drawdown and the adjusted Contract Sum be updated.
8. SIGN-OFF
| Superintendent |  | Project Manager |  | Principal / delegate
Rows above, top to bottom: Name · Position · Signature · Date
Commercial template — not legal advice. Clause references are to the unamended AS 4000-1997 General Conditions of Contract and MUST be checked against the executed contract, which is almost always amended. Time bars are strict.
Mastt template · mastt.com · © 2026 Mastt

## Lists & Settings
Variation Template — Australia
Lists & Settings — GST rate, dropdown lists, AS 4000-1997 clause references and the disclaimer
SETTINGS
| Setting | Value | Notes / source
| GST rate | 10% | Australian GST is 10% (A New Tax System (Goods and Services Tax) Act 1999). Verify at ato.gov.au before issue. Used by the Variation Pricing and Variation Request sheets.
| Contingency allowance | 1250000 | Entered on the Variation Dashboard — the contingency tracker lives there. Shown here for reference.
| Contract Sum (excl GST) | 28450000 | From the Cover & Instructions sheet. Drives 'Approved as % of Contract Sum' on the dashboard.
| Notice period (days) | 28 | 28 days is the period in the unamended AS 4000-1997 cl 34.3 for an EOT claim. CHECK the executed contract — this period is frequently amended.
| Currency | AUD | All amounts in Australian dollars, excluding GST unless expressly stated.
DROPDOWN LISTS — ADD OR EDIT AN OPTION HERE AND IT APPEARS IN EVERY DROPDOWN
| Raised By | Origin | Status | Funding Source | Cost Centre | Contract Type | Rates Basis | Recommendation | Yes / No / N/A | Request Type | Programme Impact
| Principal | Design Change | Draft | Contingency | Site Establishment & Preliminaries | AS 4000-1997 | Contract Schedule of Rates | Approve | Yes | Proposed variation (priced for approval) | Critical path affected
| Superintendent | Scope Increase | Submitted | Client Budget | Substructure | AS 4902-2000 | Reasonable Rates | Approve in Part | No | Directed variation (instruction already issued) | Non-critical — float absorbed
| Contractor | Scope Omission | Under Assessment | Provisional Sum | Structure | AS 2124-1992 | Daywork | Reject | N/A | Contractor-initiated (cl 36.3) | No programme impact
| Consultant | Latent Condition | Recommended | Other | Façade & External Walls | AS 4300-1995 | Quotation | Seek Further Information |  |  | To be determined
|  | Client Request | Approved |  | Roofing | GC21 (Edition 2) | Negotiated
|  | Authority Requirement | Rejected |  | Fitout & Finishes | Bespoke / Amended
|  | Error/Omission in Documents | Withdrawn |  | Services – Mechanical | Other
|  | Site Instruction | On Hold |  | Services – Electrical
|  | Provisional Sum Adjustment |  |  | Services – Hydraulic
|  | Other |  |  | Services – Fire
External Works & Landscape
Design & Consultants
Authority & Statutory
Other
AS 4000-1997 — CLAUSE REFERENCES FOR VARIATIONS, VALUATION, TIME AND CLAIMS
CHECK EVERY CLAUSE REFERENCE AGAINST THE ACTUAL EXECUTED CONTRACT. The references below are to the UNAMENDED AS 4000-1997 General Conditions of Contract. Standard forms are almost always amended by the Annexure or a schedule of amendments, and AS 4902-2000, AS 2124-1992, AS 4300-1995, GC21 and bespoke contracts number their clauses differently.
| Clause | Heading |  |  | What it deals with / how to use it in this workbook
| 36.1 | Variations — Directing variations |  |  | The Superintendent may direct the Contractor to vary WUC (increase, decrease, omit, change the character or quality, change levels/lines/positions/dimensions, execute additional work, demolish or remove work or materials). The Contractor must not vary WUC except as directed in writing. Use this clause for a Superintendent's instruction / site instruction.
| 36.2 | Variations — Proposed variations |  |  | The Superintendent may give the Contractor written notice of a proposed variation, and the Contractor must promptly advise the effect on the construction program, on the Date for Practical Completion, and the cost. Use this clause where the Contractor is being asked to price a variation before it is directed.
| 36.3 | Variations — Variations for the convenience of the Contractor |  |  | The Contractor may request a variation for its own convenience; the Superintendent may approve it, usually conditionally and at no additional cost to the Principal. Use for Contractor-initiated substitutions and methodology changes.
| 36.4 | Variations — Pricing |  |  | Order of precedence for valuing a variation: (a) prior agreement; (b) applicable rates or prices in the Contract; (c) rates or prices in a priced bill of quantities, schedule of rates or schedule of prices (even if not a Contract document) to the extent they are reasonable; then (d) reasonable rates or prices. Deductions for omitted work are valued on the same basis. Check the executed contract for how profit, overheads and off-site overheads are treated.
| 3 | Provisional sums |  |  | A provisional sum is not itself payable. The work is valued and the Contract Sum adjusted, commonly with an allowance for profit and attendance stated in the Annexure. Use for the 'Provisional Sum Adjustment' origin.
| 8 | Contract documents |  |  | Deals with discrepancies, ambiguities and inconsistencies between Contract documents, and the Superintendent's direction resolving them. A direction resolving a discrepancy will often be a variation — record the origin as 'Error/Omission in Documents'.
| 11 | Legislative requirements |  |  | Where a legislative requirement changes after a stated date, or differs from what was reasonably foreseeable, the difference in cost is commonly valued as a variation. Use for the 'Authority Requirement' origin.
| 20 | Superintendent |  |  | The Principal must ensure a Superintendent is appointed and that the Superintendent acts honestly and fairly, within the time prescribed (or a reasonable time), and arrives at a reasonable measure or value. This underpins every assessment recorded on the Assessment & Recommendation sheet.
| 25 | Latent conditions |  |  | Physical conditions on the site differing materially from those that should reasonably have been anticipated. Notice requirements are strict. Use for the 'Latent Condition' origin; a latent condition claim is usually valued as a variation.
| 34.2 | Time and progress — Notice of delay |  |  | The Contractor must promptly give written notice of anything likely to cause delay to WUC. Record the date in the notice and time-bar check on the Assessment & Recommendation sheet.
| 34.3 | Time and progress — Claim (extension of time) |  |  | An EOT claim must be given in writing within the period stated in the Contract (28 days in the unamended form) of the Contractor becoming aware of the cause of the delay, and must state the facts on which the claim is based.
| 34.4 | Time and progress — Assessment |  |  | The Superintendent must, within the prescribed period, assess the claim and grant a reasonable extension of time, notifying the Contractor and the Principal in writing.
| 34.5 | Time and progress — Extension of time (by the Superintendent) |  |  | The Superintendent may unilaterally extend time for the Principal's benefit at any time, whether or not the Contractor has claimed.
| 34.9 | Time and progress — Delay damages |  |  | Where the delay is caused by an act or omission of the Principal or Superintendent, delay damages (prolongation costs) may be payable in addition to the extension of time. Price these separately — do not bury them in a variation.
| 35 | Defects liability |  |  | Directions to rectify defects are NOT variations where the work is defective. Only a direction that goes beyond the Contractor's obligations should be recorded here as a variation.
| 37 | Payment |  |  | Approved variations are included in the next payment claim and payment certificate. The 'Approved Amount' column of the Variation Register is what flows into the progress claim and into the adjusted Contract Sum.
| 41 | Notification of claims |  |  | A party must give written notice of any claim for an increase to the Contract Sum or for damages within the period stated in the Contract, and follow it with a detailed claim. This is a strict time bar — check it before assessing entitlement.
| 42 | Dispute resolution |  |  | Where the Contractor does not accept the Superintendent's assessment, the notice of dispute and conference / arbitration process applies. Record the disputed amount in the Variation Register comments and keep the row open.
Sources: clause numbering and headings taken from the AS 4000-1997 General Conditions of Contract contents list; cl 36.4 valuation hierarchy and the cl 34.3 28-day EOT notice period cross-checked against published Australian construction law commentary (Turtons, 'How to claim a variation under AS 4000'; Gemma Nugent Legal, 'Variations under Clause 36 of AS 4000-1997'), accessed August 2026. GST rate of 10% per the ATO.
DISCLAIMER
COMMERCIAL TEMPLATE — NOT LEGAL ADVICE. This workbook is a commercial administration tool. It is not legal advice and does not create, vary or waive any contractual right or obligation.
Clause references in this workbook are to the unamended AS 4000-1997 General Conditions of Contract and are provided as a starting point only. Standard-form contracts are almost always amended by the Annexure or a schedule of amendments, and other forms (AS 4902-2000, AS 2124-1992, AS 4300-1995, GC21, bespoke) number their clauses differently. ALWAYS check every clause reference against the actual executed contract before issuing this document.
Time bars are strict. Notices of delay, extension of time claims and notifications of claims must be given within the periods stated in the executed contract, and failure to do so can extinguish an otherwise valid entitlement.
Amounts in this workbook are in Australian dollars and are stated EXCLUSIVE of GST unless a line is expressly labelled 'incl GST'. The GST rate is held on the Lists & Settings sheet (10% at the date of this template).
Obtain advice from a suitably qualified construction lawyer or contract specialist before relying on this workbook for any contentious variation, latent condition, delay or prolongation claim.
Mastt template · mastt.com · © 2026 Mastt