## Cover
Risk Mitigation Plan
A risk management plan and register for capital projects. The Plan sheet holds the scales, the roles and the review points; the register holds the risks; the actions sheet holds the treatments and who owes them. Ratings come from a matrix lookup and exposure is expressed in money, so the register connects to contingency rather than stopping at a colour.
HOW TO USE IT
1 | Set the plan up first | The Plan sheet is the risk mitigation plan - the scales, the roles, the appetite and the review points. It is not admin. Every rating in the register is meaningless until the likelihood and consequence bands are calibrated to this project's base estimate.
2 | Write the risk, not the worry | Use the three-part form: if CAUSE, then EVENT, resulting in EFFECT. 'Bad weather' is not a risk. 'If rainfall exceeds the 10-year average in Q3, then bulk earthworks are suspended, resulting in 15 days of delay to the critical path' is.
3 | Rate three times, not once | Inherent is before project treatments. Current is where it stands today with what is actually in place. Target is where it lands once the planned actions are done. Most templates carry one score and quietly book benefits that have not been delivered.
4 | Separate the two owners | The risk owner carries accountability and the authority to act. The action owner does the work. One risk, one owner; one risk, many actions, one owner each on the Actions sheet.
5 | Read the exposure, not the colour | Expected cost is probability band x consequence band - real money, and the only arithmetic in this workbook that is mathematically legitimate. It is what connects the register to contingency.
6 | Treat opportunities as real | Risk is the effect of uncertainty on objectives, and effects can be positive. Set the type to Opportunity and use an upside response. A register with no opportunities in it has not been done properly.
7 | Review on events, not on a calendar | Stage gates, contract award, design freeze, planning approval - plus whenever a trigger fires. No standard prescribes a monthly review; the Plan sheet is where you record what actually drives yours.
WHAT IS IN THE WORKBOOK
| Sheet | What it is for
| Plan | The plan itself - project, governance, the calibration that makes ratings mean something, the response set in use and the review trigger.
| Risk Register | One row per risk, rated inherent, current and target, with expected cost in money. Detail columns are grouped and open on demand.
| Treatment Actions | One row per action with its own owner and date. The register counts them and shows how many are done.
| Summary | Counts by rating, status, type and category, and expected cost by category against the contingency held.
| Reference | Every dropdown, the calibrated scales, the rating matrix, the three treatment sets, and the terminology map between ISO, PMI and PRINCE2.
WHAT MOST RISK TEMPLATES GET WRONG
| They multiply the scores | A likelihood rank times a consequence rank is arithmetic on an ordinal scale, and IEC 31010 states plainly that mathematical operations should not be used with ordinal scales. This workbook looks the rating up in a matrix instead, and does its only multiplication on calibrated bands - a probability per cent by a dollar amount - which is a real expected value.
| They carry one score, so the register flatters itself | A single 'risk score after mitigation' quietly books the benefit of actions nobody has done yet. Inherent, current and target are three different numbers here, and the actions that close the gap have owners and dates on their own sheet.
| They have one owner column, and no opportunities | The person accountable for a risk and the person doing the task are different people. And risk is the effect of uncertainty on objectives - effects can be positive. A register with no opportunities in it is half a register.
IMPORTANT
This workbook is a management and record-keeping tool, not advice. Rating scales, risk appetite, escalation thresholds and contingency policy are set by your organisation and by the Contract - set this workbook to match them. Expected cost is an estimate for triage and comparison; it does not replace a quantitative risk analysis where one is required for funding approval.
Built for teams delivering capital projects, programs and portfolios. Mastt · mastt.com

## Reference
RISK MITIGATION PLAN · REFERENCE
Every dropdown is sourced from this sheet. Add your own values inside the ranges, not below them.
Risk category |  | Status |  | Proximity |  | Project phase
Strategic and business case |  | Open |  | Now |  | Strategy and business case
Stakeholder and community |  | Treating |  | Within 3 months |  | Planning and approvals
Planning and approvals |  | Monitoring |  | 3 to 6 months |  | Design
Land and property acquisition |  | Escalated |  | 6 to 12 months |  | Procurement
Environmental and heritage |  | Occurred |  | Beyond 12 months |  | Construction
Design and technical |  | Closed |  | Whole of project |  | Commissioning and handover
Geotechnical and ground conditions | [5 empty] | Defects and warranty
Existing conditions and services
Procurement and contract
Contractor performance and capability
Market, supply chain and escalation
Cost and funding
Program and schedule
Construction delivery
Health, safety and wellbeing
Quality and defects
Commissioning and handover
Operations and maintenance readiness
Industrial relations and resourcing
Weather and force majeure
Regulatory and compliance
Governance and assurance
Treatment - all sets |  | Response set in use |  | Action status |  | Type
Accept |  | A - ISO 31000 (recommended) |  | Not started |  | Threat
Avoid |  | B - PMBOK threats and opportunities |  | In progress |  | Opportunity
Avoid - do not start or continue the activity |  | C - PRINCE2 |  | Complete
Change the consequences |  |  |  | Cancelled |  | Yes / No
Change the likelihood | [5 empty] | Yes
Enhance |  |  |  | Rating |  | No
Escalate |  |  |  | Extreme
Exploit |  |  |  | High
Fallback |  |  |  | Medium
Mitigate |  |  |  | Low
Reduce
Reject
Remove the risk source
Retain by informed decision
Share
Share - contract, insurance or joint venture
Take or increase the risk to pursue an opportunity
Transfer
LIKELIHOOD SCALE - the register reads the bands, not the words
Level |  | From | To | Mid |  | What it means
5 Almost certain |  | 75% | 100% | 87.5% |  | Expected to occur in most circumstances
4 Likely |  | 25% | 75% | 50% |  | Will probably occur in most circumstances
3 Possible |  | 10% | 25% | 17.5% |  | Might occur at some time
2 Unlikely |  | 1% | 10% | 5.5% |  | Could occur at some time
1 Rare |  | 0% | 1% | 0.5% |  | May occur only in exceptional circumstances
CONSEQUENCE SCALE - cost bands are a share of the base estimate on Plan
Level |  | Cost from | Cost to | Mid $ |  | Schedule (days)
5 Catastrophic |  | 10% | 25% | 14875000 |  | 180
4 Major |  | 5% | 10% | 6375000 |  | 90
3 Moderate |  | 2% | 5% | 2975000 |  | 30
2 Minor |  | 0.5% | 2% | 1062500 |  | 10
1 Insignificant |  | 0% | 0.5% | 212500 |  | 2
RATING MATRIX - the register looks the rating up here
Likelihood \ Consequence | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic
5 Almost certain | Medium | High | High | Extreme | Extreme
4 Likely | Low | Medium | High | High | Extreme
3 Possible | Low | Medium | Medium | High | High
2 Unlikely | Low | Low | Medium | Medium | High
1 Rare | Low | Low | Low | Medium | Medium
A risk matrix compares risks; it does not measure them. IEC 31010:2019 states that mathematical operations should not be used with ordinal scales - which is why this workbook never multiplies a likelihood rank by a consequence rank to make a score. The rating is a lookup into the matrix on this sheet. The only multiplication is probability band x consequence band, in per cent and dollars, which is a legitimate expected value. Research into risk matrices - Cox (2008), Thomas, Bratvold and Bickel (2014), Ball and Watt (2013) - documents range compression, centring bias and ranking instability, and none of it supports using a matrix to set contingency. Use the matrix to triage and the expected value to talk about money.
WHAT THE RATING REQUIRES OF YOU
Extreme |  | Unacceptable. Stop or re-scope the activity, or treat it down before proceeding. Owner is the project sponsor. Report at every governance meeting.
High |  | Treat it. A funded treatment plan with a named owner and a date is required. Report monthly to the project control group.
Medium |  | Manage by routine procedure with a nominated owner. Review at each stage gate.
Low |  | Accept and monitor. Review only if the trigger fires or the project changes.
THE THREE TREATMENT SETS - pick one on Plan and stay with it
A - ISO 31000 (recommended) |  | The seven options in ISO 31000:2018 clause 6.5.2, in the standard's own words. Note what is NOT there: no 'transfer' - ISO says SHARE, deliberately, because risk is rarely fully transferred; and no 'mitigate' - ISO never uses the word. Note also the two options almost every free template drops: taking or increasing risk to pursue an opportunity, and removing the risk source. The UK HM Treasury Orange Book mirrors this list almost word for word.
B - PMBOK threats and opportunities |  | Five strategies for threats - Escalate, Avoid, Transfer, Mitigate, Accept - and five for opportunities - Escalate, Exploit, Share, Enhance, Accept. Escalate was added in the 6th edition (2017) for risk outside the project's authority; it needs a named receiving authority, which is why this register has an Escalate to column.
C - PRINCE2 |  | Threats: Avoid, Reduce, Fallback, Transfer, Share, Accept. Opportunities: Exploit, Enhance, Share, Reject. Two differences that matter - PRINCE2 says REDUCE where PMI says mitigate, and it has FALLBACK, a planned response if the risk occurs, which PMI has no equivalent for.
STATUS DEFINITIONS
Open |  | Identified and rated, no treatment agreed yet. The clock is running.
Treating |  | A funded treatment is agreed and actions are in progress on the Actions sheet.
Monitoring |  | Treated as far as it will go. Watch the trigger, review on the set date.
Escalated |  | Outside the project's authority or appetite. Named in Escalate to and raised.
Occurred |  | The risk has materialised. It is now an issue - but the row stays as the record of whether it was foreseen and what was done.
Closed |  | The risk can no longer occur, or the window has passed. Never delete the row.
TERMINOLOGY - the same step has three names
The response step |  | ISO 31000 and Australian, New Zealand and UK public sector practice say RISK TREATMENT. PMI says RISK RESPONSE. US federal and defence practice says MITIGATION, which is where the popular name for this document comes from. All three mean the same step.
This document |  | ISO 31000 clause 6.5.3 names a RISK TREATMENT PLAN. PMBOK names a RISK MANAGEMENT PLAN, a RISK REGISTER and a RISK REPORT. PRINCE2 names a RISK MANAGEMENT APPROACH and a RISK REGISTER. 'Risk mitigation plan' is the common name rather than a standard's name - this workbook holds the plan on the Plan sheet and the register alongside it.
Share or transfer |  | ISO says SHARE - through a contract, insurance or a joint venture - because risk is rarely fully transferred. PMI says TRANSFER. The distinction matters when a contract moves liability but not the consequence of the event happening.
Remaining or residual risk |  | ISO 31000 says the REMAINING RISK should be documented and monitored. The defined term RESIDUAL RISK - risk remaining after risk treatment - comes from the vocabulary standard, ISO 31073:2022, which replaced ISO Guide 73:2009.
Inherent risk |  | No ISO definition exists. In capital projects it means the rating before project-specific treatments, with statutory and design controls assumed present. Say which you mean - the industry uses the word both ways.
Early Warning Register |  | Under NEC4 the NEC3 Risk Register was renamed the Early Warning Register. It is a contractual instrument holding the matter and the action to be taken, not a scored risk assessment. Do not use this workbook as one.
CELL CONVENTIONS
You complete this |  | Pale blue fill, blue text.
Calculated |  | Grey fill. A formula - do not type over it.
Section band |  | Marks the start of a section.

## Plan
RISK MITIGATION PLAN · PLAN
This sheet is the plan - the scales, the roles, the appetite and the review points. Every rating in the register depends on it. Fill it in first.
1 · PROJECT AND GOVERNANCE
Project name
Project number
Client / Owner
Project phase |  | Drives which risks are live. Sourced from Reference.
Project Director |  | Usually the escalation point for Extreme ratings.
Project Manager |  | Owns the risk process, not the risks themselves.
Risk owner group |  | Who can be named as a risk owner - they need budget authority.
Escalation authority |  | Named body a risk goes to when it exceeds project authority.
2 · CALIBRATION - what makes the ratings mean anything
Base estimate (excluding contingency and escalation) | 85000000 | The consequence cost bands on Reference are a share of this. Enter it before rating anything - it is what converts a word like Major into money.
Contingency currently held | 8500000 | Compare this against total expected cost on the Summary. If expected cost exceeds contingency, the register is telling you something.
Response set in use | A - ISO 31000 (recommended) | Three real frameworks and they are not interchangeable. Reference explains each.
Escalate at rating | Extreme | Ratings at or above this need the escalation authority named on the row.
Review at each stage gate | Yes | No standard prescribes a monthly review. Good practice is event-driven - gates, contract award, design freeze, approvals - plus whenever a trigger fires.
3 · WHERE THE REGISTER STANDS
Risks on the register | 12
Open - not yet closed | 12
Extreme and High, open | 6
Opportunities identified | 1
Expected cost - open threats | 19512812.5
Expected cost as % of contingency | 229.6%
Expected cost across the open register is the register's contribution to contingency - it is the arithmetic mean of what these risks are worth, which is the sense in which contingency is expected to be spent. It is not a P-value. A P50, P65, P80 or P90 figure comes from a Monte Carlo simulation over the base estimate and the quantified risk ranges, and the percentile required depends on who is funding the project - it differs by jurisdiction and by programme, so take it from your funding guidance rather than assuming a number.

## Risk Register
RISK MITIGATION PLAN · REGISTER
EXAMPLE DATA - 12 risks and 13 actions are worked examples. Delete them and this banner clears.
One row per risk. Blue cells are yours; grey columns calculate. The rating is looked up in the matrix on Reference - it is never a likelihood rank multiplied by a consequence rank. Columns H to M and V onward are grouped: click the + above the column headers to open the inherent, target and governance detail.
Ref | Risk ID | Category | Type | Risk event - if CAUSE, then EVENT, resulting in EFFECT | Risk owner (accountable) | Inherent likelihood | Inherent consequence | Inherent rating | Existing controls | Trigger / early warning | Proximity | Current likelihood | Current consequence | Current rating | Expected cost | Expected days | Treatment strategy | Actions | Actions done | Target likelihood | Target consequence | Target rating | Movement | Escalate to | Phase | Status | Date raised | Last reviewed | Next review | Overdue review | Closure criteria | Date closed | Notes
1 | RSK-001 | Geotechnical and ground conditions | Threat | If ground conditions below RL 12 differ from the geotechnical baseline, then piling depths increase across the podium, resulting in additional cost and delay to the structure | Design Manager | 5 Almost certain | 4 Major | Extreme | See the treatment actions listed against this risk | First 3 test piles exceed baseline depth by more than 10% | Within 3 months | 4 Likely | 4 Major | High | 3187500 | 45 | Change the likelihood | 2 | 0 | 2 Unlikely | 3 Moderate | Medium | Improving |  | Design | Treating | 2026-07-01 | 2026-08-01 | 2026-09-15 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE - delete before use
2 | RSK-002 | Planning and approvals | Threat | If the development approval condition on out-of-hours work is not varied, then night pours cannot proceed, resulting in loss of float on the structure | Project Director | 4 Likely | 4 Major | High | See the treatment actions listed against this risk | Council response not received 14 days before the first planned night pour | Now | 4 Likely | 3 Moderate | High | 1487500 | 15 | Change the consequences | 2 | 0 | 2 Unlikely | 3 Moderate | Medium | Improving |  | Planning and approvals | Treating | 2026-07-01 | 2026-08-01 | 2026-08-29 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE
3 | RSK-003 | Market, supply chain and escalation | Threat | If structural steel escalation exceeds the allowance in the base estimate, then the trade package cannot be let within budget, resulting in a funding shortfall | Commercial Manager | 4 Likely | 4 Major | High | See the treatment actions listed against this risk | Published steel index moves more than 5% in a quarter | 3 to 6 months | 3 Possible | 4 Major | High | 1115625 | 16 | Share - contract, insurance or joint venture | 1 | 0 | 2 Unlikely | 4 Major | Medium | Improving |  | Procurement | Treating | 2026-07-01 | 2026-08-01 | 2026-09-30 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE
4 | RSK-004 | Existing conditions and services | Threat | If the live HV cable alignment differs from the service authority records, then excavation in the north-east corner is suspended, resulting in delay and re-design of the substation | Construction Manager | 5 Almost certain | 3 Moderate | High | See the treatment actions listed against this risk | Potholing finds any service outside the surveyed corridor | Within 3 months | 3 Possible | 3 Moderate | Medium | 520625 | 5 | Remove the risk source | 1 | 1 | 2 Unlikely | 3 Moderate | Medium | Flat |  | Construction | Monitoring | 2026-07-01 | 2026-08-01 | 2026-09-05 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE
5 | RSK-005 | Contractor performance and capability | Threat | If the facade subcontractor's order book grows beyond its fabrication capacity, then unit delivery slips, resulting in delay to building enclosure | Contract Administrator | 4 Likely | 4 Major | High | See the treatment actions listed against this risk | Two consecutive monthly fabrication reports below the agreed rate | 6 to 12 months | 4 Likely | 4 Major | High | 3187500 | 45 | Change the likelihood | 1 | 0 | 3 Possible | 3 Moderate | Medium | Improving |  | Construction | Open | 2026-07-01 | 2026-08-01 | 2026-08-22 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE - untreated, high current rating
6 | RSK-006 | Cost and funding | Opportunity | If the early works package is tendered before the market softens in Q1, then competitive tension increases, resulting in a saving against the base estimate | Commercial Manager | 2 Unlikely | 2 Minor | Low | See the treatment actions listed against this risk | Three or more compliant tenders received | Within 3 months | 3 Possible | 3 Moderate | Medium | 520625 | 5 | Take or increase the risk to pursue an opportunity | 1 | 0 | 4 Likely | 4 Major | High | Worsening |  | Procurement | Treating | 2026-07-01 | 2026-08-01 | 2026-09-12 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE - opportunity, upside response
7 | RSK-007 | Design and technical | Threat | If the services coordination model is not resolved before the shop drawing release, then clashes are found on site, resulting in rework and delay to fit-out | Design Manager | 4 Likely | 3 Moderate | High | See the treatment actions listed against this risk | Clash report exceeds 50 unresolved hard clashes at the 90% model review | Within 3 months | 3 Possible | 3 Moderate | Medium | 520625 | 5 | Change the likelihood | 1 | 0 | 2 Unlikely | 2 Minor | Low | Improving |  | Design | Treating | 2026-07-01 | 2026-08-01 | 2026-09-01 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE
8 | RSK-008 | Health, safety and wellbeing | Threat | If work at height controls on the perimeter are not verified before the facade starts, then a fall from height occurs, resulting in serious injury and a work stoppage | Project Director | 5 Almost certain | 5 Catastrophic | Extreme | See the treatment actions listed against this risk | Any perimeter edge protection non-conformance raised at inspection | 3 to 6 months | 2 Unlikely | 5 Catastrophic | High | 818125 | 10 | Change the likelihood | 1 | 0 | 1 Rare | 5 Catastrophic | Medium | Improving |  | Construction | Monitoring | 2026-07-01 | 2026-08-01 | 2026-09-19 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE - low likelihood, catastrophic consequence
9 | RSK-009 | Stakeholder and community | Threat | If community objection to the construction traffic route is sustained, then the approved haul route is withdrawn, resulting in longer haulage and higher disposal cost | Stakeholder Manager | 3 Possible | 3 Moderate | Medium | See the treatment actions listed against this risk | More than 5 complaints received in any 30-day period | Within 3 months | 3 Possible | 2 Minor | Medium | 185937.5 | 2 | Change the consequences | 1 | 0 | 2 Unlikely | 2 Minor | Low | Improving |  | Construction | Monitoring | 2026-07-01 | 2026-08-01 | 2026-10-10 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE
10 | RSK-010 | Governance and assurance | Threat | If the funding decision for Stage 2 is deferred beyond the December gate, then the contractor demobilises, resulting in remobilisation cost and loss of program | Project Sponsor | 4 Likely | 5 Catastrophic | Extreme | See the treatment actions listed against this risk | Gate paper not lodged 6 weeks before the committee date | 6 to 12 months | 4 Likely | 5 Catastrophic | Extreme | 7437500 | 90 | Retain by informed decision | 1 | 0 | 4 Likely | 5 Catastrophic | Extreme | Flat | Infrastructure Investment Committee | Strategy and business case | Escalated | 2026-07-01 | 2026-08-01 | 2026-08-20 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE - outside project authority, escalated
11 | RSK-011 | Weather and force majeure | Threat | If rainfall in Q3 exceeds the 10-year average, then bulk earthworks are suspended, resulting in delay to the critical path | Construction Manager | 4 Likely | 3 Moderate | High | See the treatment actions listed against this risk | Cumulative monthly rainfall exceeds the 10-year average by 20% | Within 3 months | 4 Likely | 2 Minor | Medium | 531250 | 5 | Retain by informed decision | 0 | 0 | 4 Likely | 2 Minor | Medium | Flat |  | Construction | Monitoring | 2026-07-01 | 2026-08-01 | 2026-09-08 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE - weather retained, not treatable
12 | RSK-012 | Commissioning and handover | Threat | If the O&M documentation is not delivered progressively, then commissioning evidence is incomplete at handover, resulting in delay to Substantial Completion | Project Manager | 4 Likely | 3 Moderate | High | See the treatment actions listed against this risk | Less than 60% of O&M sections received by practical completion minus 8 weeks | Beyond 12 months | 3 Possible | 3 Moderate | Medium | 520625 | 5 | Change the likelihood | 1 | 0 | 2 Unlikely | 2 Minor | Low | Improving |  | Commissioning and handover | Open | 2026-07-01 | 2026-08-01 | 2026-11-28 |  | Trigger has passed without the event, or the phase is complete |  | EXAMPLE
Write the risk as if CAUSE, then EVENT, resulting in EFFECT - a register full of one-word worries cannot be treated or costed. Rate inherent, current and target separately: current is what you carry today, target is what you get once the actions on the next sheet are done. Expected cost is the probability band multiplied by the consequence band, which is the only arithmetic here that survives contact with IEC 31010. Prints A3 landscape.
Formulas:
Overdue review = IF(OR(F9="",[Next review]="",[Status]="Closed"),"",IF([Next review]<TODAY(),"Overdue",""))

## Treatment Actions
RISK MITIGATION PLAN · TREATMENT ACTIONS
One row per action. A risk has one owner who is accountable; each action has its own owner who is responsible for doing it. The register counts these automatically.
Risk ID | Risk event | Treatment action | Action owner (responsible) | Status | Due | Days to due | Flag | Notes
RSK-001 | If ground conditions below RL 12 differ from the geotechnical baseline, then piling depths increase across the podium, resulting in additional cost and delay to the structure | Commission additional boreholes at grid lines 4 to 9 to confirm rock level | Design Manager | In progress | 2026-09-05 | 23 | On track | EXAMPLE
RSK-001 | If ground conditions below RL 12 differ from the geotechnical baseline, then piling depths increase across the podium, resulting in additional cost and delay to the structure | Price a deeper pile option and hold as a contingent design | Cost Manager | Not started | 2026-09-20 | 38 | On track | EXAMPLE
RSK-002 | If the development approval condition on out-of-hours work is not varied, then night pours cannot proceed, resulting in loss of float on the structure | Lodge the section 4.55 variation for out-of-hours work | Planning Consultant | In progress | 2026-08-25 | 12 | Due soon | EXAMPLE
RSK-002 | If the development approval condition on out-of-hours work is not varied, then night pours cannot proceed, resulting in loss of float on the structure | Re-sequence the pours to avoid night work in the base program | Planner | Not started | 2026-09-10 | 28 | On track | EXAMPLE
RSK-003 | If structural steel escalation exceeds the allowance in the base estimate, then the trade package cannot be let within budget, resulting in a funding shortfall | Lock the steel rate through an early supply agreement | Commercial Manager | In progress | 2026-09-25 | 43 | On track | EXAMPLE
RSK-004 | If the live HV cable alignment differs from the service authority records, then excavation in the north-east corner is suspended, resulting in delay and re-design of the substation | Pothole the full HV alignment before excavation starts | Construction Manager | Complete | 2026-08-30 | 17 | Done | EXAMPLE
RSK-005 | If the facade subcontractor's order book grows beyond its fabrication capacity, then unit delivery slips, resulting in delay to building enclosure | Obtain and verify the facade fabricator's committed capacity | Contract Administrator | Not started | 2026-09-15 | 33 | On track | EXAMPLE
RSK-006 | If the early works package is tendered before the market softens in Q1, then competitive tension increases, resulting in a saving against the base estimate | Bring the early works tender forward to November | Commercial Manager | In progress | 2026-09-02 | 20 | On track | EXAMPLE
RSK-007 | If the services coordination model is not resolved before the shop drawing release, then clashes are found on site, resulting in rework and delay to fit-out | Run a federated model clash review at 90% design | BIM Manager | In progress | 2026-08-28 | 15 | On track | EXAMPLE
RSK-008 | If work at height controls on the perimeter are not verified before the facade starts, then a fall from height occurs, resulting in serious injury and a work stoppage | Verify perimeter edge protection against the safety plan before facade start | HSE Manager | Not started | 2026-09-18 | 36 | On track | EXAMPLE
RSK-009 | If community objection to the construction traffic route is sustained, then the approved haul route is withdrawn, resulting in longer haulage and higher disposal cost | Agree an alternative haul route with council as a fallback | Stakeholder Manager | Not started | 2026-10-01 | 49 | On track | EXAMPLE
RSK-010 | If the funding decision for Stage 2 is deferred beyond the December gate, then the contractor demobilises, resulting in remobilisation cost and loss of program | Lodge the Stage 2 gate paper 6 weeks before the committee | Project Sponsor | In progress | 2026-08-18 | 5 | Due soon | EXAMPLE
RSK-012 | If the O&M documentation is not delivered progressively, then commissioning evidence is incomplete at handover, resulting in delay to Substantial Completion | Agree progressive O&M delivery milestones in the contract | Project Manager | Not started | 2026-10-15 | 63 | On track | EXAMPLE
ISO 31000 requires a treatment plan to record who is accountable and responsible, the proposed actions, the resources, the performance measures and when the actions are expected to be completed. That is what this sheet is. An action with no owner and no date is not a treatment - it is an intention.
Formulas:
Days to due = IF(OR([Risk ID]="",[Due]=""),"",[Due]-TODAY())
Flag = IF([Risk ID]="","",IF([Status]="Complete","Done",IF([Status]="Cancelled","Cancelled",IF([Due]="","No date",IF([Due]<TODAY(),"Overdue",IF([Due]-TODAY()<=14,"Due soon","On track"))))))

## Summary
RISK MITIGATION PLAN · SUMMARY
EXAMPLE DATA - 12 risks and 13 actions are worked examples. Delete them and this banner clears.
Every figure is a formula over the register. Open means anything not Closed.
EXPOSURE
Risks on the register |  | 12 |  | Extreme, open |  | 1
Open |  | 12 |  | High, open |  | 5
Threats |  | 11 |  | Reviews overdue |  | 0
Opportunities |  | 1 |  | Escalated |  | 1
Expected cost - open threats |  | 19512812.5 |  | Contingency held |  | 8500000
Expected upside - open opportunities |  | 520625 |  | Expected cost vs contingency |  | 229.6%
Expected cost across the open register is the register's contribution to contingency - it is the arithmetic mean of what these risks are worth, which is the sense in which contingency is expected to be spent. It is not a P-value. A P50, P65, P80 or P90 figure comes from a Monte Carlo simulation over the base estimate and the quantified risk ranges, and the percentile required depends on who is funding the project - it differs by jurisdiction and by programme, so take it from your funding guidance rather than assuming a number.
Category counts show OPEN risks only.
BY CURRENT RATING |  |  |  | BY CATEGORY
Current Rating | Items | Share |  | Category | Items | Share
Extreme | 1 | 8.333% | ¦ | Strategic and business case | 0 | 0%
High | 5 | 41.67% | ¦¦¦¦¦ | Stakeholder and community | 1 | 8.333% | ¦
Medium | 6 | 50% | ¦¦¦¦¦¦ | Planning and approvals | 1 | 8.333% | ¦
Low | 0 | 0% |  | Land and property acquisition | 0 | 0%
|  |  |  | Environmental and heritage | 0 | 0%
BY STATUS |  |  |  | Design and technical | 1 | 8.333% | ¦
Status | Items | Share |  | Geotechnical and ground conditions | 1 | 8.333% | ¦
Open | 2 | 16.67% | ¦¦ | Existing conditions and services | 1 | 8.333% | ¦
Treating | 5 | 41.67% | ¦¦¦¦¦ | Procurement and contract | 0 | 0%
Monitoring | 4 | 33.33% | ¦¦¦¦ | Contractor performance and capability | 1 | 8.333% | ¦
Escalated | 1 | 8.333% | ¦ | Market, supply chain and escalation | 1 | 8.333% | ¦
Occurred | 0 | 0% |  | Cost and funding | 1 | 8.333% | ¦
Closed | 0 | 0% |  | Program and schedule | 0 | 0%
|  |  |  | Construction delivery | 0 | 0%
BY TYPE |  |  |  | Health, safety and wellbeing | 1 | 8.333% | ¦
Type | Items | Share |  | Quality and defects | 0 | 0%
Threat | 11 | 91.67% | ¦¦¦¦¦¦¦¦¦¦¦ | Commissioning and handover | 1 | 8.333% | ¦
Opportunity | 1 | 8.333% | ¦ | Operations and maintenance readiness | 0 | 0%
|  |  |  | Industrial relations and resourcing | 0 | 0%
EXPECTED COST BY CATEGORY - open threats |  |  |  | Weather and force majeure | 1 | 8.333% | ¦
Category | Risks | Expected cost |  | Regulatory and compliance | 0 | 0%
Strategic and business case | 0 | 0 |  | Governance and assurance | 1 | 8.333% | ¦
Stakeholder and community | 1 | 185937.5
Planning and approvals | 1 | 1487500
Land and property acquisition | 0 | 0
Environmental and heritage | 0 | 0
Design and technical | 1 | 520625
Geotechnical and ground conditions | 1 | 3187500
Existing conditions and services | 1 | 520625
Procurement and contract | 0 | 0
Contractor performance and capability | 1 | 3187500
Market, supply chain and escalation | 1 | 1115625
Cost and funding | 0 | 0
Program and schedule | 0 | 0
Construction delivery | 0 | 0
Health, safety and wellbeing | 1 | 818125
Quality and defects | 0 | 0
Commissioning and handover | 1 | 520625
Operations and maintenance readiness | 0 | 0
Industrial relations and resourcing | 0 | 0
Weather and force majeure | 1 | 531250
Regulatory and compliance | 0 | 0
Governance and assurance | 1 | 7437500
TOTAL - open threats | 11 | 19512812.5
Expected cost is the probability band multiplied by the consequence band - real money, and the only arithmetic in this workbook that IEC 31010 permits. It is a mean, not a percentile: it tells you what these risks are worth in aggregate, which is the sense in which contingency is expected to be spent. It is not a substitute for a quantitative risk analysis where your funding guidance requires one.