## Sheet1
EXTENSION OF TIME REGISTER TEMPLATE
Project Name: |  | < Insert Project Name > |  | Client / Principal: | < Insert Client / Principal Organisation > |  |  | Head Contractor: | < Insert Head Contractor > |  | Contract Start Date: |  | < Insert Contract Start Date >
Project Number: |  | < Insert Project Number > |  | Project Manager: | < Insert Project Manager Organisation > |  |  | Contract Number: | < Insert Contract Number >
[11 empty] | Original Practical Completion Date: |  |  |  | < Insert Original Practical Completion Date >
Date Last Updated: |  | < Insert Date Issued > | [8 empty] | Current Practical Completion Date: |  |  |  | 2025-11-01
EOT Ref No. | Date of Submission |  | Description of Delay Event |  |  | Delay Period Claimed | Relevant Contract Clause |  |  | Supporting Documentation |  | Status |  | Days Approved |  | Revised Practical Completion Date | Comments
A | B |  | C |  |  | D | E |  |  | F |  | G |  | H |  | I | J
EOT - 001 | 2025-04-05 |  | Latent Condition – Rock Excavation |  |  | 14 Working Days | Clause 35.5 – Delay Due to Variation (AS 4000) |  |  | Delay Analysis, Email Correspondence |  | Under Review |  | 0 |  | 2025-09-12 | Rejected due to late submission.
EOT - 002 | 2025-04-11 |  | Late Client Instruction |  |  | 5 Working Days | Clause 34.3 – Latent Conditions (AS 4000) |  |  | Programme Impact Analysis, RFIs |  | Approved |  | 5 |  | 2025-09-06 | Partial approval granted.
EOT - 003 | 2025-04-10 |  | Latent Condition – Rock Excavation |  |  | 5 Working Days | Clause 34.3 – Latent Conditions (AS 4000) |  |  | Programme Impact Analysis, RFIs |  | Under Review |  | 0 |  | 2025-09-10 | Valid cause but insufficient evidence.
EOT - 004 | 2025-04-24 |  | Covid-19 Restrictions |  |  | 12 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Geotechnical Report, Site Logs |  | Rejected |  | 0 |  | 2025-09-18 | Rejected due to late submission.
EOT - 005 | 2025-04-15 |  | Late Client Instruction |  |  | 7 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Photographs, Superintendent Notice |  | Approved |  | 4 |  | 2025-09-10 | Rejected due to late submission.
EOT - 006 | 2025-04-10 |  | Covid-19 Restrictions |  |  | 7 Working Days | Clause 34.9 – Inclement Weather (AS 4000) |  |  | Photographs, Superintendent Notice |  | Under Review |  | 0 |  | 2025-09-15 | Rejected due to late submission.
EOT - 007 | 2025-04-22 |  | Late Client Instruction |  |  | 5 Working Days | Clause 34.3 – Latent Conditions (AS 4000) |  |  | Delay Analysis, Email Correspondence |  | Approved |  | 3 |  | 2025-09-13 | Valid cause but insufficient evidence.
EOT - 008 | 2025-05-01 |  | Covid-19 Restrictions |  |  | 10 Working Days | Clause 34.3 – Latent Conditions (AS 4000) |  |  | Geotechnical Report, Site Logs |  | Rejected |  | 0 |  | 2025-09-23 | Partial approval granted.
EOT - 009 | 2025-04-30 |  | Unexpected Utility Services |  |  | 10 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Site Diary, Weather Report |  | Approved |  | 9 |  | 2025-09-22 | Rejected due to late submission.
EOT - 010 | 2025-04-29 |  | Wet Weather |  |  | 7 Working Days | Clause 34.3 – Latent Conditions (AS 4000) |  |  | Photographs, Superintendent Notice |  | Approved |  | 7 |  | 2025-09-29 | Valid cause but insufficient evidence.
EOT - 011 | 2025-04-29 |  | Unforeseen Soil Contamination |  |  | 10 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Delay Analysis, Email Correspondence |  | Rejected |  | 0 |  | 2025-10-06 | Rejected due to late submission.
EOT - 012 | 2025-04-01 |  | Wet Weather |  |  | 5 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Site Diary, Weather Report |  | Approved |  | 5 |  | 2025-10-04 | Awaiting additional documentation.
EOT - 013 | 2025-04-07 |  | Wet Weather |  |  | 14 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Site Diary, Weather Report |  | Under Review |  | 0 |  | 2025-10-16 | Rejected due to late submission.
EOT - 014 | 2025-04-19 |  | Wet Weather |  |  | 5 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Geotechnical Report, Site Logs |  | Partially Approved |  | 5 |  | 2025-10-09 | Rejected due to late submission.
EOT - 015 | 2025-04-24 |  | Latent Condition – Rock Excavation |  |  | 14 Working Days | Clause 34.9 – Inclement Weather (AS 4000) |  |  | Photographs, Superintendent Notice |  | Rejected |  | 0 |  | 2025-10-21 | Partial approval granted.
EOT - 016 | 2025-04-17 |  | Industrial Action |  |  | 5 Working Days | Clause 35.5 – Delay Due to Variation (AS 4000) |  |  | Photographs, Superintendent Notice |  | Under Review |  | 0 |  | 2025-10-14 | Awaiting additional documentation.
EOT - 017 | 2025-04-28 |  | Variation Works |  |  | 14 Working Days | Clause 35.5 – Delay Due to Variation (AS 4000) |  |  | Programme Impact Analysis, RFIs |  | Rejected |  | 0 |  | 2025-10-23 | Partial approval granted.
EOT - 018 | 2025-04-01 |  | Covid-19 Restrictions |  |  | 14 Working Days | Clause 35.5 – Delay Due to Variation (AS 4000) |  |  | Geotechnical Report, Site Logs |  | Under Review |  | 0 |  | 2025-10-22 | Approved subject to site verification.
EOT - 019 | 2025-04-11 |  | Access Restrictions |  |  | 14 Working Days | Clause 35.5 – Delay Due to Variation (AS 4000) |  |  | Site Diary, Weather Report |  | Partially Approved |  | 12 |  | 2025-10-21 | Partial approval granted.
EOT - 020 | 2025-04-10 |  | Design Change |  |  | 14 Working Days | Clause 34.7 – Acts of Authority (AS 4000) |  |  | Photographs, Superintendent Notice |  | Approved |  | 11 |  | 2025-11-01 | Valid cause but insufficient evidence.
EOT - 021 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 022 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 023 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 024 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 025 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 026 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 027 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 028 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 029 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 030 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 031 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 032 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 033 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 034 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 035 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 036 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 037 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 038 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 039 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 040 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 041 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 042 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 043 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 044 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 045 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 046 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 047 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 048 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 049 | … |  | … |  |  | … | … |  |  | … |  | … |  | … |  | … | …
EOT - 050 | < Insert Date > |  | < Insert Description > |  |  | < Insert Days > | < Insert Contract Clause > |  |  | < Insert Supporting Documentation > |  | < Insert Status > |  | < Insert Days > |  | < Insert Date > | < Insert Comments >