PROJECT INITIATION DOCUMENT Project Initiation Document Template and completion guide for capital works and infrastructure projects

| Project name |  | Project number |  |
| --- | --- | --- | --- |
| Client / asset owner |  | Delivery organisation |  |
| Prepared by (Project Manager) |  | Date |  |
| Document reference |  | Revision | 1.0 |
| Status | Draft / For approval / Baselined | Current gate / stage |  |

This template is provided by Mastt as general guidance for capital project delivery. It is not legal, financial or professional advice. Users must adapt it to the contract, jurisdiction, statutory regime and organisational policies applicable to their project, and should obtain independent professional advice where appropriate. Mastt accepts no liability arising from use of this template.

## Revision history

| Rev | Date | Prepared by | Reviewed by | Approved by | Description of change |
| --- | --- | --- | --- | --- | --- |
| A |  |  |  |  | First issue for review |
| B |  |  |  |  |  |
| 0 |  |  |  |  | Issued for use |

Guidance Record every issue of this PID. Once the PID is approved it is a baselined configuration item: subsequent changes are made only through the change control process in Section 8 and must be re-approved by the authority that approved the original. Show the revision that is currently in force in the header of every report that references it.

## Document control and distribution

Guidance Name the single accountable owner of this document and every party who must receive a controlled copy. 'Controlled' means the recipient is notified of, and must work to, each new revision. Uncontrolled copies are reference only and must be marked as such.

| Attribute | Detail |
| --- | --- |
| Document title | Project Initiation Document |
| Document reference / ID |  |
| Document owner (accountable) | Project Manager |
| Author(s) |  |
| Approving authority | Project Board / Investment Committee |
| Security classification |  |
| Storage location (CDE / EDMS path) |  |
| Retention period |  |
| Review cycle | At each stage boundary and on exception |
| Next scheduled review |  |

| Distribution - name | Role | Organisation | Copy type | Format | Date issued |
| --- | --- | --- | --- | --- | --- |
|  | Project Executive / Sponsor |  | Controlled | PDF |  |
|  | Senior User |  | Controlled | PDF |  |
|  | Senior Supplier |  | Controlled | PDF |  |
|  | Project Manager |  | Controlled | Native |  |
|  | Project Assurance |  | Controlled | PDF |  |
|  | Finance / Funding body |  | Controlled | PDF |  |
|  | Asset owner / Operator |  | Uncontrolled | PDF |  |

## Related documents register

Guidance The PID does not stand alone. List the documents it draws authority from (upstream) and the documents it mandates (downstream), with the exact version relied upon. If a referenced document is superseded, check whether this PID remains valid before continuing to rely on it.

| Document | Reference | Version | Owner | Relationship to PID |
| --- | --- | --- | --- | --- |
| Strategic assessment / needs case |  |  | Sponsor | Upstream - establishes the need this project answers |
| Approved business case (five-case) |  |  | Sponsor | Upstream - the investment decision this PID implements |
| Feasibility study |  |  | Client Project Director | Upstream - technical viability of the recommended option |
| Options appraisal / cost benefit analysis |  |  | Sponsor | Upstream - evidences the recommended option and value for money |
| Funding approval / appropriation instrument |  |  | Finance | Upstream - authorises expenditure and sets drawdown conditions |
| Project Execution Plan (PEP) |  |  | Project Manager | Downstream - the delivery-stage operating manual |
| Risk management plan and risk register |  |  | Project Manager | Downstream - expands Section 12 into working process |
| Benefits realisation plan |  |  | Senior User | Downstream - expands Section 11 and runs past handover |
| Stakeholder and communications plan |  |  | Project Manager | Downstream - expands Section 13 |
| HSE, quality and environmental management plans |  |  | Respective leads | Downstream - expands Section 14 |
| Information / BIM execution plan |  |  | Information Manager | Downstream - expands Section 15 |
| Procurement strategy and contract documents |  |  | Commercial Lead | Downstream - gives effect to Section 6 |
| Programme / portfolio management plan |  |  | Programme Manager | Lateral - sets the controls this project inherits |

## Approval and authorisation

Guidance Signature here is not a formality. It is the act that converts an approved business case into a mandated project: it baselines the PID, confirms the tolerances delegated to the Project Manager, and authorises the commitment of the funds described in Section 10 within those tolerances.

By signing below, each party confirms that they have read this Project Initiation Document, that it correctly records the project they are accountable for, and that:

the PID is baselined at the revision shown on the cover, and becomes the reference against which delivery performance, change and project closure are judged;

the project is authorised to proceed from initiation into the first delivery stage, subject to any conditions of approval recorded in Section 18;

the delegations, tolerances and thresholds in Sections 7 and 8 are granted to the Project Manager, and deviation beyond them must be escalated as an exception;

the expenditure and funding arrangements in Section 10 are approved in principle, subject to the approvals regime applicable in your jurisdiction and to the organisation's financial delegations;

the benefits in Section 11 are accepted as the measures of success, and named owners accept accountability for realising them.

| Role | Name | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
| Project Manager |  |  |  |  |
| Senior User |  |  |  |  |
| Senior Supplier |  |  |  |  |
| Project Executive / Sponsor |  |  |  |  |
| Client Project Director |  |  |  |  |

Conditions attached to this approval (if any) are recorded in Section 18.2 and must be discharged by the dates stated.

# Contents

Right-click and choose 'Update Field' to build the table of contents.

The table of contents is a field. Open in Microsoft Word, select the field and press F9 (or right-click → Update Field → Update entire table) to populate it.

# Glossary and abbreviations

Guidance Delete terms that do not apply and add organisation-specific or contract-specific terms. Where a term is defined in the contract, the contract definition prevails over this glossary - say so explicitly to avoid an interpretation dispute later.

| Term | Definition |
| --- | --- |
| Acceptance criteria | The measurable conditions a deliverable must meet before the client will accept it. Defined at initiation, tested at handover. |
| AIR - Asset Information Requirements | The information the asset owner needs, in defined form, to operate and maintain the completed asset (ISO 19650). |
| Assumption | A statement taken as true for planning purposes that has not been verified. Every assumption carries an owner and a validation date. |
| Assurance | Independent, systematic checking that the project is being defined and delivered as intended. Distinct from, and additional to, the Project Manager's own controls. |
| Baseline | An approved, version-controlled reference (scope, schedule, cost, benefits) against which performance is measured and change is assessed. |
| Benefit | A measurable improvement resulting from an outcome that is perceived as an advantage by one or more stakeholders. |
| Benefits realisation | The process of ensuring benefits are identified, owned, measured and delivered - typically continuing well past project closure. |
| Business as usual (BAU) | The ongoing operational activity of the organisation into which the project's outputs are transitioned. |
| Business case | The document justifying the investment: the strategic, economic, commercial, financial and management cases for proceeding. |
| Capital cost (CAPEX) | Expenditure to create or materially enhance an asset, capitalised on the balance sheet under the accounting framework applicable to your organisation. |
| CDE - Common Data Environment | The single agreed source of information for the project, with defined states, approval workflow and access control (ISO 19650). |
| Change control | The process by which proposed departures from a baseline are identified, assessed, approved or rejected, and recorded. |
| Configuration management | Identifying, controlling and accounting for the status of the project's products and the documents that define them. |
| Constraint | A limitation the project must work within - funding envelope, fixed date, site access window, operational shutdown, regulatory condition. |
| Contingency | Funds or time held to address risks that have been quantified and are expected to occur across the project as a whole. Owned and released under defined authority - not the Project Manager's spending money. |
| Cost Benefit Analysis (CBA) | The economic appraisal comparing the whole-life costs of an option with its quantified benefits and disbenefits, usually discounted to present value. |
| Critical path | The longest sequence of dependent activities determining the earliest possible completion date. Delay on it delays the project. |
| Deliverable | A tangible, verifiable output the project must produce. Called a 'product' in PRINCE2. |
| Delivery model | The contractual and organisational arrangement used to deliver the works - for example design-bid-build, design and construct, construction management, managing contractor, alliance or integrated partnership. |
| Dependency | A relationship where the project relies on another party (inbound) or another party relies on the project (outbound). |
| Disbenefit | A measurable negative consequence of the project perceived as a disadvantage by a stakeholder. Must be declared, not hidden. |
| EIR - Exchange Information Requirements | What information must be delivered, when, in what format and to what standard, by each appointed party (ISO 19650). |
| Escalation | Referring a matter to a higher authority because it is forecast to breach a delegated tolerance or cannot be resolved at the current level. |
| Exception | A forecast breach of an agreed tolerance. Triggers an Exception Report and a decision by the level above. |
| Gate / gateway review | A go/no-go decision point at a stage boundary, usually informed by an independent assurance review. |
| Handover | The formal transfer of completed works, information and responsibility to the asset owner or operator. |
| HSE | Health, safety and environment - the obligations, standards and performance requirements applying to the works and the workforce. |
| Interface | A boundary between the project and another party, system, contract or asset, across which something must be coordinated. |
| Issue | A risk that has occurred, or any unplanned event requiring management action now. Managed through the issue log, not the risk register. |
| KPI | Key performance indicator - a quantified measure of delivery or benefit performance, with a target and a reporting frequency. |
| Lifecycle | The set of stages a project passes through from strategic assessment to benefits review, each ending in a controlled decision point. |
| Milestone | A zero-duration schedule event marking the achievement of a defined state - usually a decision, an approval, a handover or a completion. |
| Operating cost (OPEX) | Recurrent expenditure to run and maintain the asset once in service. |
| Optimism bias | The demonstrated tendency to underestimate cost and duration and overestimate benefits. Corrected by reference-class adjustment or an explicit uplift. |
| Options appraisal | The structured comparison of a long list and short list of ways to meet the need, leading to a recommended option. |
| Outcome | The change in state or capability that results from using the project's outputs. Outcomes, not outputs, generate benefits. |
| Output | What the project physically produces - the asset, system, facility or document set. |
| PEP - Project Execution Plan | The delivery-stage operating manual: how the project will actually be run day to day. Subordinate to, and mandated by, this PID. |
| PID - Project Initiation Document | This document. Defines what the project is, why it is being done, who is involved and how it will be governed; baselined at the end of initiation. |
| PMBOK | The Project Management Institute's body of knowledge; PMBOK 7 is principle- and performance-domain based. |
| Portfolio | The organisation's total collection of programmes and projects, prioritised and resourced against strategy. |
| PRINCE2 | A process-based project management method structured around themes, principles and processes, in which the PID is the artefact baselined at the end of Initiating a Project. |
| Programme | A coordinated group of related projects and activities delivering outcomes and benefits that none could deliver alone. |
| Project Assurance | The Project Board's independent check on business, user and supplier interests. Cannot be delegated to the Project Manager. |
| Project Board | The decision-making body accountable for the project, comprising the Executive, Senior User and Senior Supplier. |
| RACI | Responsible, Accountable, Consulted, Informed - a responsibility assignment convention. Exactly one 'A' per activity. |
| Residual risk | The exposure remaining after planned treatments have been applied. |
| Risk appetite | The amount and type of risk the organisation is willing to pursue or retain in pursuit of its objectives (ISO 31000). |
| Senior Supplier | The Project Board role accountable for the integrity of what is supplied - design, construction and specialist services. |
| Senior User | The Project Board role representing those who will use the outputs and who is accountable for specifying and realising the benefits. |
| SMART | Specific, Measurable, Achievable, Relevant, Time-bound - the test applied to project objectives. |
| Stage | A managed section of the project, ending at a control point where continuation is authorised or refused. |
| Stakeholder | Any individual, group or organisation that can affect, is affected by, or believes it is affected by the project. |
| Tolerance | The permissible deviation from a plan (cost, time, scope, quality, risk, benefit) before escalation to the level above is required. |
| Value for money (VfM) | The optimum combination of whole-life cost and quality to meet the requirement - not lowest price. |
| WBS | Work breakdown structure - the hierarchical decomposition of total scope into manageable, assignable packages. |
| Whole-life cost | Capital, operating, maintenance, lifecycle renewal and disposal costs over the defined evaluation period. |
| ISO 19650 | International standard for organising and digitising information about buildings and civil engineering works, including BIM. |
| ISO 21502 | International standard providing guidance on project management practices. |
| ISO 31000 | International standard providing principles and guidelines for risk management. |

# 1.  Executive Summary

Guidance Write this section last, and keep it to a single page. Its reader is a board member who will not read the rest. It must answer six questions without the reader turning a page: what is being built, why, what it costs, how long it takes, what could go wrong, and what decision is being asked for today. Use numbers, not adjectives.

## 1.1  Project at a glance

| Attribute | Detail | Attribute | Detail |
| --- | --- | --- | --- |
| Project name |  | Project number |  |
| Sponsor / Executive |  | Project Manager |  |
| Client / asset owner |  | Delivery organisation |  |
| Capital cost (P50, base date) |  | Capital cost (P80) |  |
| Whole-life cost (NPV, __ years) |  | Funding source(s) |  |
| Planned start |  | Planned completion |  |
| Total duration (months) |  | Delivery model |  |
| Current lifecycle stage | Initiation | Current gate |  |
| Approval sought | Approve and baseline this PID; authorise delivery Stage 1 | Approval authority |  |
| Benefits realisation review due |  | Post-implementation review due |  |

## 1.2  What this project is and why it is being done

Guidance Three to five sentences. Sentence one: the physical thing being delivered and where. Sentence two: the problem it solves, quantified. Sentence three: the outcome the organisation buys with the money. Avoid restating the scope table.

[Describe the project in plain language - what is being built, extended, replaced or refurbished, at which site, to serve which population or operational need.]

[State the driver: capacity shortfall, asset condition, regulatory obligation, service growth, resilience, consolidation or strategic commitment - with the evidence that quantifies it.]

## 1.3  Cost, funding and duration

[Summarise the approved capital envelope, the estimate class and confidence, the contingency held and by whom, the price base date and escalation basis, the funding source and any drawdown conditions, and the programme duration with the two or three dates that cannot move.]

## 1.4  Key benefits

| Benefit | Type | Measure | Target | Realised by |
| --- | --- | --- | --- | --- |
|  | Cash-releasing |  |  |  |
|  | Non-cash-releasing |  |  |  |
|  | Service / user |  |  |  |
|  | Social / environmental |  |  |  |
|  | Statutory / compliance |  |  |  |

Full benefits register at Section 11.2 and Appendix F.

## 1.5  Key risks

| Ref | Principal risk (summary) | Residual rating | Primary treatment | Owner |
| --- | --- | --- | --- | --- |
| R01 |  |  |  |  |
| R02 |  |  |  |  |
| R03 |  |  |  |  |
| R04 |  |  |  |  |
| R05 |  |  |  |  |

Full risk register, with worked examples, at Section 12.6 and Appendix A.

## 1.6  Approval sought

The Project Board / investment authority is asked to:

approve and baseline this Project Initiation Document at the revision shown on the cover;

authorise the project to proceed from initiation into delivery, and release the funding for the next stage in accordance with Section 10;

confirm the governance, delegations and tolerances set out in Sections 7 and 8;

note the initial risk exposure at Section 12 and the conditions of approval at Section 18.2.

# 2.  Purpose and Status of this Document

## 2.1  Purpose

Guidance State plainly what this document is for. The PID is the initiation artefact: it converts an approved business case into a mandated, resourced and governed project. Do not let it drift into being a delivery manual - that is the Project Execution Plan.

This Project Initiation Document (PID) defines what the project is, why it is being undertaken, who is accountable for it, and the framework of controls under which it will be delivered. It is the artefact produced at the end of the initiation stage and, once approved, it is the baseline against which delivery performance, change and eventual project closure are judged.

Specifically, this PID:

records the agreed definition of the project - scope, objectives, deliverables, boundaries, assumptions and constraints;

restates and carries forward the justification from the approved business case, so that the investment logic remains visible during delivery;

establishes the organisation, roles, delegations and decision rights under which the project is governed;

sets the control framework - tolerances, stage gates, change control, reporting and assurance - within which the Project Manager operates;

fixes the milestone, cost, benefit and risk baselines;

mandates the subsidiary plans that will govern day-to-day delivery.

## 2.2  Authority and status of this document

On approval, this PID carries the authority of the body that approved it. It is a controlled configuration item. The Project Manager delivers to it; the Project Board holds the Project Manager to it; assurance reviewers test against it.

Nothing in this PID overrides the contract, the funding instrument, or any statutory or regulatory obligation. Where a conflict arises, the contract and the approvals regime applicable in your jurisdiction prevail, and the conflict is raised as an issue under Section 8.4.

## 2.3  When the PID is baselined, and how it is maintained

Guidance Be explicit about the lifecycle of this document. A PID that is written once and never revisited stops describing the project within months, and closure then has nothing credible to be judged against.

| Event | Action on this PID | Approval required |
| --- | --- | --- |
| End of initiation stage | Baselined at Revision 1.0 | Project Board / investment authority |
| Each stage boundary | Reviewed; updated for the next stage plan and re-approved if materially changed | Project Board |
| Approved change beyond tolerance | Affected sections updated and re-issued; revision number incremented | Change authority per Section 8.5 |
| Exception situation | Exception Report raised; PID updated only after the exception is resolved | Project Board |
| Change of sponsor, funding or strategic driver | Business justification (Section 3) re-tested | Sponsor and investment authority |
| Project closure | Used as the reference for the closure report and benefits handover | Project Board |

## 2.4  Relationship to other documents

The PID sits between the business case above it and the Project Execution Plan and subsidiary management plans below it. The distinction matters: the business case justifies the investment, the PID defines and authorises the project, and the PEP explains how the project will be run.

| Document | Position | What it answers | Owner |
| --- | --- | --- | --- |
| Strategic assessment / needs case | Upstream | Is there a problem worth solving? | Sponsor |
| Options appraisal and cost benefit analysis | Upstream | Which way of solving it gives best value? | Sponsor |
| Business case | Upstream | Should the organisation invest, and on what terms? | Sponsor |
| This PID | Initiation | What is the project, who runs it, under what controls, and is it authorised? | Project Manager |
| Project Execution Plan (PEP) | Downstream | How will the project actually be delivered, day to day? | Project Manager |
| Subsidiary management plans (risk, quality, HSE, commercial, information, communications) | Downstream | How is each discipline managed in detail? | Discipline leads |
| Stage plans and work package plans | Downstream | What is being done in this stage, by whom, by when? | Project Manager |
| Benefits realisation plan | Downstream and beyond closure | How are the benefits measured and delivered? | Senior User |

Guidance A useful test when drafting: if a sentence tells the reader what the project is or what it must achieve, it belongs in the PID. If it tells the reader how the project team will go about doing something, it belongs in the PEP. Where this PID sets a requirement, it cross-refers to the PEP section that will implement it.

## 2.5  Consequences of not following this PID

Work outside the defined scope is unfunded and unauthorised, and will not be accepted at handover;

Commitments beyond the delegations in Section 7.5 are not binding on the organisation and expose the individual to personal accountability;

Forecast breaches of tolerance that are not escalated are a governance failure in their own right, independent of the underlying problem;

Deliverables that do not meet the acceptance criteria in Section 4.5 may be rejected at the cost of the party that produced them;

Benefits that are not measured against the Section 11 baseline cannot be claimed at post-implementation review.

## 2.6  How to complete this template

Replace every bracketed prompt with project-specific content; delete prompts that do not apply rather than marking them 'TBC'.

Where information is genuinely not yet available, state what is known, who will provide the remainder, and by when - an open item with an owner and a date is acceptable; a blank is not.

Delete the grey Guidance callouts before issuing the document for approval, or retain them if your organisation issues PIDs with guidance visible for auditability.

Keep tables; they are the parts assurance reviewers read first.

Scale the document to the project. A minor works project may compress Sections 5, 15 and 16 to a paragraph each; a major programme will expand every one of them.

# 3.  Strategic Context and Business Justification

Guidance This section carries the business case forward into delivery. Do not restate the business case in full - summarise it faithfully, reference it precisely, and make the investment logic visible so that every later trade-off can be tested against it. If the justification has changed since the business case was approved, say so here; that is a material governance matter.

## 3.1  Alignment to organisational strategy

| Strategic objective / plan reference | How this project contributes | Measure of contribution | Owner |
| --- | --- | --- | --- |

## 3.2  Policy, regulatory and compliance drivers

Guidance List the obligations that make this project necessary or that shape it, described generically and by category rather than by citing a particular country's statute. Distinguish between drivers that are mandatory (compliance deadlines, licence conditions) and those that are discretionary policy commitments.

| Driver | Type | Obligation or requirement | Date / deadline | Consequence of non-compliance |
| --- | --- | --- | --- | --- |
|  | Statutory / regulatory |  |  |  |
|  | Licence or consent condition |  |  |  |
|  | Organisational policy |  |  |  |
|  | Standard / code obligation |  |  |  |
|  | Funding condition |  |  |  |

All statutory, planning, environmental and building approvals referenced in this document are subject to the approvals regime applicable in your jurisdiction. Confirm the applicable regime, consent pathway and determination timeframes with the relevant authority before relying on the dates in Section 9.

## 3.3  Portfolio and programme context

[Identify the portfolio and, if applicable, the programme this project belongs to; its relative priority; the outcomes it shares with sibling projects; and the controls, standards and reporting cadence it inherits rather than invents.]

| Portfolio / programme attribute | Detail |
| --- | --- |
| Portfolio |  |
| Programme |  |
| Programme outcome this project serves |  |
| Priority ranking / tier |  |
| Controls inherited from the programme |  |
| Sibling projects with shared scope or resources |  |
| Programme-level reporting requirement |  |

## 3.4  Problem or opportunity statement

Guidance One paragraph, evidence-led. A good problem statement contains a number, a date and a consequence. 'The pump station reaches its firm capacity at forecast 2029 demand, at which point overflow risk exceeds the licensed limit' is a problem statement. 'The pump station is old' is not.

[State the problem or opportunity, with quantified evidence.]

## 3.5  The case for change

[Explain why the problem cannot be resolved by operational, maintenance or policy measures alone, and why capital investment is the appropriate response now rather than later.]

## 3.6  Consequences of not proceeding (the do-nothing case)

| Dimension | Consequence if the project does not proceed | Timing | Severity |
| --- | --- | --- | --- |
| Service / operational |  |  |  |
| Safety |  |  |  |
| Compliance / regulatory |  |  |  |
| Financial (cost of inaction) |  |  |  |
| Asset condition and reliability |  |  |  |
| Reputation and stakeholder |  |  |  |
| Environmental / sustainability |  |  |  |

## 3.7  Demand and needs analysis

Guidance Summarise the evidence base for the quantum of scope: demand forecasts, capacity modelling, condition assessment, service standards, population or throughput projections. State the forecast horizon, the source, the date and the confidence - under-stated demand evidence is one of the most common causes of a project being resized after approval.

| Need driver | Evidence source | Date of evidence | Forecast horizon | Confidence | Implication for scope |
| --- | --- | --- | --- | --- | --- |

## 3.8  Investment logic map

Guidance The investment logic map is the single most useful page in a business case: problem → benefit → strategic response → solution. Insert the approved map here, or reproduce it as the table below. Every element of scope in Section 4 should be traceable to a line in this map; scope that is not traceable is scope creep with a head start.

INVESTMENT LOGIC MAP Insert the approved investment logic map here (problem → benefit → strategic response → solution). Keep it to one page and retain the approved version number.

| Problem / opportunity | Benefit sought | Strategic response | Solution element in this project | KPI |
| --- | --- | --- | --- | --- |

## 3.9  Summary of the approved business case

Guidance Summarise each of the five cases in three or four lines and reference the approved document and version. If any case has weakened since approval - for example the market has moved and the commercial case assumptions no longer hold - flag it here and raise it as an issue.

| Case | What it establishes | Summary position | Status |
| --- | --- | --- | --- |
| Strategic | That the investment is needed and fits strategy |  | Approved / Under review |
| Economic | That the recommended option optimises public or organisational value |  | Approved / Under review |
| Commercial | That the option is deliverable and attractive to the market |  | Approved / Under review |
| Financial | That it is affordable and funded |  | Approved / Under review |
| Management | That the organisation can deliver it |  | Approved / Under review |

| Business case attribute | Detail |
| --- | --- |
| Business case document reference and version |  |
| Date approved |  |
| Approving body |  |
| Approved capital envelope |  |
| Approved benefit-cost ratio / net present value |  |
| Conditions attached to the approval |  |
| Material changes since approval |  |

## 3.10  Options appraisal and the recommended option

| Option | Description | Capital cost | Whole-life cost / NPV | Benefit-cost ratio | Key risk | Assessment |
| --- | --- | --- | --- | --- | --- | --- |
| Do nothing |  |  |  |  |  | Rejected |
| Do minimum |  |  |  |  |  | Rejected |
| Option 1 |  |  |  |  |  |  |
| Option 2 |  |  |  |  |  |  |
| Option 3 (recommended) |  |  |  |  |  | Recommended |

### 3.10.1  Rationale for the recommended option

[State why the recommended option was selected: how it scored against the appraisal criteria, its whole-life cost position, its deliverability and risk profile, and any non-monetised factors that were decisive. Record any dissenting view and how it was resolved.]

## 3.11  Value for money and cost benefit analysis

The economic appraisal supporting the recommended option is set out in the Cost Benefit Analysis referenced in the Related Documents Register. Its headline results are carried into Section 10.11 (value for money statement) and its benefit assumptions into the benefits register at Section 11.2. Any change during delivery that materially alters cost, benefit timing or benefit quantum must be tested against the CBA before it is approved.

| CBA output | Value | Source / assumption |
| --- | --- | --- |
| Discount rate applied |  |  |
| Evaluation period (years) |  |  |
| Present value of costs |  |  |
| Present value of benefits |  |  |
| Net present value |  |  |
| Benefit-cost ratio |  |  |
| Sensitivity tested (±) |  |  |
| Optimism bias / risk uplift applied |  |  |

# 4.  Project Definition

Guidance This is the section that will be quoted back at you. Scope defined loosely here becomes a variation claim later. Write in terms a contractor and a claims consultant would both read the same way: name the works, quantify them, state what is deliberately excluded, and record the assumptions each estimate depends on.

## 4.1  Project description and physical scope

[Describe the works: location, footprint or length, principal elements, capacity or performance rating, and how the completed asset will be used. Two to four paragraphs.]

| Scope element | Description | Quantum / capacity | Unit | Notes |
| --- | --- | --- | --- | --- |

## 4.2  Project objectives

Guidance Objectives are what the project must achieve, not what it must produce. Each must be SMART and each must have a single owner. Four to eight objectives is the right number; more than ten means the project has no priorities.

| Ref | Objective (SMART) | Measure | Target | By when | Owner |
| --- | --- | --- | --- | --- | --- |
| O1 |  |  |  |  |  |
| O2 |  |  |  |  |  |
| O3 |  |  |  |  |  |
| O4 |  |  |  |  |  |
| O5 |  |  |  |  |  |
| O6 |  |  |  |  |  |

## 4.3  Outputs, outcomes and benefits

These three terms are routinely confused, and the confusion is expensive: projects that measure only outputs declare success on the day they hand over and never test whether the investment worked.

| Term | Definition | Who is accountable | When it is measured |
| --- | --- | --- | --- |
| Output | What the project produces - the physical asset, system or document set | Project Manager / Senior Supplier | At handover and acceptance |
| Outcome | The change in capability, service or state that results from using the output | Senior User | During transition and early operation |
| Benefit | The measurable improvement, valued by a stakeholder, that the outcome produces | Benefit owner (business) | At defined realisation dates, often years after closure |
| Disbenefit | A measurable negative consequence accepted as part of the trade-off | Senior User | Alongside the benefit |

| Ref | Output | Enables which outcome | Which benefit (ref) | Benefit owner |
| --- | --- | --- | --- | --- |

## 4.4  Scope inclusions and exclusions

### 4.4.1  In scope

| Ref | In-scope item | Description / limit of scope | Responsible party |
| --- | --- | --- | --- |
| IS1 |  |  |  |
| IS2 |  |  |  |
| IS3 |  |  |  |
| IS4 |  |  |  |
| IS5 |  |  |  |
| IS6 |  |  |  |

### 4.4.2  Out of scope

Guidance Be specific about the near-misses - the things a reasonable reader might assume are included. For each exclusion, name the party who will deliver it instead, or state that it is not being delivered at all.

| Ref | Out-of-scope item | Reason for exclusion | Who delivers it instead (if anyone) |
| --- | --- | --- | --- |
| OS1 |  |  |  |
| OS2 |  |  |  |
| OS3 |  |  |  |
| OS4 |  |  |  |

## 4.5  Key deliverables and acceptance criteria

Guidance Acceptance criteria must be testable by someone who was not involved in producing the deliverable. 'Fit for purpose' is not an acceptance criterion; 'commissioned and demonstrated to sustain 480 L/s against design head for 72 hours' is.

| Ref | Deliverable | Stage | Acceptance criteria | Accepting authority | Due |
| --- | --- | --- | --- | --- | --- |
| D1 | Approved design documentation | Design |  |  |  |
| D2 | Statutory and planning approvals | Approvals |  |  |  |
| D3 | Executed principal contract(s) | Procurement |  |  |  |
| D4 | Completed physical works | Construction |  |  |  |
| D5 | Commissioning and performance test records | Commissioning |  |  |  |
| D6 | Operation and maintenance manuals | Handover |  |  |  |
| D7 | As-built and asset information set | Handover |  |  |  |
| D8 | Training and operational readiness | Handover |  |  |  |
| D9 | Project closure report and lessons | Closeout |  |  |  |

## 4.6  Project boundaries and interfaces

[Define where this project stops: the physical chainage, gridline, tie-in point, system boundary or contractual boundary at which responsibility transfers to another party. Ambiguous boundaries are the single most common source of interface claims.]

The full interface register is at Section 17.1.

## 4.7  Dependencies

| Ref | Direction | Dependency | Counterparty | Required by | Impact if not met | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| DP1 | Inbound |  |  |  |  |  |
| DP2 | Inbound |  |  |  |  |  |
| DP3 | Inbound |  |  |  |  |  |
| DP4 | Outbound |  |  |  |  |  |
| DP5 | Outbound |  |  |  |  |  |
| DP6 |  |  |  |  |  |  |

## 4.8  Assumptions

Guidance An assumption without an owner and a validation date is a risk in disguise. Review this table at every stage boundary; when an assumption is disproved, raise an issue immediately rather than absorbing it silently into the estimate.

| Ref | Assumption | Basis / source | Owner | Validate by | Impact if invalid |
| --- | --- | --- | --- | --- | --- |
| A1 |  |  |  |  |  |
| A2 |  |  |  |  |  |
| A3 |  |  |  |  |  |
| A4 |  |  |  |  |  |
| A5 |  |  |  |  |  |
| A6 |  |  |  |  |  |

## 4.9  Constraints

| Ref | Constraint | Type | Description | Impact on delivery | Owner |
| --- | --- | --- | --- | --- | --- |
| C1 |  | Funding |  |  |  |
| C2 |  | Time / fixed date |  |  |  |
| C3 |  | Operational access |  |  |  |
| C4 |  | Regulatory / consent |  |  |  |
| C5 |  | Technical / standard |  |  |  |
| C6 |  | Resource / market |  |  |  |
| C7 |  |  |  |  |  |

## 4.10  Exclusions and limitations of this definition

Scope not listed in Section 4.4.1 is excluded, whether or not it appears in earlier concept material;

Quantities shown are for definition and estimating purposes only and do not constitute a warranty of quantity to any contracting party;

Where scope depends on an assumption in Section 4.8, that scope is conditional on the assumption being validated by the stated date;

Design development within the approved design intent is not a change; any departure from the design intent is change and is controlled under Section 8.5.

# 5.  Site, Asset and Technical Context

Guidance Record what is known about the physical setting at initiation, and - equally important - what is not yet known and who will find out. This is a definition-level section: it establishes context, standards and known constraints. The process for managing design and site investigation belongs in the Project Execution Plan.

## 5.1  Site description and context

| Attribute | Detail |
| --- | --- |
| Site address / location |  |
| Land parcel / title identifiers |  |
| Site area and configuration |  |
| Current use and occupancy |  |
| Surrounding land uses and sensitive receivers |  |
| Topography and levels |  |
| Site security and existing boundaries |  |
| Operational status during works (live / vacant / staged) |  |

## 5.2  Existing asset condition and constraints

| Asset / element | Age | Condition rating | Assessment source | Constraint imposed on the works | Residual life |
| --- | --- | --- | --- | --- | --- |

## 5.3  Geotechnical and environmental context

Guidance State the level of investigation completed and its adequacy for the current stage. Ground conditions are the most frequent cause of cost overrun on civil works; if investigation is preliminary, say so and carry the exposure explicitly in the risk register and the contingency basis at Section 10.3.

| Aspect | Known position | Investigation status | Residual uncertainty | Action / owner |
| --- | --- | --- | --- | --- |
| Ground conditions and geology |  |  |  |  |
| Groundwater regime |  |  |  |  |
| Contamination / made ground |  |  |  |  |
| Acid sulfate / expansive soils |  |  |  |  |
| Flooding and drainage |  |  |  |  |
| Ecology, vegetation and habitat |  |  |  |  |
| Noise, vibration and air quality |  |  |  |  |
| Waste and spoil disposal |  |  |  |  |

## 5.4  Services and utilities

| Service | Authority / owner | Existing capacity or status | Diversion / augmentation required | Lead time | Owner |
| --- | --- | --- | --- | --- | --- |
| Electrical supply / HV |  |  |  |  |  |
| Water and fire supply |  |  |  |  |  |
| Sewerage / trade waste |  |  |  |  |  |
| Stormwater and drainage |  |  |  |  |  |
| Gas |  |  |  |  |  |
| Telecommunications and data |  |  |  |  |  |
| Other (specify) |  |  |  |  |  |

## 5.5  Access, logistics and construction environment

Site access points, permitted vehicle routes and any load, height or curfew restrictions;

Laydown, site establishment and craneage constraints;

Traffic management, pedestrian management and adjacent-owner access obligations;

Working hours, noise curfews and permitted construction methods;

Interaction with live operations, including shutdown or possession windows and their frequency;

Availability of local labour, plant and materials, and distance to supply.

## 5.6  Heritage, cultural and community considerations

Guidance Address heritage and cultural obligations generically: identify whether the site or its surrounds carry built heritage, archaeological or cultural significance; what registers or determinations apply under the regime applicable in your jurisdiction; and what engagement, assessment or approval is required before ground disturbance.

| Consideration | Status / listing | Assessment required | Engagement required | Owner |
| --- | --- | --- | --- | --- |
| Built heritage |  |  |  |  |
| Archaeology / subsurface heritage |  |  |  |  |
| Cultural significance to local or Indigenous communities |  |  |  |  |
| Community facilities and amenity |  |  |  |  |
| Landscape and visual amenity |  |  |  |  |

## 5.7  Planning, consent and land tenure status

| Item | Status | Authority | Required by | Owner |
| --- | --- | --- | --- | --- |
| Land tenure / ownership confirmed |  |  |  |  |
| Easements, covenants and encumbrances |  |  |  |  |
| Land acquisition or lease required |  |  |  |  |
| Planning / development consent |  |  |  |  |
| Environmental approval or licence |  |  |  |  |
| Building / construction permit |  |  |  |  |
| Road, rail or waterway occupation permits |  |  |  |  |
| Utility connection agreements |  |  |  |  |
| Operating licence variation |  |  |  |  |

Approval titles, thresholds and determination pathways differ by jurisdiction. Confirm the correct instrument names and consent authorities locally and record them in the table above before this PID is baselined.

## 5.8  Technical standards and design brief summary

| Discipline / element | Governing standard or code | Client-specific requirement | Performance criterion | Verification method |
| --- | --- | --- | --- | --- |
| Structural |  |  |  |  |
| Civil and drainage |  |  |  |  |
| Architectural / building fabric |  |  |  |  |
| Mechanical and HVAC |  |  |  |  |
| Electrical and control systems |  |  |  |  |
| Fire and life safety |  |  |  |  |
| Accessibility |  |  |  |  |
| Durability and design life |  |  |  |  |
| Energy and sustainability |  |  |  |  |
| Security |  |  |  |  |

## 5.9  Known site risks

[Summarise the site-specific risks arising from Sections 5.1 to 5.8 and confirm each has been transferred into the risk register at Section 12.6 with a rating, treatment and owner.]

| Site risk | Source section | Risk register ref | Initial rating |
| --- | --- | --- | --- |

# 6.  Approach and Delivery Strategy

Guidance Explain the chosen route to delivery and, critically, why it was chosen over the alternatives. Assurance reviewers test the reasoning, not the choice. Keep to strategy: the operational procedures for running procurement, design and construction belong in the Project Execution Plan.

## 6.1  Delivery approach and rationale

[Describe the overall approach: staged or single-pass; traditional, integrated or collaborative; early contractor involvement or not; the extent of design completion before tender; and the reasoning tied to project risk profile, market conditions, client capability and time pressure.]

| Strategy decision | Option chosen | Alternatives considered | Rationale |
| --- | --- | --- | --- |
| Design completion at tender |  |  |  |
| Contracting approach |  |  |  |
| Risk allocation posture |  |  |  |
| Number of principal contracts |  |  |  |
| Client-supplied items |  |  |  |
| Commissioning responsibility |  |  |  |

## 6.2  Project lifecycle and stage framework

Guidance Every stage must end in a decision, and every decision must have a named authority. If a stage boundary has no gate, it is not a stage - it is a milestone. Align the stage names below to your organisation's gateway framework.

| Stage | Purpose | Key deliverables | Gate | Decision authority |
| --- | --- | --- | --- | --- |
| 0 - Strategic assessment | Confirm the need and strategic fit | Needs case, investment logic map | G0 - Need confirmed | Sponsor |
| 1 - Options and business case | Identify and appraise options | Options appraisal, CBA, business case | G1 - Investment decision | Investment authority |
| 2 - Initiation | Define, resource and govern the project | This PID, PEP outline, stage 3 plan | G2 - Project authorised | Project Board |
| 3 - Design and approvals | Develop design; obtain consents | Developed design, consents, updated estimate | G3 - Ready to procure | Project Board |
| 4 - Procurement | Select and contract the delivery party | Tender documents, evaluation report, contract | G4 - Award approval | Investment authority |
| 5 - Construction / delivery | Build and verify the works | Works, quality records, progressive assurance | G5 - Ready for commissioning | Project Board |
| 6 - Commissioning and handover | Prove, transfer and train | Commissioning records, O&M set, as-builts, training | G6 - Acceptance and handover | Senior User / asset owner |
| 7 - Closeout | Settle, close and capture lessons | Final account, closure report, lessons log | G7 - Project closure | Project Board |
| 8 - Benefits realisation | Measure and report benefits | Benefits realisation reports, PIR | G8 - Benefits confirmed | Senior User / Sponsor |

## 6.3  Delivery model selection

| Delivery model | Suited to | Risk position | Assessment for this project |
| --- | --- | --- | --- |
| Design - bid - build (traditional) | Well-defined scope, low design risk, price certainty valued | Client retains design risk |  |
| Design and construct | Scope definable by performance brief, single point of responsibility valued | Contractor takes design and construction risk |  |
| Construction management / managing contractor | Time-critical, evolving scope, client wants package control | Client retains most risk |  |
| Early contractor involvement | Constructability or ground risk material; market input valuable | Shared during development |  |
| Alliance / integrated partnership | High uncertainty, complex interfaces, collaborative behaviours essential | Shared under a pain/gain regime |  |
| Framework or panel call-off | Repeatable works, speed of engagement valued | Per the framework terms |  |

### 6.3.1  Selected model and rationale

[Name the selected delivery model and justify it against scope certainty, risk transfer objectives, market capacity and appetite, client capability and resourcing, time pressure, and the organisation's procurement rules.]

## 6.4  Procurement strategy summary

Guidance Summarise only. The detailed procurement plan, evaluation methodology, probity arrangements and contract administration procedures belong in the procurement strategy document and the PEP.

| Attribute | Position |
| --- | --- |
| Procurement method (open / selective / framework / direct) |  |
| Prequalification approach |  |
| Form of contract and amendments |  |
| Pricing mechanism (lump sum / schedule of rates / target cost / cost plus) |  |
| Evaluation basis (price / weighted value) |  |
| Key risk allocation principles |  |
| Security, bonding and insurance requirements |  |
| Local content, social value or sustainability requirements |  |
| Probity and conflict-of-interest arrangements |  |
| Approval pathway for award |  |

## 6.5  Work packaging

| Package | Scope | Procurement route | Indicative value | Award date | Interfaces |
| --- | --- | --- | --- | --- | --- |
| P1 | Early works / enabling |  |  |  |  |
| P2 | Design services |  |  |  |  |
| P3 | Principal works |  |  |  |  |
| P4 | Specialist / long-lead equipment |  |  |  |  |
| P5 | Client-supplied items |  |  |  |  |
| P6 | Commissioning and training |  |  |  |  |

## 6.6  Make versus buy

| Function | Deliver in-house | Procure externally | Decision | Rationale |
| --- | --- | --- | --- | --- |
| Project management |  |  |  |  |
| Design and engineering |  |  |  |  |
| Cost management / quantity surveying |  |  |  |  |
| Programme and controls |  |  |  |  |
| Site supervision |  |  |  |  |
| Commissioning management |  |  |  |  |
| Information / BIM management |  |  |  |  |

## 6.7  Phasing and staging strategy

[Describe how the works will be sequenced and why: operational continuity requirements, decant or relocation moves, seasonal or shutdown windows, funding profile constraints, and any partial handovers that bring benefits forward.]

| Phase | Scope | Start | Finish | Driver for the phasing | Partial handover? |
| --- | --- | --- | --- | --- | --- |

## 6.8  Key delivery principles

Risk is allocated to the party best able to assess, control and bear it - not simply transferred to the lowest bidder;

Design is frozen at defined points; changes after freeze are managed as change, not as design development;

Safety in design is addressed at each design stage and evidenced before each gate;

Long-lead items are identified at initiation and procured against the critical path, not the design programme;

Operational and asset-owner input is obtained before design freeze, not at handover;

Information is produced once, in the common data environment, and reused - not recreated per discipline;

Commissioning and operational readiness are planned from the start of design, not the end of construction.

## 6.9  Relationship to the Project Execution Plan

This section states the delivery strategy and the reasoning behind it. The Project Execution Plan converts that strategy into working procedure: schedule development and updating, cost control and forecasting, design management, procurement and contract administration, quality and inspection regimes, HSE management, site management, information management and reporting production. The PEP is prepared by the Project Manager, is consistent with this PID, and is approved before the start of the construction stage.

# 7.  Project Organisation and Governance

Guidance Governance fails in predictable ways: too many decision-makers, no single accountable executive, assurance performed by the people being assured, and delegations that nobody can find. Name individuals, not just roles, and make every decision right explicit.

## 7.1  Governance structure

PROJECT GOVERNANCE ORGANOGRAM Insert the governance organogram: investment authority, programme board (if applicable), Project Board (Executive, Senior User, Senior Supplier), Project Assurance, Project Manager, delivery team and supply chain. Show reporting lines as solid and advisory lines as dashed.

## 7.2  Project Board and terms of reference

| Attribute | Detail |
| --- | --- |
| Chair | Project Executive / Sponsor |
| Members | Executive, Senior User, Senior Supplier |
| Standing attendees | Project Manager, Project Assurance, Commercial Lead |
| Quorum |  |
| Frequency | Monthly, and at every stage boundary or exception |
| Decision rule | Consensus; the Executive decides if consensus is not reached |
| Secretariat | Project Support |
| Papers issued | Not less than five working days before the meeting |
| Standing agenda | Safety; progress against baseline; cost and forecast; risk and issues; change; benefits; decisions required |
| Escalation route | Programme board / investment authority |
| Delegated authority | As set out in Section 7.5 |
| Review of terms of reference | At each stage boundary |

A completable terms-of-reference template is at Appendix H.

## 7.3  Roles and responsibilities

| Role | Accountable for | Key decisions held | Name |
| --- | --- | --- | --- |
| Project Executive / Sponsor | The business case throughout; that the project remains desirable, viable and achievable; ultimate accountability for the investment | Authorise stages; accept exceptions; approve change beyond Project Manager tolerance; close the project |  |
| Senior User | Specifying the requirement; that the outputs meet user needs; realising the benefits | Accept deliverables against user requirements; approve changes affecting requirements or benefits |  |
| Senior Supplier | The integrity and buildability of what is supplied; supplier resourcing and capability | Commit supplier resources; approve technical solutions within the brief |  |
| Project Manager | Day-to-day management within delegated tolerance; producing the outputs to time, cost and quality | All decisions within tolerance; escalates anything beyond |  |
| Project Assurance | Independent verification that business, user and supplier interests are properly served | Advises the Board; cannot be delegated to the Project Manager |  |
| Project Support | Controls administration: registers, document control, scheduling support, reporting production | None - administrative |  |
| Client Project Director | Client-side leadership across the portfolio interface; resolution of cross-project conflicts | Client resourcing; escalated client decisions |  |
| Design Lead | Design integrity, compliance with the brief and standards, and safety in design | Design solutions within the approved brief; design freeze recommendations |  |
| Commercial Lead | Procurement, contract formation and administration, cost management and claims strategy | Recommends award; approves valuations within delegation |  |
| HSE Lead | Health, safety and environmental requirements and performance oversight | Stop-work authority; acceptance of safety-critical method |  |
| Asset Owner / Operator | Operational requirements, readiness to receive the asset, and post-handover performance | Acceptance at handover; operational constraints and shutdown windows |  |

## 7.4  Responsibility assignment

Guidance Use R (responsible), A (accountable), C (consulted), I (informed). Exactly one A per row. If two people are accountable, nobody is.

| Activity | Exec | Senior User | Senior Supplier | PM | Assurance | Commercial | HSE | Asset Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approve and baseline this PID | A | C | C | R | C | C | C | C |
| Approve stage plans | A | C | C | R | C | I | I | I |
| Approve design freeze | I | A | C | R | C | I | C | C |
| Approve change within tolerance | I | C | C | A | I | R | I | I |
| Approve change beyond tolerance | A | C | C | R | C | C | I | C |
| Recommend contract award | A | C | C | C | C | R | I | I |
| Accept deliverables | I | A | C | R | C | I | C | C |
| Own and report risk | I | C | C | A | C | C | C | C |
| Accept the asset at handover | I | C | C | R | I | I | C | A |
| Realise and report benefits | C | A | I | I | C | I | I | R |

## 7.5  Delegation of authority and financial thresholds

Guidance Populate the thresholds with your organisation's actual delegation instrument values and reference that instrument. Delegations are subject to the financial and procurement approvals regime applicable in your jurisdiction and to the funding conditions in Section 10.6.

| Decision | Project Manager | Project Board / Executive | Investment authority | Reference |
| --- | --- | --- | --- | --- |
| Commit expenditure within approved budget | Up to [ ] | Up to [ ] | Above [ ] |  |
| Approve variation / change order | Up to [ ] | Up to [ ] | Above [ ] |  |
| Release contingency | Nil | Up to [ ] | Above [ ] |  |
| Approve extension of time | Up to [ ] days | Up to [ ] days | Above [ ] days |  |
| Award a contract | Up to [ ] | Up to [ ] | Above [ ] |  |
| Accept a departure from standard contract terms | Nil | With legal advice | Material departures |  |
| Accept a risk above the tolerance in Section 8.2 | Nil | Up to [ ] | Above [ ] |  |
| Approve a change to scope in Section 4.4 | Nil | Non-material | Material |  |

## 7.6  Assurance and independent review

| Assurance activity | Type | Timing | Performed by | Reports to | Output |
| --- | --- | --- | --- | --- | --- |
| Gateway / stage gate review | Independent | At each stage boundary | Independent reviewer | Investment authority | Gate report and recommendation |
| Business case validation | Independent | Before award | Assurance function | Sponsor | Validation memo |
| Cost estimate review | Peer | At each estimate update | Independent estimator | Project Board | Estimate assurance report |
| Schedule quality review | Peer | Baseline and quarterly | Planning specialist | Project Board | Schedule health report |
| Design review and verification | Technical | At each design stage | Independent reviewer / peer | Design Lead | Review comment register |
| Safety in design review | Technical | At each design stage | HSE Lead and designers | Project Board | Risk reduction record |
| Health check / deep dive | Independent | On exception or annually | Assurance function | Project Board | Health check report |
| Audit (probity, financial, compliance) | Independent | Per audit plan | Internal / external audit | Audit committee | Audit report |
| Post-implementation review | Independent | 6 - 12 months after handover | Assurance function | Sponsor | PIR report |

## 7.7  Escalation and tolerance framework

The Project Manager manages within the tolerances set at Section 8.2. A forecast breach of any tolerance is an exception and must be escalated before the breach occurs, not after. Escalation is a control, not a failure.

| Level | Manages | Escalates to | Trigger | Response time |
| --- | --- | --- | --- | --- |
| Work package lead | Within work package tolerance | Project Manager | Forecast breach of package tolerance | Within 2 working days |
| Project Manager | Within stage tolerance | Project Board | Forecast breach of stage tolerance; unresolved issue | Within 5 working days |
| Project Board | Within project tolerance | Programme board / investment authority | Forecast breach of project tolerance; change to business case | At next scheduled meeting or sooner |
| Investment authority | The investment mandate | Executive leadership / governing body | Loss of business case viability; funding change | Per governance policy |

## 7.8  Reporting lines

The Project Manager reports to the Project Executive for project outcomes, and administratively to the Client Project Director;

Project Assurance reports directly to the Project Board and never through the Project Manager;

Discipline leads report functionally to their home function and operationally to the Project Manager for project work;

Contractors report to the Project Manager through the contract's nominated representative only - no informal direction is given to any contractor by any other party.

# 8.  Project Controls Framework

Guidance This section sets the control framework - what is controlled, to what limits, and by whom. It does not describe how the controls are operated; the procedures, systems, templates and cadence sit in the Project Execution Plan. Keep the two aligned: if the PEP contradicts this section, this section prevails until it is formally changed.

## 8.1  Control principles

Manage by exception: the Project Manager has freedom to act within tolerance and an obligation to escalate outside it;

Nothing is measured against an unapproved baseline;

A forecast, not an actual, triggers escalation - control is anticipatory;

Every register has a named owner and a defined review cycle;

One source of truth: registers and reports are drawn from the systems named in Section 15.5, not from private spreadsheets;

Bad news travels fastest - no report is edited to soften a forecast.

## 8.2  Tolerances

Guidance Set tolerances that are meaningful for this project's size. A ±10% cost tolerance on a large programme delegates more authority than most boards intend; a ±2% tolerance on a small refurbishment guarantees monthly escalation over trivia. Express cost tolerance in both percentage and absolute terms.

| Dimension | Project level | Stage level | Work package level | Who may authorise a deviation |
| --- | --- | --- | --- | --- |
| Cost | ± [ ]% / [ ] | ± [ ]% / [ ] | ± [ ]% / [ ] | Investment authority / Board / PM respectively |
| Time | ± [ ] weeks | ± [ ] weeks | ± [ ] days | Investment authority / Board / PM respectively |
| Scope | No reduction in Section 4.4.1 scope without approval | Defined stage outputs | Defined package outputs | Board (project and stage); PM (package) |
| Quality | No departure from Section 14.1 quality expectations | Stage acceptance criteria | Package inspection and test plan | Senior User / Design Lead |
| Risk | No risk rated Extreme accepted without Board approval | Aggregate stage exposure limit | Package residual risk limit | Board / PM per Section 12.8 |
| Benefits | No reduction in Section 11.2 targets | Benefit enablers delivered per stage | n/a | Senior User and Sponsor |

## 8.3  Stage and gate control

Authority to proceed is granted one stage at a time. At each boundary the Project Manager submits an end-stage report and the next stage plan; the Board tests continued viability against the business case and either authorises the next stage, authorises it with conditions, requires rework, or stops the project.

| Gate submission item | Prepared by | Reviewed by | Mandatory? |
| --- | --- | --- | --- |
| End-stage report (performance against baseline) | Project Manager | Project Assurance | Yes |
| Next stage plan with resourced schedule | Project Manager | Project Board | Yes |
| Updated cost estimate and forecast to completion | Commercial Lead | Independent estimator | Yes |
| Updated risk register and contingency drawdown position | Project Manager | Project Assurance | Yes |
| Business case viability confirmation | Sponsor | Investment authority | Yes |
| Benefits position and any change to targets | Senior User | Sponsor | Yes |
| Assurance / gateway review recommendation | Independent reviewer | Investment authority | As required |
| Lessons captured in the stage | Project Manager | Project Support | Yes |

## 8.4  Exception and issue management

| Step | Action | Responsible | Timeframe |
| --- | --- | --- | --- |
| 1 | Identify the forecast breach or unplanned event | Anyone; logged by Project Manager | Immediately |
| 2 | Log in the issue register with severity and owner | Project Manager | Within 1 working day |
| 3 | Assess impact on cost, time, scope, quality, risk and benefits | Project Manager with discipline leads | Within 5 working days |
| 4 | Prepare an Exception Report with options and a recommendation | Project Manager | Within 5 working days |
| 5 | Decide: accept, direct an exception plan, or stop | Project Board | At the next meeting or an extraordinary session |
| 6 | Implement the approved response and update the baseline | Project Manager | On approval |
| 7 | Close the issue and record the lesson | Project Manager | On completion |

## 8.5  Change control

Guidance Distinguish clearly between design development (within the approved intent, not a change) and change (a departure from an approved baseline). Record the distinction in writing at the point it arises - reconstructing it during a claim is expensive and rarely successful.

| Change value or impact | Assessed by | Recommended by | Approved by | Baseline update |
| --- | --- | --- | --- | --- |
| No cost or schedule impact; within design intent | Project Manager | n/a | Project Manager | Register only |
| Up to [ ] and no critical-path impact | Commercial Lead | Project Manager | Project Manager | Stage baseline |
| Up to [ ] or up to [ ] days critical-path impact | Commercial Lead | Project Manager | Project Board | Project baseline |
| Above [ ] or affecting scope in Section 4.4.1 | Commercial Lead and Assurance | Project Board | Investment authority | PID re-issued |
| Any change affecting benefits, safety or compliance | Relevant lead | Project Board | Sponsor and Senior User | PID re-issued |

| Change register field | Purpose |
| --- | --- |
| Change reference and date raised | Traceability |
| Originator and reason | Tests whether the change is client-driven, design-driven or site-driven |
| Description and affected scope element | Links change to Section 4.4.1 |
| Cost impact (best / expected / worst) | Supports the decision |
| Schedule impact and criticality | Distinguishes float consumption from delay |
| Risk, benefit, quality and safety impact | Prevents narrow cost-only assessment |
| Options considered and recommendation | Evidences the decision |
| Decision, decision-maker and date | Authority record |
| Baseline updated (Y/N) and revision | Closes the loop |

## 8.6  Baseline management

| Baseline | Contents | Set at | Re-baselined when | Owner |
| --- | --- | --- | --- | --- |
| Scope baseline | Sections 4.1 - 4.5 and the WBS | PID approval | Approved change to Section 4.4.1 | Project Manager |
| Schedule baseline | Milestones in Section 9.2 and the stage schedule | PID approval; stage plan approval | Approved extension of time or re-sequencing beyond tolerance | Project Manager |
| Cost baseline | Section 10.1 estimate plus approved contingency | PID approval | Approved change or contingency release beyond tolerance | Commercial Lead |
| Benefits baseline | Section 11.2 register | PID approval | Approved change to benefit targets | Senior User |
| Risk baseline | Section 12.6 register and exposure position | PID approval | At each stage boundary | Project Manager |
| Quality baseline | Section 14.1 expectations and acceptance criteria | PID approval | Approved change to acceptance criteria | Senior User |

## 8.7  Configuration and document control principles

Every deliverable is a configuration item with a unique identifier, owner, current revision and status;

Documents are issued only from the common data environment; local copies are uncontrolled;

Superseded revisions are retained and marked, never deleted;

The status of every configuration item is reportable at any time (configuration status accounting);

Changes to a configuration item follow Section 8.5 and update the item's revision;

Naming, numbering and metadata conventions follow Section 15 and the information standard adopted for the project.

## 8.8  Performance reporting framework

| Report | Purpose | Prepared by | Audience | Frequency |
| --- | --- | --- | --- | --- |
| Weekly delivery report | Short-cycle progress, safety, issues | Project Manager | Client team | Weekly |
| Monthly project report | Progress, cost, forecast, risk, change, safety, benefits | Project Manager | Project Board | Monthly |
| Cost report and forecast to completion | Committed, expended, forecast, contingency drawdown | Commercial Lead | Project Board | Monthly |
| Schedule update and critical-path analysis | Progress against baseline, float erosion, forecast completion | Planner | Project Board | Monthly |
| Risk and issue report | Movement in exposure, new and closed items | Project Manager | Project Board | Monthly |
| Exception report | Forecast breach of tolerance and recommendation | Project Manager | Project Board | On exception |
| End-stage report | Stage performance and readiness for the gate | Project Manager | Project Board | At each stage boundary |
| Programme / portfolio return | Roll-up for portfolio reporting | Project Manager | Programme office | Monthly |
| Benefits realisation report | Benefit measurement against baseline | Senior User | Sponsor | Per Section 11.5 |
| Closure report | Final performance, lessons, outstanding matters | Project Manager | Project Board | At closure |

Report content, templates, data sources and production responsibilities are detailed in the Project Execution Plan.

## 8.9  Lessons capture

Lessons are captured continuously, not reconstructed at closure. The lessons log is reviewed at every stage boundary; lessons material to other projects are transferred to the organisational lessons repository within 20 working days of the stage boundary, and lessons from previous projects that shaped this PID are recorded below.

| Lesson from a previous project | Source project | How this PID responds to it |
| --- | --- | --- |

# 9.  Milestone Schedule and Timeline

Guidance The PID carries the milestone-level schedule only: the dates the Board will hold the project to. The detailed critical-path programme, the schedule management procedure, progress measurement and float-management rules belong in the Project Execution Plan. Every milestone below must be a state that can be objectively verified, with a named owner and a stated tolerance.

## 9.1  Schedule strategy

| Attribute | Position |
| --- | --- |
| Scheduling tool and calendar |  |
| Level of schedule maintained (L1 milestone / L2 summary / L3 detailed) | L1 in this PID; L2 and L3 maintained per the PEP |
| Baseline date and revision |  |
| Progress measurement method |  |
| Update cycle | Monthly, with a critical-path review each cycle |
| Float ownership | Project float is owned by the client and released only by the Project Board |
| Schedule risk analysis method | Quantitative (Monte Carlo) at each gate; qualitative between gates |
| Confidence level reported | P50 and P80 |

## 9.2  Key milestone schedule

| Ref | Milestone | Stage | Planned date | Tolerance | Predecessor / dependency | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| M01 | Business case approved and funding confirmed | Initiation |  | 0 days | Investment decision | Sponsor |
| M02 | PID approved and baselined; project authorised | Initiation |  | 0 days | M01 | Project Board |
| M03 | Project team mobilised and PEP outline issued | Initiation |  | ± 2 weeks | M02 | Project Manager |
| M04 | Site investigation and survey complete | Design |  | ± 3 weeks | M03 | Design Lead |
| M05 | Concept design accepted by Senior User | Design |  | ± 3 weeks | M04 | Design Lead |
| M06 | Statutory / planning application lodged | Approvals |  | ± 2 weeks | M05 | Approvals Lead |
| M07 | Developed design complete; design freeze | Design |  | ± 4 weeks | M05 | Design Lead |
| M08 | Cost plan updated and estimate assured | Design |  | ± 2 weeks | M07 | Commercial Lead |
| M09 | Statutory / planning approval granted | Approvals |  | ± 8 weeks | M06 | Approvals Lead |
| M10 | Gate: ready to procure | Approvals |  | 0 days | M07, M09 | Project Board |
| M11 | Tender documents issued to market | Procurement |  | ± 2 weeks | M10 | Commercial Lead |
| M12 | Tenders received and evaluation complete | Procurement |  | ± 3 weeks | M11 | Commercial Lead |
| M13 | Contract award approved and executed | Procurement |  | ± 3 weeks | M12 | Investment authority |
| M14 | Long-lead equipment orders placed | Procurement |  | ± 2 weeks | M13 | Commercial Lead |
| M15 | Contractor mobilised; site possession granted | Construction |  | ± 2 weeks | M13 | Project Manager |
| M16 | Enabling works and utility diversions complete | Construction |  | ± 4 weeks | M15 | Contractor |
| M17 | Substructure complete | Construction |  | ± 4 weeks | M16 | Contractor |
| M18 | Structure complete / weathertight | Construction |  | ± 6 weeks | M17 | Contractor |
| M19 | Services installation complete | Construction |  | ± 4 weeks | M18 | Contractor |
| M20 | Practical / substantial completion of the works | Construction |  | ± 4 weeks | M19 | Contractor |
| M21 | Commissioning and performance testing complete | Commissioning |  | ± 3 weeks | M20 | Commissioning Manager |
| M22 | Operational readiness confirmed; training complete | Commissioning |  | ± 3 weeks | M21 | Asset Owner |
| M23 | Regulatory occupation / operating approval obtained | Commissioning |  | ± 3 weeks | M21 | Approvals Lead |
| M24 | Asset information and as-built set accepted | Handover |  | ± 3 weeks | M21 | Information Manager |
| M25 | Handover to asset owner; asset in service | Handover |  | ± 2 weeks | M22, M23, M24 | Senior User |
| M26 | Defects liability period commences | Handover |  | 0 days | M25 | Project Manager |
| M27 | Final account agreed and settled | Closeout |  | ± 6 weeks | M25 | Commercial Lead |
| M28 | Project closure report approved; project closed | Closeout |  | ± 4 weeks | M27 | Project Board |
| M29 | End of defects liability period; final certificate | Closeout |  | ± 4 weeks | M26 | Project Manager |
| M30 | Post-implementation review complete | Benefits |  | ± 6 weeks | M25 | Sponsor |
| M31 | First benefits realisation review | Benefits |  | ± 6 weeks | M25 | Senior User |
| M32 | Final benefits realisation review | Benefits |  | ± 8 weeks | M31 | Senior User |

## 9.3  Critical dates and immovable constraints

Guidance Separate the dates that are genuinely immovable - a funding expiry, a licence deadline, a lease end, an operational shutdown window that occurs once a year - from dates that are merely desired. Boards routinely treat all dates as equally hard, which destroys the ability to trade time for cost or risk.

| Date | What it is | Why it cannot move | Consequence of missing it | Owner |
| --- | --- | --- | --- | --- |

## 9.4  Indicative phasing

HIGH-LEVEL PHASING BAR CHART Insert a one-page summary bar chart showing the stages in Section 6.2 across the project timeline, with the gates from Section 9.2 marked, the long-lead procurement bars shown against the critical path, and any operational shutdown or seasonal windows shaded.

[Describe the phasing in words for readers of the printed document: total duration, the stages and their durations, which activities overlap and why, where the critical path runs, and where float exists.]

## 9.5  Schedule assumptions

| Ref | Schedule assumption | Basis | Owner | Validate by |
| --- | --- | --- | --- | --- |
| SA1 | Statutory approval determination periods as advised by the consent authority |  |  |  |
| SA2 | Design review and client comment turnaround of [ ] working days |  |  |  |
| SA3 | Tender period and evaluation duration |  |  |  |
| SA4 | Long-lead equipment delivery periods as quoted |  |  |  |
| SA5 | Weather allowance of [ ] days per annum |  |  |  |
| SA6 | Access and possession windows available as scheduled |  |  |  |
| SA7 | No industrial action beyond agreed award conditions |  |  |  |
| SA8 | Contractor mobilisation period |  |  |  |

## 9.6  Key schedule risks

| Schedule risk | Milestone(s) affected | Risk register ref | Mitigation in the schedule |
| --- | --- | --- | --- |
| Approval determination longer than assumed |  |  |  |
| Design maturity insufficient at tender |  |  |  |
| Market capacity limits tender response |  |  |  |
| Long-lead equipment slippage |  |  |  |
| Utility diversion coordination |  |  |  |
| Adverse ground conditions on early works |  |  |  |
| Operational access window missed |  |  |  |
| Commissioning and operational readiness lag |  |  |  |

# 10.  Cost, Funding and Financial Framework

Guidance State the cost position honestly and show its basis. An estimate without an estimate class, a price base date and a stated confidence level is not an estimate - it is a number. The framework here is the financial envelope and the authority to spend within it; cost management procedure, valuation, payment and forecasting method sit in the Project Execution Plan.

## 10.1  Capital cost estimate summary

| Ref | Cost element | Amount | % of total | Estimate class | Basis of estimate | Confidence |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Land, acquisition and easements |  |  |  |  |  |
| 2 | Investigations, surveys and studies |  |  |  |  |  |
| 3 | Design and professional services |  |  |  |  |  |
| 4 | Statutory fees, approvals and levies |  |  |  |  |  |
| 5 | Enabling and early works |  |  |  |  |  |
| 6 | Utility diversions and connections |  |  |  |  |  |
| 7 | Principal construction works |  |  |  |  |  |
| 8 | Specialist and long-lead equipment |  |  |  |  |  |
| 9 | Fit-out, furniture and equipment |  |  |  |  |  |
| 10 | ICT, controls and security systems |  |  |  |  |  |
| 11 | Commissioning, training and transition |  |  |  |  |  |
| 12 | Client-side project management and controls |  |  |  |  |  |
| 13 | Insurances and bonds |  |  |  |  |  |
| 14 | Subtotal - base estimate (excluding risk) |  |  |  |  |  |
| 15 | Contingency (risk allowance) |  |  |  |  |  |
| 16 | Escalation to mid-point of construction |  |  |  |  |  |
| 17 | Total capital cost (P50) |  |  |  |  |  |
| 18 | Total capital cost (P80) |  |  |  |  |  |

Guidance Name the estimate classification system you are using (for example an AACE-style Class 5 to Class 1 scale, or your organisation's equivalent) and state the expected accuracy range for the class claimed. Do not present a Class 4 concept estimate with a Class 1 level of apparent precision.

## 10.2  Whole-life cost summary

| Cost category | Description | Annual / periodic amount | Evaluation period | Present value | Owner |
| --- | --- | --- | --- | --- | --- |
| Capital (CAPEX) | Delivery of the asset |  |  |  | Project Manager |
| Operating (OPEX) | Energy, consumables, staffing, rates |  |  |  | Asset Owner |
| Maintenance | Planned and reactive maintenance |  |  |  | Asset Owner |
| Lifecycle renewal | Periodic replacement of components |  |  |  | Asset Owner |
| Decommissioning / disposal | End-of-life removal and remediation |  |  |  | Asset Owner |
| Total whole-life cost |  |  |  |  |  |

## 10.3  Contingency and risk allowance

| Attribute | Position |
| --- | --- |
| Method used to size contingency | Quantitative risk analysis (Monte Carlo) on the Section 12.6 register, cross-checked against a percentage benchmark |
| Confidence level adopted for the budget | P[ ] |
| Contingency as a percentage of base estimate |  |
| Contingency held by the Project Manager |  |
| Contingency held by the Project Board |  |
| Contingency held by the investment authority (management reserve) |  |
| Release authority and evidence required | Per Section 7.5; release requires the linked risk to have materialised and been assessed |
| Reporting of drawdown | Monthly, showing the remaining allowance against remaining risk exposure |
| Treatment of unused contingency | Returned to the funder at stage boundaries; never reallocated to scope |

Guidance Contingency is not a slush fund and it is not the Project Manager's money. Say who holds it, on what evidence it is released, and what happens to what is left. Projects that allow contingency to be absorbed into scope lose the ability to report a truthful forecast.

## 10.4  Escalation and price basis

| Attribute | Position |
| --- | --- |
| Price base date |  |
| Currency and any exchange rate assumptions |  |
| Escalation index or source used |  |
| Escalation rate assumed (per annum) |  |
| Period escalated (base date to construction mid-point) |  |
| Treatment of escalation in the contract (fixed / rise and fall) |  |
| Sensitivity tested |  |

## 10.5  Cash flow forecast

| Period | Design and approvals | Procurement | Construction | Commissioning and handover | Client costs | Total | Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Year 1 Q1 |  |  |  |  |  |  |  |
| Year 1 Q2 |  |  |  |  |  |  |  |
| Year 1 Q3 |  |  |  |  |  |  |  |
| Year 1 Q4 |  |  |  |  |  |  |  |
| Year 2 |  |  |  |  |  |  |  |
| Year 3 |  |  |  |  |  |  |  |
| Year 4 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |

## 10.6  Funding sources, approvals and conditions

| Funding source | Amount | Type | Approval status | Conditions attached | Expiry / drawdown window | Owner |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Capital appropriation |  |  |  |  |
|  |  | Grant / contribution |  |  |  |  |
|  |  | Borrowing |  |  |  |  |
|  |  | Developer or third-party contribution |  |  |  |  |
|  |  | Reserves / retained earnings |  |  |  |  |

Funding is subject to the appropriation, grant and financial approvals regime applicable in your jurisdiction. Where funding is appropriated annually, unspent allocations may lapse; the cash flow at Section 10.5 must therefore be reconciled to the funding profile at every stage boundary and any mismatch escalated.

## 10.7  Budget authority and financial thresholds

Financial delegations are set out in Section 7.5. This section records the instrument that grants them and any project-specific variation.

| Attribute | Detail |
| --- | --- |
| Delegation instrument and version |  |
| Budget holder |  |
| Cost centre / project code |  |
| Commitment approval workflow |  |
| Payment authorisation workflow |  |
| Procurement thresholds triggering competitive process |  |
| Thresholds requiring external or central approval |  |

## 10.8  Financial reporting requirements

Monthly cost report showing approved budget, commitments, expenditure to date, accruals, forecast to completion and variance to baseline;

Contingency drawdown statement reconciling releases to the risks that materialised;

Cash flow actual versus forecast, with re-profiling requests raised before the funding period closes;

Change register financial summary showing approved, pending and rejected change values;

Earned value or equivalent physical-progress measure where required by the funder;

Year-end financial return, capitalisation schedule and asset recognition data for the finance function.

## 10.9  Tax and accounting treatment

Guidance Keep this generic and confirm it with your finance function - capitalisation rules, indirect tax recovery and asset recognition thresholds differ by jurisdiction and by entity type. The point of the section is to make sure the question is asked at initiation, not discovered at year end.

| Consideration | Position | Confirmed by | Date |
| --- | --- | --- | --- |
| Capital versus operating expenditure split |  |  |  |
| Capitalisation policy and thresholds |  |  |  |
| Treatment of borrowing and financing costs |  |  |  |
| Indirect / value-added tax treatment and recoverability |  |  |  |
| Withholding or cross-border tax on foreign suppliers |  |  |  |
| Asset componentisation and depreciation profile |  |  |  |
| Impairment or write-off of abortive costs |  |  |  |
| Grant accounting and acquittal obligations |  |  |  |

## 10.10  Affordability statement

[Confirm that the total capital cost is within the approved funding envelope, that the operating and maintenance cost consequences are provided for in the asset owner's forward budget, and that the cash flow profile matches the funding availability. State any affordability gap, its size, and the action being taken to close it.]

## 10.11  Value for money statement

[State how value for money is being secured and demonstrated: the economic appraisal result carried from Section 3.11, the competitive tension created by the procurement strategy, whole-life rather than lowest-capital decision-making, benchmarking of rates, and the controls that will preserve the position during delivery.]

Cross-reference: Cost Benefit Analysis (see Related Documents Register) and Section 3.11.

# 11.  Benefits and Success Criteria

Guidance Benefits are the reason the money was approved, yet they are the first thing to be forgotten once construction starts. Every benefit needs a named owner outside the project team, a measure, a baseline value taken before the project changes anything, and a realisation date that is usually after project closure.

## 11.1  Benefits management approach

Benefits are owned by the business, not by the project; the Senior User is accountable for their specification and realisation;

Each benefit is traced back to an output in Section 4.3 and forward to a measure in Section 11.5;

Baseline measurements are taken before delivery begins - a benefit with no baseline cannot be evidenced;

Disbenefits are declared and tracked with the same rigour as benefits;

Benefit forecasts are reviewed at each stage boundary and any change is treated as change under Section 8.5;

Benefit measurement continues past closure under the benefits realisation plan, and is reported to the Sponsor until the final review.

## 11.2  Benefits register

| Ref | Benefit | Type | Measure | Baseline | Target | Realisation date | Owner | Dependency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B1 |  | Cash-releasing |  |  |  |  |  |  |
| B2 |  | Cash-releasing |  |  |  |  |  |  |
| B3 |  | Non-cash-releasing |  |  |  |  |  |  |
| B4 |  | Non-cash-releasing |  |  |  |  |  |  |
| B5 |  | Service / user |  |  |  |  |  |  |
| B6 |  | Social |  |  |  |  |  |  |
| B7 |  | Environmental |  |  |  |  |  |  |
| B8 |  | Statutory / compliance |  |  |  |  |  |  |

## 11.3  Disbenefits

| Ref | Disbenefit | Affected group | Measure | Scale | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| DB1 |  |  |  |  |  |  |
| DB2 |  |  |  |  |  |  |
| DB3 |  |  |  |  |  |  |

## 11.4  Success and acceptance criteria

| Ref | Criterion | Category | How it is verified | Verified by | When |
| --- | --- | --- | --- | --- | --- |
| SC1 | Delivered within the approved capital envelope | Cost | Final account against baseline | Commercial Lead | Closeout |
| SC2 | Handed over by the contract completion date | Time | Certificate of completion | Project Manager | Handover |
| SC3 | Meets the scope and performance in Sections 4.1 and 5.8 | Scope / quality | Commissioning and performance test records | Senior User | Commissioning |
| SC4 | Zero fatalities and lost-time injury rate within target | Safety | HSE performance records | HSE Lead | Throughout |
| SC5 | Asset information set accepted at handover | Information | Information audit against Section 15.4 | Information Manager | Handover |
| SC6 | Operational readiness achieved before handover | Transition | Readiness checklist signed by the asset owner | Asset Owner | Handover |
| SC7 | Sustainability and carbon targets met | Sustainability | Verification against Section 14.5 targets | Design Lead | Handover |
| SC8 | Benefits realised to target | Benefits | Benefits realisation report | Senior User | Post-closure |
| SC9 | Stakeholder satisfaction at or above target | Stakeholder | Survey against baseline | Project Manager | Post-handover |

## 11.5  Key performance indicators

| KPI | Definition | Target | Threshold for escalation | Frequency | Owner |
| --- | --- | --- | --- | --- | --- |
| Cost performance against baseline | Forecast final cost ÷ approved budget | ≤ 1.00 |  | Monthly | Commercial Lead |
| Schedule performance against baseline | Milestones achieved ÷ milestones planned | ≥ 0.95 |  | Monthly | Project Manager |
| Contingency drawdown versus progress | Contingency used ÷ progress complete | ≤ 1.00 |  | Monthly | Commercial Lead |
| Change value as a share of contract sum | Approved change ÷ contract sum |  |  | Monthly | Commercial Lead |
| Recordable injury frequency rate | Per contract definition |  |  | Monthly | HSE Lead |
| Open high or extreme risks | Count |  |  | Monthly | Project Manager |
| Defects at handover | Count of category A defects | 0 |  | At handover | Project Manager |
| Benefit realisation index | Benefits realised ÷ benefits forecast | ≥ 1.00 |  | Per review | Senior User |

## 11.6  Benefits responsibilities and review points

| Review point | Timing | Purpose | Chaired by | Output |
| --- | --- | --- | --- | --- |
| Benefits baseline confirmation | At PID approval | Confirm measures, baselines and owners | Senior User | Baselined register |
| Stage boundary benefit check | Each gate | Confirm enablers remain deliverable and forecasts hold | Project Board | Gate paper section |
| Pre-handover readiness check | Before handover | Confirm the business is ready to convert outputs into outcomes | Senior User | Readiness report |
| Post-implementation review | 6 - 12 months after handover | Assess delivery performance and early benefit trends | Sponsor | PIR report |
| Benefits realisation review | Per the realisation plan | Measure benefits against baseline and report | Senior User | Realisation report |
| Final benefits review | At the end of the realisation period | Confirm the investment delivered what was promised | Sponsor | Closure of the benefits case |

## 11.7  Transition to business as usual

Operational readiness requirements are defined at initiation and tested before handover, not after;

Operating and maintenance resourcing, budgets and spares are secured by the asset owner before the asset enters service;

Training, competency and authorisation of operators are complete before commissioning ends;

Asset data is loaded into the asset management system and verified before handover (see Section 15.4);

Warranty, defects liability and support arrangements are documented and communicated to the operator;

Responsibility for benefit measurement transfers formally from the project to the business at closure.

# 12.  Risk, Issue and Opportunity Framework

Guidance Set the framework here - approach, appetite, scales, initial exposure and escalation thresholds. The working risk management procedure, workshop cadence, quantitative analysis method and register administration belong in the risk management plan and the Project Execution Plan. The initial register below must be a genuine assessment, not a formality: it sizes the contingency in Section 10.3 and shapes the delivery strategy in Section 6.

## 12.1  Risk management approach

Risk is managed in accordance with ISO 31000 and the organisation's risk management policy. Risk management is integrated into decision-making rather than run as a parallel exercise: no gate is passed, no change is approved and no contingency is released without the risk position being considered.

| ISO 31000 process step | How it is applied on this project |
| --- | --- |
| Scope, context and criteria | Set in this section; reviewed at each stage boundary |
| Risk identification | Facilitated workshops at each stage, plus continuous identification by any team member |
| Risk analysis | Qualitative 5×5 rating for all risks; quantitative simulation for cost and schedule at each gate |
| Risk evaluation | Rated exposure compared against the appetite and tolerance in Section 12.2 |
| Risk treatment | Avoid, reduce, transfer, share or accept - with a named owner, funded actions and a target date |
| Monitoring and review | Monthly review by the Project Manager; formal review at each stage boundary |
| Recording and reporting | Single register in the system named at Section 15.5; reported monthly per Section 8.8 |
| Communication and consultation | Risk is a standing item on the Project Board agenda and in supplier progress meetings |

## 12.2  Risk appetite and tolerance

| Risk category | Appetite | Statement |
| --- | --- | --- |
| Safety and health | Averse | No tolerance for practices that expose people to serious harm; safety risk is eliminated or reduced so far as is reasonably practicable before cost or time is considered |
| Regulatory and compliance | Averse | No tolerance for knowingly proceeding without required approvals or outside licence conditions |
| Cost | Cautious | Exposure managed within the contingency in Section 10.3; extreme cost risks require Board treatment before acceptance |
| Schedule | Cautious to open | Time may be traded for cost or quality where the immovable dates in Section 9.3 are protected |
| Quality and technical | Cautious | Proven solutions preferred; novel solutions require documented verification and Senior Supplier endorsement |
| Environmental and community | Averse | No tolerance for avoidable environmental harm or for breaching commitments made to the community |
| Reputation | Cautious | Managed proactively through Section 13; adverse coverage escalated immediately |
| Innovation and commercial | Open | Innovation encouraged where the downside is bounded, insurable or contractually allocated |

## 12.3  Likelihood scale

| Score | Descriptor | Probability of occurrence | Indicative frequency |
| --- | --- | --- | --- |
| 5 | Almost certain | > 80% | Expected to occur in most circumstances |
| 4 | Likely | 50 - 80% | Will probably occur |
| 3 | Possible | 20 - 50% | Might occur at some time |
| 2 | Unlikely | 5 - 20% | Could occur but is not expected |
| 1 | Rare | < 5% | Only in exceptional circumstances |

## 12.4  Consequence scale

| Score | Descriptor | Cost | Time | Safety | Quality / performance | Reputation and compliance |
| --- | --- | --- | --- | --- | --- | --- |
| 5 | Severe | > [ ]% of budget | > [ ] months | Fatality or permanent disability | Objectives not achievable | Prosecution; sustained adverse national coverage |
| 4 | Major | [ ] - [ ]% of budget | [ ] - [ ] months | Serious injury requiring hospitalisation | Major objective compromised | Regulatory action; adverse regional coverage |
| 3 | Moderate | [ ] - [ ]% of budget | [ ] - [ ] weeks | Injury requiring medical treatment | Objective met only with rework | Formal complaint; local coverage |
| 2 | Minor | [ ] - [ ]% of budget | [ ] - [ ] weeks | First aid injury | Minor rework within tolerance | Stakeholder dissatisfaction managed locally |
| 1 | Insignificant | < [ ]% of budget | < [ ] week | Near miss, no injury | Negligible effect | No external interest |

## 12.5  Risk matrix

Guidance Rated exposure is likelihood multiplied by consequence, read from the matrix below. The rating determines the response required, the authority who may accept the residual exposure, and the reporting level - see Section 12.9.

| Likelihood ↓ / Consequence → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe |
| --- | --- | --- | --- | --- | --- |
| 5 Almost certain | Medium | High | High | Extreme | Extreme |
| 4 Likely | Medium | Medium | High | High | Extreme |
| 3 Possible | Low | Medium | High | High | Extreme |
| 2 Unlikely | Low | Low | Medium | Medium | High |
| 1 Rare | Low | Low | Medium | Medium | High |

| Rating | Response required | Residual exposure accepted by | Reporting |
| --- | --- | --- | --- |
| Extreme | Treatment mandatory and funded before the risk is accepted; stop-and-review if untreatable | Investment authority | Every report, to the investment authority |
| High | Treatment plan with named owner and target date; reviewed monthly | Project Board | Monthly to the Project Board |
| Medium | Treatment where cost-effective; monitored | Project Manager | Monthly in the register summary |
| Low | Accept and monitor; no active treatment required | Risk owner | Register only |

## 12.6  Initial risk register

Guidance The examples below are typical of capital works projects and are written in cause - event - effect form: 'because of [cause], [event] may occur, resulting in [effect]'. Replace the wording with project-specific risks, re-rate them, and delete any that do not apply. A register that could belong to any project belongs to none.

| Ref | Risk (cause → event → effect) | Category | L | C | Rating | Treatment strategy and key actions | Owner | Residual |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Because determination timeframes for the principal statutory approval are outside the project's control and supporting assessments are incomplete, approval may be granted later than assumed, delaying tender award and pushing construction into an adverse season | Approvals | 4 | 4 | High | Reduce - pre-lodgement engagement with the consent authority; complete supporting studies before lodgement; sequence early works that do not depend on the approval | Approvals Lead | Medium |
| R02 | Because site investigation to date is preliminary and the site has a history of filling, ground conditions may differ materially from those assumed in the design, resulting in redesign of foundations and additional excavation and disposal cost | Technical | 4 | 4 | High | Reduce - complete a targeted geotechnical investigation before design freeze; adopt a foundation solution tolerant of variation; retain a quantified ground allowance in contingency | Design Lead | Medium |
| R03 | Because regional construction demand is high and tender capacity is constrained, the project may receive few or non-conforming tenders at prices above the estimate, resulting in a funding shortfall or retender | Commercial | 4 | 4 | High | Reduce - early market sounding; package to suit available bidders; review the tender window against the regional pipeline; prepare a priced descoping schedule before tender | Commercial Lead | High |
| R04 | Because design is taken to tender at a lower level of maturity than the contract assumes, the contractor may price provisionally and claim variations for design development, resulting in cost growth and adversarial contract administration | Design | 3 | 4 | High | Reduce - define and enforce a design maturity gate before tender; independent design review; unambiguous employer's requirements and a documented design intent | Design Lead | Medium |
| R05 | Because the works affect amenity for adjoining residents and businesses, sustained objection may be raised during the approval or construction phase, resulting in conditions, delay or design change | Stakeholder | 3 | 3 | High | Reduce - early and structured engagement per Section 13; publish mitigation commitments; establish a responsive complaints process with defined response times | Project Manager | Medium |
| R06 | Because utility records are incomplete and diversion approvals depend on third-party authorities, service diversions may take longer or cost more than assumed, delaying enabling works and the critical path | Utilities | 4 | 3 | High | Reduce - non-destructive location survey and potholing before design freeze; early application to each authority; separate the diversion package so it can start ahead of the principal works | Project Manager | Medium |
| R07 | Because contractor margins in the current market are thin, the principal contractor or a critical subcontractor may become insolvent during the works, resulting in suspension, re-procurement, delay and additional cost | Commercial | 2 | 5 | High | Transfer and reduce - financial capacity assessment at prequalification and ongoing monitoring; performance security and bonding; step-in and novation rights; avoid over-reliance on a single subcontractor | Commercial Lead | Medium |
| R08 | Because user groups were not fully engaged during option development, additional requirements may be introduced after design freeze, resulting in rework, variation cost and delay | Scope | 4 | 3 | High | Reduce - Senior User sign-off of the brief before design freeze; a single client requirements channel; strict application of change control under Section 8.5 | Senior User | Medium |
| R09 | Because client-side project management and technical resources are shared across a busy portfolio, key roles may be unfilled or part-committed, resulting in slow decisions, late approvals and loss of project knowledge | Resourcing | 3 | 3 | High | Reduce - secure named resources and mobilisation dates per Section 16.1; document delegations; maintain succession cover for the Project Manager and Commercial Lead | Client Project Director | Medium |
| R10 | Because the construction period spans a wet season and the works include extensive earthworks, adverse weather may exceed the allowance in the programme, resulting in delay and standing-time cost | Weather | 4 | 3 | High | Reduce - schedule earthworks outside the peak wet period where possible; include a quantified weather allowance based on historical records; define contractual entitlement clearly | Project Manager | Medium |
| R11 | Because enterprise agreements in the region are due for renegotiation during the construction period, industrial action may occur, resulting in lost production days and delay to completion | Industrial | 2 | 3 | Medium | Monitor and transfer - track agreement expiry dates; allocate the risk clearly in the contract; require the contractor's industrial relations plan as a tender deliverable | Commercial Lead | Medium |
| R12 | Because the works are undertaken adjacent to a live operating facility, construction activity may disrupt operations or breach an operating licence condition, resulting in operational loss, regulatory action and suspension of work | Operations | 3 | 4 | High | Reduce - agreed interface protocol and permit-to-work regime with the asset owner; scheduled shutdown windows per Section 5.5; operations representation at site coordination meetings | Asset Owner | Medium |
| R13 | Because project and asset information is held in cloud systems shared with multiple suppliers, a cyber incident or uncontrolled disclosure may occur, resulting in loss of information, exposure of security-sensitive asset data and delay | Information | 3 | 4 | High | Reduce - apply the organisation's information security controls to the common data environment; classify and restrict security-sensitive information; contractual security obligations and audit rights | Information Manager | Medium |
| R14 | Because specified long-lead plant is sourced from constrained international supply chains, delivery may extend beyond quoted lead times, resulting in delay to commissioning and to the in-service date | Supply chain | 4 | 4 | High | Reduce - identify long-lead items at initiation and order against the critical path; consider client-supplied procurement; specify alternative acceptable manufacturers; require a supply chain plan from tenderers | Commercial Lead | Medium |
| R15 | Because funding is appropriated annually and the cash flow is back-loaded, the available funding profile may not match the expenditure profile, resulting in forced slowdown, re-mobilisation cost or lapse of unspent allocation | Funding | 3 | 4 | High | Reduce - reconcile the Section 10.5 cash flow to the funding profile monthly; agree a re-profiling mechanism with the funder; sequence commitments to match drawdown windows | Sponsor | Medium |

The same register is reproduced as a working table at Appendix A.

## 12.7  Issue management framework

| Attribute | Position |
| --- | --- |
| Definition of an issue | A risk that has occurred, or any unplanned event or unresolved question requiring management action now |
| Register | Single issue log maintained by the Project Manager |
| Severity scale | Uses the consequence scale at Section 12.4 |
| Resolution authority | Per the escalation ladder at Section 7.7 |
| Target resolution times | Severity 5: 48 hours; 4: 5 working days; 3: 10 working days; 2 and 1: next reporting cycle |
| Relationship to change | An issue that requires a baseline change is converted to a change request under Section 8.5 |
| Closure | Closed only by the issue owner, with the resolution and any lesson recorded |

## 12.8  Opportunity register

Guidance Opportunities are the upside of uncertainty and are routinely ignored. Manage them with the same discipline as threats: an owner, an action, a date and a quantified upside.

| Ref | Opportunity (cause → event → benefit) | L | C | Rating | Exploitation action | Value if realised | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OP1 | Because the market is competitive in the planned tender window, tender prices may fall below the estimate, releasing contingency for scope enhancement or return to the funder | 3 | 3 | Medium | Time the tender to the assessed market window; package to attract mid-tier bidders |  | Commercial Lead |
| OP2 | Because adjacent works are programmed on the same corridor, sharing site establishment and traffic management may reduce preliminaries | 3 | 3 | Medium | Engage the adjacent project sponsor; test a shared establishment arrangement before tender |  | Project Manager |
| OP3 | Because early contractor involvement is available, constructability input may shorten the construction programme | 3 | 3 | Medium | Include a constructability review as a priced deliverable in the design contract |  | Design Lead |
| OP4 | Because the asset owner is renewing adjacent plant, a combined shutdown may avoid a second outage | 2 | 4 | Medium | Align outage planning with the asset owner's maintenance programme |  | Asset Owner |
| OP5 |  |  |  |  |  |  |  |

## 12.9  Escalation thresholds

| Trigger | Escalate to | Within |
| --- | --- | --- |
| Any new or re-rated Extreme risk | Project Board and investment authority | 24 hours |
| Any new or re-rated High risk | Project Board | 5 working days |
| Aggregate quantified exposure exceeding remaining contingency | Project Board | Immediately |
| A risk that, if realised, would breach a Section 8.2 tolerance | Project Board | 5 working days |
| Any safety or environmental risk rated 4 or 5 for consequence | HSE Lead and Project Board | 24 hours |
| A risk affecting a benefit target in Section 11.2 | Senior User and Sponsor | 5 working days |
| An issue unresolved beyond its target resolution time | Next level in Section 7.7 | On expiry |

# 13.  Stakeholders and Communications

Guidance Identify who can affect or is affected by the project, and set the engagement posture for each. This is the strategy level: the detailed communications plan, media protocol, collateral, channels and engagement calendar sit in the communications plan referenced by the Project Execution Plan.

## 13.1  Stakeholder identification approach

Stakeholders are identified at initiation through a facilitated mapping session with the Sponsor, Senior User and asset owner, and refreshed at each stage boundary;

Identification covers internal, delivery-chain, authority, community and end-user groups, including those who will not self-identify;

Each stakeholder is assessed for interest, influence and the impact the project has on them, and assigned a single relationship owner;

Engagement commitments made to any stakeholder are recorded and tracked as obligations, not as goodwill;

Stakeholder sentiment is monitored and reported as a leading indicator of approval and acceptance risk.

## 13.2  Stakeholder register

| Ref | Stakeholder | Interest in the project | Influence | Impact on them | Engagement approach | Owner | Frequency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | Project Executive / Sponsor |  | High | High | Manage closely - direct, formal | Project Manager | Weekly |
| S2 | Senior User / operational business unit |  | High | High | Manage closely - workshops and sign-offs | Project Manager | Fortnightly |
| S3 | Asset owner / operator |  | High | High | Manage closely - technical and readiness forums | Project Manager | Monthly |
| S4 | Funding body |  | High | Low | Keep satisfied - formal reporting | Sponsor | Monthly |
| S5 | Consent and regulatory authorities |  | High | Low | Keep satisfied - pre-lodgement and formal submissions | Approvals Lead | As required |
| S6 | Utility and service authorities |  | Medium | Medium | Keep informed - technical liaison | Project Manager | Monthly |
| S7 | Adjoining owners, residents and businesses |  | Medium | High | Keep informed - briefings, notifications, complaints line | Communications Lead | Per milestone |
| S8 | Community and interest groups |  | Medium | Medium | Keep informed - public information and consultation | Communications Lead | Per milestone |
| S9 | End users and customers |  | Low | High | Keep informed - service change notifications | Senior User | Per milestone |
| S10 | Contractors and supply chain |  | Medium | High | Manage closely - contractual and coordination forums | Commercial Lead | Weekly |
| S11 | Internal support functions (finance, legal, procurement, ICT) |  | Medium | Low | Keep informed - scheduled touchpoints | Project Manager | Monthly |
| S12 | Media |  | Medium | Low | Monitor - respond through the approved spokesperson only | Communications Lead | As required |
| S13 | Emergency services and access-dependent parties |  | Low | High | Keep informed - access and traffic notifications | Project Manager | Per milestone |
| S14 |  |  |  |  |  |  |  |

## 13.3  Power and interest positioning

Stakeholders are positioned on a power/interest grid to set the engagement posture. Those with high influence and high interest are managed closely with direct, frequent and largely two-way engagement. Those with high influence and low interest are kept satisfied through concise formal reporting - their interest tends to rise sharply when something goes wrong, and an established relationship is the cheapest form of insurance. Those with low influence and high interest are kept informed, consistently and early, because they are most affected by disruption and are the source of most objections. Those with low influence and low interest are monitored only.

POWER / INTEREST GRID Insert the power/interest grid plotting the stakeholders in Section 13.2, with quadrants labelled Manage closely, Keep satisfied, Keep informed and Monitor. Re-plot at each stage boundary - positions move as the project moves.

## 13.4  Communication principles

One version of the truth: external and internal messages are consistent and drawn from the same reported position;

Say it first and say it early - the project informs affected parties before they discover the impact themselves;

Commitments made in engagement are recorded, owned and delivered;

One approved spokesperson for media and public statements;

Communication is two-way: every channel that pushes information has a defined route for a response and a response time;

Culturally appropriate, accessible and, where required, multi-language communication for affected communities.

## 13.5  Communications summary matrix

| Audience | Message / purpose | Channel | Frequency | Owner | Feedback route |
| --- | --- | --- | --- | --- | --- |
| Project Board | Performance against baseline and decisions required | Board pack and meeting | Monthly | Project Manager | Board minutes |
| Funder | Financial and delivery performance | Formal report | Monthly / quarterly | Sponsor | Funder review meeting |
| Project team | Priorities, risks, actions | Team meeting and action log | Weekly | Project Manager | Team meeting |
| Contractors | Coordination, safety, interfaces | Site meeting and contract correspondence | Weekly | Project Manager | Contract correspondence |
| Authorities | Applications, conditions, compliance | Formal submission and liaison meeting | As required | Approvals Lead | Formal response |
| Adjoining owners and residents | Works notification, disruption, mitigation | Letter drop, site signage, email list | Before each disruptive activity | Communications Lead | Enquiries and complaints line |
| Community | Progress, benefits, opportunities | Web page, newsletter, information session | Per milestone | Communications Lead | Feedback form and sessions |
| End users | Service impacts and transition | Service notices and briefings | Per milestone | Senior User | Service channels |
| Internal organisation | Progress and readiness | Intranet and leadership briefings | Quarterly | Sponsor | Leadership forum |

## 13.6  Community and public engagement

[Describe the engagement approach for the affected community: the level of participation offered (inform, consult, involve, collaborate), the engagement activities planned at each stage, how feedback influences decisions, and how commitments are recorded and reported back. State any consultation that is mandatory under the approvals regime applicable in your jurisdiction.]

## 13.7  Approvals and authority engagement

| Authority | Approval or interest | Engagement stage | Pre-lodgement engagement | Owner |
| --- | --- | --- | --- | --- |

## 13.8  Relationship to the communications plan

This section sets who must be engaged and to what end. The communications plan referenced by the Project Execution Plan converts it into an engagement calendar, message library, collateral set, complaints handling procedure, media protocol and measurement regime.

# 14.  Quality, Health, Safety, Environment and Sustainability Requirements

Guidance This section states the requirements and standards the project must meet. It does not describe how they will be managed - the quality plan, HSE plan, environmental management plan and their procedures sit under the Project Execution Plan. Requirements stated here become acceptance criteria and contract obligations, so write them so they can be tested.

## 14.1  Quality expectations

| Quality expectation | Requirement | Acceptance criterion | Verified by | Evidence |
| --- | --- | --- | --- | --- |
| Fitness for operational purpose |  |  | Senior User |  |
| Compliance with the design brief and standards in Section 5.8 |  |  | Design Lead |  |
| Design life and durability |  |  | Design Lead |  |
| Workmanship and finishes |  |  | Project Manager |  |
| Performance testing and commissioning |  |  | Commissioning Manager |  |
| Maintainability and access for maintenance |  |  | Asset Owner |  |
| Completeness of handover information |  |  | Information Manager |  |
| Defects at handover |  |  | Project Manager |  |

## 14.2  Applicable management system standards

| Domain | Standard / framework | Applies to | Certification required? |
| --- | --- | --- | --- |
| Quality management | ISO 9001 or equivalent | Delivery organisation and principal contractor |  |
| Occupational health and safety | ISO 45001 or equivalent | All parties performing work |  |
| Environmental management | ISO 14001 or equivalent | Principal contractor |  |
| Risk management | ISO 31000 | Project risk management framework | n/a |
| Project management | ISO 21502 / PRINCE2 / PMBOK 7 | Project delivery method | n/a |
| Information management | ISO 19650 series | All information producers |  |
| Energy management | ISO 50001 or equivalent | Operational phase |  |
| Asset management | ISO 55001 or equivalent | Handover and operations |  |

## 14.3  Health and safety requirements

All parties comply with the work health and safety legislation, regulations and codes applicable in the jurisdiction of the works, and with the client's own safety requirements where these are more onerous;

Safety in design is applied at every design stage: hazards are eliminated at source where reasonably practicable, and residual hazards are recorded, communicated and carried into the operations and maintenance information;

The party with control of the workplace is defined contractually before any work starts, together with the interface arrangements where control is shared with an operating facility;

High-risk construction activities are identified at initiation and require documented safe work methods accepted before commencement;

Incident notification, investigation and reporting obligations apply to all parties, with immediate notification of any notifiable incident to the client;

Safety performance is reported monthly and is the first standing item at every Project Board meeting;

Stop-work authority is held by every person on site and is exercised without consequence.

| Safety requirement | Applies at stage | Evidence required | Owner |
| --- | --- | --- | --- |
| Safety in design reviews and risk reduction record | Each design stage |  | Design Lead |
| Principal contractor safety management plan accepted | Before site mobilisation |  | HSE Lead |
| Site induction and competency verification | Ongoing |  | Contractor |
| High-risk activity method statements accepted | Before each activity |  | HSE Lead |
| Emergency response and rescue arrangements | Before mobilisation |  | Contractor |
| Commissioning and energisation safety controls | Commissioning |  | Commissioning Manager |
| Residual hazard register transferred to the operator | Handover |  | Design Lead |

## 14.4  Environmental approvals and obligations

| Approval / obligation | Instrument type | Authority | Status | Conditions to be managed | Owner |
| --- | --- | --- | --- | --- | --- |
| Environmental impact assessment or equivalent |  |  |  |  |  |
| Vegetation clearing or habitat approval |  |  |  |  |  |
| Water take, discharge or dewatering licence |  |  |  |  |  |
| Contaminated land and remediation approval |  |  |  |  |  |
| Waste classification and disposal approval |  |  |  |  |  |
| Noise and vibration limits or exemption |  |  |  |  |  |
| Air quality and dust management obligation |  |  |  |  |  |
| Heritage or cultural approval |  |  |  |  |  |
| Erosion and sediment control obligation |  |  |  |  |  |

Instrument names, thresholds and consent authorities vary; confirm the correct titles under the approvals regime applicable in your jurisdiction and record them above. Conditions attached to any approval become project obligations and must be transferred into the obligations register and the relevant contract.

## 14.5  Sustainability and carbon targets

| Target area | Requirement / target | Measure | Verification | Owner |
| --- | --- | --- | --- | --- |
| Rating scheme certification (e.g. building or infrastructure sustainability rating) |  |  |  | Design Lead |
| Embodied carbon reduction against a reference design |  |  |  | Design Lead |
| Operational energy performance and emissions |  |  |  | Asset Owner |
| Renewable energy provision |  |  |  | Design Lead |
| Water efficiency and reuse |  |  |  | Design Lead |
| Construction and demolition waste diverted from landfill |  |  |  | Contractor |
| Sustainable materials and responsible sourcing |  |  |  | Commercial Lead |
| Biodiversity and net gain |  |  |  | Design Lead |

## 14.6  Social value commitments

| Commitment | Target | Measure | Contract mechanism | Owner |
| --- | --- | --- | --- | --- |
| Local employment and apprenticeships |  |  |  |  |
| Local and small-business supply chain participation |  |  |  |  |
| Participation by under-represented or Indigenous businesses |  |  |  |  |
| Skills, training and workforce development |  |  |  |  |
| Community investment and legacy initiatives |  |  |  |  |
| Accessible and inclusive design outcomes |  |  |  |  |

## 14.7  Climate resilience requirements

Guidance State the climate scenario and horizon the design must be robust against, and the adaptation measures required. An asset designed only to historical conditions may be obsolete well within its design life, and funders increasingly require this to be evidenced.

| Climate hazard | Design scenario / horizon | Design response | Residual exposure | Owner |
| --- | --- | --- | --- | --- |
| Extreme rainfall and flooding |  |  |  |  |
| Extreme heat |  |  |  |  |
| Drought and water availability |  |  |  |  |
| Bushfire or wildfire |  |  |  |  |
| Storm, wind and coastal inundation |  |  |  |  |
| Sea level rise / groundwater rise |  |  |  |  |
| Supply chain and utility disruption |  |  |  |  |

## 14.8  Statutory compliance obligations register

| Obligation category | Source | Applies to | Evidence of compliance | Frequency | Owner |
| --- | --- | --- | --- | --- | --- |
| Work health and safety | Legislation and regulation | All parties |  | Continuous | HSE Lead |
| Environmental protection | Legislation and approval conditions | Contractor |  | Continuous | HSE Lead |
| Planning and development consent | Consent conditions | Project |  | Per condition | Approvals Lead |
| Building and construction regulation | Building code / permit | Contractor and certifier |  | Per inspection | Project Manager |
| Employment and industrial relations | Legislation and agreements | All employers |  | Continuous | Commercial Lead |
| Procurement and probity | Organisational policy and law | Client |  | Per procurement | Commercial Lead |
| Privacy and data protection | Legislation and policy | All parties |  | Continuous | Information Manager |
| Accessibility and anti-discrimination | Legislation and standards | Design and works |  | Per design stage | Design Lead |
| Modern slavery and ethical sourcing | Legislation and policy | Supply chain |  | Annual | Commercial Lead |

## 14.9  Relationship to the Project Execution Plan

The requirements above are given effect through the quality management plan, HSE management plan, environmental management plan and sustainability management plan, each of which is subordinate to the Project Execution Plan and must demonstrate traceability back to this section.

# 15.  Information, Data and Digital Requirements

Guidance Set the information requirements at initiation, before any consultant or contractor is appointed. Information requirements written after appointment cannot be enforced without a variation, and asset data specified at handover is never delivered to a usable standard.

## 15.1  Information requirements (ISO 19650)

| Requirement set | What it defines | Owner | Status |
| --- | --- | --- | --- |
| Organisational Information Requirements (OIR) | The information the organisation needs to meet its strategic objectives | Asset Owner |  |
| Asset Information Requirements (AIR) | The information needed to operate, maintain and manage the asset | Asset Owner |  |
| Project Information Requirements (PIR) | The information needed to make project decisions at each stage | Project Manager |  |
| Exchange Information Requirements (EIR) | What each appointed party must deliver, when, in what format and to what standard | Information Manager |  |
| Information delivery plans (MIDP / TIDP) | The programme of information deliverables and who produces them | Information Manager |  |

## 15.2  Digital delivery expectations

| Requirement | Position |
| --- | --- |
| Level of information need by stage |  |
| Model federation and coordination requirements |  |
| Clash detection and resolution expectations |  |
| Geometric and non-geometric data requirements |  |
| Classification system to be used |  |
| Naming and numbering convention |  |
| Open exchange formats required at handover |  |
| Digital twin or asset model requirement (if any) |  |
| Survey and spatial reference framework |  |
| Reality capture / point cloud requirements |  |

## 15.3  Common data environment

A single common data environment is nominated for the project before the first appointment is made, and all parties work within it;

Information moves through defined states - work in progress, shared, published and archived - with authorisation required at each transition;

Every container carries a unique identifier, revision, status code and suitability;

Access is role-based; security-classified information is restricted and its distribution logged;

Superseded information is archived, never deleted, and the audit trail is retained for the period at Section 15.6;

The client owns the project information and retains access independently of any supplier's system.

## 15.4  Asset data and handover information

| Handover information set | Format | Standard | Accepted by | Due |
| --- | --- | --- | --- | --- |
| As-built drawings and models |  |  | Information Manager | Handover |
| Asset register with unique asset identifiers |  |  | Asset Owner | Before handover |
| Operation and maintenance manuals |  |  | Asset Owner | Before handover |
| Maintenance strategy and schedules |  |  | Asset Owner | Before handover |
| Warranties, guarantees and certificates |  |  | Project Manager | Handover |
| Commissioning and test records |  |  | Commissioning Manager | Handover |
| Spares, consumables and tooling schedule |  |  | Asset Owner | Before handover |
| Residual hazard and safety file |  |  | HSE Lead | Handover |
| Software, licences and control system configuration |  |  | Asset Owner | Handover |
| Training records and competency evidence |  |  | Asset Owner | Before handover |

## 15.5  Systems to be used

| Function | System | Owner | Access arrangements | Data export at closure |
| --- | --- | --- | --- | --- |
| Common data environment / document control |  |  |  |  |
| Project controls, cost and reporting |  |  |  |  |
| Scheduling |  |  |  |  |
| Risk register |  |  |  |  |
| Contract and change management |  |  |  |  |
| Design authoring and model federation |  |  |  |  |
| Site quality, inspection and defects |  |  |  |  |
| HSE incident and observation reporting |  |  |  |  |
| Asset management system |  |  |  |  |

## 15.6  Records, retention and security

| Attribute | Requirement |
| --- | --- |
| Record-keeping obligations | As required by the records management regime applicable in your jurisdiction and by organisational policy |
| Retention period for project records |  |
| Retention period for asset and safety records |  |
| Security classification scheme applied |  |
| Handling of security-sensitive asset information |  |
| Personal information and privacy obligations |  |
| Intellectual property and licence to use deliverables |  |
| Freedom of information / public access considerations |  |
| Cyber security controls required of suppliers |  |
| Archive and transfer to the asset owner at closure |  |

## 15.7  Relationship to the Project Execution Plan

The requirements above are implemented through the information management plan (or BIM execution plan) prepared under the Project Execution Plan, which sets out workflows, responsibility matrices, software versions, exchange schedules and quality assurance of information.

# 16.  Resourcing and Capability

Guidance Under-resourcing the client side is one of the most reliable predictors of poor project outcomes, and one of the least visible at approval. Show the roles, the effort, where the people come from, when they are needed and what they cost - and be honest about the gaps.

## 16.1  Project team structure and resourcing

| Role | Name | FTE | Source | Mobilisation date | Duration | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Project Executive / Sponsor |  | 0.1 | Internal |  |  |  |
| Client Project Director |  |  | Internal |  |  |  |
| Project Manager |  | 1.0 | Internal / consultant |  |  |  |
| Assistant Project Manager |  |  |  |  |  |  |
| Design Lead |  |  | Consultant |  |  |  |
| Commercial Lead / Quantity Surveyor |  |  | Consultant |  |  |  |
| Planner / scheduler |  |  | Consultant |  |  |  |
| Project controls / cost engineer |  |  |  |  |  |  |
| HSE Lead |  |  | Internal |  |  |  |
| Information Manager |  |  |  |  |  |  |
| Approvals / planning specialist |  |  | Consultant |  |  |  |
| Stakeholder and communications lead |  |  |  |  |  |  |
| Site supervision / superintendent's representative |  |  |  |  |  |  |
| Commissioning Manager |  |  |  |  |  |  |
| Asset owner representative |  |  | Internal |  |  |  |
| Project Support / administrator |  |  | Internal |  |  |  |
| Total |  |  |  |  |  |  |

## 16.2  Capability assessment and gaps

| Capability required | Current position | Gap | Mitigation | Owner | By when |
| --- | --- | --- | --- | --- | --- |
| Project management of this scale and complexity |  |  |  |  |  |
| Technical and design assurance in the relevant discipline |  |  |  |  |  |
| Commercial and contract administration |  |  |  |  |  |
| Programme and schedule management |  |  |  |  |  |
| Approvals and regulatory navigation |  |  |  |  |  |
| Commissioning and operational transition |  |  |  |  |  |
| Information and digital delivery |  |  |  |  |  |
| Stakeholder and community engagement |  |  |  |  |  |

## 16.3  Consultant and advisor appointments

| Appointment | Scope of services | Procurement route | Value | Appointed by | Status |
| --- | --- | --- | --- | --- | --- |
| Design consultant(s) |  |  |  |  |  |
| Cost consultant / quantity surveyor |  |  |  |  |  |
| Programme / planning consultant |  |  |  |  |  |
| Geotechnical and environmental consultants |  |  |  |  |  |
| Planning and approvals consultant |  |  |  |  |  |
| Legal advisor |  |  |  |  |  |
| Independent certifier / superintendent |  |  |  |  |  |
| Specialist advisors (specify) |  |  |  |  |  |

## 16.4  Training and onboarding

Every team member is inducted into this PID, the governance structure and the delegations before taking up their role;

Training needs are identified for the systems in Section 15.5 and delivered before those systems are used in anger;

Contract and change control training is provided to anyone who may instruct or receive an instruction;

Operational staff training requirements for the completed asset are planned from the start of design and delivered before commissioning ends;

Handover of role knowledge is required on any change of key personnel, with a documented handover note.

## 16.5  Key person risks

| Role | Key person dependency | Impact if lost | Succession cover | Knowledge capture | Owner |
| --- | --- | --- | --- | --- | --- |
| Project Manager |  |  |  |  |  |
| Design Lead |  |  |  |  |  |
| Commercial Lead |  |  |  |  |  |
| Asset owner representative |  |  |  |  |  |
| Specialist technical authority |  |  |  |  |  |

# 17.  Interfaces and Dependencies

Guidance Most claims and most delays originate at an interface that nobody owned. For each interface, name a single owner on each side, state what must be agreed, and set the date by which it must be resolved - usually well before the works reach it.

## 17.1  Interface register

| Ref | Interface | Counterparty | Type | Description / what must be agreed | Owner | Resolve by | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| I1 |  |  | Physical / tie-in |  |  |  |  |
| I2 |  |  | Contractual |  |  |  |  |
| I3 |  |  | Operational |  |  |  |  |
| I4 |  |  | Systems / controls |  |  |  |  |
| I5 |  |  | Utility / authority |  |  |  |  |
| I6 |  |  | Land / access |  |  |  |  |
| I7 |  |  | Information |  |  |  |  |
| I8 |  |  |  |  |  |  |  |

## 17.2  Programme and portfolio dependencies

| Ref | Related project or programme | Nature of the dependency | Direction | Required by | Owner | Escalation route |
| --- | --- | --- | --- | --- | --- | --- |

## 17.3  Operational and business-as-usual interfaces

| Operational interface | Impact on operations | Coordination arrangement | Owner | Agreed by |
| --- | --- | --- | --- | --- |
| Access and possession windows |  |  |  |  |
| Shutdowns and outages |  |  |  |  |
| Temporary service arrangements |  |  |  |  |
| Decant, relocation and staging |  |  |  |  |
| Emergency access and egress |  |  |  |  |
| Security and site control |  |  |  |  |
| Operator training and familiarisation |  |  |  |  |
| Transition of maintenance responsibility |  |  |  |  |

## 17.4  Third-party and authority dependencies

| Third party | What the project needs from them | Lead time | Required by | Consequence of delay | Owner |
| --- | --- | --- | --- | --- | --- |
| Consent authority |  |  |  |  |  |
| Environmental regulator |  |  |  |  |  |
| Electricity network operator |  |  |  |  |  |
| Water and wastewater authority |  |  |  |  |  |
| Telecommunications carrier |  |  |  |  |  |
| Road or rail authority |  |  |  |  |  |
| Adjoining landowners |  |  |  |  |  |
| Heritage or cultural body |  |  |  |  |  |

# 18.  Initiation Stage Assessment and Readiness

Guidance This is the honesty section. Complete it before the approval meeting, not during it. Every criterion is either met with evidence, or it is a gap with an owner and a date. A project authorised with unacknowledged gaps carries them, unfunded, into delivery.

## 18.1  Readiness assessment

| Criterion | Required evidence | Status | Gap | Action | Owner |
| --- | --- | --- | --- | --- | --- |
| Approved business case in force | Business case reference and approval record |  |  |  | Sponsor |
| Funding confirmed and profiled | Funding approval and drawdown conditions |  |  |  | Sponsor |
| Scope defined and agreed | Sections 4.1 - 4.5 complete and signed off |  |  |  | Project Manager |
| Objectives and success criteria agreed | Sections 4.2 and 11.4 signed off by the Senior User |  |  |  | Senior User |
| Benefits baselined with named owners | Section 11.2 register with baseline measurements |  |  |  | Senior User |
| Governance established and roles filled | Section 7 complete; appointment letters issued |  |  |  | Sponsor |
| Delegations and tolerances confirmed | Section 7.5 and 8.2 approved against the delegation instrument |  |  |  | Sponsor |
| Cost estimate prepared and assured | Section 10.1 with estimate class and independent review |  |  |  | Commercial Lead |
| Contingency sized on quantified risk | Risk analysis output supporting Section 10.3 |  |  |  | Project Manager |
| Milestone schedule baselined | Section 9.2 with logic-linked supporting schedule |  |  |  | Project Manager |
| Risk register populated and rated | Section 12.6 with owners and treatments |  |  |  | Project Manager |
| Key assumptions and constraints documented | Sections 4.8 and 4.9 with validation dates |  |  |  | Project Manager |
| Site and asset context understood | Section 5 complete; investigations adequate for stage |  |  |  | Design Lead |
| Approvals pathway identified and timed | Sections 5.7 and 13.7; pre-lodgement advice obtained |  |  |  | Approvals Lead |
| Land tenure and access secured or programmed | Title, easement and access evidence |  |  |  | Client Project Director |
| Delivery and procurement strategy approved | Section 6 and the procurement strategy document |  |  |  | Commercial Lead |
| Client-side resources secured | Section 16.1 with confirmed mobilisation dates |  |  |  | Client Project Director |
| Stakeholders identified and engagement started | Section 13.2 register and engagement record |  |  |  | Project Manager |
| Information requirements defined | Section 15.1 issued ahead of appointments |  |  |  | Information Manager |
| HSE and sustainability requirements defined | Section 14 complete and reflected in the brief |  |  |  | HSE Lead |
| Interfaces and dependencies identified | Sections 17.1 and 4.7 with owners |  |  |  | Project Manager |
| Controls framework and reporting agreed | Section 8 approved; systems available |  |  |  | Project Manager |
| PEP scope agreed and drafting under way | PEP outline and issue date |  |  |  | Project Manager |
| Lessons from comparable projects considered | Section 8.9 completed |  |  |  | Project Manager |
| Assurance plan agreed | Section 7.6 with booked review dates |  |  |  | Project Assurance |

## 18.2  Conditions of approval

Guidance Where the Board is prepared to authorise the project despite an open item, record it as a condition with a discharge date and an owner. Conditions are tracked to closure and reported at every Board meeting until discharged.

| Ref | Condition of approval | Rationale | Discharge by | Evidence of discharge | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CA1 |  |  |  |  |  | Open |
| CA2 |  |  |  |  |  | Open |
| CA3 |  |  |  |  |  | Open |
| CA4 |  |  |  |  |  | Open |

## 18.3  Overall readiness conclusion

[State the Project Manager's assessment: whether the project is ready to proceed into delivery, the residual gaps, the conditions recommended, and any recommendation to defer. A recommendation to defer, made early and with evidence, is a sign of a well-run initiation stage - not a failure.]

# 19.  Recommendation and Approval Sought

## 19.1  Recommendation

It is recommended that the Project Board and the investment authority approve this Project Initiation Document and authorise the project to proceed from initiation into delivery.

[Add a short project-specific paragraph: why the project should proceed now, the strength of the justification, the principal residual exposures and why they are acceptable or manageable.]

## 19.2  Decision sought

| Ref | Decision sought | Authority required | Reference |
| --- | --- | --- | --- |
| 1 | Approve and baseline this Project Initiation Document at the revision shown on the cover | Project Board | Whole document |
| 2 | Authorise the project to proceed into delivery Stage [ ] | Project Board | Section 6.2 |
| 3 | Approve the total capital cost envelope and the funding arrangements | Investment authority | Sections 10.1 and 10.6 |
| 4 | Release funding for the next stage | Investment authority | Sections 10.5 and 10.6 |
| 5 | Confirm the governance structure and the appointment of the named role-holders | Project Board | Section 7 |
| 6 | Grant the delegations, thresholds and tolerances to the Project Manager | Project Board | Sections 7.5 and 8.2 |
| 7 | Accept the initial risk position and the contingency basis | Project Board | Sections 12.6 and 10.3 |
| 8 | Accept the benefits baseline and confirm the benefit owners | Sponsor and Senior User | Section 11.2 |
| 9 | Note and impose the conditions of approval | Project Board | Section 18.2 |

## 19.3  What is being baselined by this approval

| Baseline | Reference | Owner after approval |
| --- | --- | --- |
| Scope baseline | Sections 4.1 to 4.5 | Project Manager |
| Milestone schedule baseline | Section 9.2 | Project Manager |
| Cost baseline and contingency | Sections 10.1 and 10.3 | Commercial Lead |
| Benefits baseline | Section 11.2 | Senior User |
| Risk baseline | Section 12.6 | Project Manager |
| Quality and acceptance baseline | Sections 11.4 and 14.1 | Senior User |
| Governance, delegations and tolerances | Sections 7 and 8 | Project Executive |

## 19.4  Effect of approval

The PID becomes the controlled baseline against which delivery performance, change and closure are judged;

The Project Manager is authorised to act within the delegations and tolerances granted, and is obliged to escalate outside them;

The Project Execution Plan and the subsidiary management plans mandated by this PID must be prepared and approved to the timetable agreed with the Project Board;

Any subsequent change to the baselines listed above requires approval under Section 8.5 and a re-issue of this document;

The conditions of approval at Section 18.2 take effect immediately and are reported to the Board until discharged.

Signatures authorising this recommendation are recorded in the Approval and Authorisation block in the front matter of this document.

# Appendix A  Initial Risk Register

Guidance Working copy of the register at Section 12.6, with the tracking columns a live register needs. Maintain it in the risk system named at Section 15.5 - this table is the baselined snapshot taken at PID approval. Re-rate at every stage boundary and record the residual position after treatment.

| Ref | Risk (cause → event → effect) | Category | L | C | Rating | Treatment strategy and key actions | Owner | Target date | Residual | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Because determination timeframes for the principal statutory approval are outside the project's control and supporting assessments are incomplete, approval may be granted later than assumed, delaying tender award and pushing construction into an adverse season | Approvals | 4 | 4 | High | Reduce - pre-lodgement engagement with the consent authority; complete supporting studies before lodgement; sequence early works that do not depend on the approval | Approvals Lead |  | Medium | Open |
| R02 | Because site investigation to date is preliminary and the site has a history of filling, ground conditions may differ materially from those assumed in the design, resulting in redesign of foundations and additional excavation and disposal cost | Technical | 4 | 4 | High | Reduce - complete a targeted geotechnical investigation before design freeze; adopt a foundation solution tolerant of variation; retain a quantified ground allowance in contingency | Design Lead |  | Medium | Open |
| R03 | Because regional construction demand is high and tender capacity is constrained, the project may receive few or non-conforming tenders at prices above the estimate, resulting in a funding shortfall or retender | Commercial | 4 | 4 | High | Reduce - early market sounding; package to suit available bidders; review the tender window against the regional pipeline; prepare a priced descoping schedule before tender | Commercial Lead |  | High | Open |
| R04 | Because design is taken to tender at a lower level of maturity than the contract assumes, the contractor may price provisionally and claim variations for design development, resulting in cost growth and adversarial contract administration | Design | 3 | 4 | High | Reduce - define and enforce a design maturity gate before tender; independent design review; unambiguous employer's requirements and a documented design intent | Design Lead |  | Medium | Open |
| R05 | Because the works affect amenity for adjoining residents and businesses, sustained objection may be raised during the approval or construction phase, resulting in conditions, delay or design change | Stakeholder | 3 | 3 | High | Reduce - early and structured engagement per Section 13; publish mitigation commitments; establish a responsive complaints process with defined response times | Project Manager |  | Medium | Open |
| R06 | Because utility records are incomplete and diversion approvals depend on third-party authorities, service diversions may take longer or cost more than assumed, delaying enabling works and the critical path | Utilities | 4 | 3 | High | Reduce - non-destructive location survey and potholing before design freeze; early application to each authority; separate the diversion package so it can start ahead of the principal works | Project Manager |  | Medium | Open |
| R07 | Because contractor margins in the current market are thin, the principal contractor or a critical subcontractor may become insolvent during the works, resulting in suspension, re-procurement, delay and additional cost | Commercial | 2 | 5 | High | Transfer and reduce - financial capacity assessment at prequalification and ongoing monitoring; performance security and bonding; step-in and novation rights; avoid over-reliance on a single subcontractor | Commercial Lead |  | Medium | Open |
| R08 | Because user groups were not fully engaged during option development, additional requirements may be introduced after design freeze, resulting in rework, variation cost and delay | Scope | 4 | 3 | High | Reduce - Senior User sign-off of the brief before design freeze; a single client requirements channel; strict application of change control under Section 8.5 | Senior User |  | Medium | Open |
| R09 | Because client-side project management and technical resources are shared across a busy portfolio, key roles may be unfilled or part-committed, resulting in slow decisions, late approvals and loss of project knowledge | Resourcing | 3 | 3 | High | Reduce - secure named resources and mobilisation dates per Section 16.1; document delegations; maintain succession cover for the Project Manager and Commercial Lead | Client Project Director |  | Medium | Open |
| R10 | Because the construction period spans a wet season and the works include extensive earthworks, adverse weather may exceed the allowance in the programme, resulting in delay and standing-time cost | Weather | 4 | 3 | High | Reduce - schedule earthworks outside the peak wet period where possible; include a quantified weather allowance based on historical records; define contractual entitlement clearly | Project Manager |  | Medium | Open |
| R11 | Because enterprise agreements in the region are due for renegotiation during the construction period, industrial action may occur, resulting in lost production days and delay to completion | Industrial | 2 | 3 | Medium | Monitor and transfer - track agreement expiry dates; allocate the risk clearly in the contract; require the contractor's industrial relations plan as a tender deliverable | Commercial Lead |  | Medium | Open |
| R12 | Because the works are undertaken adjacent to a live operating facility, construction activity may disrupt operations or breach an operating licence condition, resulting in operational loss, regulatory action and suspension of work | Operations | 3 | 4 | High | Reduce - agreed interface protocol and permit-to-work regime with the asset owner; scheduled shutdown windows per Section 5.5; operations representation at site coordination meetings | Asset Owner |  | Medium | Open |
| R13 | Because project and asset information is held in cloud systems shared with multiple suppliers, a cyber incident or uncontrolled disclosure may occur, resulting in loss of information, exposure of security-sensitive asset data and delay | Information | 3 | 4 | High | Reduce - apply the organisation's information security controls to the common data environment; classify and restrict security-sensitive information; contractual security obligations and audit rights | Information Manager |  | Medium | Open |
| R14 | Because specified long-lead plant is sourced from constrained international supply chains, delivery may extend beyond quoted lead times, resulting in delay to commissioning and to the in-service date | Supply chain | 4 | 4 | High | Reduce - identify long-lead items at initiation and order against the critical path; consider client-supplied procurement; specify alternative acceptable manufacturers; require a supply chain plan from tenderers | Commercial Lead |  | Medium | Open |
| R15 | Because funding is appropriated annually and the cash flow is back-loaded, the available funding profile may not match the expenditure profile, resulting in forced slowdown, re-mobilisation cost or lapse of unspent allocation | Funding | 3 | 4 | High | Reduce - reconcile the Section 10.5 cash flow to the funding profile monthly; agree a re-profiling mechanism with the funder; sequence commitments to match drawdown windows | Sponsor |  | Medium | Open |
| R16 |  |  |  |  |  |  |  |  |  |  |
| R17 |  |  |  |  |  |  |  |  |  |  |
| R18 |  |  |  |  |  |  |  |  |  |  |

# Appendix B  Stakeholder Register

Guidance Expand the summary at Section 13.2 into a working register. Record the current position of each stakeholder (supportive, neutral, opposed) and the position required - the gap between the two is the engagement task.

| Ref | Stakeholder | Group | Interest in the project | Influence | Impact | Current position | Engagement approach | Owner | Frequency | Last engaged |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S1 | Project Executive / Sponsor | Internal |  | High | High | Supportive | Manage closely | Project Manager | Weekly |  |
| S2 | Senior User | Internal |  | High | High | Supportive | Manage closely | Project Manager | Fortnightly |  |
| S3 | Asset owner / operator | Internal |  | High | High |  | Manage closely | Project Manager | Monthly |  |
| S4 | Funding body | External |  | High | Low |  | Keep satisfied | Sponsor | Monthly |  |
| S5 | Consent authority | Authority |  | High | Low |  | Keep satisfied | Approvals Lead | As required |  |
| S6 | Environmental regulator | Authority |  | High | Low |  | Keep satisfied | Approvals Lead | As required |  |
| S7 | Utility and service authorities | Authority |  | Medium | Medium |  | Keep informed | Project Manager | Monthly |  |
| S8 | Adjoining owners and residents | Community |  | Medium | High |  | Keep informed | Communications Lead | Per milestone |  |
| S9 | Local businesses | Community |  | Medium | High |  | Keep informed | Communications Lead | Per milestone |  |
| S10 | Community and interest groups | Community |  | Medium | Medium |  | Keep informed | Communications Lead | Per milestone |  |
| S11 | End users / customers | External |  | Low | High |  | Keep informed | Senior User | Per milestone |  |
| S12 | Contractors and supply chain | Delivery |  | Medium | High |  | Manage closely | Commercial Lead | Weekly |  |
| S13 | Design consultants | Delivery |  | Medium | High |  | Manage closely | Design Lead | Weekly |  |
| S14 | Internal support functions | Internal |  | Medium | Low |  | Keep informed | Project Manager | Monthly |  |
| S15 | Media | External |  | Medium | Low |  | Monitor | Communications Lead | As required |  |
| S16 | Emergency services | Authority |  | Low | High |  | Keep informed | Project Manager | Per milestone |  |
| S17 | Heritage / cultural body | Authority |  | Medium | Medium |  | Keep satisfied | Approvals Lead | As required |  |
| S18 |  |  |  |  |  |  |  |  |  |  |
| S19 |  |  |  |  |  |  |  |  |  |  |

# Appendix C  Milestone Schedule

Guidance Baselined milestone list from Section 9.2, with columns for tracking. Baseline dates change only through approved change; forecast dates change every cycle. Never overwrite the baseline column.

| Ref | Milestone | Stage | Baseline date | Forecast date | Actual date | Tolerance | Predecessor | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M01 | Business case approved and funding confirmed | Initiation |  |  |  | 0 days | Investment decision | Sponsor |  |
| M02 | PID approved and baselined; project authorised | Initiation |  |  |  | 0 days | M01 | Project Board |  |
| M03 | Project team mobilised and PEP outline issued | Initiation |  |  |  | ± 2 weeks | M02 | Project Manager |  |
| M04 | Site investigation and survey complete | Design |  |  |  | ± 3 weeks | M03 | Design Lead |  |
| M05 | Concept design accepted by Senior User | Design |  |  |  | ± 3 weeks | M04 | Design Lead |  |
| M06 | Statutory / planning application lodged | Approvals |  |  |  | ± 2 weeks | M05 | Approvals Lead |  |
| M07 | Developed design complete; design freeze | Design |  |  |  | ± 4 weeks | M05 | Design Lead |  |
| M08 | Cost plan updated and estimate assured | Design |  |  |  | ± 2 weeks | M07 | Commercial Lead |  |
| M09 | Statutory / planning approval granted | Approvals |  |  |  | ± 8 weeks | M06 | Approvals Lead |  |
| M10 | Gate: ready to procure | Approvals |  |  |  | 0 days | M07, M09 | Project Board |  |
| M11 | Tender documents issued to market | Procurement |  |  |  | ± 2 weeks | M10 | Commercial Lead |  |
| M12 | Tenders received and evaluation complete | Procurement |  |  |  | ± 3 weeks | M11 | Commercial Lead |  |
| M13 | Contract award approved and executed | Procurement |  |  |  | ± 3 weeks | M12 | Investment authority |  |
| M14 | Long-lead equipment orders placed | Procurement |  |  |  | ± 2 weeks | M13 | Commercial Lead |  |
| M15 | Contractor mobilised; site possession granted | Construction |  |  |  | ± 2 weeks | M13 | Project Manager |  |
| M16 | Enabling works and utility diversions complete | Construction |  |  |  | ± 4 weeks | M15 | Contractor |  |
| M17 | Substructure complete | Construction |  |  |  | ± 4 weeks | M16 | Contractor |  |
| M18 | Structure complete / weathertight | Construction |  |  |  | ± 6 weeks | M17 | Contractor |  |
| M19 | Services installation complete | Construction |  |  |  | ± 4 weeks | M18 | Contractor |  |
| M20 | Practical / substantial completion of the works | Construction |  |  |  | ± 4 weeks | M19 | Contractor |  |
| M21 | Commissioning and performance testing complete | Commissioning |  |  |  | ± 3 weeks | M20 | Commissioning Manager |  |
| M22 | Operational readiness confirmed; training complete | Commissioning |  |  |  | ± 3 weeks | M21 | Asset Owner |  |
| M23 | Regulatory occupation / operating approval obtained | Commissioning |  |  |  | ± 3 weeks | M21 | Approvals Lead |  |
| M24 | Asset information and as-built set accepted | Handover |  |  |  | ± 3 weeks | M21 | Information Manager |  |
| M25 | Handover to asset owner; asset in service | Handover |  |  |  | ± 2 weeks | M22, M23, M24 | Senior User |  |
| M26 | Defects liability period commences | Handover |  |  |  | 0 days | M25 | Project Manager |  |
| M27 | Final account agreed and settled | Closeout |  |  |  | ± 6 weeks | M25 | Commercial Lead |  |
| M28 | Project closure report approved; project closed | Closeout |  |  |  | ± 4 weeks | M27 | Project Board |  |
| M29 | End of defects liability period; final certificate | Closeout |  |  |  | ± 4 weeks | M26 | Project Manager |  |
| M30 | Post-implementation review complete | Benefits |  |  |  | ± 6 weeks | M25 | Sponsor |  |
| M31 | First benefits realisation review | Benefits |  |  |  | ± 6 weeks | M25 | Senior User |  |
| M32 | Final benefits realisation review | Benefits |  |  |  | ± 8 weeks | M31 | Senior User |  |

# Appendix D  Assumptions and Constraints Log

Guidance Assumptions expire. Give every one a validation date and review the log at each stage boundary; a disproved assumption is an issue on the day it is disproved, not at the next reporting cycle.

## D.1  Assumptions log

| Ref | Assumption | Category | Basis / source | Owner | Validate by | Impact if invalid | Linked risk | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A01 |  |  |  |  |  |  |  | Open |
| A02 |  |  |  |  |  |  |  | Open |
| A03 |  |  |  |  |  |  |  | Open |
| A04 |  |  |  |  |  |  |  | Open |
| A05 |  |  |  |  |  |  |  | Open |
| A06 |  |  |  |  |  |  |  | Open |
| A07 |  |  |  |  |  |  |  | Open |
| A08 |  |  |  |  |  |  |  | Open |
| A09 |  |  |  |  |  |  |  | Open |
| A10 |  |  |  |  |  |  |  | Open |

## D.2  Constraints log

| Ref | Constraint | Type | Description | Source | Impact on delivery | Managed by | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C01 |  |  |  |  |  |  |  |
| C02 |  |  |  |  |  |  |  |
| C03 |  |  |  |  |  |  |  |
| C04 |  |  |  |  |  |  |  |
| C05 |  |  |  |  |  |  |  |
| C06 |  |  |  |  |  |  |  |
| C07 |  |  |  |  |  |  |  |
| C08 |  |  |  |  |  |  |  |

# Appendix E  Dependency Register

Guidance Inbound dependencies are things the project needs from others; outbound are things others need from the project. Both fail silently unless a named person on each side agrees the date. Confirm every dependency in writing with the counterparty - an unacknowledged dependency is not a dependency, it is a hope.

| Ref | Direction | Dependency | Counterparty | Counterparty contact | Required by | Confirmed? | Impact if not met | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DP01 |  |  |  |  |  |  |  |  | Open |
| DP02 |  |  |  |  |  |  |  |  | Open |
| DP03 |  |  |  |  |  |  |  |  | Open |
| DP04 |  |  |  |  |  |  |  |  | Open |
| DP05 |  |  |  |  |  |  |  |  | Open |
| DP06 |  |  |  |  |  |  |  |  | Open |
| DP07 |  |  |  |  |  |  |  |  | Open |
| DP08 |  |  |  |  |  |  |  |  | Open |
| DP09 |  |  |  |  |  |  |  |  | Open |
| DP10 |  |  |  |  |  |  |  |  | Open |

# Appendix F  Benefits Register

Guidance A benefit with no baseline measurement cannot be evidenced, and a benefit with no owner outside the project team will not be realised. Capture the baseline before delivery changes anything on the ground.

| Ref | Benefit | Type | Measure | Baseline value | Baseline date | Target value | Realisation date | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B01 |  |  |  |  |  |  |  |  |  |
| B02 |  |  |  |  |  |  |  |  |  |
| B03 |  |  |  |  |  |  |  |  |  |
| B04 |  |  |  |  |  |  |  |  |  |
| B05 |  |  |  |  |  |  |  |  |  |
| B06 |  |  |  |  |  |  |  |  |  |
| B07 |  |  |  |  |  |  |  |  |  |
| B08 |  |  |  |  |  |  |  |  |  |
| B09 |  |  |  |  |  |  |  |  |  |

## F.1  Disbenefits log

| Ref | Disbenefit | Affected group | Measure | Scale | Mitigation | Accepted by | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DB01 |  |  |  |  |  |  |  |
| DB02 |  |  |  |  |  |  |  |
| DB03 |  |  |  |  |  |  |  |
| DB04 |  |  |  |  |  |  |  |

# Appendix G  Cost Estimate Breakdown

Guidance Expand Section 10.1 to the level of detail supporting the estimate. Show quantities and rates where they exist and mark allowances clearly - an allowance presented as a priced item creates false confidence and is the usual origin of an unexplained overrun.

| WBS | Cost element | Quantity | Unit | Rate | Amount | Basis (measured / allowance / quotation) | Source and date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Land and acquisition |  |  |  |  |  |  |
| 1.1 | Land purchase / compensation |  |  |  |  |  |  |
| 1.2 | Easements and access rights |  |  |  |  |  |  |
| 2 | Investigations and studies |  |  |  |  |  |  |
| 2.1 | Survey and geotechnical investigation |  |  |  |  |  |  |
| 2.2 | Environmental and heritage assessment |  |  |  |  |  |  |
| 3 | Design and professional services |  |  |  |  |  |  |
| 3.1 | Design consultancy |  |  |  |  |  |  |
| 3.2 | Specialist advisors |  |  |  |  |  |  |
| 3.3 | Independent certification and assurance |  |  |  |  |  |  |
| 4 | Approvals, fees and levies |  |  |  |  |  |  |
| 5 | Enabling and early works |  |  |  |  |  |  |
| 5.1 | Site clearance and demolition |  |  |  |  |  |  |
| 5.2 | Temporary works and site establishment |  |  |  |  |  |  |
| 6 | Utility diversions and connections |  |  |  |  |  |  |
| 7 | Principal construction works |  |  |  |  |  |  |
| 7.1 | Substructure and earthworks |  |  |  |  |  |  |
| 7.2 | Structure |  |  |  |  |  |  |
| 7.3 | Building fabric / civil works |  |  |  |  |  |  |
| 7.4 | Mechanical services |  |  |  |  |  |  |
| 7.5 | Electrical services |  |  |  |  |  |  |
| 7.6 | Hydraulic and fire services |  |  |  |  |  |  |
| 7.7 | External works and landscaping |  |  |  |  |  |  |
| 8 | Specialist and long-lead equipment |  |  |  |  |  |  |
| 9 | Fit-out, furniture and equipment |  |  |  |  |  |  |
| 10 | ICT, controls and security |  |  |  |  |  |  |
| 11 | Commissioning, training and transition |  |  |  |  |  |  |
| 12 | Client-side project management and controls |  |  |  |  |  |  |
| 13 | Insurances and bonds |  |  |  |  |  |  |
| 14 | Base estimate subtotal |  |  |  |  |  |  |
| 15 | Contingency (risk allowance) |  |  |  |  |  |  |
| 16 | Escalation to construction mid-point |  |  |  |  |  |  |
| 17 | Total capital cost (P50) |  |  |  |  |  |  |
| 18 | Total capital cost (P80) |  |  |  |  |  |  |

## G.1  Estimate basis statement

| Attribute | Position |
| --- | --- |
| Estimate class and expected accuracy range |  |
| Documents the estimate is based on |  |
| Price base date |  |
| Escalation applied |  |
| Exclusions from the estimate |  |
| Allowances included and their basis |  |
| Benchmarks used for validation |  |
| Independent review completed by / date |  |
| Known areas of estimating uncertainty |  |

# Appendix H  Governance Terms of Reference Template

Guidance Complete one of these for each governance body - Project Board, and any steering, technical, design or user reference group. Terms of reference that do not state what the body decides are decoration; the 'Decisions this body makes' row is the important one.

## H.1 Terms of reference - [name of body]

| Item | Detail |
| --- | --- |
| Name of body |  |
| Purpose |  |
| Authority - under what instrument it is established |  |
| Decisions this body makes |  |
| Decisions escalated from this body |  |
| Decisions delegated by this body |  |
| Chair |  |
| Members (name and role) |  |
| Standing attendees and advisors |  |
| Quorum |  |
| Decision rule (consensus / majority / chair decides) |  |
| Frequency and duration of meetings |  |
| Extraordinary meetings - who may call one |  |
| Secretariat |  |
| Papers - issued how many days in advance |  |
| Standing agenda items |  |
| Minutes - issued within how many days |  |
| Action tracking method |  |
| Conflict of interest declaration requirement |  |
| Confidentiality and information handling |  |
| Reporting obligations to a higher body |  |
| Review of these terms of reference |  |
| Date established and version |  |

## H.2  Standing agenda template

| # | Agenda item | Purpose | Papers | Lead | Time |
| --- | --- | --- | --- | --- | --- |
| 1 | Safety, health and environment | Report and discuss | HSE report | HSE Lead | 10 min |
| 2 | Minutes and actions from the previous meeting | Confirm | Minutes and action log | Chair | 5 min |
| 3 | Progress against baseline | Report | Monthly project report | Project Manager | 15 min |
| 4 | Cost, forecast and contingency position | Report | Cost report | Commercial Lead | 10 min |
| 5 | Schedule and critical path | Report | Schedule update | Project Manager | 10 min |
| 6 | Risks and issues | Discuss and decide | Risk and issue report | Project Manager | 15 min |
| 7 | Change requests | Decide | Change register and papers | Commercial Lead | 10 min |
| 8 | Benefits and conditions of approval | Report | Benefits and conditions status | Senior User | 10 min |
| 9 | Decisions required | Decide | Decision papers | Chair | 15 min |
| 10 | Any other business and next meeting | Note | - | Chair | 5 min |

# Appendix I  PID Completeness Checklist

Guidance Complete this checklist before submitting the PID for approval. Any item marked 'No' or 'Partial' must appear either as a gap in Section 18.1 or as a proposed condition of approval in Section 18.2. Submit the checklist with the PID.

| Section | Check | Yes / No / Partial | Comment or gap reference |
| --- | --- | --- | --- |
| FRONT MATTER |  |  |  |
|  | Revision history complete and the current revision identified |  |  |
|  | Document control and distribution list complete |  |  |
|  | Related documents register lists the version of every document relied upon |  |  |
|  | Approval block lists the correct approvers for this project |  |  |
|  | Contents field updated |  |  |
|  | Glossary tailored to the project and the contract |  |  |
| 1 - 2 SUMMARY AND STATUS |  |  |  |
|  | Executive summary is one page and answers the six questions |  |  |
|  | 'Project at a glance' table fully populated |  |  |
|  | Approval sought is stated unambiguously |  |  |
|  | Relationship to the business case and to the PEP is stated |  |  |
|  | Baselining and maintenance arrangements are stated |  |  |
| 3 STRATEGIC CONTEXT |  |  |  |
|  | Strategy alignment table completed with measures |  |  |
|  | Problem statement is quantified and evidenced |  |  |
|  | Do-nothing consequences are stated |  |  |
|  | Five-case business case summary completed and current |  |  |
|  | Options appraisal summarised and the recommendation justified |  |  |
|  | Cost benefit analysis results carried across |  |  |
| 4 - 5 DEFINITION AND CONTEXT |  |  |  |
|  | Scope inclusions and exclusions are unambiguous |  |  |
|  | Objectives are SMART and owned |  |  |
|  | Deliverables have testable acceptance criteria |  |  |
|  | Assumptions have owners and validation dates |  |  |
|  | Constraints are recorded with their impact |  |  |
|  | Site, asset, geotechnical and services context recorded |  |  |
|  | Planning, land tenure and approvals status recorded |  |  |
|  | Technical standards and design brief summarised |  |  |
| 6 - 8 STRATEGY, GOVERNANCE AND CONTROLS |  |  |  |
|  | Delivery model selected with documented rationale |  |  |
|  | Stage and gate framework defined with decision authorities |  |  |
|  | Procurement strategy summarised and packaging defined |  |  |
|  | Governance structure shown and roles named |  |  |
|  | Responsibility assignment has exactly one accountable party per activity |  |  |
|  | Delegations and financial thresholds confirmed against the delegation instrument |  |  |
|  | Assurance and independent review regime agreed and booked |  |  |
|  | Tolerances set at project, stage and work-package level |  |  |
|  | Change control authority and thresholds defined |  |  |
|  | Reporting framework and report register agreed |  |  |
| 9 - 10 SCHEDULE AND COST |  |  |  |
|  | Milestone schedule complete, logic-linked and owned |  |  |
|  | Immovable dates identified and justified |  |  |
|  | Schedule assumptions and risks recorded |  |  |
|  | Cost estimate presented with class, basis and confidence |  |  |
|  | Whole-life cost summarised |  |  |
|  | Contingency sized on quantified risk and its holder named |  |  |
|  | Price base date and escalation basis stated |  |  |
|  | Cash flow reconciled to the funding profile |  |  |
|  | Funding conditions and drawdown windows recorded |  |  |
|  | Affordability and value for money statements complete |  |  |
| 11 - 13 BENEFITS, RISK AND STAKEHOLDERS |  |  |  |
|  | Benefits have measures, baselines, targets, dates and owners |  |  |
|  | Disbenefits declared |  |  |
|  | Success and acceptance criteria are testable |  |  |
|  | Risk appetite stated and scales defined |  |  |
|  | Initial risk register populated with project-specific risks |  |  |
|  | Escalation thresholds defined |  |  |
|  | Opportunities recorded |  |  |
|  | Stakeholder register complete with owners and frequencies |  |  |
|  | Community engagement approach defined |  |  |
| 14 - 17 REQUIREMENTS, INFORMATION, RESOURCES, INTERFACES |  |  |  |
|  | Quality expectations and acceptance criteria stated |  |  |
|  | HSE requirements and safety-in-design expectations stated |  |  |
|  | Environmental approvals and obligations registered |  |  |
|  | Sustainability, social value and climate resilience targets set |  |  |
|  | Information requirements (OIR, AIR, PIR, EIR) defined before appointments |  |  |
|  | Common data environment and systems nominated |  |  |
|  | Handover information requirements specified |  |  |
|  | Resourcing table complete with mobilisation dates and cost |  |  |
|  | Capability gaps identified with mitigation |  |  |
|  | Interfaces and dependencies registered with owners and dates |  |  |
| 18 - 19 READINESS AND APPROVAL |  |  |  |
|  | Readiness assessment completed honestly with evidence |  |  |
|  | Conditions of approval drafted with discharge dates |  |  |
|  | Decision sought is specific and matched to the right authority |  |  |
|  | What is being baselined is listed |  |  |
|  | Document has been reviewed by Project Assurance before submission |  |  |

| Checklist completed by | Role | Signature | Date |
| --- | --- | --- | --- |
|  | Project Manager |  |  |
|  | Project Assurance |  |  |