## Cover
Construction Project Handover Checklist
Global edition · Transfer of the completed asset to the owner, operator and end users
Purpose
A jurisdiction-neutral, auditable checklist for the physical, operational and informational transfer of a completed construction asset to its owner, operator and end users. It covers completion and certification, commissioning, asset data, O&M and record information, warranties, training, FM service transition, occupancy readiness, soft landings aftercare and formal acceptance - across 237 checklist items in 16 categories, supported by nine working registers and a live readiness dashboard.
How to use this template
• Complete the document control block below, then work through the Handover Checklist sheet. Set Status, Criticality, Gate, target dates and evidence references for every row.
• Mark items that do not apply as N/A rather than deleting them - the dashboard excludes N/A items from all completion percentages so your reporting stays honest.
• Use the supporting registers (commissioning, assets, O&M, training, warranties, spares, outstanding works, aftercare) as the evidence behind the checklist rows.
• Watch the Handover Dashboard. It recalculates automatically and shows category performance, critical outstanding items, overdue items and the three readiness gates.
• Record the formal transfer on the Handover Acceptance & Sign-off sheet, which pulls project details from this Cover sheet automatically.
Scope, standards and jurisdiction
• Handover is distinct from project closeout. Final account, contract close-out, archiving, lessons learned and governance closure belong in the companion Mastt Construction Project Closeout Checklist; cross-references are flagged in this workbook.
• Anchored to international good practice: BSRIA Soft Landings and Government Soft Landings principles, RIBA Plan of Work Stages 5-7, ISO 19650 information management (AIR / AIM), ISO 55000 asset management and CIBSE commissioning codes.
• Contractual language is generic and drawn from concepts common to FIDIC and NEC style contracts - Tests on Completion, Taking-Over Certificate and Defects Notification Period. Substitute your own contract's defined terms before use.
• Statutory steps are phrased generically, for example 'Statutory occupancy/use approval issued (as applicable in your jurisdiction)'. Confirm the actual approvals, certificates and inspections required in your country, state or municipality.
• Roles are expressed as functions, not job titles. Map them to your own project organisation chart before issuing the checklist to the delivery team.
Document control
Field | Detail | Field | Detail
Template name | Construction Project Handover Checklist | Template version | 1.0
Project name |  | Project number
Client / asset owner |  | Prepared by
Date prepared |  | Reviewed by
Revision |  | Approved by
Disclaimer
This template is provided by Mastt as general guidance for capital project delivery. It is not legal, financial or professional advice. Users must adapt it to the contract, jurisdiction, statutory regime and organisational policies applicable to their project, and should obtain independent professional advice where appropriate. Mastt accepts no liability arising from use of this template.
Built for capital project teams - plan, track and report with Mastt. |  |  |  | Visit mastt.com ↗

## Instructions
How to use this workbook
Global edition · Transfer of the completed asset to the owner, operator and end users
1. What this workbook is for
• This workbook tracks the handover of a completed asset: the physical transfer of the building and its systems, the operational transfer of maintenance and service responsibility, and the informational transfer of records, models and asset data.
• It is deliberately separate from project closeout. Where the two touch - retention and security for performance, financial reconciliation of the asset register, lessons learned - the checklist row carries a '(see Closeout Checklist)' note so you do not duplicate effort or reporting.
• Every checklist row is written to be auditable: it names the evidence required, the responsible and accountable roles, its criticality and the readiness gate it belongs to.
2. Working through the checklist
• Do not delete rows. Mark anything out of scope as N/A. The dashboard excludes N/A rows from the applicable count and from every completion percentage, so scoping decisions are visible rather than hidden.
• Set a target date for every applicable row. Target dates drive the overdue counters on the dashboard and the amber highlight in the Target date column.
• Record a document reference in the Evidence / document reference column for every item you mark Complete. An item marked Complete with no evidence reference will not survive an audit or a handover dispute.
• Use the Comments column for conditions, qualifications and agreed departures. If an item is accepted conditionally, say so and record the condition and its owner.
3. RACI convention
• Responsible - the role that does the work and produces the evidence. One role only.
• Accountable - the role that owns the outcome, accepts the evidence and answers for it at the gate review. One role only, and it should not be the same as Responsible.
• Consulted and Informed parties are not columns in this workbook; capture them in your project RACI matrix and reference it from the Comments column where it matters.
• The roles supplied are functional. Replace them with your project's own role names on the Lists sheet and the dropdowns will update everywhere.
4. Criticality and gate logic
• Criticality is weighted for the readiness score: Critical = 5, High = 3, Medium = 2, Low = 1. The weights sit on the Lists sheet and can be tuned.
• Critical items are those that prevent safe, lawful or effective operation if incomplete. A gate cannot be declared ready while any Critical item mapped to it is outstanding.
• Gate 1 - Ready for Commissioning Review: planning, commissioning management and pre-commissioning evidence in place.
• Gate 2 - Ready for Handover: completion certification, commissioning results, asset data, O&M and record information, warranties and acceptance evidence in place.
• Gate 3 - Ready for Occupancy: statutory approvals, life safety, FM and service transition, security, migration and formal acceptance in place.
• Post-handover items are tracked but excluded from the three gates - they belong to the aftercare and defects liability period.
5. How the dashboard reads
• Every dashboard figure is a live formula over the Handover Checklist sheet. Nothing is typed in. Refresh happens on recalculation - if figures look stale, press F9.
• Applicable = total rows less rows marked N/A. Percentages are always calculated on applicable items only and are wrapped in IFERROR so an empty sheet shows 0%, not an error.
• Handover readiness is a criticality-weighted percentage: the weight of all Complete items divided by the weight of all applicable items. It moves more when a Critical item closes than when a Low item does.
• Overdue counts rows where the target date has passed and the status is neither Complete nor N/A. It is computed by a hidden helper column on the checklist sheet.
6. Inserting rows safely
• Insert new checklist rows inside the existing block - never above the header row or below the last row - so the dashboard ranges expand with them.
• Copy an adjacent row first so borders, banding, dropdowns, conditional formatting and the hidden helper formulas in columns O and P come with it.
• Columns O and P on the Handover Checklist are hidden helper columns (criticality weight and overdue flag). Do not delete them; the dashboard depends on them.
• If you add a row at the very bottom, check that the dashboard formulas still end at the new last row, and extend them if not.
7. Filtering, sorting and printing
• The checklist and every register carry an AutoFilter on the header row and frozen panes, so you can filter by category, gate, criticality, responsible role or status.
• Always filter rather than sort where possible. If you must sort, select the whole table including the hidden helper columns.
• Print setup is A4, fit to one page wide, with the header row repeating on every page and a Mastt footer. Set your own print area if you only need part of a register.
• The Handover Acceptance & Sign-off sheet is formatted portrait as a standalone printable certificate and pulls project details from the Cover sheet automatically.
8. Status legend and conditional formatting
Status | Colour | Meaning | Counts as applicable? | Counts as complete?
Not started | Not started | Work has not commenced. Default state for a new checklist. | Yes | No
In progress | In progress | Work has commenced but the evidence is not yet complete or accepted. | Yes | No
Complete | Complete | Work done, evidence produced, referenced and accepted by the accountable role. | Yes | Yes
Blocked | Blocked | Cannot progress. Requires escalation - record the blocker in Comments. | Yes | No
N/A | N/A | Not applicable to this project. Excluded from all completion percentages. | No | No
Target dates highlight amber automatically once they pass while the item is not Complete or N/A. Warranty expiry dates highlight amber within 90 days and red once expired.

## Handover Dashboard
Handover Dashboard
Global edition · Transfer of the completed asset to the owner, operator and end users
Every figure on this sheet is a live formula reading the Handover Checklist. Percentages are calculated on applicable items only (items marked N/A are excluded) and are wrapped in IFERROR. Press F9 if figures look stale.
Headline metrics |  | Live from the Handover Checklist
TOTAL ITEMS | APPLICABLE |  | COMPLETE |  | IN PROGRESS |  | BLOCKED
237 | 237 |  | 0 |  | 0 |  | 0
NOT STARTED | % COMPLETE (APPLICABLE) |  | CRITICAL OUTSTANDING |  | OVERDUE |  | HANDOVER READINESS
237 | 0% |  | 91 |  | 0 |  | 0%
Readiness gates |  | A gate is Ready only when every Critical item mapped to it is Complete
Gate | Scope assessed |  |  |  |  | Critical items | Critical outstanding | Gate status
Gate 1 - Ready for Commissioning Review | Handover planning, commissioning management, pre-commissioning and static commissioning evidence in place. |  |  |  |  | 9 | 9 | Not ready
Gate 2 - Ready for Handover | Cumulative: Gate 1 plus completion certification, dynamic commissioning and IST, asset data, O&M and record information, warranties and acceptance evidence. |  |  |  |  | 52 | 52 | Not ready
Gate 3 - Ready for Occupancy | Cumulative: Gates 1 and 2 plus statutory approvals, fire and life safety, FM and service transition, security, migration and formal acceptance. |  |  |  |  | 91 | 91 | Not ready
Category performance |  | COUNTIFS across all 16 categories
Category | Items | Applicable | Complete | % complete | Critical outstanding | Blocked | Overdue
1. Handover Readiness & Planning | 15 | 15 | 0 | 0% | 5 | 0 | 0
2. Completion & Certification | 16 | 16 | 0 | 0% | 11 | 0 | 0
3. Commissioning, Testing & Balancing | 18 | 18 | 0 | 0% | 13 | 0 | 0
4. Building Systems & Services Handover | 17 | 17 | 0 | 0% | 8 | 0 | 0
5. Asset Register & Asset Data | 14 | 14 | 0 | 0% | 4 | 0 | 0
6. Operation & Maintenance Documentation | 16 | 16 | 0 | 0% | 5 | 0 | 0
7. Record Documentation & Information Exchange | 16 | 16 | 0 | 0% | 7 | 0 | 0
8. Warranties, Guarantees & Defects Liability | 15 | 15 | 0 | 0% | 6 | 0 | 0
9. Spares, Consumables, Tools & Attic Stock | 13 | 13 | 0 | 0% | 2 | 0 | 0
10. Training & Knowledge Transfer | 14 | 14 | 0 | 0% | 3 | 0 | 0
11. FM, Operations & Service Transition | 16 | 16 | 0 | 0% | 6 | 0 | 0
12. Occupancy, Migration & End User Readiness | 15 | 15 | 0 | 0% | 4 | 0 | 0
13. Security, Access & Digital Systems | 13 | 13 | 0 | 0% | 6 | 0 | 0
14. Environmental, Sustainability & Certification | 13 | 13 | 0 | 0% | 1 | 0 | 0
15. Soft Landings & Aftercare | 13 | 13 | 0 | 0% | 0 | 0 | 0
16. Handover Acceptance & Sign-off | 13 | 13 | 0 | 0% | 10 | 0 | 0
TOTAL | 237 | 237 | 0 | 0% | 91 | 0 | 0
Reading the dashboard: Applicable excludes items marked N/A. Handover readiness is criticality-weighted (Critical 5, High 3, Medium 2, Low 1) so closing a Critical item moves the number further than closing a Low one. Overdue counts items whose target date has passed while the status is neither Complete nor N/A.

## Handover Checklist
Handover Checklist
Global edition · Transfer of the completed asset to the owner, operator and end users
237 auditable items across 16 categories. Mark out-of-scope rows as N/A rather than deleting them. Columns O and P are hidden helper columns (criticality weight and overdue flag) used by the dashboard - do not delete them.
Ref | Category | Checklist item | Acceptance evidence required | Responsible (role) | Accountable (role) | Criticality | Gate | Status | Target date | Completed date | Evidence / document reference | Comments | Wt | Ovd
1.01 | 1. Handover Readiness & Planning | Handover strategy defined and agreed with client, operator and end users | Approved handover strategy document with client endorsement | Project Manager | Client Project Director | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
1.02 | 1. Handover Readiness & Planning | Handover plan issued setting out milestones, responsibilities and deliverable dates | Baselined handover plan issued under transmittal | Project Manager | Client Project Director | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
1.03 | 1. Handover Readiness & Planning | Soft landings approach adopted and embedded in the delivery programme (BSRIA / Government Soft Landings principles) | Soft landings strategy with stage gateway sign-off record | Soft Landings Champion | Client Project Director | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
1.04 | 1. Handover Readiness & Planning | Soft landings champions appointed for both client and contractor organisations | Appointment letters and role descriptions | Client Project Director | Asset Owner | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
1.05 | 1. Handover Readiness & Planning | Handover core team, responsibilities and RACI matrix agreed | Signed RACI matrix distributed to all parties | Project Manager | Client Project Director | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
1.06 | 1. Handover Readiness & Planning | Phased or sectional handover strategy defined with boundaries, dates and interfaces | Sectional completion schedule and demarcation drawings | Project Manager | Superintendent / Contract Administrator | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
1.07 | 1. Handover Readiness & Planning | Readiness gate criteria and evidence thresholds agreed for each handover gate | Gate criteria register signed by the client | Project Manager | Client Project Director | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
1.08 | 1. Handover Readiness & Planning | Handover readiness reviews scheduled at agreed intervals ahead of completion | Review schedule and terms of reference | Project Manager | Client Project Director | Medium | G1 Commissioning Review | Not started |  |  |  |  | 2 | 0
1.09 | 1. Handover Readiness & Planning | Migration and occupation plan prepared covering sequence, dates and dependencies | Approved migration / occupation plan | FM / Operations Lead | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
1.10 | 1. Handover Readiness & Planning | Exclusion zones, shared occupancy and interface arrangements agreed where works continue | Shared occupancy agreement, zone plans and safety controls | Contractor | Superintendent / Contract Administrator | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
1.11 | 1. Handover Readiness & Planning | Beneficial use or early access arrangements documented, risk-assessed and insured | Early access agreement and insurance endorsement | Project Manager | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
1.12 | 1. Handover Readiness & Planning | Handover information requirements issued to the contractor and supply chain | Information requirements schedule (AIR / EIR extract) with acknowledgement | Information Manager | Client Project Director | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
1.13 | 1. Handover Readiness & Planning | Handover risk register maintained with owners, mitigations and review cadence | Current handover risk register | Project Manager | Client Project Director | Medium | G1 Commissioning Review | Not started |  |  |  |  | 2 | 0
1.14 | 1. Handover Readiness & Planning | Handover budget, resourcing and aftercare funding confirmed | Approved budget allocation and resource plan | Client Project Director | Asset Owner | Medium | G1 Commissioning Review | Not started |  |  |  |  | 2 | 0
1.15 | 1. Handover Readiness & Planning | Interfaces with project closeout activities identified and de-duplicated (see Closeout Checklist) | Cross-reference matrix between handover and closeout registers | Project Manager | Client Project Director | Low | Post-handover | Not started |  |  |  |  | 1 | 0
2.01 | 2. Completion & Certification | Inspection and test plans closed out with all hold and witness points released | Signed ITP records with released hold points | Contractor | Superintendent / Contract Administrator | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
2.02 | 2. Completion & Certification | Tests on completion carried out and passed in accordance with the contract | Tests on completion results and pass certificates | Contractor | Superintendent / Contract Administrator | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
2.03 | 2. Completion & Certification | Non-conformance reports raised during construction closed or formally dispositioned | NCR register showing closure or accepted disposition | Contractor | Superintendent / Contract Administrator | High | G2 Handover | Not started |  |  |  |  | 3 | 0
2.04 | 2. Completion & Certification | Practical / substantial completion certificate issued for the works | Executed completion certificate | Superintendent / Contract Administrator | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
2.05 | 2. Completion & Certification | Taking-over certificate (or contract equivalent) issued for each completed section | Executed taking-over certificates per section | Superintendent / Contract Administrator | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
2.06 | 2. Completion & Certification | Statutory occupancy / use approval issued (as applicable in your jurisdiction) | Occupancy or use approval document from the approving authority | Certifier / Approving Authority | Client Project Director | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
2.07 | 2. Completion & Certification | Fire and life-safety certification issued by the responsible certifier | Fire safety certificate or statement of compliance | Fire Engineer | Certifier / Approving Authority | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
2.08 | 2. Completion & Certification | Fire system installation and verification certificates obtained for all fire services | Detection, suppression, pressurisation and passive protection certificates | Contractor | Fire Engineer | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
2.09 | 2. Completion & Certification | Statutory registration and inspection of lifts and vertical transportation completed (as applicable) | Registration and inspection certificates | Contractor | Certifier / Approving Authority | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
2.10 | 2. Completion & Certification | Statutory registration and inspection of pressure vessels and plant completed (as applicable) | Plant registration numbers and inspection reports | Contractor | Certifier / Approving Authority | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
2.11 | 2. Completion & Certification | Electrical installation compliance certification issued with test results | Certificate of electrical compliance and test result schedules | Contractor | Certifier / Approving Authority | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
2.12 | 2. Completion & Certification | Hydraulic, plumbing and gas compliance certification issued | Compliance certificates including backflow prevention testing | Contractor | Certifier / Approving Authority | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
2.13 | 2. Completion & Certification | Structural, facade and waterproofing design compliance statements obtained | Certifier and designer compliance statements | Design Team | Certifier / Approving Authority | High | G2 Handover | Not started |  |  |  |  | 3 | 0
2.14 | 2. Completion & Certification | Accessibility compliance verified and certified (as applicable in your jurisdiction) | Access consultant report or certificate of compliance | Design Team | Certifier / Approving Authority | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
2.15 | 2. Completion & Certification | Conditions attached to development, planning or building approvals discharged | Conditions discharge register with supporting evidence | Project Manager | Certifier / Approving Authority | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
2.16 | 2. Completion & Certification | All certifier, consultant and specialist sign-offs collated into a single certification register | Certification register with document references | Project Manager | Client Project Director | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
3.01 | 3. Commissioning, Testing & Balancing | Commissioning management plan and programme approved before commissioning starts | Approved commissioning plan aligned to CIBSE commissioning codes | Commissioning Manager | Project Manager | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
3.02 | 3. Commissioning, Testing & Balancing | Independent commissioning agent appointed where required by the brief | Appointment and scope of services document | Client Project Director | Asset Owner | Medium | G1 Commissioning Review | Not started |  |  |  |  | 2 | 0
3.03 | 3. Commissioning, Testing & Balancing | Pre-commissioning checks completed for all systems and signed off | Signed pre-commissioning checklists per system | Contractor | Commissioning Manager | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
3.04 | 3. Commissioning, Testing & Balancing | Static commissioning completed (installation, cleanliness, pressure and continuity testing) | Static commissioning records and test certificates | Contractor | Commissioning Manager | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
3.05 | 3. Commissioning, Testing & Balancing | Dynamic commissioning completed with plant operating under representative load | Dynamic commissioning results against design criteria | Contractor | Commissioning Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.06 | 3. Commissioning, Testing & Balancing | Witnessed testing programme delivered with client and consultant attendance | Witness test sheets signed by all attendees | Commissioning Manager | Superintendent / Contract Administrator | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.07 | 3. Commissioning, Testing & Balancing | Air balancing completed to design tolerances across all systems | Air balance report compared against design schedules | Contractor | Commissioning Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.08 | 3. Commissioning, Testing & Balancing | Water balancing, flushing and chemical treatment completed and certified | Water balance report and water treatment certificates | Contractor | Commissioning Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.09 | 3. Commissioning, Testing & Balancing | Integrated systems testing completed across all interfacing systems | IST plan, scenario matrix and signed results | Commissioning Manager | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.10 | 3. Commissioning, Testing & Balancing | Black building test completed including generator changeover and UPS autonomy | Black building test report with timings and observations | Commissioning Manager | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.11 | 3. Commissioning, Testing & Balancing | Fire alarm cause-and-effect matrix verified end to end | Signed cause-and-effect verification matrix | Fire Engineer | Certifier / Approving Authority | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
3.12 | 3. Commissioning, Testing & Balancing | Smoke control, pressurisation and egress systems tested under fire mode | Fire mode test results and remedial closure record | Contractor | Fire Engineer | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
3.13 | 3. Commissioning, Testing & Balancing | BMS / BAS point-to-point verification completed and graphics validated | Point-to-point schedule signed off, graphics acceptance record | Contractor | Commissioning Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
3.14 | 3. Commissioning, Testing & Balancing | Control strategies, set-points and time schedules verified against the control philosophy | As-commissioned set-point and time schedule register | Commissioning Manager | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
3.15 | 3. Commissioning, Testing & Balancing | Metering and sub-metering verified, labelled and mapped to the metering strategy | Meter schedule with verification and mapping records | Contractor | Sustainability Consultant | High | G2 Handover | Not started |  |  |  |  | 3 | 0
3.16 | 3. Commissioning, Testing & Balancing | Energy and performance verification testing completed against design targets | Performance verification report with variance commentary | Sustainability Consultant | Client Project Director | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
3.17 | 3. Commissioning, Testing & Balancing | Seasonal commissioning schedule agreed, diarised and resourced | Seasonal commissioning plan with dates and owners | Commissioning Manager | FM / Operations Lead | High | Post-handover | Not started |  |  |  |  | 3 | 0
3.18 | 3. Commissioning, Testing & Balancing | Commissioning records compiled, indexed and issued in the agreed structure | Complete commissioning dossier accepted by the client | Commissioning Manager | Information Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
4.01 | 4. Building Systems & Services Handover | HVAC systems handed over with commissioning records, set-points and control philosophy | HVAC handover pack accepted by operations | Contractor | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
4.02 | 4. Building Systems & Services Handover | Electrical distribution handed over with schedules, protection settings and discrimination study | Electrical handover pack and protection settings record | Contractor | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
4.03 | 4. Building Systems & Services Handover | Standby power and UPS systems handed over with load test and autonomy records | Generator and UPS handover pack with load test results | Contractor | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
4.04 | 4. Building Systems & Services Handover | Hydraulic and plumbing systems handed over with isolation and valve schedules | Hydraulic handover pack and verified valve schedule | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
4.05 | 4. Building Systems & Services Handover | Fire protection systems handed over with certification and ongoing maintenance obligations | Fire systems handover pack and maintenance obligations schedule | Contractor | Fire Engineer | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
4.06 | 4. Building Systems & Services Handover | Vertical transportation handed over with logbooks, keys and entrapment release procedures | Lift handover pack and written rescue procedure | Contractor | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
4.07 | 4. Building Systems & Services Handover | Security and access control systems handed over with device schedules and configuration | Security handover pack and device schedule | Security Manager | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
4.08 | 4. Building Systems & Services Handover | ICT and structured cabling handed over with test results and patching schedules | Cabling test results, patching schedules and floor plans | ICT Lead | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
4.09 | 4. Building Systems & Services Handover | Audio-visual systems handed over with configuration files and user guides | AV handover pack and configuration backups | ICT Lead | End User Representative | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
4.10 | 4. Building Systems & Services Handover | BMS / BAS handed over with graphics, licences, backups and administrator accounts | BMS handover pack, backup media and licence transfer | Contractor | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
4.11 | 4. Building Systems & Services Handover | Alarm schedules, priorities and escalation routes configured and agreed with operations | Alarm schedule and escalation matrix signed by FM | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
4.12 | 4. Building Systems & Services Handover | Specialist and process systems handed over (medical gases, laboratory, kitchen, cold rooms, etc.) | Specialist system handover packs and certificates | Contractor | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
4.13 | 4. Building Systems & Services Handover | Loading dock, goods handling and waste management systems demonstrated and handed over | Demonstration record and operating instructions | Contractor | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
4.14 | 4. Building Systems & Services Handover | Facade access, roof anchor and fall-arrest systems certified and demonstrated | Certification, load test records and safe work procedures | Contractor | Health & Safety Adviser | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
4.15 | 4. Building Systems & Services Handover | Landscape, irrigation and external works handed over with establishment regimes | Landscape handover record and establishment maintenance regime | Contractor | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
4.16 | 4. Building Systems & Services Handover | Building fabric, finishes and joinery inspected and handed over with care instructions | Fabric handover record and finishes care schedule | Contractor | FM / Operations Lead | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
4.17 | 4. Building Systems & Services Handover | System labelling, signage and colour coding verified on site against schedules | Labelling verification audit record | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
5.01 | 5. Asset Register & Asset Data | Client asset data standard issued and applied by the supply chain | Asset data standard and supply chain compliance statement | Information Manager | Asset Owner | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
5.02 | 5. Asset Register & Asset Data | Asset register populated for all in-scope assets to the required attribute set | Completed asset register in the agreed template | Contractor | Information Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
5.03 | 5. Asset Register & Asset Data | Asset hierarchy and classification aligned to the client structure (ISO 55000 aligned) | Approved asset hierarchy and classification mapping | Information Manager | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
5.04 | 5. Asset Register & Asset Data | Asset tagging and physical labelling verified on site against the register | Tagging verification audit with sample evidence | FM / Operations Lead | Information Manager | High | G2 Handover | Not started |  |  |  |  | 3 | 0
5.05 | 5. Asset Register & Asset Data | Asset criticality assigned and agreed with the operations team | Criticality assessment record signed by operations | FM / Operations Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
5.06 | 5. Asset Register & Asset Data | Asset attribute completeness validated (manufacturer, model, serial, capacity, location) | Data quality report showing completeness by attribute | Information Manager | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
5.07 | 5. Asset Register & Asset Data | Structured data exchange delivered and validated (COBie-style or client equivalent) | Validated data exchange file and validation report | Information Manager | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
5.08 | 5. Asset Register & Asset Data | CMMS / EAM upload completed and reconciled against the asset register | Upload reconciliation report signed by FM | FM / Operations Lead | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
5.09 | 5. Asset Register & Asset Data | Warranty and lifecycle data attached to each asset record | CMMS extract evidencing populated warranty fields | FM / Operations Lead | Information Manager | High | G2 Handover | Not started |  |  |  |  | 3 | 0
5.10 | 5. Asset Register & Asset Data | Spares and consumables linked to parent assets in the CMMS | CMMS spares linkage report | FM / Operations Lead | Information Manager | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
5.11 | 5. Asset Register & Asset Data | Asset geolocation, floor plans and space data loaded to the operational systems | Space and location data load confirmation | Information Manager | FM / Operations Lead | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
5.12 | 5. Asset Register & Asset Data | Expected life and replacement cost data provided to support lifecycle planning | Lifecycle data set issued to the asset owner | Design Team | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
5.13 | 5. Asset Register & Asset Data | Asset data governance, ownership and update process agreed for the operational phase | Data governance procedure with named owners | Information Manager | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
5.14 | 5. Asset Register & Asset Data | Asset register reconciled with the financial fixed asset schedule (see Closeout Checklist) | Reconciliation record signed by finance | Asset Owner | Client Project Director | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
6.01 | 6. Operation & Maintenance Documentation | O&M manual structure, format and indexing agreed before drafting commences | Approved O&M content plan and template | Information Manager | FM / Operations Lead | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
6.02 | 6. Operation & Maintenance Documentation | Draft O&M manuals received by the date required in the handover plan | Draft O&M submission transmittal | Contractor | Information Manager | Critical | G1 Commissioning Review | Not started |  |  |  |  | 5 | 0
6.03 | 6. Operation & Maintenance Documentation | O&M manuals reviewed by client, FM and consultants with consolidated comments issued | Consolidated review comment schedule | FM / Operations Lead | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
6.04 | 6. Operation & Maintenance Documentation | O&M review comments closed out and verified as incorporated | Comment closure log with verification sign-off | Contractor | Information Manager | High | G2 Handover | Not started |  |  |  |  | 3 | 0
6.05 | 6. Operation & Maintenance Documentation | Final O&M manuals issued in native and portable formats to the agreed structure | Final O&M issue transmittal and acceptance | Contractor | Information Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
6.06 | 6. Operation & Maintenance Documentation | Maintenance strategy defined for each system (planned, condition-based, reactive, statutory) | Maintenance strategy document approved by the asset owner | FM / Operations Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
6.07 | 6. Operation & Maintenance Documentation | Planned maintenance schedules provided with frequencies, durations and task lists | Planned preventive maintenance schedule | Contractor | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
6.08 | 6. Operation & Maintenance Documentation | Statutory and mandatory maintenance obligations identified for every applicable asset | Statutory maintenance schedule mapped to assets | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
6.09 | 6. Operation & Maintenance Documentation | Manufacturers' literature, technical data sheets and part numbers compiled | Indexed manufacturer documentation set | Contractor | Information Manager | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
6.10 | 6. Operation & Maintenance Documentation | Control philosophies and sequences of operation documented as-commissioned | As-commissioned control philosophy document | Commissioning Manager | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
6.11 | 6. Operation & Maintenance Documentation | Single-line diagrams, schematics and system topologies provided | Schematic drawing set issued with the O&M manuals | Design Team | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
6.12 | 6. Operation & Maintenance Documentation | Valve, damper, isolation and emergency shutdown schedules provided and verified on site | Verified schedules cross-checked against site labelling | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
6.13 | 6. Operation & Maintenance Documentation | Cleaning regimes and materials care instructions provided for all finishes | Cleaning and materials care schedule | Contractor | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
6.14 | 6. Operation & Maintenance Documentation | Building user guide produced in non-technical language for occupants | Building user guide issued to occupants | Soft Landings Champion | End User Representative | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
6.15 | 6. Operation & Maintenance Documentation | Emergency, out-of-hours and business continuity procedures documented and issued | Emergency procedures document and contact tree | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
6.16 | 6. Operation & Maintenance Documentation | O&M documentation loaded to the client document management system with access rights set | DMS load confirmation and access matrix | Information Manager | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
7.01 | 7. Record Documentation & Information Exchange | As-built drawings issued in the agreed formats and verified against the constructed works | As-built drawing register and site verification record | Contractor | Information Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
7.02 | 7. Record Documentation & Information Exchange | As-built / record models delivered to the agreed level of information need | Record model files with validation report | Information Manager | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
7.03 | 7. Record Documentation & Information Exchange | Information exchange at the handover milestone completed in accordance with ISO 19650 | Information exchange record and client acceptance | Information Manager | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
7.04 | 7. Record Documentation & Information Exchange | Asset Information Model populated and verified against the Asset Information Requirements | AIM verification report against AIR | Information Manager | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
7.05 | 7. Record Documentation & Information Exchange | Model federation, naming and classification compliance checked and reported | Model audit report with non-compliance closure | Information Manager | Design Team | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
7.06 | 7. Record Documentation & Information Exchange | Common data environment content migrated to the client operational environment | Migration completion record and access confirmation | Information Manager | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
7.07 | 7. Record Documentation & Information Exchange | Survey, setting-out and dilapidation records provided | Survey record pack with coordinates and datum | Contractor | Design Team | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
7.08 | 7. Record Documentation & Information Exchange | Geotechnical, structural and foundation records provided | Structural records pack including pile and slab records | Contractor | Design Team | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
7.09 | 7. Record Documentation & Information Exchange | Health and safety file / safety information compiled and issued to the client | Health and safety file transmittal and acceptance | Health & Safety Adviser | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
7.10 | 7. Record Documentation & Information Exchange | Residual hazards, restrictions and safe access information documented for operators | Residual hazard register issued to FM | Health & Safety Adviser | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
7.11 | 7. Record Documentation & Information Exchange | Fire safety information, strategy and evacuation plans issued to the responsible person | Fire safety information pack with acknowledgement | Fire Engineer | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
7.12 | 7. Record Documentation & Information Exchange | Building information / golden thread record established and transferred where applicable | Information transfer record and custody confirmation | Information Manager | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
7.13 | 7. Record Documentation & Information Exchange | Document register issued listing every handover document with revision and storage location | Handover document register signed as complete | Information Manager | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
7.14 | 7. Record Documentation & Information Exchange | Software, model and document access rights transferred to client personnel | Access rights transfer record | ICT Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
7.15 | 7. Record Documentation & Information Exchange | Intellectual property, licence and reuse rights for documentation confirmed | IP and licence confirmation letter | Project Manager | Client Project Director | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
7.16 | 7. Record Documentation & Information Exchange | Physical document, drawing and sample sets delivered where required by the contract | Signed delivery receipt | Contractor | FM / Operations Lead | Low | G3 Occupancy | Not started |  |  |  |  | 1 | 0
8.01 | 8. Warranties, Guarantees & Defects Liability | Consolidated warranty schedule prepared showing start and expiry dates per element | Warranty schedule cross-referenced to the asset register | Contractor | Project Manager | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
8.02 | 8. Warranties, Guarantees & Defects Liability | Warranty commencement dates aligned to the completion / taking-over certificate | Cross-check record between certificates and warranty schedule | Project Manager | Superintendent / Contract Administrator | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
8.03 | 8. Warranties, Guarantees & Defects Liability | Manufacturer warranties registered with suppliers in the owner's name | Registration confirmations from manufacturers | Contractor | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
8.04 | 8. Warranties, Guarantees & Defects Liability | Extended and system warranties obtained (roofing, facade, waterproofing, flooring, coatings) | Executed extended warranty documents | Contractor | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
8.05 | 8. Warranties, Guarantees & Defects Liability | Collateral warranties and third-party rights executed where required | Executed collateral warranties and rights notices | Project Manager | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
8.06 | 8. Warranties, Guarantees & Defects Liability | Warranty conditions, exclusions and maintenance obligations communicated to operations | Warranty obligations briefing note issued to FM | Project Manager | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
8.07 | 8. Warranties, Guarantees & Defects Liability | Defects liability / defects notification period start date confirmed and recorded | Certificate confirming the period start date | Superintendent / Contract Administrator | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
8.08 | 8. Warranties, Guarantees & Defects Liability | Defects reporting, response and rectification process agreed with target response times | Defects management procedure signed by both parties | Project Manager | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
8.09 | 8. Warranties, Guarantees & Defects Liability | Defects management system or register established with access granted to operations | Live defects register with user access confirmed | Project Manager | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
8.10 | 8. Warranties, Guarantees & Defects Liability | Warranty claim process, contacts and escalation routes issued to operations | Warranty claim procedure and contact directory | Contractor | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
8.11 | 8. Warranties, Guarantees & Defects Liability | Security for performance or retention arrangements for the defects period confirmed (see Closeout Checklist) | Security instrument details and expiry dates | Project Manager | Client Project Director | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
8.12 | 8. Warranties, Guarantees & Defects Liability | Latent defects insurance or decennial cover arranged where applicable | Policy documents and certificate of currency | Client Project Director | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
8.13 | 8. Warranties, Guarantees & Defects Liability | Emergency and after-hours contractor call-out arrangements confirmed for the defects period | Call-out schedule with names, numbers and response times | Contractor | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
8.14 | 8. Warranties, Guarantees & Defects Liability | Warranty expiry review points diarised ahead of each expiry date | Diarised review schedule in the operational calendar | FM / Operations Lead | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
8.15 | 8. Warranties, Guarantees & Defects Liability | Warranty and defects obligations transferred into the CMMS and compliance calendar | CMMS records evidencing warranty obligations | FM / Operations Lead | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
9.01 | 9. Spares, Consumables, Tools & Attic Stock | Agreed spares list reviewed against asset criticality and supplier lead times | Approved spares list endorsed by operations | FM / Operations Lead | Asset Owner | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
9.02 | 9. Spares, Consumables, Tools & Attic Stock | Contract spares delivered, inspected and receipted | Signed delivery receipts and inspection record | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
9.03 | 9. Spares, Consumables, Tools & Attic Stock | Special tools and proprietary test equipment delivered and demonstrated | Tool register and signed receipt | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
9.04 | 9. Spares, Consumables, Tools & Attic Stock | Keys, key schedule and master key hierarchy handed over and receipted | Key register and signed handover receipt | Contractor | Security Manager | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
9.05 | 9. Spares, Consumables, Tools & Attic Stock | Access cards, fobs and security devices issued and recorded against holders | Card issue register | Security Manager | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
9.06 | 9. Spares, Consumables, Tools & Attic Stock | Attic stock of finishes delivered (tiles, carpet, paint, ceiling tiles, cladding) | Attic stock schedule and delivery receipt | Contractor | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
9.07 | 9. Spares, Consumables, Tools & Attic Stock | Consumables for the initial operating period supplied (filters, lamps, chemicals, belts) | Consumables delivery record | Contractor | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
9.08 | 9. Spares, Consumables, Tools & Attic Stock | Spares storage location allocated, secure and environmentally suitable | Storage allocation record and photographs | FM / Operations Lead | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
9.09 | 9. Spares, Consumables, Tools & Attic Stock | Spares and attic stock recorded in the CMMS with minimum and maximum levels | CMMS spares records with reorder levels | FM / Operations Lead | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
9.10 | 9. Spares, Consumables, Tools & Attic Stock | Supply chain and reorder routes for consumables established | Supplier contact list and reorder procedure | FM / Operations Lead | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
9.11 | 9. Spares, Consumables, Tools & Attic Stock | Software, firmware and configuration backups provided on durable media | Backup media receipt and restore verification | ICT Lead | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
9.12 | 9. Spares, Consumables, Tools & Attic Stock | Calibration certificates for instruments and test equipment handed over | Calibration certificates with next due dates | Contractor | FM / Operations Lead | Low | G2 Handover | Not started |  |  |  |  | 1 | 0
9.13 | 9. Spares, Consumables, Tools & Attic Stock | Surplus materials, samples and mock-ups dispositioned as agreed | Disposition record and removal confirmation | Contractor | Project Manager | Low | Post-handover | Not started |  |  |  |  | 1 | 0
10.01 | 10. Training & Knowledge Transfer | Training needs analysis completed for FM, operations and end user audiences | Training needs analysis signed by operations | FM / Operations Lead | Client Project Director | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
10.02 | 10. Training & Knowledge Transfer | Training plan agreed with sessions, audiences, durations, dates and venues | Approved training plan | Contractor | FM / Operations Lead | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
10.03 | 10. Training & Knowledge Transfer | Training materials issued in advance of delivery for review | Training material register and issue record | Contractor | FM / Operations Lead | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
10.04 | 10. Training & Knowledge Transfer | Operator training delivered for all major plant and systems | Signed attendance sheets and session records | Contractor | FM / Operations Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
10.05 | 10. Training & Knowledge Transfer | Supplier-led specialist training delivered for proprietary systems | Supplier training records and certificates | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
10.06 | 10. Training & Knowledge Transfer | Competency verification completed and signed for critical systems | Competency sign-off sheets per operator and system | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
10.07 | 10. Training & Knowledge Transfer | Training sessions recorded and lodged for future reference and inductions | Recordings lodged in the document management system | Contractor | Information Manager | Medium | G2 Handover | Not started |  |  |  |  | 2 | 0
10.08 | 10. Training & Knowledge Transfer | Familiarisation walkthroughs completed for plant rooms, risers and roof areas | Walkthrough attendance record | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
10.09 | 10. Training & Knowledge Transfer | Super-users identified for each system and briefed on escalation routes | Super-user list with contact details | FM / Operations Lead | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
10.10 | 10. Training & Knowledge Transfer | End user induction and building user briefing delivered before occupation | Induction attendance records | Soft Landings Champion | End User Representative | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
10.11 | 10. Training & Knowledge Transfer | Emergency response and evacuation training delivered including warden training | Training records and first evacuation drill report | Health & Safety Adviser | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
10.12 | 10. Training & Knowledge Transfer | Refresher and seasonal training scheduled across the aftercare period | Refresher training schedule with owners | Soft Landings Champion | FM / Operations Lead | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
10.13 | 10. Training & Knowledge Transfer | Training effectiveness reviewed and identified gaps addressed | Post-training review record and gap closure actions | FM / Operations Lead | Client Project Director | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
10.14 | 10. Training & Knowledge Transfer | Training records transferred to the client learning or compliance system | Transfer confirmation from the client system | FM / Operations Lead | Asset Owner | Low | Post-handover | Not started |  |  |  |  | 1 | 0
11.01 | 11. FM, Operations & Service Transition | FM delivery model confirmed (in-house, outsourced or hybrid) | FM operating model decision paper | Asset Owner | Client Project Director | High | G1 Commissioning Review | Not started |  |  |  |  | 3 | 0
11.02 | 11. FM, Operations & Service Transition | FM contract awarded and mobilisation plan in place ahead of handover | Executed FM contract and mobilisation programme | Asset Owner | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
11.03 | 11. FM, Operations & Service Transition | Service level agreements and KPIs agreed, measurable and baselined | Signed SLA and KPI schedule | FM / Operations Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
11.04 | 11. FM, Operations & Service Transition | Helpdesk and fault reporting routes live and communicated to occupants | Helpdesk go-live confirmation and user communication | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
11.05 | 11. FM, Operations & Service Transition | Planned maintenance loaded into the CMMS with the first cycle scheduled | CMMS planned maintenance schedule extract | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
11.06 | 11. FM, Operations & Service Transition | Statutory compliance calendar loaded with inspection and testing obligations | Compliance calendar with due dates and owners | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
11.07 | 11. FM, Operations & Service Transition | Specialist maintenance subcontracts in place for proprietary systems | Executed specialist maintenance subcontracts | FM / Operations Lead | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
11.08 | 11. FM, Operations & Service Transition | Cleaning contract mobilised including transition from builder's clean to occupation clean | Cleaning mobilisation record and scope | FM / Operations Lead | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
11.09 | 11. FM, Operations & Service Transition | Waste, recycling and grounds maintenance services arranged and commenced | Service commencement confirmations | FM / Operations Lead | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
11.10 | 11. FM, Operations & Service Transition | Security operations, manning and reception services mobilised | Security mobilisation record and post orders | Security Manager | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
11.11 | 11. FM, Operations & Service Transition | Utility accounts transferred to the owner or operator with opening meter readings recorded | Account transfer confirmations and photographed meter readings | FM / Operations Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
11.12 | 11. FM, Operations & Service Transition | Temporary services and construction utilities disconnected and reconciled | Disconnection records and final reconciliation | Contractor | Project Manager | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
11.13 | 11. FM, Operations & Service Transition | Pest control, water hygiene and indoor air quality regimes commenced | Service commencement records and initial reports | FM / Operations Lead | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
11.14 | 11. FM, Operations & Service Transition | Water systems flushing, sampling and hygiene regime completed before occupation | Water sampling results within acceptance limits | Contractor | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
11.15 | 11. FM, Operations & Service Transition | Operating budget for the first year of operation approved | Approved operating budget | Asset Owner | Client Project Director | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
11.16 | 11. FM, Operations & Service Transition | Service transition acceptance signed by the incoming FM provider | FM acceptance record listing any qualifications | FM / Operations Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
12.01 | 12. Occupancy, Migration & End User Readiness | Occupancy permit or approval in force and displayed as required | Approval document and display confirmation | Client Project Director | Certifier / Approving Authority | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
12.02 | 12. Occupancy, Migration & End User Readiness | Property and operational insurance in force from the transfer date | Certificates of currency covering the asset | Asset Owner | Client Project Director | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
12.03 | 12. Occupancy, Migration & End User Readiness | FF&E procured, delivered, installed and inspected against the schedule | FF&E installation sign-off and snag closure | Project Manager | End User Representative | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
12.04 | 12. Occupancy, Migration & End User Readiness | FF&E asset tagging and register completed and loaded | FF&E register with tags and locations | FM / Operations Lead | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
12.05 | 12. Occupancy, Migration & End User Readiness | ICT migration and cut-over plan executed with rollback provisions tested | Cut-over report and rollback test evidence | ICT Lead | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
12.06 | 12. Occupancy, Migration & End User Readiness | Telephony, printing and end user devices operational and tested | Service verification record | ICT Lead | End User Representative | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
12.07 | 12. Occupancy, Migration & End User Readiness | Wayfinding, statutory and room signage installed and verified | Signage verification record against the signage schedule | Project Manager | End User Representative | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
12.08 | 12. Occupancy, Migration & End User Readiness | User communications plan delivered including move guides and frequently asked questions | Communications pack and distribution record | Soft Landings Champion | End User Representative | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
12.09 | 12. Occupancy, Migration & End User Readiness | Move management plan executed with staging, sequencing and labelling | Move plan and completion report | FM / Operations Lead | End User Representative | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
12.10 | 12. Occupancy, Migration & End User Readiness | Day-one support arrangements mobilised with floor walkers and a visible help point | Day-one support roster and briefing pack | Soft Landings Champion | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
12.11 | 12. Occupancy, Migration & End User Readiness | Cleaning to occupation standard completed and inspected before move-in | Occupation clean sign-off with inspection sheets | Contractor | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
12.12 | 12. Occupancy, Migration & End User Readiness | Accessibility, ergonomics and workplace setup verified for end users | Workplace verification record | End User Representative | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
12.13 | 12. Occupancy, Migration & End User Readiness | Legacy premises decant, decommissioning and make-good planned and resourced | Decant and make-good plan | FM / Operations Lead | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
12.14 | 12. Occupancy, Migration & End User Readiness | Occupancy loading, furniture layouts and egress capacity verified against the fire strategy | Verification record signed by the fire engineer | Fire Engineer | Certifier / Approving Authority | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
12.15 | 12. Occupancy, Migration & End User Readiness | First aid, welfare and emergency equipment installed, stocked and registered | Equipment inspection and stocking record | Health & Safety Adviser | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
13.01 | 13. Security, Access & Digital Systems | Access control database configured with zones, schedules and permission groups | Access control configuration record and zone plans | Security Manager | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
13.02 | 13. Security, Access & Digital Systems | Access cards and credentials issued to authorised personnel and recorded | Card issue register with authorisations | Security Manager | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
13.03 | 13. Security, Access & Digital Systems | CCTV commissioned with camera schedule, retention settings and privacy compliance verified | CCTV commissioning record and privacy impact assessment | Security Manager | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
13.04 | 13. Security, Access & Digital Systems | Intruder alarm and monitoring contract in place and tested end to end | Monitoring contract and signal test record | Security Manager | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
13.05 | 13. Security, Access & Digital Systems | Cyber security review of operational technology and BMS systems completed | Security review report with remediation closure | ICT Lead | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
13.06 | 13. Security, Access & Digital Systems | Default passwords changed and credentials handed over through a secure channel | Credential handover record and password policy confirmation | Contractor | ICT Lead | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
13.07 | 13. Security, Access & Digital Systems | Network segregation between operational technology and corporate IT verified | Network architecture verification and test evidence | ICT Lead | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
13.08 | 13. Security, Access & Digital Systems | Remote access arrangements for vendors documented, approved and controlled | Remote access policy, approvals and access log | ICT Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
13.09 | 13. Security, Access & Digital Systems | Administrator accounts, licences and software keys transferred to the owner | Licence and account transfer schedule | ICT Lead | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
13.10 | 13. Security, Access & Digital Systems | Software subscriptions and support agreements assigned with renewal dates recorded | Subscription register with renewal diary entries | ICT Lead | Asset Owner | High | G2 Handover | Not started |  |  |  |  | 3 | 0
13.11 | 13. Security, Access & Digital Systems | System backups configured, tested and the restore procedure documented | Backup configuration and successful restore test record | ICT Lead | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
13.12 | 13. Security, Access & Digital Systems | Digital twin or analytics platform populated and access granted where applicable | Platform handover record and user access list | Information Manager | Asset Owner | Low | Post-handover | Not started |  |  |  |  | 1 | 0
13.13 | 13. Security, Access & Digital Systems | Key management, restricted area and lockdown protocols agreed and issued | Key management procedure and restricted area register | Security Manager | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
14.01 | 14. Environmental, Sustainability & Certification | Sustainability rating evidence compiled and submitted for certification | Submission pack and assessor correspondence | Sustainability Consultant | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
14.02 | 14. Environmental, Sustainability & Certification | As-built sustainability certification achieved or provisional rating confirmed | Certificate or provisional rating letter | Sustainability Consultant | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
14.03 | 14. Environmental, Sustainability & Certification | Energy performance baseline established and documented for operational benchmarking | Baseline energy model and initial metering data | Sustainability Consultant | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
14.04 | 14. Environmental, Sustainability & Certification | Water performance baseline and leak detection strategy documented | Baseline water consumption data and leak strategy | Sustainability Consultant | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
14.05 | 14. Environmental, Sustainability & Certification | Measurement and verification plan agreed for the first year of operation | Approved M&V plan with responsibilities | Sustainability Consultant | Asset Owner | High | Post-handover | Not started |  |  |  |  | 3 | 0
14.06 | 14. Environmental, Sustainability & Certification | Commissioning for performance activities scheduled beyond practical completion | Performance commissioning schedule | Commissioning Manager | Asset Owner | High | Post-handover | Not started |  |  |  |  | 3 | 0
14.07 | 14. Environmental, Sustainability & Certification | Construction waste reporting closed and the operational waste regime commenced | Final waste reports and operational waste plan | Contractor | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
14.08 | 14. Environmental, Sustainability & Certification | Environmental management plan transitioned to operational environmental controls | Operational environmental management plan | Sustainability Consultant | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
14.09 | 14. Environmental, Sustainability & Certification | Environmental approvals, licences and monitoring obligations transferred to the operator | Licence transfer records and monitoring schedule | Project Manager | Asset Owner | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
14.10 | 14. Environmental, Sustainability & Certification | Contaminated land, asbestos and hazardous materials registers issued to the operator | Registers and associated management plans | Health & Safety Adviser | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
14.11 | 14. Environmental, Sustainability & Certification | Indoor environmental quality testing completed before occupation | IEQ test results against agreed criteria | Sustainability Consultant | FM / Operations Lead | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
14.12 | 14. Environmental, Sustainability & Certification | Refrigerant, fuel and chemical inventories recorded with compliance obligations | Inventory register and compliance obligation schedule | FM / Operations Lead | Asset Owner | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
14.13 | 14. Environmental, Sustainability & Certification | Embodied and operational carbon records handed over for lifecycle reporting | Carbon data set and reporting methodology | Sustainability Consultant | Asset Owner | Low | Post-handover | Not started |  |  |  |  | 1 | 0
15.01 | 15. Soft Landings & Aftercare | Aftercare team, roles, duration and funding agreed and resourced | Aftercare charter signed by client and contractor | Soft Landings Champion | Client Project Director | High | G2 Handover | Not started |  |  |  |  | 3 | 0
15.02 | 15. Soft Landings & Aftercare | On-site aftercare presence provided during the initial weeks of occupation | Aftercare attendance log and issue register | Contractor | Soft Landings Champion | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
15.03 | 15. Soft Landings & Aftercare | Aftercare help point and single point of contact communicated to occupants | Communication record and signage | Soft Landings Champion | FM / Operations Lead | Medium | G3 Occupancy | Not started |  |  |  |  | 2 | 0
15.04 | 15. Soft Landings & Aftercare | Extended aftercare programme defined, typically running to three years | Extended aftercare plan with milestones | Soft Landings Champion | Asset Owner | High | Post-handover | Not started |  |  |  |  | 3 | 0
15.05 | 15. Soft Landings & Aftercare | Seasonal commissioning completed in the first heating and cooling seasons | Seasonal commissioning reports and adjustments log | Commissioning Manager | Asset Owner | High | Post-handover | Not started |  |  |  |  | 3 | 0
15.06 | 15. Soft Landings & Aftercare | Fine-tuning and optimisation actions logged, prioritised and closed | Optimisation log with closure evidence | FM / Operations Lead | Soft Landings Champion | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
15.07 | 15. Soft Landings & Aftercare | Post-occupancy evaluation scoped, scheduled and funded | POE scope, method and schedule | Soft Landings Champion | Asset Owner | High | Post-handover | Not started |  |  |  |  | 3 | 0
15.08 | 15. Soft Landings & Aftercare | Occupant satisfaction survey issued and results analysed and communicated | Survey results report and response plan | Soft Landings Champion | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
15.09 | 15. Soft Landings & Aftercare | Energy and water consumption reviewed against targets at agreed intervals | Performance review reports with variance analysis | Sustainability Consultant | Asset Owner | High | Post-handover | Not started |  |  |  |  | 3 | 0
15.10 | 15. Soft Landings & Aftercare | Performance review meetings scheduled with agreed cadence, attendees and agenda | Meeting schedule and terms of reference | Soft Landings Champion | Client Project Director | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
15.11 | 15. Soft Landings & Aftercare | Lessons from aftercare fed back into client design standards and briefs (see Closeout Checklist) | Feedback record accepted by the client standards owner | Soft Landings Champion | Client Project Director | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
15.12 | 15. Soft Landings & Aftercare | Aftercare exit criteria agreed and the final aftercare report issued | Final aftercare report and exit sign-off | Soft Landings Champion | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
15.13 | 15. Soft Landings & Aftercare | Design intent reality-checked against measured operational performance | Design intent review record | Design Team | Asset Owner | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
16.01 | 16. Handover Acceptance & Sign-off | Handover documentation completeness review completed against the document register | Completeness review record with exceptions listed | Information Manager | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
16.02 | 16. Handover Acceptance & Sign-off | Acceptance criteria verified item by item against the agreed gate criteria | Gate assessment record with evidence references | Project Manager | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
16.03 | 16. Handover Acceptance & Sign-off | Outstanding works and defects list agreed and signed by both parties | Agreed outstanding works and defects schedule | Superintendent / Contract Administrator | Client Project Director | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
16.04 | 16. Handover Acceptance & Sign-off | Programme and access arrangements for completing outstanding works agreed | Rectification programme and access protocol | Contractor | FM / Operations Lead | High | G2 Handover | Not started |  |  |  |  | 3 | 0
16.05 | 16. Handover Acceptance & Sign-off | Items affecting occupancy identified and resolved or formally accepted in writing | Occupancy impact assessment and acceptance record | Project Manager | Client Project Director | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
16.06 | 16. Handover Acceptance & Sign-off | Conditional or unconditional acceptance decision made and documented | Acceptance decision record with conditions listed | Client Project Director | Asset Owner | Critical | G2 Handover | Not started |  |  |  |  | 5 | 0
16.07 | 16. Handover Acceptance & Sign-off | Formal handover acceptance certificate executed by all required parties | Executed acceptance certificate (see Acceptance & Sign-off sheet) | Client Project Director | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
16.08 | 16. Handover Acceptance & Sign-off | Care, custody and control of the asset transferred with the date recorded | Transfer of custody record | Superintendent / Contract Administrator | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
16.09 | 16. Handover Acceptance & Sign-off | Risk of loss or damage transferred and confirmed in writing | Risk transfer confirmation letter | Project Manager | Asset Owner | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
16.10 | 16. Handover Acceptance & Sign-off | Insurance transferred from contract works cover to the owner's operational policy | Insurance transfer confirmation and certificates | Asset Owner | Client Project Director | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
16.11 | 16. Handover Acceptance & Sign-off | Keys, credentials and site control formally handed over and receipted | Signed handover receipt for keys and credentials | Contractor | FM / Operations Lead | Critical | G3 Occupancy | Not started |  |  |  |  | 5 | 0
16.12 | 16. Handover Acceptance & Sign-off | Post-handover obligations register issued listing residual contractor duties | Post-handover obligations register | Project Manager | Client Project Director | High | G3 Occupancy | Not started |  |  |  |  | 3 | 0
16.13 | 16. Handover Acceptance & Sign-off | Handover close-out report issued and lessons transferred to project closeout (see Closeout Checklist) | Handover close-out report accepted by the client | Project Manager | Client Project Director | Medium | Post-handover | Not started |  |  |  |  | 2 | 0
Formulas:
Ovd = IF(AND([Target date]<>"",[Target date]<TODAY(),[Status]<>"Complete",[Status]<>"N/A"),1,0)

## Systems Commissioning Register
Systems Commissioning Register
Global edition · Transfer of the completed asset to the owner, operator and end users
One row per system or sub-system. Record each commissioning stage, the witnessed test, whether the system was included in integrated systems testing, and when seasonal commissioning falls due.
SYSTEMS LISTED |  | FULLY COMMISSIONED |  | DYNAMIC COMPLETE |  | INCLUDED IN IST |  | OUTSTANDING
48 |  | 0 |  | 0 |  | 0 |  | 48
System | Sub-system | Contractor / specialist | Pre-commissioning | Static commissioning | Dynamic commissioning | Witnessed test date | Witnessed by | IST included | Certificate ref | Seasonal commissioning due | Status
HVAC | Chilled water plant and pumps |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Heating hot water plant and pumps |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Air handling units |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Fan coil and terminal units |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Ductwork and air distribution |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Car park and basement ventilation |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Split and VRF systems |  | Not started | Not started | Not started | [5 empty] | Not started
HVAC | Kitchen and specialist exhaust |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | Incoming supply and main switchboard |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | Distribution boards and submains |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | Standby generator and fuel system |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | UPS and critical power |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | Lighting and lighting control |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | Emergency and exit lighting |  | Not started | Not started | Not started | [5 empty] | Not started
Electrical | Earthing and lightning protection |  | Not started | Not started | Not started | [5 empty] | Not started
Hydraulic | Cold water service and storage |  | Not started | Not started | Not started | [5 empty] | Not started
Hydraulic | Hot water generation and reticulation |  | Not started | Not started | Not started | [5 empty] | Not started
Hydraulic | Sanitary and trade waste drainage |  | Not started | Not started | Not started | [5 empty] | Not started
Hydraulic | Stormwater and pump-out systems |  | Not started | Not started | Not started | [5 empty] | Not started
Hydraulic | Backflow prevention devices |  | Not started | Not started | Not started | [5 empty] | Not started
Hydraulic | Irrigation and external services |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Fire detection and alarm |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Sprinkler and hydrant systems |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Fire pumps, tanks and boosters |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Gaseous and special hazard suppression |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Stair pressurisation and smoke control |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Passive fire protection and fire doors |  | Not started | Not started | Not started | [5 empty] | Not started
Fire | Emergency warning and intercom system |  | Not started | Not started | Not started | [5 empty] | Not started
Vertical transport | Passenger lifts |  | Not started | Not started | Not started | [5 empty] | Not started
Vertical transport | Goods and service lift |  | Not started | Not started | Not started | [5 empty] | Not started
Vertical transport | Escalators and travelators |  | Not started | Not started | Not started | [5 empty] | Not started
Security | Access control system |  | Not started | Not started | Not started | [5 empty] | Not started
Security | CCTV and video management |  | Not started | Not started | Not started | [5 empty] | Not started
Security | Intruder detection and monitoring |  | Not started | Not started | Not started | [5 empty] | Not started
Security | Intercom and duress |  | Not started | Not started | Not started | [5 empty] | Not started
ICT | Structured cabling and containment |  | Not started | Not started | Not started | [5 empty] | Not started
ICT | Active network equipment |  | Not started | Not started | Not started | [5 empty] | Not started
ICT | Wireless network and DAS |  | Not started | Not started | Not started | [5 empty] | Not started
Audio visual | Meeting and conference room AV |  | Not started | Not started | Not started | [5 empty] | Not started
Audio visual | Digital signage and paging |  | Not started | Not started | Not started | [5 empty] | Not started
BMS / BAS | Field devices and controllers |  | Not started | Not started | Not started | [5 empty] | Not started
BMS / BAS | Head end, graphics and reporting |  | Not started | Not started | Not started | [5 empty] | Not started
BMS / BAS | Third-party system integration |  | Not started | Not started | Not started | [5 empty] | Not started
Metering | Energy and power quality metering |  | Not started | Not started | Not started | [5 empty] | Not started
Metering | Water and thermal metering |  | Not started | Not started | Not started | [5 empty] | Not started
Specialist | Cold rooms and refrigeration |  | Not started | Not started | Not started | [5 empty] | Not started
Specialist | Medical or laboratory gases |  | Not started | Not started | Not started | [5 empty] | Not started
Facade | Building maintenance unit and anchors |  | Not started | Not started | Not started | [5 empty] | Not started

## Asset Register (Handover)
Asset Register (Handover)
Global edition · Transfer of the completed asset to the owner, operator and end users
Populate to your organisation's asset data standard (ISO 55000 aligned) and reconcile against the CMMS / EAM upload. Warranty expiry and days to expiry are calculated - rows highlight amber within 90 days of expiry and red once expired. Three worked examples are provided.
ASSETS LISTED |  | UPLOADED TO CMMS |  | CRITICAL ASSETS |  | WARRANTIES EXPIRING <90D |  | REPLACEMENT VALUE
40 |  | 3 |  | 0 |  | 0 |  | 75
Asset ID / tag | Asset name | Category | System | Location (building / level / room) | Manufacturer | Model | Serial number | Install date | Warranty start | Warranty months | Warranty expiry | Days to expiry | Criticality | Expected life (yrs) | Replacement cost (local currency) | Maintenance strategy | CMMS uploaded
AST-001 | Chiller No.1 | Mechanical | Chilled water | Level 2 Plant Room / PR-02 | Trane | RTAC-350 | TRN-2026-114857 | 2026-04-18 | 2026-08-28 | 24 | 2028-08-28 | 746 | Critical | 25 | 480000 | Planned preventive | Yes
AST-002 | Chiller No.2 | Mechanical | Chilled water | Level 2 Plant Room / PR-02 | Trane | RTAC-350 | TRN-2026-114858 | 2026-04-22 | 2026-08-28 | 24 | 2028-08-28 | 746 | Critical | 25 | 480000 | Planned preventive | Yes
AST-003 | Primary chilled water pump set | Mechanical | Chilled water
AST-004 | Cooling tower No.1 | Mechanical | Condenser water
AST-005 | Boiler No.1 | Mechanical | Heating hot water
AST-006 | Heating hot water pump set | Mechanical | Heating hot water
AST-007 | Air handling unit AHU-01 | Mechanical | Air side
AST-008 | Air handling unit AHU-02 | Mechanical | Air side
AST-009 | Car park exhaust fan CPF-01 | Mechanical | Ventilation
AST-010 | Kitchen exhaust fan KEF-01 | Mechanical | Ventilation
AST-011 | Stair pressurisation fan SPF-01 | Fire | Smoke control
AST-012 | Main switchboard MSB-01 | Electrical | LV distribution
AST-013 | Distribution board DB-L01 | Electrical | LV distribution
AST-014 | Standby generator GEN-01 | Electrical | Standby power | Basement 1 Generator Room / B1-GR | Cummins | C1100D5 | CUM-2026-77201 | 2026-05-06 | 2026-08-28 | 24 | 2028-08-28 | 746 | Critical | 25 | 395000 | Planned preventive | Yes
AST-015 | Diesel fuel storage tank | Electrical | Standby power
AST-016 | UPS-01 critical power | Electrical | Critical power
AST-017 | Lighting control panel LCP-01 | Electrical | Lighting
AST-018 | Solar photovoltaic array | Electrical | Renewables
AST-019 | Cold water booster pump set | Hydraulic | Cold water
AST-020 | Domestic hot water plant | Hydraulic | Hot water
AST-021 | Sewage ejection pump station | Hydraulic | Drainage
AST-022 | Stormwater pump-out pit | Hydraulic | Drainage
AST-023 | Rainwater harvesting tank | Hydraulic | Water reuse
AST-024 | Backflow prevention device BF-01 | Hydraulic | Cold water
AST-025 | Fire indicator panel FIP-01 | Fire | Detection and alarm
AST-026 | Electric fire pump FP-01 | Fire | Sprinkler and hydrant
AST-027 | Diesel fire pump FP-02 | Fire | Sprinkler and hydrant
AST-028 | Fire water storage tank | Fire | Sprinkler and hydrant
AST-029 | Sprinkler control valve set | Fire | Sprinkler and hydrant
AST-030 | Gaseous suppression system | Fire | Special hazard
AST-031 | Passenger lift LIFT-01 | Vertical transport | Lifts
AST-032 | Passenger lift LIFT-02 | Vertical transport | Lifts
AST-033 | Goods lift LIFT-03 | Vertical transport | Lifts
AST-034 | Access control head end | Security | Access control
AST-035 | CCTV network video recorder | Security | CCTV
AST-036 | BMS head end server | BMS / BAS | Head end
AST-037 | BMS field controller FC-01 | BMS / BAS | Field devices
AST-038 | Main network core switch | ICT | Active equipment
AST-039 | Building maintenance unit | Facade | Facade access
AST-040 | Main energy meter EM-01 | Metering | Energy metering
Formulas:
Warranty expiry = IFERROR(IF(OR([Warranty start]="",[Warranty months]=""),"",EDATE([Warranty start],[Warranty months])),"")
Days to expiry = IFERROR(IF([Warranty expiry]="","",[Warranty expiry]-TODAY()),"")

## O&M Documentation Register
O&M Documentation Register
Global edition · Transfer of the completed asset to the owner, operator and end users
Tracks every operation and maintenance document from draft to final acceptance. Completeness percentages at the top are live formulas and exclude documents marked N/A.
DOCUMENTS LISTED |  | DRAFT RECEIVED |  | REVIEWED |  | COMMENTS CLOSED |  | FINAL RECEIVED |  | ACCEPTED
35 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0
Doc ref | Title | System / discipline | Author / originator | Format | Draft received | Reviewed | Comments closed | Final received | Location / system | Verified by | Status
OM-001 | Mechanical services O&M manual | Mechanical |  |  | No | No | No | No |  |  | Not received
OM-002 | Chilled water plant O&M section | Mechanical |  |  | No | No | No | No |  |  | Not received
OM-003 | Heating hot water plant O&M section | Mechanical |  |  | No | No | No | No |  |  | Not received
OM-004 | Air handling and ventilation O&M section | Mechanical |  |  | No | No | No | No |  |  | Not received
OM-005 | Mechanical control philosophy (as-commissioned) | Mechanical |  |  | No | No | No | No |  |  | Not received
OM-006 | Electrical services O&M manual | Electrical |  |  | No | No | No | No |  |  | Not received
OM-007 | Standby power and UPS O&M section | Electrical |  |  | No | No | No | No |  |  | Not received
OM-008 | Lighting and lighting control O&M section | Electrical |  |  | No | No | No | No |  |  | Not received
OM-009 | Protection settings and discrimination study | Electrical |  |  | No | No | No | No |  |  | Not received
OM-010 | Hydraulic services O&M manual | Hydraulic |  |  | No | No | No | No |  |  | Not received
OM-011 | Water hygiene and treatment management plan | Hydraulic |  |  | No | No | No | No |  |  | Not received
OM-012 | Fire services O&M manual | Fire |  |  | No | No | No | No |  |  | Not received
OM-013 | Fire safety strategy and evacuation plan | Fire |  |  | No | No | No | No |  |  | Not received
OM-014 | Cause and effect matrix (verified) | Fire |  |  | No | No | No | No |  |  | Not received
OM-015 | Passive fire protection register | Fire |  |  | No | No | No | No |  |  | Not received
OM-016 | Vertical transportation O&M manual | Vertical transport |  |  | No | No | No | No |  |  | Not received
OM-017 | Lift entrapment and rescue procedure | Vertical transport |  |  | No | No | No | No |  |  | Not received
OM-018 | Security systems O&M manual | Security |  |  | No | No | No | No |  |  | Not received
OM-019 | ICT and structured cabling O&M manual | ICT |  |  | No | No | No | No |  |  | Not received
OM-020 | Audio visual O&M manual and user guide | Audio visual |  |  | No | No | No | No |  |  | Not received
OM-021 | BMS / BAS O&M manual and graphics guide | BMS / BAS |  |  | No | No | No | No |  |  | Not received
OM-022 | Metering strategy and meter schedule | Metering |  |  | No | No | No | No |  |  | Not received
OM-023 | Building fabric and finishes care manual | Architectural |  |  | No | No | No | No |  |  | Not received
OM-024 | Facade and waterproofing maintenance manual | Architectural |  |  | No | No | No | No |  |  | Not received
OM-025 | Facade access system operating manual | Facade |  |  | No | No | No | No |  |  | Not received
OM-026 | Landscape and irrigation maintenance manual | Landscape |  |  | No | No | No | No |  |  | Not received
OM-027 | Structural record and design certification pack | Structural |  |  | No | No | No | No |  |  | Not received
OM-028 | Planned preventive maintenance schedule | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-029 | Statutory maintenance and compliance schedule | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-030 | Valve, damper and isolation schedules | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-031 | Single-line diagrams and schematics set | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-032 | Building user guide (non-technical) | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-033 | Emergency and out-of-hours procedures | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-034 | Health and safety file / safety information | Multi-discipline |  |  | No | No | No | No |  |  | Not received
OM-035 | Warranty schedule and warranty documents | Multi-discipline |  |  | No | No | No | No |  |  | Not received

## Training Register
Training Register
Global edition · Transfer of the completed asset to the owner, operator and end users
Plan, deliver and evidence knowledge transfer to FM, operations, security, ICT and end users. Competency verification is the evidence a gate reviewer will ask for - not attendance alone.
SESSIONS PLANNED |  | DELIVERED |  | COMPETENCY VERIFIED |  | TOTAL ATTENDEES |  | % DELIVERED
26 |  | 0 |  | 0 |  | 0 |  | 0%
Session | System / topic | Audience | Trainer / provider | Delivery method | Duration (hrs) | Planned date | Delivered date | Attendees | Competency verified | Recording / materials ref | Status
TR-001 | Chilled water plant operation and fault finding | FM / operations | [6 empty] | No |  | Planned
TR-002 | Heating hot water plant operation | FM / operations | [6 empty] | No |  | Planned
TR-003 | Air handling units and terminal units | FM / operations | [6 empty] | No |  | Planned
TR-004 | Ventilation and smoke exhaust systems | FM / operations | [6 empty] | No |  | Planned
TR-005 | Main switchboard and LV distribution safety | FM / operations | [6 empty] | No |  | Planned
TR-006 | Standby generator start, test and changeover | FM / operations | [6 empty] | No |  | Planned
TR-007 | UPS operation, bypass and battery care | FM / operations | [6 empty] | No |  | Planned
TR-008 | Lighting control system programming | FM / operations | [6 empty] | No |  | Planned
TR-009 | Cold and hot water systems and water hygiene | FM / operations | [6 empty] | No |  | Planned
TR-010 | Pump stations and drainage systems | FM / operations | [6 empty] | No |  | Planned
TR-011 | Fire indicator panel operation and isolation | FM / operations and wardens | [6 empty] | No |  | Planned
TR-012 | Fire pumps and sprinkler valve sets | FM / operations | [6 empty] | No |  | Planned
TR-013 | Smoke control and stair pressurisation | FM / operations | [6 empty] | No |  | Planned
TR-014 | Lift operation, logbooks and entrapment release | FM / operations | [6 empty] | No |  | Planned
TR-015 | Access control administration and card issue | Security team | [6 empty] | No |  | Planned
TR-016 | CCTV operation, export and privacy obligations | Security team | [6 empty] | No |  | Planned
TR-017 | BMS graphics, alarms and set-point adjustment | FM / operations | [6 empty] | No |  | Planned
TR-018 | BMS trending, reporting and energy analysis | FM / operations | [6 empty] | No |  | Planned
TR-019 | Network, wireless and remote access management | ICT team | [6 empty] | No |  | Planned
TR-020 | Audio visual room systems operation | End users | [6 empty] | No |  | Planned
TR-021 | Building user induction and building user guide | End users | [6 empty] | No |  | Planned
TR-022 | Emergency response, evacuation and warden duties | All occupants | [6 empty] | No |  | Planned
TR-023 | CMMS use, work orders and asset records | FM / operations | [6 empty] | No |  | Planned
TR-024 | Facade access system safe operation | FM / operations and contractors | [6 empty] | No |  | Planned
TR-025 | Waste, recycling and cleaning regimes | Cleaning and FM | [6 empty] | No |  | Planned
TR-026 | Seasonal commissioning refresher | FM / operations | [6 empty] | No |  | Planned

## Warranty & Defects Schedule
Warranty & Defects Liability Schedule
Global edition · Transfer of the completed asset to the owner, operator and end users
Expiry is calculated with EDATE from the start date and duration. Status is calculated: Expired, Expiring soon (within 90 days) or Active. Set the defects liability / defects notification period start to the date on the completion or taking-over certificate.
WARRANTIES LISTED |  | ACTIVE |  | EXPIRING SOON |  | EXPIRED |  | START DATES SET
30 |  | 0 |  | 0 |  | 0 |  | 0
Element / system | Contractor / supplier | Warranty type | Start date | Duration (months) | Expiry | Status | Claim process | Contact | Document ref
Main works - general building |  | Contractor defects liability |  | 12
Structural frame and substructure |  | Contractor defects liability |  | 12
Roofing membrane and flashings |  | Extended system warranty |  | 120
Facade, curtain wall and glazing |  | Extended system warranty |  | 120
Waterproofing - wet areas and podium |  | Extended system warranty |  | 120
External cladding and coatings |  | Extended system warranty |  | 120
Windows, doors and hardware |  | Manufacturer warranty |  | 24
Internal finishes and joinery |  | Contractor defects liability |  | 12
Floor coverings and carpet |  | Manufacturer warranty |  | 60
Chillers |  | Manufacturer warranty |  | 24
Boilers and heat generation |  | Manufacturer warranty |  | 24
Air handling units |  | Manufacturer warranty |  | 24
Pumps and drives |  | Manufacturer warranty |  | 24
Ductwork and air distribution |  | Contractor defects liability |  | 12
Main switchboard and distribution |  | Manufacturer warranty |  | 24
Standby generator |  | Manufacturer warranty |  | 24
UPS and batteries |  | Manufacturer warranty |  | 24
Luminaires and lighting control |  | Manufacturer warranty |  | 60
Solar photovoltaic array and inverters |  | Manufacturer warranty |  | 120
Hot water plant and storage |  | Manufacturer warranty |  | 24
Booster and sewage pump sets |  | Manufacturer warranty |  | 24
Fire detection and alarm system |  | Manufacturer warranty |  | 12
Fire pumps and sprinkler installation |  | Manufacturer warranty |  | 12
Lifts and vertical transportation |  | Manufacturer warranty |  | 24
Access control and CCTV systems |  | Manufacturer warranty |  | 24
BMS / BAS controls and head end |  | Manufacturer warranty |  | 24
Structured cabling installation |  | Extended system warranty |  | 300
Audio visual equipment |  | Manufacturer warranty |  | 24
Landscape establishment and irrigation |  | Contractor defects liability |  | 24
Whole-of-works latent defects cover |  | Latent defects insurance |  | 120
Formulas:
Expiry = IFERROR(IF(OR([Start date]="",[EXPIRING SOON]=""),"",EDATE([Start date],[EXPIRING SOON])),"")
EXPIRED = IF([Expiry]="","",IF([Expiry]<TODAY(),"Expired",IF([Expiry]-TODAY()<=90,"Expiring soon","Active")))

## Spares, Keys & Attic Stock
Spares, Keys & Attic Stock
Global edition · Transfer of the completed asset to the owner, operator and end users
Variance is calculated as delivered less required - a negative variance is a shortfall and should be reflected on the Outstanding Works & Defects sheet. Receipt every delivery; unreceipted spares are the most commonly disputed handover item.
LINE ITEMS |  | FULLY DELIVERED |  | SHORTFALLS |  | RECEIPTED
29 |  | 0 |  | 0 |  | 0
Item | System | Specification / part reference | Qty required | Qty delivered | Variance | Receipted by | Date received | Storage location | Notes
Air filters - AHU primary and secondary | HVAC | Full set per unit
Fan and pump drive belts | HVAC | One set per drive
Chiller refrigerant charge (top-up) | HVAC | As specified
Chilled and heating water treatment chemicals | HVAC | 3 months supply
Terminal unit actuators | HVAC | 2% of installed
Temperature and pressure sensors | BMS / BAS | 2% of installed
BMS controller spare module | BMS / BAS | 1 per controller type
Circuit breakers - each frame size | Electrical | 2 per type
Fuses and fuse links | Electrical | 5 per type
Luminaires and LED drivers | Electrical | 2% of installed
Emergency lighting batteries | Electrical | 2% of installed
Generator service kit (filters, oils) | Electrical | 1 service interval
UPS battery module | Electrical | 1 module
Tap sets, cartridges and washers | Hydraulic | 2% of installed
Pump mechanical seals | Hydraulic | 1 per pump type
Backflow device repair kits | Hydraulic | 1 per device type
Sprinkler heads - each type and rating | Fire | 6 per type
Fire detectors - each type | Fire | 2% of installed
Fire alarm panel spare cards | Fire | 1 per card type
Access control readers and cards | Security | 2% plus 100 cards
CCTV camera - each type | Security | 1 per type
Ceiling tiles | Attic stock | 2% of installed area
Floor and wall tiles - each type | Attic stock | 2% of installed area
Carpet tiles / broadloom | Attic stock | 2% of installed area
Paint - each colour and finish | Attic stock | 10 litres per colour
Facade panels and gaskets | Attic stock | 1% of installed
Master key set and key blanks | Security | Per key schedule
Special tools and proprietary keys | Multi-discipline | Per O&M manuals
Software, firmware and config backups | Multi-discipline | 1 set durable media

## Outstanding Works & Defects
Outstanding Works & Defects at Handover
Global edition · Transfer of the completed asset to the owner, operator and end users
The agreed list of works and defects carried past handover. Days open is calculated - it runs to today while the item is open and stops at the date closed. Anything with an occupancy impact of Yes must be resolved or formally accepted before Gate 3. Two worked examples are provided.
ITEMS RAISED |  | OPEN |  | CLOSED |  | P1 CRITICAL OPEN |  | OCCUPANCY IMPACTING |  | OVERDUE
2 |  | 2 |  | 0 |  | 1 |  | 1 |  | 0
Ref | Location | Description | Category | Raised by | Date raised | Responsible | Priority | Agreed completion date | Status | Date closed | Days open | Impact on occupancy | Notes
OW-001 | Level 3 / Open office north | Ceiling tile grid distorted around AHU-02 supply diffusers; tiles do not sit flush. | Defect | FM / Operations Lead | 2026-08-03 | Contractor | P3 Medium | 2026-09-12 | In progress |  | 10 | No | Access outside occupied hours agreed with the tenant.
OW-002 | Basement 1 / Generator room | Acoustic louvre to generator exhaust not installed - material on order, 6 week lead time. | Incomplete work | Commissioning Manager | 2026-07-28 | Contractor | P1 Critical | 2026-09-30 | Awaiting access |  | 16 | Yes | Noise limit compliance evidence required before unrestricted generator testing.
OW-003
OW-004
OW-005
OW-006
OW-007
OW-008
OW-009
OW-010
OW-011
OW-012
OW-013
OW-014
OW-015
OW-016
OW-017
OW-018
OW-019
OW-020
OW-021
OW-022
OW-023
OW-024
OW-025
OW-026
OW-027
OW-028
OW-029
OW-030
Formulas:
Days open = IFERROR(IF([Date raised]="","",IF([OVERDUE]="",TODAY()-[Date raised],[OVERDUE]-[Date raised])),"")

## Soft Landings & Aftercare
Soft Landings & Aftercare Plan
Global edition · Transfer of the completed asset to the owner, operator and end users
Aftercare typically runs to three years under BSRIA Soft Landings and Government Soft Landings principles: intensive initial aftercare, then months 2-6, then annual reviews to Year 3. Each activity needs a named owner and a deliverable.
ACTIVITIES |  | WEEKS 1-4 |  | MONTHS 2-6 |  | YEAR 1 |  | COMPLETE
27 |  | 7 |  | 7 |  | 6 |  | 0
Ref | Activity | Aftercare period | Owner | Frequency | Start | End | Deliverable | Status
AC-001 | Aftercare team mobilised and help point communicated | Weeks 1-4 |  | One-off |  |  |  | Not started
AC-002 | Daily on-site aftercare presence (floor walkers) | Weeks 1-4 |  | Weekly |  |  |  | Not started
AC-003 | Daily building walkround and issue capture | Weeks 1-4 |  | Weekly |  |  |  | Not started
AC-004 | Weekly aftercare issue review with contractor | Weeks 1-4 |  | Weekly |  |  |  | Not started
AC-005 | BMS set-point and comfort fine-tuning | Weeks 1-4 |  | Weekly |  |  |  | Not started
AC-006 | Occupant comfort feedback capture (pulse check) | Weeks 1-4 |  | Weekly |  |  |  | Not started
AC-007 | Handover documentation gap closure | Weeks 1-4 |  | One-off |  |  |  | Not started
AC-008 | Monthly aftercare performance meeting | Months 2-6 |  | Monthly |  |  |  | Not started
AC-009 | Energy and water consumption review against baseline | Months 2-6 |  | Monthly |  |  |  | Not started
AC-010 | Defects and outstanding works progress review | Months 2-6 |  | Monthly |  |  |  | Not started
AC-011 | Refresher training for FM and operations | Months 2-6 |  | Quarterly |  |  |  | Not started
AC-012 | First seasonal commissioning (heating or cooling) | Months 2-6 |  | One-off |  |  |  | Not started
AC-013 | Metering data validation and reporting setup | Months 2-6 |  | Monthly |  |  |  | Not started
AC-014 | Occupant satisfaction survey - first round | Months 2-6 |  | One-off |  |  |  | Not started
AC-015 | Second seasonal commissioning (opposite season) | Year 1 |  | One-off |  |  |  | Not started
AC-016 | Quarterly performance review meeting | Year 1 |  | Quarterly |  |  |  | Not started
AC-017 | Post-occupancy evaluation - year one | Year 1 |  | One-off |  |  |  | Not started
AC-018 | Warranty expiry review ahead of 12-month expiries | Year 1 |  | One-off |  |  |  | Not started
AC-019 | End of defects liability inspection and close-out | Year 1 |  | One-off |  |  |  | Not started
AC-020 | Fine-tuning and optimisation actions review | Year 1 |  | Quarterly |  |  |  | Not started
AC-021 | Six-monthly performance review meeting | Year 2 |  | Six-monthly |  |  |  | Not started
AC-022 | Energy performance verification against targets | Year 2 |  | Six-monthly |  |  |  | Not started
AC-023 | Occupant satisfaction survey - second round | Year 2 |  | One-off |  |  |  | Not started
AC-024 | Lifecycle plan update from operational experience | Year 2 |  | One-off |  |  |  | Not started
AC-025 | Final post-occupancy evaluation and benchmarking | Year 3 |  | One-off |  |  |  | Not started
AC-026 | Lessons learned feedback to client design standards | Year 3 |  | One-off |  |  |  | Not started
AC-027 | Aftercare exit review and final aftercare report | Year 3 |  | One-off |  |  |  | Not started

## Handover Acceptance & Sign-off
Handover Acceptance & Sign-off
Global edition · Transfer of the completed asset to the owner, operator and end users
Printable acceptance certificate. Project details populate automatically from the Cover sheet. Execute one certificate per handover or per section where sectional handover applies.
1. Project and asset details
Project name
Project number
Client / asset owner
Prepared by
Template / revision | Construction Project Handover Checklist
Asset / facility handed over
Section or stage (if sectional handover)
Date of practical / substantial completion
Date of handover / transfer of custody
Defects liability / notification period ends
2. Position at the date of acceptance |  | Live from the checklist and registers
Checklist items applicable | 237
Checklist items complete | 0
Checklist completion | 0%
Critical items outstanding | 91
Outstanding works / defects open | 2
Occupancy impacting items open | 1
3. Acceptance statements
Ref | Statement |  |  | Confirmed | Reference / comment
A01 | The works described above have reached practical / substantial completion and a completion or taking-over certificate (or contract equivalent) has been issued.
A02 | Statutory occupancy / use approval has been issued as applicable in the relevant jurisdiction, and all approval conditions relevant to occupation have been discharged.
A03 | Fire and life-safety systems have been installed, commissioned, verified and certified, and the fire safety information and evacuation strategy have been issued to the responsible person.
A04 | Tests on completion, commissioning, balancing and integrated systems testing have been completed and the commissioning dossier has been issued and accepted.
A05 | As-built drawings, record models, the Asset Information Model and the structured asset data exchange have been delivered and verified against the Asset Information Requirements.
A06 | Operation and maintenance manuals, maintenance schedules, statutory maintenance obligations and the building user guide have been issued in final form and accepted.
A07 | The health and safety file / safety information, including residual hazards and safe access information, has been issued to the client.
A08 | The asset register has been delivered to the client asset data standard and uploaded to and reconciled with the CMMS / EAM.
A09 | Warranties, guarantees and collateral warranties have been provided, registered and scheduled, and the defects liability / defects notification period start date is confirmed.
A10 | Spares, special tools, keys, credentials, attic stock and consumables have been delivered and receipted, and software, firmware and configuration backups have been provided.
A11 | Training has been delivered to the agreed plan and competency has been verified for all critical systems.
A12 | Facilities management and service transition are complete: helpdesk live, planned and statutory maintenance loaded, and utility accounts transferred with opening meter readings.
A13 | The outstanding works and defects list has been agreed, programmed and signed by both parties, and no open item prevents safe and lawful occupation.
A14 | The soft landings aftercare team, duration, seasonal commissioning and post-occupancy evaluation arrangements have been agreed and resourced.
A15 | Care, custody and control of the asset, and the risk of loss or damage, transfer to the client / asset owner on the handover date stated above.
A16 | Insurance has been transferred from contract works cover to the owner's operational policy with effect from the handover date, and is in force.
4. Acceptance decision, conditions and exclusions
Acceptance decision
Sections / areas excluded from this handover
Condition 1
Condition 2
Condition 3
Condition 4
Exclusion 1
Exclusion 2
5. Documents and items transferred
Document / item set |  | Transferred | Reference / location |  | Date
Completion, taking-over and statutory approval certificates
Fire and life-safety certification and fire safety information
Commissioning dossier, test results and balancing reports
As-built drawings, record models and Asset Information Model
Operation and maintenance manuals and maintenance schedules
Building user guide and emergency / out-of-hours procedures
Asset register and CMMS / EAM upload reconciliation
Health and safety file / safety information
Warranty schedule, warranties and collateral warranties
Training records, materials and competency sign-offs
Spares, special tools, attic stock and consumables
Keys, access credentials and security devices
Software licences, administrator credentials and backups
Utility account transfers and opening meter readings
Agreed outstanding works and defects schedule
6. Signatures
Role | Name | Organisation | Signature |  | Date
Contractor's Representative
Superintendent / Contract Administrator
Project Manager
Client Project Director
Asset Owner
FM / Operations Lead
End User Representative
Execution of this certificate records the transfer of the asset described above. It does not of itself discharge the contractor's obligations during the defects liability / defects notification period, nor does it complete the commercial closeout of the contract - see the Mastt Construction Project Closeout Checklist.

## Lists
Lists & dropdown sources
Global edition · Transfer of the completed asset to the owner, operator and end users
Every dropdown in this workbook reads from the labelled columns below. Add or amend values here - extend a column downwards and the corresponding dropdown range in the source sheet will need widening.
Status | Criticality | Gate | Category | Roles (Responsible / Accountable) | Yes / No | Commissioning stage status | Document format | Document status | Training status | Warranty type | Priority | Works category | Aftercare period | Frequency | Maintenance strategy | Works status | Criticality (weights) | Weight
Not started | Critical | G1 Commissioning Review | 1. Handover Readiness & Planning | Project Manager | Yes | Not started | PDF | Not received | Planned | Contractor defects liability | P1 Critical | Defect | Weeks 1-4 | One-off | Planned preventive | Open | Critical | 5
In progress | High | G2 Handover | 2. Completion & Certification | Client Project Director | No | In progress | Native + PDF | Draft received | Scheduled | Manufacturer warranty | P2 High | Incomplete work | Months 2-6 | Weekly | Condition-based | In progress | High | 3
Complete | Medium | G3 Occupancy | 3. Commissioning, Testing & Balancing | Asset Owner | N/A | Complete | Hard copy | Under review | Delivered | Extended system warranty | P3 Medium | Omission | Year 1 | Fortnightly | Statutory | Awaiting access | Medium | 2
Blocked | Low | Post-handover | 4. Building Systems & Services Handover | Superintendent / Contract Administrator |  | Witnessed | Digital model | Comments issued | Competency verified | Collateral warranty | P4 Low | Damage | Year 2 | Monthly | Reactive | Resolved | Low | 1
N/A |  |  | 5. Asset Register & Asset Data | Contractor |  | N/A | Structured data | Final received | Deferred | Performance guarantee |  | Non-conformance | Year 3 | Quarterly | Run to failure | Closed
|  |  | 6. Operation & Maintenance Documentation | Commissioning Manager |  |  | Video | Accepted | Cancelled | Latent defects insurance |  |  |  | Six-monthly |  | Rejected
|  |  | 7. Record Documentation & Information Exchange | Independent Commissioning Agent |  |  |  | N/A | [5 empty] | Annually
|  |  | 8. Warranties, Guarantees & Defects Liability | FM / Operations Lead
|  |  | 9. Spares, Consumables, Tools & Attic Stock | Information Manager
|  |  | 10. Training & Knowledge Transfer | Design Team
|  |  | 11. FM, Operations & Service Transition | Soft Landings Champion
|  |  | 12. Occupancy, Migration & End User Readiness | Health & Safety Adviser
|  |  | 13. Security, Access & Digital Systems | Fire Engineer
|  |  | 14. Environmental, Sustainability & Certification | Certifier / Approving Authority
|  |  | 15. Soft Landings & Aftercare | ICT Lead
|  |  | 16. Handover Acceptance & Sign-off | Security Manager
Sustainability Consultant
End User Representative
Supplier / Manufacturer
Cost Manager