PROJECT EXECUTION PLAN Project Execution Plan The definitive statement of how a capital project will be delivered - governance, controls, standards and reporting

| Project name |  | Project number |  |
| --- | --- | --- | --- |
| Client / asset owner |  | Delivery model |  |
| Prepared by |  | Role / organisation |  |
| Date |  | Document reference |  |
| Revision | 1.0 | Status | Draft / For review / Issued |
| Approved by (Sponsor) |  | Baseline date |  |

This template is provided by Mastt as general guidance for capital project delivery. It is not legal, financial or professional advice. Users must adapt it to the contract, jurisdiction, statutory regime and organisational policies applicable to their project, and should obtain independent professional advice where appropriate. Mastt accepts no liability arising from use of this template.

# Document control

Guidance Complete every field below before the Project Execution Plan (PEP) is issued. The revision history is the authoritative record of what changed and why - never overwrite a row, always add one. A PEP that cannot be traced to an approved revision has no standing in a dispute, an audit or a gateway review.

## Revision history

| Rev | Date | Prepared by | Reviewed by | Approved by | Description of change |
| --- | --- | --- | --- | --- | --- |
| A |  |  |  |  | First issue for review |
| B |  |  |  |  |  |
| 0 |  |  |  |  | Issued for use |

## Distribution list

The Project Manager maintains distribution. Controlled copies are reissued automatically on each revision; uncontrolled copies are issued for information only and are not maintained.

| Name | Role | Organisation | Copy type | Format |
| --- | --- | --- | --- | --- |
|  | Project Sponsor |  | Controlled | PDF |
|  | Project Director |  | Controlled | PDF + native |
|  | Project Manager (owner) |  | Master | Native |
|  | Client Representative |  | Controlled | PDF |
|  | Commercial Manager |  | Controlled | PDF |
|  | Design Manager |  | Controlled | PDF |
|  | HSE Manager |  | Controlled | PDF |
|  | Contractor's Project Manager |  | Uncontrolled | PDF |

## Related documents register

Guidance List every document that this PEP depends on, governs or is governed by. State the relationship precisely - 'subordinate to', 'referenced by', 'expanded by' - so a reader knows which document prevails where they conflict. The order of precedence between the contract and this PEP must always favour the contract.

| Document | Reference | Version | Owner | Relationship to this PEP |
| --- | --- | --- | --- | --- |
| Business case / investment case |  |  | Sponsor | PEP delivers the approved investment; PEP is subordinate |
| Project Initiation Document (PID) / charter |  |  | Sponsor | PEP expands the PID into delivery detail |
| Contract(s) and conditions of contract |  |  | Commercial Manager | Contract prevails over the PEP in all cases |
| Client project management framework |  |  | PMO | PEP must comply; deviations require PMO endorsement |
| Risk management plan and risk register |  |  | Risk Manager | Expanded by Section 10 |
| Health, safety and wellbeing plan |  |  | HSE Manager | Expanded by Section 12 |
| Environmental and sustainability management plan |  |  | ESG Lead | Expanded by Section 13 |
| Quality management plan and ITPs |  |  | Quality Manager | Expanded by Section 11 |
| Information / BIM execution plan |  |  | Information Manager | Expanded by Section 14 |
| Commissioning and operational readiness plan |  |  | Comm. Manager | Expanded by Section 20 |
| Handover checklist |  |  | Project Manager | Referenced by Section 20 |
| Closeout checklist and final report |  |  | Project Manager | Referenced by Sections 20 and 22 |
| Benefits realisation plan |  |  | Sponsor | Expanded by Section 21 |
| Stakeholder and communications plan |  |  | Comms Lead | Expanded by Section 5 |

# Approval and authorisation

This Project Execution Plan is the approved statement of how the project will be delivered. On approval it becomes the delivery baseline for scope, governance, schedule, cost, risk, quality, safety, environment and information management. All members of the project team, and all consultants, contractors and suppliers to the extent incorporated into their contracts, are to work in accordance with it.

No person may depart from this plan without an approved change in accordance with Section 18 (Change Control). Where this plan conflicts with an executed contract, the contract prevails. Where it conflicts with a statutory obligation applicable in the relevant jurisdiction, the statutory obligation prevails and the Project Manager must raise a plan revision immediately.

By signing below, each signatory confirms they have read the plan, accept the responsibilities assigned to their role, and are satisfied that the resources, controls and authorities described are adequate for the project as currently defined.

| Role | Name | Organisation | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by - Project Manager |  |  |  |  |
| Reviewed by - Project Director |  |  |  |  |
| Reviewed by - Commercial Manager |  |  |  |  |
| Reviewed by - HSE Manager |  |  |  |  |
| Endorsed by - Client Representative |  |  |  |  |
| Approved by - Project Sponsor |  |  |  |  |

Approval date establishes the PEP baseline. Record the approved revision number in the revision history and in the project controls system on the same day.

# Contents

Right-click and choose 'Update Field' to build the table of contents.

# Glossary, abbreviations and definitions

Guidance Delete terms that do not apply to your project and add any project-specific or contract-specific terms. Where a term is defined in the contract, the contract definition prevails and this glossary should cross-reference it rather than restate it.

| Term | Definition |
| --- | --- |
| AFC | Approved for Construction - the drawing or model status at which documentation may be used to build. |
| As-built | Records showing the works as physically constructed, including all approved changes, verified before handover. |
| Assurance | Independent, objective confirmation that project controls are designed and operating effectively. |
| BIM | Building Information Modelling - collaborative production and use of structured digital information about a built asset. |
| BCR | Benefit cost ratio - present value of benefits divided by present value of costs. |
| Baseline | The approved version of scope, schedule, cost or another plan against which performance is measured; changed only by approved change control. |
| CDE | Common Data Environment - the single agreed source of information for the project, per ISO 19650. |
| CBS | Cost breakdown structure - hierarchical decomposition of project cost into controllable accounts. |
| Contingency | Funds held within the baseline for identified risk within the Project Manager's or Sponsor's control. |
| Control account | The management point where scope, budget, schedule and actual cost are integrated and measured. |
| CPI | Cost performance index - earned value divided by actual cost. |
| Critical path | The longest sequence of logically linked activities that determines the earliest project completion date. |
| DLP | Defects liability period - the period after taking over during which the contractor must rectify notified defects. |
| Design freeze | The point beyond which design changes require formal change control and impact assessment. |
| EAC | Estimate at completion - the forecast total cost of the project. |
| Early warning | A prompt notice of any matter that could affect cost, time, quality or safety, raised before it becomes a formal claim. |
| EIR | Exchange information requirements - what information the appointing party requires, when, and in what form. |
| EOT | Extension of time - a contractual adjustment to the date for completion arising from a qualifying delay event. |
| EVM | Earned value management - integrated scope, schedule and cost performance measurement technique. |
| Float | The time an activity can be delayed without delaying a successor (free float) or the project completion (total float). |
| Gateway review | An independent review at a defined decision point confirming readiness to proceed to the next stage. |
| Hold point | A mandatory verification point beyond which work must not proceed without documented release. |
| IFC | Issued for construction - see AFC; usage varies by contract. |
| ITP | Inspection and test plan - the sequenced record of inspections, tests, hold and witness points for a work activity. |
| Interface | A defined boundary between parties, systems, packages or physical works requiring coordinated management. |
| Level of information need | The extent of geometrical, alphanumerical and documentation content required for a given information exchange. |
| LTIFR | Lost time injury frequency rate - lost time injuries per million hours worked. |
| Milestone | A zero-duration schedule event marking a significant achievement, decision or obligation. |
| Mock-up | A physical sample of an assembly built for approval of appearance, workmanship and performance before production. |
| NCR | Non-conformance report - the record of work that does not meet specified requirements, and its disposition. |
| Novation | Transfer of a consultant's appointment from the client to the contractor, with the consultant's obligations continuing to the new party. |
| OBS | Organisational breakdown structure - mapping of scope to the people and organisations accountable for it. |
| Operational readiness | The activities that prepare the operator, users and systems to accept and run the asset. |
| PC | Practical completion / taking over - the point at which the works are fit for their intended use, subject to minor defects. |
| PEP | Project Execution Plan - this document; the operating manual for delivery. |
| PID | Project Initiation Document - the mandate defining why the project exists, its objectives and its authority. |
| PMO | Project (or portfolio) management office - the function setting and assuring delivery standards. |
| Provisional sum | An allowance in the contract price for work not yet sufficiently defined, adjusted when instructed. |
| Quantitative risk analysis | Probabilistic modelling of cost and schedule risk to derive confidence levels and contingency. |
| RACI | Responsible, Accountable, Consulted, Informed - the responsibility assignment convention used in this plan. |
| Rebaseline | Formal replacement of an approved baseline following an authorised change of sufficient magnitude. |
| Residual risk | The risk remaining after planned treatments have been implemented. |
| Risk appetite | The amount and type of risk the organisation is willing to pursue or retain in pursuit of its objectives. |
| RFI | Request for information - a formal query seeking clarification of the design or contract documents. |
| Snagging / punch list | The register of minor defects and outstanding items identified at completion inspections. |
| Soft landings | A structured process extending designer and contractor involvement beyond handover to tune performance in use. |
| SPI | Schedule performance index - earned value divided by planned value. |
| Stage gate | A control point at which continuation, change or termination of the project is formally decided. |
| TRIFR | Total recordable injury frequency rate - recordable injuries per million hours worked. |
| Value engineering | Structured review of function against cost to improve value without reducing required performance. |
| Variation / change order | An instructed change to the scope, quality or sequence of the contract works. |
| VAC | Variance at completion - budget at completion less estimate at completion. |
| WBS | Work breakdown structure - hierarchical decomposition of the total scope into deliverable-oriented elements. |
| Witness point | A notified verification point that the client may attend; work may proceed if the client does not attend within the notice period. |

# How to use this template

Guidance This template is deliberately comprehensive so that it can be cut down rather than built up. Delete what does not apply to your project, but record in the revision history what you removed and why - an unexplained omission is indistinguishable from an oversight at an audit.

Work front to back. Sections 1 to 4 set the frame; everything after depends on them being right.

Replace every square-bracketed prompt and every italic guidance line with project-specific content. Delete the grey Guidance callouts before issuing - they are written for the author, not the reader.

Populate every table. A table left with only header rows tells a reviewer the section was not thought about.

Reconcile the three places where authority thresholds appear - Sections 3.8, 4.6 and 18.4 - so that they state identical figures.

Reconcile the milestone list in Section 8.5 with Appendix A and with the baseline schedule.

Have each discipline lead review and accept their own section before the plan goes for approval; ownership of a section is ownership of the process it describes.

Issue the approved plan to everyone on the distribution list and withdraw the superseded revision.

Review the plan at every stage gate and whenever a trigger in Section 1.5 occurs.

Standards alignment. This template is written to be jurisdiction-neutral and draws on ISO 21500 and ISO 21502 (project, programme and portfolio management guidance), ISO 21501, the PMBOK Guide performance domains, ISO 31000 (risk management), ISO 19650 (information management using building information modelling), ISO 9001, ISO 14001 and ISO 45001 (quality, environmental and occupational health and safety management systems), ISO 55000 (asset management), the RIBA Plan of Work stage framework, and generic contract concepts common to the FIDIC and NEC families. It does not assert which contract form, statute or regulatory regime applies to your project. Legal and statutory requirements must be confirmed for the applicable jurisdiction.

# 1.  Introduction and purpose

## 1.1  Purpose of this plan

Guidance State in two or three sentences why this plan exists and what a reader should be able to do with it. A good PEP answers a single question for every member of the delivery team: 'how do we do this here?' It is not a restatement of the business case and it is not a contract - it is the operating manual for delivery.

This Project Execution Plan (PEP) defines how the project will be delivered. It sets out the governance, organisation, processes, controls, standards and reporting that the delivery team will apply from the point of approval through to closeout and benefits realisation. It converts the intent recorded in the business case and Project Initiation Document into an executable delivery system.

The plan is written to be used, not filed. Every section states who does what, by when, to what standard, and what happens when the standard is not met.

[Insert a project-specific purpose statement. Name the asset, the client, the delivery model and the outcome the project must achieve.]

## 1.2  Scope of application

This plan applies to:

All phases of the project from delivery mobilisation through design, procurement, construction, commissioning, handover and closeout.

All members of the client-side project team, including seconded and contracted personnel.

All consultants, contractors, subcontractors and suppliers, to the extent that the plan or its subordinate plans are incorporated into their contracts.

All project information, records and reporting produced for or by the project.

This plan does not replace: the executed contract or any of its conditions; statutory duties applicable in the relevant jurisdiction; the client's corporate policies; or the contractor's own management system documentation, which must be separately reviewed and accepted.

## 1.3  Relationship to the business case, PID and contract

Guidance Show the document hierarchy explicitly. Reviewers and auditors consistently find that projects fail here - the PEP quietly restates outdated objectives from a superseded business case. State the order of precedence and the version of each parent document that this PEP was written against.

| Document | Establishes | Precedence over this PEP | Version relied on |
| --- | --- | --- | --- |
| Applicable law and regulation | Mandatory statutory duties | Prevails absolutely | Current at date of issue |
| Executed contract(s) | Legal obligations between parties | Prevails |  |
| Approved business case | Investment rationale, benefits, funding envelope | Prevails on objectives and benefits |  |
| Project Initiation Document / charter | Mandate, objectives, authority, tolerances | Prevails on authority and tolerance |  |
| Client PM framework / PMO standards | Mandatory process and gateway requirements | Prevails unless a deviation is endorsed |  |
| This Project Execution Plan | How delivery is executed and controlled | - |  |
| Subordinate management plans | Discipline-specific method and control detail | Subordinate to this PEP |  |

## 1.4  Ownership and maintenance

The Project Manager owns this plan and is accountable for its accuracy, currency and use. The Project Director reviews it. The Project Sponsor approves it. The Project Management Office (or equivalent assurance function) may audit compliance with it at any time.

A plan that does not reflect how the project is actually run is worse than no plan, because it creates a false record. If practice diverges from the plan, either practice or the plan must change within one reporting cycle.

## 1.5  Review triggers and update cadence

| Trigger | Action required | Owner | Timeframe |
| --- | --- | --- | --- |
| Stage gate or gateway review | Full review and reissue of the PEP | Project Manager | Before the gate submission |
| Approved change to scope, budget or completion date beyond tolerance | Targeted revision of affected sections and rebaseline | Project Manager | Within 10 working days of approval |
| Change of delivery model or contract strategy | Full review of Sections 6, 17 and 18 | Commercial Manager | Before market approach |
| Change of Project Manager, Sponsor or Project Director | Review and re-endorsement of Sections 4 and 16 | Project Director | Within 20 working days |
| Material change in risk profile or a red-rated risk materialising | Review of Section 10 and contingency position | Risk Manager | At the next monthly control cycle |
| Notifiable incident, enforcement action or serious non-conformance | Review of Sections 11, 12 and 13 | HSE Manager | Within 5 working days |
| Change in applicable statutory or consent requirements | Review of Sections 12, 13 and 7 | Project Manager | Immediately |
| No other trigger | Scheduled periodic review | Project Manager | At least every 6 months |

## 1.6  Authorising a deviation from this plan

Guidance Deviations happen. What separates a well-run project is that they are visible, time-bound and authorised by someone with the standing to carry the consequence. Never allow an undocumented deviation to become custom and practice.

A deviation is any departure from a process, control, standard or authority defined in this plan.

The person proposing the deviation records it in the deviation log with the reason, the duration, the risk created and the compensating control.

Deviations affecting safety, statutory compliance or a contractual obligation are not permitted under any circumstances.

Minor process deviations are approved by the Project Manager for a period not exceeding one reporting cycle.

Deviations affecting governance, authority limits, baseline control or assurance are approved by the Project Director and reported to the Sponsor.

Any deviation lasting more than two reporting cycles must be closed by a formal revision of this plan.

| Ref | Deviation | Reason | Compensating control | Expiry | Approved by |
| --- | --- | --- | --- | --- | --- |
| DEV-01 |  |  |  |  |  |
| DEV-02 |  |  |  |  |  |
| DEV-03 |  |  |  |  |  |
| DEV-04 |  |  |  |  |  |

# 2.  Project overview

## 2.1  Project description

Guidance Write this so that a competent professional joining the team on day one understands what is being built, for whom, and why, in under two minutes. Avoid marketing language. State physical quantities - floor area, capacity, length, number of units - because these drive every estimate and programme downstream.

[Describe the works: asset type, principal quantities, key systems, phasing, and what 'complete' physically means.]

## 2.2  Location and site context

Site context drives cost, programme and risk more than almost any other factor. Record the conditions that constrain delivery.

| Aspect | Detail | Delivery implication |
| --- | --- | --- |
| Site address / location |  |  |
| Land tenure and access rights |  |  |
| Existing site condition and occupancy |  |  |
| Ground conditions and known contamination |  |  |
| Existing services and utilities |  |  |
| Adjacent property and sensitive receivers |  |  |
| Heritage, cultural or ecological constraints |  |  |
| Access, laydown and craneage constraints |  |  |
| Traffic management and permitted working hours |  |  |
| Climate, seasonal and weather exposure |  |  |
| Security and site establishment requirements |  |  |

## 2.3  Project drivers and strategic alignment

State the organisational strategy, service need or regulatory obligation the project serves, and identify which driver takes priority when they conflict. Almost every difficult project decision is a trade-off between time, cost and scope quality - the team must know in advance which one gives way.

| Driver | Description | Priority (1 = highest) | Consequence if not met |
| --- | --- | --- | --- |
| Time / operational date |  |  |  |
| Capital cost / affordability |  |  |  |
| Functional performance and quality |  |  |  |
| Safety and statutory compliance |  |  |  |
| Sustainability and carbon |  |  |  |
| Stakeholder and community outcomes |  |  |  |
| Whole-of-life cost and operability |  |  |  |

## 2.4  Objectives and success criteria

Guidance Objectives must be measurable and owned. An objective without a target, a tolerance and a named owner is an aspiration. Tolerance is the band inside which the Project Manager may act without escalation - set it deliberately, because it defines the Sponsor's workload as much as the Project Manager's freedom.

| Objective | Measure | Target | Tolerance | Owner |
| --- | --- | --- | --- | --- |
| Deliver with no serious harm to any person | Recordable injury frequency rate | 0 serious injuries | Zero tolerance | HSE Manager |
| Achieve operational date | Date of practical completion |  |  | Project Manager |
| Deliver within approved funding | Final outturn cost vs approved budget |  |  | Commercial Manager |
| Meet functional performance requirements | Verified compliance against the design brief | 100% of mandatory requirements | None | Design Manager |
| Achieve quality standard at handover | Defects open at practical completion |  |  | Quality Manager |
| Meet sustainability commitments | Certified rating / carbon vs baseline |  |  | ESG Lead |
| Maintain stakeholder confidence | Substantiated complaints per month |  |  | Comms Lead |
| Enable operational readiness | Operator acceptance of asset data and training | 100% complete before taking over | None | Operations Representative |

## 2.5  Critical success factors

Critical success factors are the conditions that must hold for the objectives to be achievable. They are inputs, not outcomes, and each should be actively monitored.

A single, empowered decision-maker on the client side, available within the decision timeframes set out in Section 4.

Design sufficiently complete and coordinated before each procurement package goes to market.

Early and continuous engagement with authorities, utility owners and adjacent asset owners.

Realistic contingency held at the right level and released only against identified risk.

Stable scope after design freeze, enforced through change control.

Continuity of key personnel across the design-to-construction transition.

Operator and end-user involvement from design through to commissioning.

Timely, accurate and trusted performance information.

## 2.6  Project characteristics

| Characteristic | Detail |
| --- | --- |
| Approved capital value (excluding tax) |  |
| Total investment including escalation and contingency |  |
| Funding source(s) and drawdown constraints |  |
| Planned duration (delivery mobilisation to closeout) |  |
| Delivery model | Traditional / Design and build / Construction management / Managing contractor / Alliance / PPP / IPD |
| Principal contract form | To be confirmed on award |
| Number of principal contract packages |  |
| Complexity rating and rationale | Low / Medium / High / Major |
| Assurance tier / gateway regime |  |
| Design stage framework in use | e.g. RIBA Plan of Work stages 0-7 or equivalent |
| Sustainability rating scheme and target |  |
| Operational readiness owner |  |
| Programme / portfolio this project belongs to |  |

# 3.  Scope management

## 3.1  Scope statement

Guidance The scope statement is the reference point for every change assessment for the life of the project. Write it as a boundary, not a wish list: what is included, what is deliberately excluded, and what condition the works must be in when handed over. Ambiguity here is paid for later at variation rates.

[State the total scope of the project in a single controlled paragraph, then reference the documents that define it in detail - design brief, drawing register, specification, schedule of quantities.]

## 3.2  In scope

| Ref | Scope element | Description | Responsible party |
| --- | --- | --- | --- |
| S01 | Site establishment and enabling works |  |  |
| S02 | Demolition and site preparation |  |  |
| S03 | Design development and documentation |  |  |
| S04 | Statutory approvals and permits |  |  |
| S05 | Substructure and civil works |  |  |
| S06 | Superstructure and building fabric |  |  |
| S07 | Building services and systems |  |  |
| S08 | External works, landscaping and services |  |  |
| S09 | Fit-out, fixtures and equipment |  |  |
| S10 | Testing, commissioning and operational readiness |  |  |
| S11 | Training, documentation and asset data |  |  |

## 3.3  Out of scope

Exclusions must be as explicit as inclusions. Each exclusion should name the party who will deliver it instead, or state that it is not being delivered at all - an unowned exclusion is a programme risk.

| Ref | Excluded item | Rationale | Delivered by (if at all) |
| --- | --- | --- | --- |
| X01 | Operational equipment procured by the operator |  |  |
| X02 | Relocation of existing occupants and their contents |  |  |
| X03 | Upstream utility network reinforcement |  |  |
| X04 | Ongoing operation and maintenance after the defects period |  |  |
| X05 | Land acquisition and easement negotiation |  |  |
| X06 | Loose furniture and consumables |  |  |

## 3.4  Key deliverables

| Ref | Deliverable | Stage | Owner | Acceptance authority | Planned date |
| --- | --- | --- | --- | --- | --- |
| D01 | Approved design brief and requirements schedule | Definition | Design Manager | Sponsor |  |
| D02 | Concept design and cost plan | Concept | Design Manager | Project Board |  |
| D03 | Developed design and updated cost plan | Developed | Design Manager | Project Board |  |
| D04 | Technical design / tender documentation | Technical | Design Manager | Project Director |  |
| D05 | Statutory approvals and permits | Technical | Planning Lead | Authority |  |
| D06 | Executed construction contract(s) | Procurement | Commercial Manager | Sponsor |  |
| D07 | Constructed works | Construction | Contractor | Project Manager |  |
| D08 | Commissioning records and test certificates | Commissioning | Commissioning Manager | Operations |  |
| D09 | Asset data, O&M manuals and as-builts | Handover | Information Manager | Operations |  |
| D10 | Training and operational readiness sign-off | Handover | Operations Rep | Operations |  |
| D11 | Closeout report and lessons learned | Closeout | Project Manager | Sponsor |  |

## 3.5  Work breakdown structure

The work breakdown structure (WBS) is the spine of scope, schedule, cost and reporting. It is decomposed to deliverables, not to activities, and it is aligned one-to-one with the cost breakdown structure so that every dollar and every day can be traced to a piece of scope.

| Level | Name | Purpose | Typical owner | Used for |
| --- | --- | --- | --- | --- |
| 1 | Project | Total authorised scope | Sponsor | Investment reporting |
| 2 | Phase or major asset element | Delivery phasing | Project Director | Board reporting, Level 1 schedule |
| 3 | Work package / contract package | Procurement and contracting | Project Manager | Level 2 schedule, control accounts |
| 4 | Deliverable or sub-package | Progress and cost control | Package Manager | Level 3 schedule, earned value |
| 5 | Activity / work item | Execution and short-term control | Contractor / discipline lead | Level 4 look-ahead, ITPs |

Each WBS element has one owner, one control account and one set of acceptance criteria.

The 100% rule applies: the sum of the children equals the parent, with no scope outside the structure.

WBS codes are never reused or renumbered once the baseline is set; superseded elements are closed, not deleted.

The WBS dictionary records for each element its scope, exclusions, assumptions, owner, budget and acceptance criteria.

## 3.6  Deliverable acceptance criteria

Guidance Define acceptance before work starts, not at the point of handover. State the evidence required, who verifies it and who accepts it. 'Acceptance by the Project Manager' is not an acceptance criterion - 'design compliance matrix showing 100% of mandatory requirements closed, verified by the independent reviewer' is.

| Deliverable type | Acceptance criteria | Evidence required | Accepted by |
| --- | --- | --- | --- |
| Design deliverable | Complies with the brief, coordinated, reviewer comments closed | Compliance matrix, clash report, comment response register | Design Manager |
| Procurement deliverable | Evaluated against approved criteria, probity confirmed | Evaluation report, probity sign-off | Commercial Manager |
| Physical work | Conforms to specification, ITP complete, no open NCRs | Signed ITP, test results, NCR register | Quality Manager |
| System / installation | Passes commissioning to specified performance | Commissioning records, certificates, witness sheets | Commissioning Manager |
| Information deliverable | Meets the level of information need and naming convention | CDE status, validation report | Information Manager |
| Operational readiness | Operator trained, spares held, procedures issued | Training records, readiness checklist | Operations Representative |

## 3.7  Scope change control

Scope change is managed through the process in Section 18. The steps below are the scope-specific application of that process.

Identify - anyone may raise a potential change; it is logged in the change register within 2 working days.

Screen - the Project Manager confirms whether it is a change to the approved baseline or clarification of existing scope.

Assess - impact on cost, time, risk, safety, quality, operations, benefits and interfaces is quantified by the responsible discipline leads.

Price - commercial impact is established under the contract mechanism before, not after, instruction wherever practicable.

Authorise - approved at the level set by the authority matrix below.

Instruct - issued formally under the contract by the person authorised to do so.

Baseline - approved changes are incorporated into the schedule, cost and scope baselines at the next control cycle.

Communicate - the change is communicated to every affected party, including designers and the operator.

## 3.8  Scope change authority matrix

| Change value or impact | Assessed by | Recommended by | Approved by | Notified to |
| --- | --- | --- | --- | --- |
| No cost or time impact; clarification only | Package Manager | - | Project Manager | Change register |
| Up to [X] and no impact on completion date | Discipline lead | Project Manager | Project Manager | Project Director |
| Up to [Y] or up to [n] days of float consumed | Commercial Manager | Project Manager | Project Director | Sponsor |
| Up to [Z] or any change to the completion date | Commercial Manager | Project Director | Sponsor | Project Board |
| Above [Z], any change to approved benefits, or any change to the funding envelope | Commercial Manager | Sponsor | Project Board / investment authority | All parties |
| Any change affecting statutory compliance or safety in design | HSE Manager | Project Manager | Project Director (with HSE endorsement) | Sponsor |

Insert the monetary thresholds [X], [Y] and [Z] from the client's delegation of authority. Thresholds must reconcile exactly with Section 4.6 and Section 9.12.

## 3.9  Scope interfaces and exclusions

Scope boundaries between packages, between the project and the existing asset, and between the project and third parties are managed as interfaces under Section 15. Every exclusion in Section 3.3 must have a corresponding entry in the interface register or an accepted risk in the risk register.

## 3.10  Assumptions

Guidance An assumption is something taken to be true for planning purposes that has not been verified. Each one is a risk in waiting. Give every assumption an owner and a date by which it must be confirmed or converted to a risk.

| Ref | Assumption | Basis | Owner | Validate by | Impact if invalid |
| --- | --- | --- | --- | --- | --- |
| A01 |  |  |  |  |  |
| A02 |  |  |  |  |  |
| A03 |  |  |  |  |  |
| A04 |  |  |  |  |  |
| A05 |  |  |  |  |  |
| A06 |  |  |  |  |  |

## 3.11  Constraints

| Ref | Constraint | Type | Source | Management approach |
| --- | --- | --- | --- | --- |
| C01 |  | Time |  |  |
| C02 |  | Cost / funding |  |  |
| C03 |  | Site access / possession |  |  |
| C04 |  | Statutory / consent |  |  |
| C05 |  | Operational continuity |  |  |
| C06 |  | Resource / market capacity |  |  |
| C07 |  | Technical / interface |  |  |

# 4.  Project governance and organisation

## 4.1  Governance framework

Guidance Governance exists to make decisions at the pace the project needs, with the right people accountable. Test every forum you propose against three questions: what decision does it make, who cannot make that decision without it, and what does it produce? If a forum has no decision rights, it is a meeting, not governance - say so.

The governance framework separates three distinct roles: direction (the Sponsor and Project Board, accountable for the investment and the benefits), management (the Project Director and Project Manager, accountable for delivery within tolerance), and assurance (independent of both, accountable for confirming that controls work).

## 4.2  Governance forums

| Forum | Purpose | Membership | Frequency | Quorum | Decision rights | Outputs |
| --- | --- | --- | --- | --- | --- | --- |
| Project Board / Steering Committee | Direct the investment, approve baselines and stage gates | Sponsor (chair), Project Director, client business owner, operations representative, finance | Monthly | Chair + 3 including finance | Approve baseline change beyond PM tolerance; approve stage gate progression | Minutes, decisions register, approved baseline |
| Project Control Group | Manage delivery performance, risk and change | Project Director (chair), Project Manager, Commercial Manager, Design Manager, HSE Manager, Planner | Fortnightly | Chair + 3 | Approve change within delegated limits; endorse recommendations to the Board | Actions, change decisions, risk decisions |
| Project Delivery Team meeting | Coordinate day-to-day delivery and resolve blockers | Project Manager (chair), package managers, discipline leads | Weekly | Chair + 2 | Operational decisions within the plan | Actions, look-ahead, issues log |
| Design Coordination Meeting | Resolve design coordination, RFIs and clashes | Design Manager (chair), lead consultants, contractor design lead, information manager | Weekly during design | Chair + lead disciplines | Design direction within the approved brief | Clash report, RFI status, decisions |
| Risk Review Workshop | Review and re-assess risk and opportunity | Risk Manager (facilitator), Project Manager, discipline leads, key contractors | Monthly | Facilitator + 4 | Assign treatments and owners; recommend contingency drawdown | Updated risk register, treatment actions |
| Health, Safety and Wellbeing Committee | Oversee HSE performance and assurance | HSE Manager (chair), Project Manager, contractor HSE leads, worker representatives | Monthly | Chair + worker representative | Direct corrective action; stop-work authority | HSE actions, incident review, performance report |
| Commercial and Contract Meeting | Administer the contract, valuations, claims and notices | Commercial Manager (chair), Project Manager, contractor commercial lead | Monthly | Chair + contractor lead | Certify payments and determine entitlement within delegation | Payment certificates, notices register |
| Stakeholder and Communications Group | Coordinate engagement and community response | Comms Lead (chair), Project Manager, client comms, contractor comms | Monthly | Chair + 2 | Approve external communications within policy | Engagement log, approved communications |
| Operational Readiness Group | Prepare the operator to accept and run the asset | Operations Representative (chair), Project Manager, Commissioning Manager, FM lead | Monthly, weekly from 6 months before completion | Chair + 2 | Accept readiness deliverables | Readiness checklist status, training plan |
| Assurance and Gateway Review | Independent review of readiness to proceed | Independent reviewers appointed by the PMO | At each gate | As appointed | Recommend proceed / proceed with conditions / do not proceed | Gateway report and actions |

## 4.3  Project organisation

Insert the project organisation chart below. Show reporting lines, functional lines and the boundary between the client organisation, the delivery team and the supply chain. Mark each role as full-time, part-time or on-call, and show the date each role mobilises.

[Insert project organisation chart - client, delivery team, consultants and contractors, showing reporting and functional lines]

## 4.4  Roles and responsibilities

Guidance Every role needs one accountable person, not a committee. Where a role is shared or part-time, say what proportion of time is committed and who covers it in absence. Vacant roles must be shown as vacant with a mobilisation date - hiding them is how projects start behind.

| Role | Accountable for | Key authorities | Reports to |
| --- | --- | --- | --- |
| Project Sponsor | The investment, the benefits and the business case; removing organisational obstacles | Approves the PEP, baselines and gate progression; approves change above the Director's limit | Investment authority / executive |
| Project Board / Steering Committee | Direction, oversight and resolution of matters beyond the Sponsor's delegation | Approves stage gates and funding release | Executive |
| Project Director | Delivery within the approved baseline and tolerances; commercial outcome | Approves change within delegation; appoints and removes key personnel | Sponsor |
| Project Manager | Day-to-day delivery, this plan, and integration of all disciplines | Instructs the team; approves change within delegation; issues contract notices as authorised | Project Director |
| Client Representative / Superintendent | Formal client role under the contract | Issues instructions, certifies and determines as the contract provides | Project Director |
| Commercial / Contracts Manager | Procurement, cost, contract administration and claims | Certifies payment within delegation; issues commercial notices | Project Director |
| Cost Manager / Quantity Surveyor | Estimating, cost planning, valuation and cost reporting | Recommends valuations and forecasts | Commercial Manager |
| Planner / Scheduler | Schedule integrity, baseline control and critical path analysis | Controls the schedule baseline; validates contractor programmes | Project Manager |
| Design Manager | Design delivery, coordination, compliance with the brief and design change discipline | Accepts design deliverables; chairs design coordination | Project Manager |
| Lead Designer / Design Consultants | Design that is safe, compliant, coordinated and buildable | Design decisions within the approved brief | Design Manager |
| Information Manager | Information standard, CDE, model federation and asset data | Sets and enforces the information standard | Project Manager |
| HSE Manager | Safety, health and wellbeing systems and assurance | Stop-work authority; approves high-risk activity permits | Project Director |
| Quality Manager | Quality system, ITPs, NCRs and audit programme | Approves ITPs; releases hold points; issues NCRs | Project Manager |
| Environmental / Sustainability Lead | Environmental compliance, consents and sustainability targets | Stop-work authority for environmental incidents | Project Manager |
| Risk Manager | Risk process integrity, register quality and quantitative analysis | Facilitates assessment; recommends contingency | Project Manager |
| Stakeholder / Communications Lead | Engagement, community relations and media | Approves external communications within policy | Project Manager |
| Commissioning Manager | Commissioning strategy, integrated testing and performance verification | Accepts commissioning evidence | Project Manager |
| Operations / Asset Representative | Operability, maintainability and operational readiness | Accepts the asset on behalf of operations | Client business owner |
| Contractor's Project Manager | Execution of the contract works | Directs the contractor's resources and supply chain | Contractor's management |
| Package Managers | Delivery of an assigned package to cost, time and quality | Manages package scope within the baseline | Project Manager |
| Document Controller | Document control, registers and records management | Enforces numbering, status and distribution | Information Manager |
| Independent Reviewer / Assurance | Objective assessment of readiness and control effectiveness | Recommends gate outcomes | PMO / Sponsor |

## 4.5  Responsibility assignment (RACI)

R = Responsible (does the work); A = Accountable (one only, owns the outcome); C = Consulted (two-way); I = Informed (one-way). Every row has exactly one A. Where a project role is not applicable, mark the cell ' - ' rather than leaving it blank.

| Activity | SPO | PD | PM | CM | DM | PL | HSE | QM | IM | CON |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approve the business case and funding | A | C | C | C | I | I | I | I | I | I |
| Own and maintain this PEP | A | C | R | C | C | C | C | C | C | I |
| Define and approve the design brief | A | C | R | I | R | I | C | C | C | I |
| Manage design delivery and coordination | I | A | C | I | R | C | C | C | R | C |
| Approve design deliverables | I | A | R | C | R | I | C | C | C | I |
| Develop the procurement strategy | A | R | C | R | C | C | I | I | I | - |
| Run tender and evaluation | I | A | C | R | C | C | C | C | I | - |
| Award contracts | A | R | C | R | I | I | I | I | I | - |
| Develop and baseline the schedule | I | A | R | C | C | R | C | C | I | R |
| Report schedule performance | I | I | A | C | C | R | I | I | C | R |
| Prepare and maintain the cost plan | I | A | C | R | C | C | I | I | I | C |
| Certify payments | I | I | C | A | I | I | I | C | I | R |
| Forecast cost at completion | I | A | C | R | C | C | I | I | I | C |
| Manage the risk register | I | A | R | C | C | C | C | C | I | C |
| Approve contingency drawdown | A | R | C | R | I | I | I | I | I | I |
| Assess and authorise change | C | A | R | R | C | C | C | C | I | C |
| Manage the quality system and ITPs | I | I | A | I | C | I | C | R | I | R |
| Release hold and witness points | - | I | I | - | C | - | C | A | I | R |
| Manage safety in design | I | A | C | I | R | I | R | C | I | C |
| Manage site HSE performance | I | A | C | I | I | I | R | C | I | R |
| Investigate incidents | I | A | C | I | I | I | R | C | I | R |
| Obtain approvals, consents and permits | I | A | R | C | R | C | C | I | I | C |
| Manage environmental and sustainability targets | I | A | C | I | C | I | C | C | I | R |
| Manage stakeholders and communications | C | A | R | I | I | I | I | I | I | C |
| Set the information standard and manage the CDE | I | I | A | I | C | I | I | I | R | R |
| Manage interfaces | I | A | R | C | C | C | C | C | C | R |
| Manage commissioning and testing | I | A | C | I | C | C | C | R | C | R |
| Accept handover on behalf of operations | A | C | R | C | C | I | C | C | C | C |
| Close out the contract | I | A | C | R | I | I | I | C | C | C |
| Capture and share lessons learned | I | A | R | C | C | C | C | C | C | C |
| Report benefits realisation | A | C | R | I | I | I | I | I | I | - |

SPO Sponsor · PD Project Director · PM Project Manager · CM Commercial Manager · DM Design Manager · PL Planner · HSE HSE Manager · QM Quality Manager · IM Information Manager · CON Contractor

## 4.6  Delegation of authority and financial approval thresholds

Guidance These thresholds must be copied from the client's delegation instrument, not invented. Confirm the currency, whether the figures are inclusive or exclusive of tax, and whether they apply per transaction or cumulatively per package.

| Authority | Project Manager | Project Director | Sponsor | Project Board |
| --- | --- | --- | --- | --- |
| Approve a variation / change order | Up to [X] | Up to [Y] | Up to [Z] | Above [Z] |
| Release contingency | Up to [X] | Up to [Y] | Up to [Z] | Above [Z] |
| Release management reserve | Nil | Nil | Recommend | Approve |
| Certify a progress payment | Up to [X] | Up to [Y] | Up to [Z] | Above [Z] |
| Award a contract or purchase order | Up to [X] | Up to [Y] | Up to [Z] | Above [Z] |
| Grant an extension of time | Up to [n] days | Up to [n] days | Beyond | Beyond |
| Accept a departure from specification | Nil | With designer concurrence | Material departures | Departures affecting performance |
| Approve rebaseline of the schedule | Recommend | Within tolerance | Beyond tolerance | Beyond Sponsor tolerance |
| Settle a claim or dispute | Recommend | Up to [Y] | Up to [Z] | Above [Z] |
| Appoint or remove key personnel | Recommend | Approve | Approve (PM/PD) | Noted |

## 4.7  Escalation pathway

| Level | Trigger | Escalate to | Response timeframe | If unresolved |
| --- | --- | --- | --- | --- |
| 1 | Issue blocking work at package level | Package Manager | Same working day | Escalate to Level 2 within 2 days |
| 2 | Issue affecting a package's cost, time or quality | Project Manager | 2 working days | Escalate to Level 3 within 5 days |
| 3 | Issue threatening the project baseline or tolerance | Project Director | 5 working days | Escalate to Level 4 at the next Board or sooner if urgent |
| 4 | Issue exceeding tolerance, affecting benefits or funding | Sponsor / Project Board | Next scheduled Board or an extraordinary session within 10 working days | Escalate to the investment authority |
| Immediate | Serious safety or environmental incident, statutory breach, or event threatening life, asset or reputation | HSE Manager and Project Director simultaneously; Sponsor within 1 hour | Immediate | Invoke the crisis management protocol |

## 4.8  Decision-making protocol

Decisions are made by the accountable role at the lowest level with sufficient authority and information.

Every decision requiring governance is presented with options, a recommendation, the cost, time, risk and benefit impact of each option, and the consequence of not deciding.

Papers are circulated at least 5 working days before the forum; papers tabled on the day are for noting only unless the chair rules otherwise.

Decisions are recorded in the decisions register with the date, the decision-maker, the rationale and the review date.

Where a decision is required faster than the forum cycle, the chair may make it out of session and it is ratified at the next meeting.

A decision is not made until it is recorded; verbal direction is confirmed in writing within 2 working days.

| Ref | Decision required | Options considered | Decision | Decision-maker | Date | Review date |
| --- | --- | --- | --- | --- | --- | --- |
| DEC-01 |  |  |  |  |  |  |
| DEC-02 |  |  |  |  |  |  |
| DEC-03 |  |  |  |  |  |  |
| DEC-04 |  |  |  |  |  |  |

## 4.9  Assurance and gateway reviews

Guidance Assurance is not the same as reporting. It must be carried out by people independent of the delivery team, against defined criteria, with findings that the Sponsor is obliged to act on. Set the gate dates in the baseline schedule so that reviews do not become the reason for delay.

| Gate | Stage boundary | Key question | Evidence required | Outcome authority |
| --- | --- | --- | --- | --- |
| G0 | Strategic assessment complete | Is the need real and the strategic fit clear? | Business case, options analysis | Investment authority |
| G1 | Business case approved | Is the preferred option affordable and deliverable? | Business case, cost plan, risk assessment, PID | Investment authority |
| G2 | Delivery strategy confirmed | Is the delivery and procurement strategy sound? | This PEP, procurement strategy, market assessment | Sponsor / Board |
| G3 | Design complete / ready to tender | Is the design compliant, coordinated and buildable? | Design compliance matrix, cost plan, consents | Board |
| G4 | Ready to award / start on site | Is the price, programme and risk allocation acceptable? | Evaluation report, contract, updated risk and contingency | Board / investment authority |
| G5 | Ready for commissioning | Is the work complete and testing ready to proceed? | ITP status, NCR position, commissioning plan | Project Director |
| G6 | Ready for handover | Is the operator ready to accept and operate? | Readiness checklist, asset data, training, certificates | Sponsor / operations |
| G7 | Closeout and benefits | Were the benefits delivered and what did we learn? | Closeout report, benefits review, lessons register | Sponsor |

Gateway findings are assigned an owner and a due date and are tracked to closure in the actions register. A red or amber-red gate outcome suspends progression until the Sponsor accepts a remediation plan.

# 5.  Stakeholder management and communications

## 5.1  Approach

Guidance Stakeholder management is a delivery control, not a public relations exercise. Most schedule loss on complex projects comes from consent, approval and access decisions made by people outside the project team. Identify who can stop the project, engage them before you need them, and record every commitment you make.

Stakeholders are identified at initiation and reviewed at every stage gate and whenever the works enter a new area or phase. Analysis uses power and interest, supplemented by an assessment of each stakeholder's attitude and the specific decisions or approvals they control.

## 5.2  Stakeholder analysis

| Position | Characteristics | Engagement strategy | Typical cadence |
| --- | --- | --- | --- |
| High power / high interest | Can stop or materially change the project and are actively engaged | Manage closely - direct, senior-level, two-way engagement with named relationship owners | Weekly to fortnightly |
| High power / low interest | Can stop the project but are not currently engaged | Keep satisfied - brief early, avoid surprises, escalate only what matters | Monthly |
| Low power / high interest | Strongly affected and vocal but cannot directly stop the project | Keep informed - regular, honest, accessible information and responsive complaint handling | Fortnightly to monthly |
| Low power / low interest | Marginally affected | Monitor - general information channels, review position at each stage | Quarterly |

## 5.3  Stakeholder register

| Ref | Stakeholder | Interest / requirement | Power | Interest | Attitude | Strategy | Relationship owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SH01 | Project Sponsor and executive |  | High | High | Supportive | Manage closely |  |
| SH02 | Asset owner / operator |  | High | High |  | Manage closely |  |
| SH03 | End users and occupants |  | Medium | High |  | Keep informed |  |
| SH04 | Consent and permitting authority |  | High | Medium |  | Keep satisfied |  |
| SH05 | Building control / regulator |  | High | Medium |  | Keep satisfied |  |
| SH06 | Utility and service providers |  | High | Low |  | Keep satisfied |  |
| SH07 | Adjacent property owners |  | Medium | High |  | Keep informed |  |
| SH08 | Local community and residents |  | Low | High |  | Keep informed |  |
| SH09 | Emergency services |  | Medium | Medium |  | Keep satisfied |  |
| SH10 | Funding body / lender |  | High | High |  | Manage closely |  |
| SH11 | Contractors and supply chain |  | Medium | High |  | Manage closely |  |
| SH12 | Media |  | Medium | Variable |  | Monitor |  |
| SH13 | Trade unions / worker representatives |  | Medium | High |  | Keep informed |  |

## 5.4  Communications matrix

Guidance Every row should answer: if this communication did not happen, what decision would be made badly or late? Delete anything that fails that test - over-reporting destroys the credibility of the reports that matter.

| Audience | Message / content | Channel | Frequency | Owner | Format |
| --- | --- | --- | --- | --- | --- |
| Project Board | Performance against baseline, risk, change, decisions required | Board pack and meeting | Monthly | Project Manager | PDF pack + dashboard |
| Sponsor | Exceptions, decisions required, early warnings | Direct briefing | Weekly | Project Director | Verbal + one-page note |
| Delivery team | Priorities, look-ahead, blockers, safety message | Team meeting | Weekly | Project Manager | Agenda and actions |
| Design team | Design status, RFIs, clashes, decisions | Coordination meeting + CDE | Weekly | Design Manager | Minutes, clash report |
| Contractors | Instructions, programme, quality and HSE requirements | Site meeting + formal correspondence | Weekly / as required | Project Manager | Minutes, formal notices |
| Operations and end users | Readiness, training, disruption, handover dates | Readiness group + user briefings | Monthly | Operations Representative | Briefing pack |
| Authorities and regulators | Compliance, notifications, permit status | Formal correspondence and meetings | As required by consent conditions | Planning Lead | Formal letter / portal submission |
| Adjacent owners and residents | Works notices, disruption, complaints response | Letter drop, email, site notice board | Before each disruptive activity, minimum 7 days | Comms Lead | Notice + contact number |
| Wider community | Progress, benefits, opportunities | Website, newsletter, community sessions | Quarterly | Comms Lead | Newsletter, web update |
| Media | Approved position only | Client media office | As required | Client communications | Approved statement |
| Supply chain / market | Upcoming packages and prequalification | Industry briefing, tender portal | Before each market approach | Commercial Manager | Notice and briefing pack |
| Workforce | Safety, wellbeing, project purpose | Toolbox talks, site notice boards | Weekly | HSE Manager | Toolbox record |

## 5.5  Reporting calendar

| Reporting activity | Cut-off | Draft due | Issue date | Owner |
| --- | --- | --- | --- | --- |
| Site progress and HSE data capture | Friday close of business | - | - | Contractor |
| Cost and commitment data cut-off | Last working day of the month | - | - | Cost Manager |
| Schedule update and progress claim | 25th of the month | Working day 2 | Working day 4 | Planner |
| Risk register update | Working day 3 | Working day 4 | Working day 5 | Risk Manager |
| Monthly project report | Working day 5 | Working day 7 | Working day 8 | Project Manager |
| Board pack issue | - | - | 5 working days before the Board | Project Manager |
| Executive / portfolio dashboard | Working day 8 | - | Working day 10 | PMO |
| Quarterly assurance report | Quarter end | +10 working days | +15 working days | Assurance Lead |

## 5.6  Meeting schedule

| Meeting | Chair | Attendees | Frequency | Duration | Output |
| --- | --- | --- | --- | --- | --- |
| Project Board | Sponsor | Board members | Monthly | 90 min | Minutes and decisions |
| Project Control Group | Project Director | Delivery leads | Fortnightly | 90 min | Actions and change decisions |
| Delivery team meeting | Project Manager | Package and discipline leads | Weekly | 60 min | Actions and look-ahead |
| Design coordination | Design Manager | Consultants and contractor design | Weekly | 90 min | Clash and RFI status |
| Site progress meeting | Project Manager | Contractor and client team | Weekly | 60 min | Progress, issues, look-ahead |
| Commercial meeting | Commercial Manager | Contractor commercial lead | Monthly | 90 min | Valuation and notices |
| Risk workshop | Risk Manager | Delivery leads and key contractors | Monthly | 120 min | Updated register |
| HSE committee | HSE Manager | HSE leads and worker representatives | Monthly | 60 min | HSE actions |
| Operational readiness group | Operations Representative | Operations, FM, commissioning | Monthly | 60 min | Readiness status |
| Interface forum | Project Manager | Interface owners | Monthly | 60 min | Interface register update |
| Lessons learned session | Project Manager | Whole team | At each stage gate | 120 min | Lessons register entries |

## 5.7  Community and public engagement

Engagement begins before the first disruptive activity, not after the first complaint.

Notification of disruptive works - piling, demolition, road closures, out-of-hours activity, service shutdowns - is issued at least 7 days in advance, or as the consent conditions require, whichever is longer.

A single publicised contact number and email address is monitored during working hours, with an out-of-hours emergency number.

Complaints are acknowledged within 1 working day and substantively responded to within 5 working days, and are recorded in the complaints register with the root cause and corrective action.

Commitments made to the community are logged in the commitments register and tracked to closure like any other obligation.

Engagement with Indigenous, traditional owner and culturally significant interests is undertaken in accordance with the requirements and protocols applicable in the relevant jurisdiction.

## 5.8  Media protocol

Only the client's authorised spokesperson speaks to media. No member of the project team, consultant or contractor comments on the project publicly without written authorisation.

All media enquiries are referred to the client communications function within 1 hour of receipt and logged.

In the event of an incident, no comment is made on cause, liability or casualties; the approved holding statement is used until the client communications function issues direction.

Site photography, filming and drone operation require prior written approval and must comply with privacy and security requirements applicable in the relevant jurisdiction.

## 5.9  Records of engagement

| Ref | Date | Stakeholder | Method | Issues raised | Commitment made | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ENG-01 |  |  |  |  |  |  |  |
| ENG-02 |  |  |  |  |  |  |  |
| ENG-03 |  |  |  |  |  |  |  |
| ENG-04 |  |  |  |  |  |  |  |
| ENG-05 |  |  |  |  |  |  |  |

# 6.  Delivery and procurement strategy

## 6.1  Delivery model options and rationale

Guidance State which delivery model has been selected and why, with reference to the project's risk profile, the certainty of scope, the client's capability and capacity, and market conditions. Never assert which contract form applies until it is executed - describe the intended family of contract and the risk allocation you are seeking.

| Delivery model | Best suited to | Client retains | Key risks | Selected? |
| --- | --- | --- | --- | --- |
| Traditional (design-bid-build) | Well-defined scope, price certainty before commitment, client control of design | Design risk and coordination risk | Design completeness; claims at the design/construction interface |  |
| Design and build | Scope that can be defined by output requirements; single-point responsibility | Requirement definition risk | Loss of design control; quality drift; change is expensive |  |
| Construction management | Fast-track programmes, phased release, complex fit-out | Trade package risk and interface risk | Cost certainty is late; heavy client-side resourcing |  |
| Managing contractor | Complex projects needing early contractor involvement with client control | Some scope and cost risk until packages are let | Two-stage price escalation; alignment of incentives |  |
| Alliance / collaborative | High uncertainty, high interface complexity, need for shared risk | Shared risk under a pain/gain regime | Cost transparency and governance overhead |  |
| Public-private partnership | Long-term whole-of-life outcomes with private finance | Availability and demand risk as allocated | Long procurement, inflexibility to change |  |
| Integrated project delivery | Sophisticated parties, shared information, aligned incentives | Shared risk and reward | Requires cultural and contractual maturity |  |

[State the selected delivery model, the options assessment that supported it, the date and forum at which it was approved, and the risk allocation principles being sought.]

## 6.2  Packaging strategy

Packaging determines how many interfaces the project must manage and who carries them. Fewer, larger packages reduce interface risk but narrow the market and reduce competitive tension; more, smaller packages do the opposite. Set the packaging strategy against the project's principal risk.

Package boundaries are drawn at natural physical or system breaks, not at organisational convenience.

Every package boundary generates an entry in the interface register (Section 15).

Long-lead items are identified and separately procured or reserved before the main package where the programme requires it.

Enabling and early works are packaged to allow site activity to start while the main design completes, where the risk of abortive work is acceptable.

The number of packages is tested against the client's capacity to administer them.

## 6.3  Procurement plan

| Package | Scope summary | Est. value | Procurement route | Intended contract family | Tender release | Award | Start on site |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P01 | Early works and site establishment |  | Open / selective | Lump sum |  |  |  |
| P02 | Demolition and remediation |  | Selective | Schedule of rates |  |  |  |
| P03 | Design consultancy services |  | Quality-price | Services agreement |  |  |  |
| P04 | Main works contract |  | Selective / two-stage | To be confirmed |  |  |  |
| P05 | Long-lead plant and equipment |  | Direct / reserved | Supply agreement |  |  |  |
| P06 | Building services and specialist systems |  | Selective | Subcontract |  |  |  |
| P07 | Fit-out and loose furniture |  | Panel / framework | Supply and install |  |  |  |
| P08 | Commissioning and independent verification |  | Quality-price | Services agreement |  |  |  |
| P09 | External works and landscaping |  | Selective | Lump sum |  |  |  |

## 6.4  Prequalification and evaluation

Prequalification tests capability and capacity before price is considered. Evaluation criteria and weightings are approved before the market approach and are not changed once tenders are received.

| Criterion | Assessed at | Typical weighting | Evidence |
| --- | --- | --- | --- |
| Financial capacity and stability | Prequalification | Pass / fail | Audited accounts, credit assessment, capacity headroom |
| Safety record and management system | Prequalification | Pass / fail | Certification, incident statistics, system review |
| Relevant experience and past performance | Prequalification and tender | 15-25% | Project references, referee checks |
| Proposed team and key personnel | Tender | 10-20% | CVs, commitment of named individuals, availability |
| Methodology and programme | Tender | 10-20% | Method statement, programme, resource histogram |
| Quality and technical compliance | Tender | 5-15% | Compliance schedule, departures register |
| Sustainability and social value | Tender | 5-15% | Carbon plan, local content and workforce commitments |
| Risk allocation and contractual position | Tender | Pass / fail or weighted | Departures from the conditions of contract |
| Price | Tender | 30-60% | Priced schedule, rates, provisional sums |

Evaluation is undertaken by a panel with declared conflicts of interest and a documented consensus method.

Non-conforming and alternative tenders are only considered where the tender documents expressly permit them and a conforming tender is also submitted.

Clarifications are issued to all tenderers simultaneously.

The evaluation report records the score, the rationale and the recommendation, and is retained for the period required by the client's records policy.

## 6.5  Contract administration responsibilities

| Function | Client-side owner | Delegation | Record kept in |
| --- | --- | --- | --- |
| Issue of instructions and directions | Client Representative | Within delegation | Instruction register |
| Assessment of variations | Commercial Manager | Recommend | Change register |
| Certification of payment | Client Representative / Commercial Manager | Within delegation | Payment register |
| Assessment of extension of time | Project Manager with Planner | Recommend | EOT register |
| Issue and receipt of contractual notices | Commercial Manager | Full | Notices register |
| Determination of claims | Client Representative | Within delegation | Claims register |
| Release of securities and bonds | Commercial Manager | With Director approval | Securities register |
| Certification of completion | Client Representative | Full | Completion records |

## 6.6  Supply chain and local content

Supply chain capacity and single points of failure are assessed before the market approach; critical suppliers are identified and monitored.

Local content, local employment and small-business participation commitments are specified in the tender documents, priced, and reported monthly against the commitments register.

Flow-down obligations for safety, quality, environment, information management, payment terms and ethical sourcing are mandated to every tier of the supply chain.

Subcontractor payment security arrangements applicable in the relevant jurisdiction are confirmed and monitored.

## 6.7  Market engagement

Early, structured market engagement improves pricing and reduces programme risk. It must be conducted so that no participant gains an advantage and no participant is excluded from the subsequent tender.

| Activity | Purpose | Timing | Owner |
| --- | --- | --- | --- |
| Market sounding / capability survey | Test appetite, capacity and risk appetite | Before delivery strategy approval | Commercial Manager |
| Industry briefing | Explain scope, programme and requirements | 6-8 weeks before tender release | Commercial Manager |
| Expression of interest / prequalification | Establish a capable tender list | 8-12 weeks before tender release | Commercial Manager |
| Tender period interactive sessions | Resolve ambiguity and improve tender quality | During tender period | Project Manager |
| Post-award debrief | Maintain market confidence and improve future tenders | Within 20 working days of award | Commercial Manager |

## 6.8  Probity

All participants declare actual, potential and perceived conflicts of interest before any evaluation activity, and update declarations as circumstances change.

Confidentiality undertakings are signed by everyone with access to tender information.

Communication with tenderers during the tender period is only through the nominated contact and the tender portal.

An independent probity adviser is appointed where the value, sensitivity or complexity of the procurement warrants it.

Gifts, benefits and hospitality are declined or declared in accordance with the client's policy.

Records of every probity-relevant event are retained for the period required in the relevant jurisdiction.

# 7.  Design management

## 7.1  Design stages and deliverables

Guidance Map your project onto a recognised stage framework - RIBA Plan of Work stages 0-7 or the equivalent used in your jurisdiction - and define what must be complete at the end of each stage. The single most common cause of cost growth is proceeding to the next stage on an incomplete previous stage.

| Stage | Purpose | Key deliverables | Design completion | Gate |
| --- | --- | --- | --- | --- |
| 0 Strategic definition | Confirm the business need and best means of achieving it | Strategic brief, options appraisal | - | G0 |
| 1 Preparation and brief | Establish the project brief and feasibility | Project brief, site information, feasibility studies, initial cost plan | - | G1 |
| 2 Concept design | Establish the architectural and engineering concept | Concept drawings, outline specification, cost plan 1, concept-stage carbon assessment | ~30% | G2 |
| 3 Spatial coordination / developed design | Coordinate the design spatially and confirm compliance | Coordinated models and drawings, developed specification, cost plan 2, consent submission | ~60% | G3 |
| 4 Technical design | Produce all information required to construct | Technical drawings, full specification, schedules, tender documentation | 100% | G4 |
| 5 Manufacturing and construction | Construct, supported by contractor design | Shop drawings, contractor design portions, AFC issue, as-built development | - | G5 |
| 6 Handover | Complete, commission and hand over | As-built information, O&M manuals, asset data | - | G6 |
| 7 Use | Operate, tune and review performance | Post-occupancy evaluation, performance review | - | G7 |

## 7.2  Design responsibility matrix

The design responsibility matrix records, element by element, who designs it, who checks it, who approves it and who warrants it. It is produced before the market approach and updated on award and on any novation.

| Element | Design by | Checked by | Approved by | Warranty / certification |
| --- | --- | --- | --- | --- |
| Architectural fabric and finishes |  |  |  |  |
| Structural frame and substructure |  |  |  |  |
| Geotechnical and civil works |  |  |  |  |
| Façade and building envelope |  |  |  |  |
| Mechanical services |  |  |  |  |
| Electrical services and power |  |  |  |  |
| Hydraulic and public health services |  |  |  |  |
| Fire engineering and life safety |  |  |  |  |
| Vertical transportation |  |  |  |  |
| Controls, BMS and digital systems |  |  |  |  |
| Security and access control |  |  |  |  |
| Specialist / process equipment |  |  |  |  |
| Temporary works |  |  |  |  |
| Landscape and external works |  |  |  |  |

## 7.3  Design brief and requirements traceability

Every requirement in the design brief is uniquely numbered and carries a source, a priority (mandatory / desirable) and an owner.

A requirements traceability matrix links each requirement to the design element that satisfies it, the verification method and the evidence at handover.

The matrix is reviewed at every design gate; a stage cannot be closed with unresolved mandatory requirements.

Changes to the brief are managed under Section 18, not by design development.

| Req ID | Requirement | Source | Priority | Satisfied by | Verification method | Status |
| --- | --- | --- | --- | --- | --- | --- |
| REQ-001 |  |  |  |  |  |  |
| REQ-002 |  |  |  |  |  |  |
| REQ-003 |  |  |  |  |  |  |
| REQ-004 |  |  |  |  |  |  |

## 7.4  Design review and approval

Guidance Design review is a control, not a courtesy. Set the review period, the comment format and the closure discipline in advance, and hold to them. Comments that are not closed with a documented response become claims and defects.

| Review type | Purpose | Participants | Timing | Output |
| --- | --- | --- | --- | --- |
| Brief compliance review | Confirm the design meets mandatory requirements | Design Manager, client user representatives | End of each stage | Compliance matrix |
| Technical / peer review | Confirm technical adequacy and standards compliance | Independent discipline reviewers | Stages 2, 3 and 4 | Review report and comment register |
| Interdisciplinary coordination review | Confirm the design is spatially and functionally coordinated | All disciplines, Information Manager | Every model federation cycle | Clash report |
| Buildability / constructability review | Confirm the design can be built safely, efficiently and in sequence | Contractor or construction adviser, HSE Manager | Stages 2, 3 and 4 | Buildability report |
| Safety in design review | Eliminate or reduce risk at source | Designers, HSE Manager, constructor, operator | Each stage and on material change | Design risk register |
| Operability and maintainability review | Confirm the asset can be operated and maintained | Operations, FM, commissioning | Stages 3 and 4 | Operability comments |
| Value management review | Confirm the design delivers required function at best value | Full team, facilitated | End of stages 2 and 3 | Value register |
| Statutory and consent review | Confirm compliance with approvals and codes | Planning Lead, certifier | Before submission and before AFC | Compliance statement |

Reviewers are given a defined review period - typically 10 working days for a stage deliverable and 5 for a package - measured from issue in the common data environment.

Comments are raised in a single consolidated comment register in the agreed format; comments raised outside the register are not actioned.

Each comment receives a documented response: accepted, accepted with amendment, or rejected with reason. Rejected comments are escalated to the Design Manager for resolution.

No design is issued for construction with open mandatory comments.

## 7.5  Design freeze and change discipline

Design freeze is applied progressively, element by element, as each reaches the maturity required by the procurement and construction programme. After freeze, any change requires a change request under Section 18 with a full impact assessment, regardless of whether the change is cost-neutral.

| Element / package | Freeze point | Freeze date | Approved by | Change after freeze requires |
| --- | --- | --- | --- | --- |
| Spatial layout and gross areas | End of stage 3 |  |  | Sponsor approval |
| Structural grid and load paths | End of stage 3 |  |  | Project Director approval |
| Façade system | Before façade procurement |  |  | Project Director approval |
| Services capacity and plant selection | Before services procurement |  |  | Project Manager approval |
| Room data and equipment schedules | Before fit-out procurement |  |  | Project Manager approval |
| Finishes and specification | Before AFC issue |  |  | Design Manager approval |

## 7.6  Value engineering and value management

Value management is applied at the end of stages 2 and 3 as a facilitated, function-led exercise - what must this element do, and what is the least-cost way of doing it to the required standard?

Value engineering proposals are recorded in a value register with the capital saving, the whole-of-life impact, the risk created and the programme impact.

No value engineering proposal is implemented without the designer's confirmation that performance requirements remain satisfied.

Proposals that reduce operational performance, maintainability or safety are rejected regardless of capital saving.

Accepted proposals are progressed as changes under Section 18.

| Ref | Proposal | Capital saving | Whole-of-life impact | Risk created | Decision | Date |
| --- | --- | --- | --- | --- | --- | --- |
| VE-01 |  |  |  |  |  |  |
| VE-02 |  |  |  |  |  |  |
| VE-03 |  |  |  |  |  |  |
| VE-04 |  |  |  |  |  |  |

## 7.7  Buildability and constructability

Construction expertise is brought into the design process no later than the end of stage 2, through early contractor involvement, a construction adviser or the client's own delivery experience.

Buildability reviews examine sequence, access, craneage, tolerances, temporary works, standardisation, off-site manufacture, and the practicality of the specified installation methods.

Findings are recorded and either designed out or accepted as a construction risk with an owner.

## 7.8  Design coordination and clash management

| Clash class | Definition | Resolution requirement | Owner |
| --- | --- | --- | --- |
| Class 1 - hard clash | Physical intersection of elements | Zero tolerance; resolved before the next federation cycle | Originating discipline |
| Class 2 - clearance clash | Insufficient clearance for installation, access or maintenance | Resolved before the stage gate | Design Manager |
| Class 3 - workflow clash | Sequence or constructability conflict | Resolved before the affected package is issued for construction | Contractor / Design Manager |
| Class 4 - information clash | Inconsistency between model, drawings and specification | Resolved before the deliverable is accepted | Information Manager |

Federated model coordination is run on a fixed cycle - typically fortnightly during stages 3 and 4 - with a published clash report, an assigned owner for each clash and a due date. Clash counts and closure rates are reported as a design health indicator.

## 7.9  Standards and codes compliance

The design must comply with the codes, standards and regulations applicable in the jurisdiction in which the works are constructed, and with any client standards specified in the brief. Record the governing edition of each standard at the point of design freeze; later editions do not apply retrospectively unless the applicable regulatory regime requires it.

| Discipline | Governing code / standard | Edition / date | Compliance evidence |
| --- | --- | --- | --- |

## 7.10  Design assurance and independent verification

Design assurance is proportionate to consequence: independent verification is mandatory for structural, geotechnical, fire engineering, façade and life-safety systems.

Independent verifiers are appointed directly by the client and are not subcontracted to the designer whose work they review.

Verification findings are categorised (critical / major / minor) and closed before the affected element is issued for construction.

Design certificates required in the applicable jurisdiction are collected progressively, not at handover.

## 7.11  Novation

Where consultants are novated to the contractor, the following must be settled before novation and recorded here: the scope and fee novated; the continuing duty of care and collateral warranties to the client; the status of design completed before novation; the client's right to be consulted on design changes after novation; and the arrangements for the client to retain independent design advice.

| Consultant | Novated? | Novation date | Retained client-side scope | Warranty in place |
| --- | --- | --- | --- | --- |

# 8.  Schedule management

## 8.1  Approach

Guidance State how the schedule is built, who owns it, and what makes it credible. A schedule that is not resource-loaded, logic-driven and regularly re-forecast is a picture, not a control. Name the software and the calendar conventions, because they determine what can be exchanged with contractors.

The project uses a critical path method schedule, developed from the work breakdown structure, resource-loaded at the level required for progress measurement, and maintained on a monthly update cycle with weekly short-interval control.

| Element | Detail |
| --- | --- |
| Scheduling software and version |  |
| Schedule owner | Planner, under the Project Manager |
| Calendar convention | Working days, [n]-day week, with declared public holidays and weather-affected calendars |
| Data date and update cycle | Monthly, data date on the [25th] |
| Progress measurement | Physical percent complete against defined rules of credit |
| Contractor programme submission | As required by the contract; reviewed within 10 working days |
| Schedule quality metrics | Logic density, open ends, negative float, constraint count, long durations, high float |
| Archive | Every accepted update is archived and retained for the life of the project plus the period required by the records policy |

## 8.2  Schedule levels

| Level | Name | Detail | Owner | Audience | Update cycle |
| --- | --- | --- | --- | --- | --- |
| 1 | Executive summary schedule | Phases and principal milestones on a single page | Project Manager | Board and Sponsor | Monthly |
| 2 | Management schedule | Work packages, key milestones, interfaces and dependencies | Planner | Project Control Group | Monthly |
| 3 | Control schedule | Deliverable-level activities, resource-loaded, fully logic-linked | Planner with package managers | Delivery team | Monthly, with weekly progress |
| 4 | Execution / look-ahead schedule | Task-level detail for the next 3-6 weeks, constraint-analysed | Contractor / package manager | Site team | Weekly |

## 8.3  WBS, OBS and CBS alignment

Schedule activities, cost accounts and organisational responsibilities are aligned through a single coding structure. Every Level 3 activity carries the WBS code, the control account code and the responsible organisation code, so that time and cost performance can be reported from the same source and reconciled.

WBS - what is being delivered (scope).

OBS - who is accountable for delivering it (organisation).

CBS - how it is funded and where cost is booked (cost).

The intersection of WBS and OBS defines the control account.

No activity may exist without a WBS code; no cost may be booked without a control account.

## 8.4  Baseline and rebaselining

The baseline schedule is approved at the delivery gate and is not changed except by approved change.

Progress is always reported against the current approved baseline and, where a rebaseline has occurred, also against the original baseline.

Rebaselining is permitted only where: an approved change materially alters the scope or completion date; the baseline has become meaningless as a measurement tool; or a new contract or phase is incorporated.

A rebaseline requires a documented reason, a comparison to the superseded baseline, and approval at the level set in Section 4.6.

Rebaselining does not extinguish the record of prior performance - the original baseline is retained and reported.

## 8.5  Key milestones

Guidance Milestones must be unambiguous, verifiable events with a single owner. 'Design complete' is not a milestone; 'Stage 4 technical design accepted by the Design Manager with zero open mandatory comments' is. Set a tolerance so the team knows when a slip becomes an escalation.

| Ref | Milestone | Definition of achievement | Planned date | Tolerance | Owner |
| --- | --- | --- | --- | --- | --- |
| M01 | PEP approved and delivery baseline set | Signed approval page |  | 0 days | Project Manager |
| M02 | Design brief approved | Sponsor sign-off of the requirements schedule |  | ±5 days | Design Manager |
| M03 | Concept design accepted (stage 2) | Board acceptance and cost plan 1 endorsed |  | ±10 days | Design Manager |
| M04 | Consent / development approval submitted | Lodgement receipt |  | ±5 days | Planning Lead |
| M05 | Developed design accepted (stage 3) | Gate G3 passed |  | ±10 days | Design Manager |
| M06 | Consent / development approval granted | Determination issued |  | Authority-dependent | Planning Lead |
| M07 | Main works tender released | Tender issued to the approved list |  | ±5 days | Commercial Manager |
| M08 | Technical design complete (stage 4) | 100% documentation accepted |  | ±10 days | Design Manager |
| M09 | Main works contract awarded | Contract executed by both parties |  | ±10 days | Commercial Manager |
| M10 | Site possession granted | Access certificate issued |  | 0 days | Project Manager |
| M11 | Start on site | Contractor mobilised and first permanent works activity started |  | ±5 days | Contractor |
| M12 | Enabling and demolition complete | Handover of cleared site accepted |  | ±10 days | Contractor |
| M13 | Substructure complete | Verified survey and structural certification |  | ±10 days | Contractor |
| M14 | Structure topped out | Final structural element placed |  | ±10 days | Contractor |
| M15 | Building weathertight | Envelope complete and verified by water test |  | ±10 days | Contractor |
| M16 | Permanent power energised | Utility connection live |  | ±15 days | Contractor |
| M17 | Services installation complete | All systems installed and pre-commissioned |  | ±10 days | Contractor |
| M18 | Commissioning start | Systems energised and static commissioning begun |  | ±5 days | Commissioning Manager |
| M19 | Integrated systems testing complete | All witnessed tests passed |  | ±10 days | Commissioning Manager |
| M20 | Regulatory occupation approval obtained | Certificate issued by the relevant authority |  | 0 days | Planning Lead |
| M21 | Practical completion / taking over | Certificate issued |  | 0 days | Client Representative |
| M22 | Operational readiness confirmed | Readiness checklist complete and accepted |  | 0 days | Operations Representative |
| M23 | Asset data and O&M handover accepted | Operations acceptance recorded |  | ±10 days | Information Manager |
| M24 | Defects liability period ends | Final defects certificate |  | 0 days | Project Manager |
| M25 | Final account agreed | Signed final account |  | ±20 days | Commercial Manager |
| M26 | Project closeout report approved | Sponsor approval |  | ±10 days | Project Manager |
| M27 | Post-implementation / benefits review complete | Review report accepted |  | ±20 days | Sponsor |

## 8.6  Critical path and float ownership

The critical path is identified in every schedule update and reported with the near-critical paths (typically activities with total float below 15 working days). Changes to the critical path between updates are explained in the narrative.

Float is a project resource, not the property of any one party, unless the contract expressly provides otherwise. State the contract position here once it is known.

Float is consumed on a first-come, first-served basis by whichever party needs it, and its consumption is reported.

Terminal float or a completion buffer, where used, is held by the Project Manager and released only by approved change.

Negative float is not permitted to persist: any negative float requires a recovery plan within 10 working days.

Constraints are minimised; every date constraint requires the Planner's documented justification.

## 8.7  Look-ahead programmes and short-interval control

A rolling 6-week look-ahead is produced weekly by each package, derived from and reconciled to the Level 3 schedule.

Every look-ahead activity is constraint-analysed: design, approval, material, labour, plant, access, permit and predecessor.

Percent plan complete (activities completed as promised divided by activities promised) is measured weekly as a leading indicator of schedule reliability, with reasons for non-completion recorded and trended.

## 8.8  Progress measurement

| Method | Applied to | Rules of credit |
| --- | --- | --- |
| Units complete | Repetitive physical work - piles, panels, fixtures | Credit proportional to verified installed quantity |
| Incremental milestone | Discrete deliverables with defined steps | Fixed percentages at defined steps, e.g. 20/50/80/100 |
| Start / finish | Short activities under one reporting period | 0% on start, 100% on completion |
| Weighted milestone | Engineering and design deliverables | Credit at issue for review, issue for coordination, issue for construction |
| Level of effort | Management, supervision and site facilities | Credit accrues with elapsed time; never used for physical work |
| Earned value / apportioned | Packages measured against a control account | Credit in proportion to the parent activity |

Physical percent complete claimed by a contractor is verified by the client team before it is accepted into the schedule or a payment valuation. Time-based or cost-based progress is not accepted as evidence of physical progress.

## 8.9  Schedule risk analysis

A quantitative schedule risk analysis is performed at the delivery gate, before award, and at least annually thereafter, or whenever the critical path changes materially.

Duration uncertainty is applied to the driving activities using three-point estimates, and discrete risk events from the risk register are mapped as probabilistic branches.

The output is a confidence-level completion date distribution; the committed date is set at an agreed confidence level (commonly P80 for external commitments and P50 for internal targets).

The difference between the deterministic date and the committed date establishes the schedule contingency, which is owned and released like cost contingency.

## 8.10  Delay and extension of time

Delay is notified in accordance with the contract's notice provisions; notice periods are recorded in the notices register in Section 17 and diarised.

Entitlement is assessed using a method appropriate to the circumstances - commonly time impact analysis for prospective assessment and as-planned versus as-built windows for retrospective assessment.

The contemporaneous records required to support or resist a claim - daily records, delay events, resource returns, weather records, progress photographs - are maintained from day one, not assembled after the event.

Concurrent delay is assessed in accordance with the contract and the principles applicable in the relevant jurisdiction.

Acceleration is only instructed in writing, with the cost and risk agreed before the acceleration begins wherever practicable.

## 8.11  Schedule reporting

| Report | Content | Frequency | Audience |
| --- | --- | --- | --- |
| Milestone status report | Planned, forecast and actual dates against tolerance | Monthly | Board |
| Critical path narrative | Current and near-critical paths, changes, drivers | Monthly | Control Group |
| Schedule performance report | SPI, float trend, milestone variance, recovery actions | Monthly | Control Group |
| Look-ahead and constraint report | 6-week look-ahead, constraints, percent plan complete | Weekly | Delivery team |
| Schedule quality report | Logic, open ends, constraints, negative float, out-of-sequence | Monthly | Planner and PM |
| Delay and EOT register | Notified events, status, assessed entitlement | Monthly | Commercial |

# 9.  Cost management

## 9.1  Approach

Guidance Cost control is the discipline of knowing, at any moment, what has been committed, what has been spent, what remains to be spent and what the project will finally cost. State how each of those four numbers is produced and by whom. If your forecast is derived from the budget rather than from the work remaining, you do not have a forecast.

Cost is controlled at the level of the control account: the intersection of a work breakdown element and an accountable organisation. Commitments are recorded when an order is placed, not when an invoice is received. The estimate at completion is rebuilt each month from actual cost to date plus an independently assessed cost to complete, and is reconciled to the previous month's forecast with every movement explained.

## 9.2  Cost breakdown structure

| Level | Element | Content | Owner |
| --- | --- | --- | --- |
| 1 | Total project cost | The full authorised investment | Sponsor |
| 2 | Cost category | Construction; design and consultancy; client costs; land and statutory; equipment; escalation; contingency | Commercial Manager |
| 3 | Package / control account | Aligned one-to-one with WBS Level 3 | Package Manager |
| 4 | Element / trade | Elemental or trade breakdown for estimating and benchmarking | Cost Manager |
| 5 | Cost item | Individual measured item or resource | Cost Manager |

## 9.3  Budget baseline and control accounts

| Control account | Scope | Owner | Approved budget | Committed | Actual to date | Forecast to complete | Forecast at completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CA-100 | Design and consultancy |  |  |  |  |  |  |
| CA-200 | Statutory approvals, fees and charges |  |  |  |  |  |  |
| CA-300 | Enabling works and demolition |  |  |  |  |  |  |
| CA-400 | Main construction works |  |  |  |  |  |  |
| CA-500 | Building services and specialist systems |  |  |  |  |  |  |
| CA-600 | Fit-out, furniture and equipment |  |  |  |  |  |  |
| CA-700 | Commissioning and operational readiness |  |  |  |  |  |  |
| CA-800 | Client-side project costs |  |  |  |  |  |  |
| CA-900 | Escalation allowance |  |  |  |  |  |  |
| CA-950 | Contingency |  |  |  |  |  |  |
| CA-980 | Management reserve |  |  |  |  |  |  |
|  | Total |  |  |  |  |  |  |

## 9.4  Estimating basis and classes of estimate

Every estimate records its basis: the documents relied on, the quantities source, the pricing date, the inclusions and exclusions, the assumptions, and the accuracy range. An estimate issued without a basis of estimate is not accepted into the cost plan.

| Class | Typical stage | Design maturity | Method | Expected accuracy |
| --- | --- | --- | --- | --- |
| Class 5 - order of magnitude | Strategic definition | 0-2% | Capacity factored, parametric, benchmark rates | -30% to +50% |
| Class 4 - concept / feasibility | Preparation and brief | 1-15% | Elemental rates, functional unit rates | -20% to +30% |
| Class 3 - budget / cost plan | Concept design | 10-40% | Elemental cost plan with measured principal quantities | -15% to +20% |
| Class 2 - control estimate | Developed design | 30-75% | Measured quantities with priced rates | -10% to +15% |
| Class 1 - check / tender estimate | Technical design | 65-100% | Fully measured bill or schedule of quantities | -5% to +10% |

## 9.5  Cost coding

Every cost transaction carries a control account code, a WBS code and a cost category code.

Codes are issued centrally by the Cost Manager and never reused.

Miscoded transactions are corrected in the period identified, with the correction disclosed in the cost report.

The cost coding structure is agreed with the client's finance function before the first commitment so that the project ledger and the corporate ledger reconcile.

## 9.6  Commitment and expenditure control

| Stage | Control | Owner | System record |
| --- | --- | --- | --- |
| Requisition | Confirm budget availability before any commitment is created | Package Manager | Requisition register |
| Approval | Approve within the delegation in Section 4.6 | Delegated approver | Approval record |
| Commitment | Raise the order or execute the contract; record the full committed value | Commercial Manager | Commitment register |
| Valuation | Assess work properly executed and materials on site | Cost Manager | Valuation record |
| Certification | Certify payment within the contractual timeframe | Client Representative | Payment certificate |
| Payment | Pay within the terms required by the contract and the applicable jurisdiction | Client finance | Ledger |
| Accrual | Recognise work done but not yet invoiced at each period end | Cost Manager | Cost report |
| Reconciliation | Reconcile the project cost report to the corporate ledger monthly | Cost Manager | Reconciliation statement |

## 9.7  Forecasting

The forecast is built from the bottom up each month. Cost to complete is assessed from the work remaining, the current rate of expenditure, known changes not yet approved, the risk exposure assessed in Section 10, and the escalation profile - not by subtracting actual cost from budget.

Each control account owner submits a cost to complete with a stated basis.

Approved changes are added to the budget; pending changes are shown separately as a forecast movement, never hidden in contingency.

The forecast is reconciled month on month: opening forecast, plus approved change, plus forecast movement, plus contingency drawdown, equals closing forecast. Every movement above the reporting threshold is explained by exception.

Trend analysis is applied to expenditure rate, change rate and contingency drawdown rate to identify deterioration before it reaches the forecast.

## 9.8  Earned value metrics

Guidance Use earned value only where physical progress can be measured objectively and the baseline is stable. Applied to an unstable baseline it produces confident nonsense. Where earned value is not appropriate, say so and state what is used instead.

| Metric | Formula | Interpretation |
| --- | --- | --- |
| Planned value (PV) | Budgeted cost of work scheduled | What the baseline said should have been done by now |
| Earned value (EV) | Budget at completion × physical percent complete | The budget value of what has actually been done |
| Actual cost (AC) | Cost actually incurred for the work performed | What has been spent to do it |
| Budget at completion (BAC) | Total approved budget for the control account | The approved cost baseline |
| Cost variance (CV) | CV = EV − AC | Positive is under budget; negative is over budget |
| Schedule variance (SV) | SV = EV − PV | Positive is ahead of plan; negative is behind |
| Cost performance index (CPI) | CPI = EV ÷ AC | Below 1.00 means every unit of work costs more than budgeted |
| Schedule performance index (SPI) | SPI = EV ÷ PV | Below 1.00 means work is being earned slower than planned |
| To-complete performance index (TCPI) | TCPI = (BAC − EV) ÷ (BAC − AC) | The efficiency required for the rest of the work to finish on budget |
| Estimate to complete (ETC) | ETC = (BAC − EV) ÷ CPI (or a bottom-up assessment) | The forecast cost of the work remaining |
| Estimate at completion (EAC) | EAC = AC + ETC; EAC = BAC ÷ CPI; EAC = AC + (BAC − EV) ÷ (CPI × SPI) | Forecast final cost - use the method matching the cause of variance |
| Variance at completion (VAC) | VAC = BAC − EAC | Forecast over- or under-run at completion |
| Percent complete | EV ÷ BAC × 100 | Budget-weighted physical progress |
| Percent spent | AC ÷ BAC × 100 | Compared with percent complete, exposes over-spend against progress |

Thresholds: a CPI or SPI below 0.95 at control account level requires a written variance explanation; below 0.90 requires a recovery plan approved by the Project Director. Favourable variances above 1.10 are investigated with equal rigour, as they usually indicate a measurement error.

## 9.9  Variation and change order pricing

| Priority | Pricing basis | When used |
| --- | --- | --- |
| 1 | Rates and prices in the contract | The changed work is of the same character and executed under similar conditions |
| 2 | Contract rates applied by analogy, adjusted for difference in character or conditions | Similar work but different quantity, location or timing |
| 3 | Fair valuation / reasonable cost plus the contractual margin | No comparable rate exists |
| 4 | Daywork or cost reimbursement against verified records | Work cannot be measured in advance; requires prior written authorisation and signed daily records |
| 5 | Competitive quotation from the supply chain | Specialist or subcontracted scope where market pricing is available |

Time-related and prolongation costs are assessed separately from direct cost and are only payable where an extension of time entitlement is established.

Overhead and profit are applied at the contractual percentage, not re-negotiated per change.

Omissions are valued on the same basis as additions, including the removal of associated preliminaries where the omission changes the duration.

No variation is instructed without an approved budget source identified.

## 9.10  Payment and valuation cycle

| Day | Activity | Responsible |
| --- | --- | --- |
| Day 1 (25th of month) | Valuation cut-off; contractor submits the payment claim with supporting measure | Contractor |
| Days 2-3 | Joint site measure and assessment of work properly executed | Cost Manager and contractor |
| Day 4 | Assessment of materials on site, off-site materials and vesting | Cost Manager |
| Day 5 | Assessment of variations, claims and retention | Commercial Manager |
| Day 6 | Recommendation prepared and reviewed | Cost Manager |
| Day 7-8 | Payment certificate issued within the contractual timeframe | Client Representative |
| Per contract | Payment made within the period required by the contract and the applicable jurisdiction | Client finance |
| Ongoing | Payment to subcontractors and suppliers in accordance with flow-down obligations and any statutory security of payment regime applicable in the jurisdiction | Contractor |

## 9.11  Cash flow, escalation and currency

An S-curve cash flow forecast is produced from the resource-loaded schedule and updated monthly; actual against forecast drawdown is reported and explained.

Funding drawdown requirements are advised to the client's finance function at least one quarter in advance.

Escalation is estimated using published cost indices appropriate to the market and asset type, applied to the expenditure profile rather than to the total, and reviewed at least every six months.

Where any element of cost is denominated in a foreign currency, the exposure, the hedging position and the rate assumed in the budget are recorded and reported; unhedged exposure is carried as a risk in the risk register.

Interest, financing and holding costs, where they form part of the investment, are forecast alongside capital cost.

| Period | Forecast expenditure | Cumulative forecast | Actual | Cumulative actual | Variance | Comment |
| --- | --- | --- | --- | --- | --- | --- |

## 9.12  Contingency and management reserve

Guidance Contingency is not a slush fund and it is not the contractor's. It exists to fund identified risk within the delivery team's control, it is drawn down against a specific risk closing, and the remaining balance must always be defensible against the remaining risk exposure. Plot planned versus actual drawdown from day one - a contingency consumed faster than the programme is the earliest reliable signal of trouble.

| Reserve | Purpose | Held by | Released by | Basis |
| --- | --- | --- | --- | --- |
| Package allowance | Known unknowns within a package, e.g. provisional items | Package Manager | Project Manager | Elemental assessment |
| Project contingency | Identified risks within the Project Manager's control | Project Manager | Project Director | Quantitative risk analysis, typically to P50-P80 |
| Escalation allowance | Market movement over the expenditure profile | Commercial Manager | Project Director | Indexed forecast |
| Management reserve | Unknown unknowns and scope emergent beyond the approved baseline | Sponsor | Project Board | Portfolio-level policy |

| Ref | Date | Risk / reason | Amount | Balance remaining | Approved by |
| --- | --- | --- | --- | --- | --- |
| CD-01 |  |  |  |  |  |
| CD-02 |  |  |  |  |  |
| CD-03 |  |  |  |  |  |
| CD-04 |  |  |  |  |  |
| CD-05 |  |  |  |  |  |

## 9.13  Cost reporting suite

| Report | Content | Frequency | Audience |
| --- | --- | --- | --- |
| Cost summary report | Budget, commitment, actual, forecast and variance by control account | Monthly | Board and Control Group |
| Change and variation report | Approved, pending and rejected change with cumulative impact | Monthly | Control Group |
| Contingency drawdown report | Drawdown against plan and against remaining risk exposure | Monthly | Control Group and Sponsor |
| Cash flow report | Forecast versus actual drawdown, funding requirement | Monthly | Client finance |
| Earned value report | CPI, SPI, TCPI, EAC and VAC with variance narrative | Monthly | Control Group |
| Final account status | Agreed, in negotiation and disputed values | Monthly from practical completion | Commercial and Sponsor |

# 10.  Risk and opportunity management

## 10.1  Approach

Guidance Align the process to ISO 31000: establish the context, identify, analyse, evaluate, treat, then monitor, review, communicate and consult throughout. The test of a risk process is not the size of the register - it is whether treatments actually change the project's exposure. Retire risks that have passed and close treatments that have been done.

Risk management is integrated with cost, schedule and change control. The risk register informs contingency; contingency drawdown closes risks; realised risks become issues and are managed to closure. Opportunities are managed with the same rigour as threats.

## 10.2  Risk appetite and tolerance

| Category | Appetite | Tolerance statement |
| --- | --- | --- |
| Safety and health | Averse | No tolerance for any risk of serious injury or fatality. Work stops until the risk is eliminated or controlled to as low as reasonably practicable. |
| Statutory and regulatory compliance | Averse | No tolerance for non-compliance. Any potential breach is escalated immediately. |
| Cost | Cautious | Accept exposure within the approved contingency. Escalate any single risk with an expected value above [X] or aggregate exposure above the remaining contingency. |
| Schedule | Cautious | Accept the consumption of float on non-critical paths. Escalate any risk that could delay a contractual milestone. |
| Quality and technical performance | Cautious | Accept innovation where independently verified. No tolerance for departures from mandatory performance requirements. |
| Environment | Averse | No tolerance for a reportable environmental incident or a breach of consent conditions. |
| Reputation and stakeholder | Cautious | Accept short-term criticism arising from unavoidable disruption where it is properly notified and managed. |
| Commercial and contractual | Balanced | Accept risk that the project is better placed to manage than the market, priced accordingly. |
| Innovation and new technology | Open | Accept where proven alternatives exist as a fallback and the failure mode is not safety-critical. |

## 10.3  Risk breakdown structure

| Level 1 | Level 2 categories |
| --- | --- |
| Strategic | Business case validity; funding; political and policy change; portfolio dependency; benefits |
| Commercial | Market capacity; tender price; contractor solvency; claims and disputes; escalation; currency |
| Design and technical | Brief change; design completeness; coordination; interface; technology; standards change |
| Construction | Productivity; workmanship; temporary works; plant and equipment; logistics; sequencing |
| Site and ground | Ground conditions; contamination; groundwater; unexploded ordnance; unrecorded services; archaeology |
| External | Weather and climate; utility providers; adjacent projects; supply chain disruption; industrial action |
| Statutory and approvals | Consent conditions; approval delay; regulatory change; certification |
| Health and safety | High-risk activities; public interface; asbestos and hazardous materials; working at height |
| Environmental and social | Contamination; ecology; heritage; noise and dust; community opposition |
| Organisational | Key person dependency; resource availability; capability; governance and decision latency |
| Information and digital | Data loss; cyber security; model quality; system interoperability |
| Operational | Operability; asset data completeness; operational readiness; transition to service |

## 10.4  Likelihood scale

| Rating | Descriptor | Qualitative definition | Indicative probability | Indicative frequency |
| --- | --- | --- | --- | --- |
| 5 | Almost certain | Expected to occur in most circumstances; already occurring elsewhere on the project | >80% | More than once per quarter |
| 4 | Likely | Will probably occur; has occurred on comparable projects | 50-80% | Once per quarter |
| 3 | Possible | Might occur; credible pathway exists | 20-50% | Once per year |
| 2 | Unlikely | Could occur but is not expected | 5-20% | Once in the project life |
| 1 | Rare | Only in exceptional circumstances | <5% | Less than once in the project life |

## 10.5  Consequence scales

Guidance Calibrate the cost and time thresholds to your project's size. A consequence table copied from another project is the fastest way to produce a register full of medium risks that nobody acts on. As a rule of thumb, 'catastrophic' cost should be set near the point at which the business case fails.

| Rating | Cost | Time | Safety and health | Environment | Reputation and stakeholder | Quality and performance |
| --- | --- | --- | --- | --- | --- | --- |
| 5 Catastrophic | >10% of project cost or exceeds total contingency | >6 months delay to a contractual milestone | Fatality or permanent disabling injury | Major long-term harm; prosecution; licence revoked | Sustained national coverage; loss of licence to operate | Asset cannot meet its functional purpose; rebuild required |
| 4 Major | 5-10% of project cost | 3-6 months delay | Serious injury requiring hospitalisation; notifiable incident | Significant harm; enforcement notice; remediation required | Regional coverage; formal complaint by a major stakeholder | Major rework; performance materially below requirement |
| 3 Moderate | 2-5% of project cost | 1-3 months delay | Lost time injury; medical treatment injury | Moderate, reversible harm; reportable to the regulator | Local coverage; multiple sustained complaints | Significant rework; performance below target but acceptable |
| 2 Minor | 0.5-2% of project cost | 2-4 weeks delay | First aid injury; near miss with serious potential | Minor, contained and quickly reversible harm | Isolated complaints resolved locally | Local rework within the programme |
| 1 Insignificant | <0.5% of project cost | <2 weeks delay | No injury; hazard identified and controlled | Negligible effect within the site boundary | No external interest | Minor defect corrected in normal work |

## 10.6  Risk matrix

Inherent risk is rated before treatment; residual risk is rated assuming planned treatments are fully implemented. Both are recorded. The rating drives the escalation and review requirements in Section 10.10.

| Likelihood ↓ / Consequence → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Catastrophic |
| --- | --- | --- | --- | --- | --- |
| 5 Almost certain | Medium | High | High | Extreme | Extreme |
| 4 Likely | Medium | Medium | High | High | Extreme |
| 3 Possible | Low | Medium | Medium | High | Extreme |
| 2 Unlikely | Low | Low | Medium | High | High |
| 1 Rare | Low | Low | Low | Medium | High |

| Rating | Meaning | Owner | Review | Action required |
| --- | --- | --- | --- | --- |
| Extreme | Unacceptable; threatens project objectives | Sponsor | Fortnightly | Immediate treatment plan; escalate to the Board at the next meeting or sooner |
| High | Requires active management and senior attention | Project Director | Monthly | Treatment plan with funded actions and dates; reported to the Board |
| Medium | Manage by routine process | Project Manager | Monthly | Treatment assigned; monitored at the Control Group |
| Low | Tolerable | Package Manager | Quarterly | Monitor; treat if cost-effective |

## 10.7  Risk assessment and treatment process

Establish context - confirm objectives, criteria and the scope of the assessment before identifying risk.

Identify - through workshops, checklists, prior-project lessons, design reviews, contractor input and assurance findings. Risks are written as cause, event and consequence.

Analyse - assess inherent likelihood and consequence, identify existing controls, and test whether those controls are actually operating.

Evaluate - compare the residual rating against appetite and tolerance to decide whether treatment is required.

Treat - select from avoid, reduce (likelihood or consequence), transfer (contract or insurance), or accept with a documented rationale. Every treatment has an owner, a due date and a cost.

Monitor and review - at the cadence set by the rating, with the register audited quarterly for quality, not just currency.

Communicate and consult - risk is a standing item at every governance forum, and material risks are shared with the parties best placed to manage them.

## 10.8  Risk register structure

| Field | Content |
| --- | --- |
| Risk ID and category | Unique reference and risk breakdown structure category |
| Risk description | Cause → event → consequence, written so a reader outside the project understands it |
| Date raised and raised by | Traceability of origin |
| Risk owner | The single person accountable for managing the risk - never a team |
| Existing controls | What is already in place and whether it is verified as effective |
| Inherent likelihood, consequence and rating | Before treatment |
| Treatment strategy and actions | Avoid / reduce / transfer / accept, with specific actions |
| Action owner and due date | One owner per action |
| Treatment cost | Cost of implementing the treatment |
| Residual likelihood, consequence and rating | After treatment is fully implemented |
| Expected cost and time impact | Probability × consequence, feeding quantitative analysis |
| Proximity | When the risk could realistically occur |
| Status and trend | Open / treated / realised / closed; increasing, stable or decreasing |
| Linked issue or change reference | Where a risk has been realised |

## 10.9  Quantitative risk analysis and contingency

Quantitative cost and schedule risk analysis is performed at the delivery gate, before contract award, and at least annually thereafter.

Modelling combines uncertainty ranges on base estimate elements with discrete risk events from the register, with correlation applied between related elements.

The output is a cumulative probability distribution; contingency is set at the confidence level directed by the client's policy - commonly P50 for the delivery contingency and P80 for the total investment envelope.

The tornado diagram identifies the small number of drivers that dominate the exposure; management attention is directed to those drivers.

Contingency adequacy is re-tested every time the residual exposure changes materially, and the result is reported alongside the drawdown position in Section 9.12.

## 10.10  Escalation thresholds and review cadence

| Trigger | Escalate to | Timeframe |
| --- | --- | --- |
| Any new risk rated Extreme | Sponsor and Project Board | Within 2 working days |
| Any risk rated High that increases in rating | Project Director | Within 5 working days |
| Aggregate residual exposure exceeding remaining contingency | Sponsor | At the next monthly report or immediately if material |
| A risk realised with impact above the change authority limit | Per Section 4.6 | Immediately |
| Any safety, environmental or compliance risk rated High or above | HSE Manager and Project Director | Immediately |
| Treatment action overdue by more than 20 working days | Project Manager, then Project Director | At the monthly review |

## 10.11  Opportunity management

Opportunities are recorded in the same register with a positive consequence scale and are managed through exploit, enhance, share or accept strategies. Realised opportunity value is reported separately and is not automatically absorbed into the forecast - the Sponsor decides whether it is returned, reinvested in scope, or held against risk.

| Ref | Opportunity | Owner | Strategy | Potential value | Action | Status |
| --- | --- | --- | --- | --- | --- | --- |
| OPP-01 |  |  |  |  |  |  |
| OPP-02 |  |  |  |  |  |  |
| OPP-03 |  |  |  |  |  |  |
| OPP-04 |  |  |  |  |  |  |

## 10.12  Insurance

Guidance Confirm who places each policy, who is named as insured, the sums insured, the deductibles and - critically - the period of cover, including the tail after practical completion. Insurance is not risk treatment; it is financial recovery after the risk has already damaged the project.

| Policy | Placed by | Insured parties | Sum insured / limit | Deductible | Period of cover |
| --- | --- | --- | --- | --- | --- |
| Contract works / construction all risks |  |  |  |  |  |
| Public and products liability |  |  |  |  |  |
| Professional indemnity (design) |  |  |  |  |  |
| Workers compensation / employers liability |  |  |  |  |  |
| Plant and equipment |  |  |  |  |  |
| Marine and transit |  |  |  |  |  |
| Delay in start-up / advance loss of profits |  |  |  |  |  |
| Environmental impairment liability |  |  |  |  |  |
| Latent defects / decennial (if applicable) |  |  |  |  |  |
| Cyber liability |  |  |  |  |  |

# 11.  Quality management

## 11.1  Quality policy and objectives

Guidance Quality on a construction project means one thing: what is built matches what was specified, and there is evidence to prove it. State the objectives in terms of verifiable outcomes - closed ITPs, zero open non-conformances at completion, first-time pass rates - not aspirations about excellence.

| Quality objective | Measure | Target |
| --- | --- | --- |
| Work conforms to specification first time | First-time inspection pass rate | ≥95% |
| Non-conformances are closed promptly | NCRs open beyond 20 working days | 0 |
| No defective work is concealed | Hold points released before cover-up | 100% |
| Handover is clean | Category A defects open at practical completion | 0 |
| Materials are as specified | Approved material submissions before order | 100% |
| Records are complete | ITP and test records available at handover | 100% |
| Repeat defects are eliminated | Recurring NCRs of the same cause | 0 |

## 11.2  Quality management system alignment

The project quality system aligns to ISO 9001 principles and to the client's quality framework. Every consultant, contractor and significant supplier maintains a quality management system that is reviewed and accepted before mobilisation, and a project-specific quality plan that is accepted before the commencement of their work.

Contractor and consultant quality plans are submitted within 20 working days of award and accepted before work begins.

Acceptance of a quality plan does not transfer responsibility for quality to the client.

Quality requirements flow down to every tier of the supply chain.

The client reserves the right to audit any party's quality system at any time.

## 11.3  Quality planning

Quality requirements are established at design stage through the specification, and are testable - a requirement that cannot be verified is rewritten.

Critical quality characteristics are identified for each element and are the focus of inspection and testing effort.

Quality risk is assessed alongside project risk: new methods, new materials, unfamiliar suppliers and concealed work all warrant increased surveillance.

## 11.4  Inspection and test plans

An inspection and test plan (ITP) is prepared for every work activity where conformance must be demonstrated. The ITP is the sequenced record of what is inspected, against what criterion, by whom, with what evidence, and at what verification level.

| ITP field | Requirement |
| --- | --- |
| Activity and reference | Unique ITP number tied to the WBS and specification clause |
| Inspection or test step | Sequenced, matching the construction method |
| Acceptance criteria | The specification clause, standard or drawing reference and the numeric tolerance |
| Verification level | Hold point (H), witness point (W), surveillance (S) or review of records (R) |
| Responsible party | Who performs the inspection or test |
| Verifying party | Contractor, client, designer, certifier or independent testing authority |
| Record / evidence | Checksheet, test certificate, survey, photograph, calibration record |
| Sign-off | Name, signature and date of each party at each point |

## 11.5  Hold and witness points

| Type | Definition | Notice period | Consequence of proceeding without release |
| --- | --- | --- | --- |
| Hold point (H) | Work must not proceed past this point until the nominated party has inspected and released it in writing | Minimum 48 hours' written notice | Work is opened up at the contractor's cost; NCR raised |
| Witness point (W) | The nominated party is entitled to attend; work may proceed if they do not attend within the notice period | Minimum 24 hours' written notice | Work may proceed; attendance waived and recorded |
| Surveillance (S) | Random or planned monitoring without a mandatory stop | No notice required | Not applicable |
| Review of records (R) | Verification by examination of documentation | On submission | Deliverable not accepted |

Typical mandatory hold points include: foundation excavation before pour; reinforcement before concealment; waterproofing before covering; structural connections before encasement; fire-stopping before ceiling closure; services before concealment; and any safety-critical element identified in the design risk register.

## 11.6  ITP approval process

ITPs are submitted at least 15 working days before the affected work begins.

The Quality Manager reviews for completeness, correct acceptance criteria and appropriate verification levels; the designer confirms the criteria where the element is design-critical.

The client inserts its own hold and witness points before acceptance.

No work covered by an ITP starts until the ITP is accepted.

Signed ITPs are lodged in the common data environment progressively - not at completion - and form part of the handover record.

## 11.7  Non-conformance and corrective action

| Step | Action | Owner | Timeframe |
| --- | --- | --- | --- |
| 1 Identify | Raise an NCR describing the non-conformance and the requirement not met | Any party | Within 1 working day of identification |
| 2 Contain | Stop related work; prevent the non-conformance propagating | Contractor | Immediately |
| 3 Assess | Determine extent - is this isolated or systemic? | Quality Manager | Within 3 working days |
| 4 Propose disposition | Rework to specification, repair to an approved method, use-as-is with designer concurrence, or reject and replace | Contractor | Within 5 working days |
| 5 Approve disposition | Designer approves any use-as-is or repair; client approves any departure | Designer and Client Representative | Within 5 working days |
| 6 Implement and verify | Carry out the disposition and re-inspect | Contractor and Quality Manager | Per agreed plan |
| 7 Root cause and corrective action | Identify the cause and change the process so it cannot recur | Contractor | Within 15 working days |
| 8 Close | Verify effectiveness and close the NCR with evidence | Quality Manager | On verification |

NCR trends are reported monthly by cause, by trade and by package. A use-as-is disposition is a departure from specification and must be recorded in the departures register and disclosed at handover.

## 11.8  Audit and surveillance programme

| Audit | Scope | Frequency | Auditor | Reported to |
| --- | --- | --- | --- | --- |
| Contractor quality system audit | Compliance with the accepted quality plan | Within 3 months of mobilisation, then 6-monthly | Quality Manager | Control Group |
| ITP compliance audit | Are ITPs being followed and signed in real time? | Monthly | Quality Manager | Control Group |
| Materials and traceability audit | Are materials as approved and traceable? | Quarterly | Quality Manager | Control Group |
| Design compliance audit | Does construction match the AFC documentation? | At each major element | Design Manager | Control Group |
| Subcontractor surveillance | Off-site fabrication and specialist installation | Per fabrication programme | Quality Manager / third party | Project Manager |
| Records audit | Completeness of quality records against the handover requirement | Quarterly, monthly from 6 months before completion | Information Manager | Project Manager |
| Independent technical audit | Client-commissioned review of high-consequence elements | At stage gates | Independent | Sponsor |

## 11.9  Materials approval and samples

Every specified material, product and system requires an approved submission before order. Submissions include compliance evidence, certification, warranty terms, sustainability data and maintenance requirements.

Substitutions are treated as design changes and require designer approval and, where they affect performance, client approval under Section 18.

Samples are retained on site in a controlled sample store and are the reference standard for acceptance of installed work.

Material traceability is maintained for structural, fire-rated, pressure-retaining and safety-critical products.

## 11.10  Benchmarks and mock-ups

Benchmark installations and full-size mock-ups are constructed before production for elements where appearance, workmanship or performance cannot be judged from a sample. Once approved, the benchmark is the acceptance standard and is protected and retained until the element is complete.

| Element | Benchmark / mock-up type | Approval required from | Retain until |
| --- | --- | --- | --- |
| Façade system (visual and performance) | Full-size test mock-up |  |  |
| External wall and roof waterproofing | In-situ benchmark |  |  |
| Typical room / apartment / ward | Full fit-out benchmark |  |  |
| Exposed concrete and finishes | Sample panel |  |  |
| Feature joinery and stone | Physical sample and benchmark |  |  |
| Services in exposed areas | Benchmark installation |  |  |

## 11.11  Testing and commissioning interface

Quality verification and commissioning are sequential and interdependent: no system enters commissioning until its installation ITPs are complete and its NCRs are closed. The commissioning strategy is set out in Section 20.

## 11.12  Quality records and traceability

Quality records are created at the point of inspection and uploaded to the common data environment within 5 working days.

Records are indexed to the asset structure so that any element can be traced to its approval, material, installation and test record.

Records are retained for the period required by the contract, the client's records policy and the applicable jurisdiction.

## 11.13  Quality reporting

| Metric | Definition | Target | Frequency |
| --- | --- | --- | --- |
| First-time pass rate | Inspections passed without rework ÷ total inspections | ≥95% | Monthly |
| Open NCRs | NCRs raised and not closed | Downward trend | Monthly |
| NCR ageing | NCRs open more than 20 working days | 0 | Monthly |
| Hold point compliance | Hold points released before work proceeded ÷ total hold points | 100% | Monthly |
| ITP currency | Signed ITP records lodged within 5 working days | ≥95% | Monthly |
| Repeat non-conformance | NCRs with a cause already recorded | 0 | Monthly |
| Defects at completion | Open defects by category at practical completion | 0 Category A | At completion |

# 12.  Health, safety and wellbeing

## 12.1  Policy and framework

Guidance Describe the safety management system, not the sentiment. Reference the duties applicable in the relevant jurisdiction generically - duties of the client or appointing party, the designer, the principal contractor and the worker - and state how each is discharged on this project. Safety obligations cannot be delegated by contract.

The project's health, safety and wellbeing arrangements align to ISO 45001 principles and to the client's safety management system. All parties comply with the work health and safety duties applicable in the jurisdiction in which the works are carried out. Where this plan and a statutory duty differ, the statutory duty prevails.

The overriding principle is that risk is eliminated at source wherever reasonably practicable, and where it cannot be eliminated, it is minimised through the hierarchy of control - elimination, substitution, isolation, engineering controls, administrative controls, and personal protective equipment as the last resort.

## 12.2  Duties and appointments

| Party | Generic duty | Discharged on this project by |
| --- | --- | --- |
| Client / appointing party | Make suitable arrangements for managing the project, allow adequate time and resources, and provide pre-construction information | Project Director, supported by the HSE Manager |
| Designer | Eliminate foreseeable risk in design so far as is reasonably practicable and inform others of residual risk | Lead Designer, through the design risk register and safety in design reviews |
| Principal designer / design coordinator | Plan, manage and coordinate health and safety in the pre-construction phase | Design Manager |
| Principal contractor | Plan, manage and coordinate health and safety in construction; control the site | Contractor's Project Manager |
| Contractors and subcontractors | Plan and carry out their own work safely and cooperate with others | Each contractor |
| Workers | Take reasonable care, follow instruction, report hazards and stop unsafe work | All personnel |
| Suppliers and manufacturers | Provide safe plant, substances and structures with adequate information | Each supplier |

## 12.3  Safety in design

Safety in design workshops are held at the end of each design stage and whenever a material design change is proposed.

The design risk register records each hazard, the design response, the residual risk and the information passed to those who will construct, operate, maintain and eventually demolish the asset.

Residual design risks that cannot be eliminated are formally communicated to the contractor before construction and to the operator before handover.

Design decisions that increase construction, maintenance or demolition risk require documented justification and Project Director endorsement.

Particular attention is given to: work at height, fragile surfaces, confined spaces, lifting, hazardous substances, façade and plant access, roof and atrium maintenance, and the safety of the public interface.

## 12.4  Safety management plan requirements

The principal contractor prepares a construction phase health and safety plan, accepted before site mobilisation, covering as a minimum:

Site rules, access control, security and segregation of the public and site traffic.

Organisation, competence, supervision ratios and safety leadership expectations.

Hazard identification and risk assessment methodology and the safe work method statement regime for high-risk work.

Traffic and pedestrian management, both on site and on the surrounding network.

Temporary works design, checking and permit regime.

Plant and equipment management, inspection and operator competence.

Emergency preparedness, first aid, rescue plans and evacuation.

Health monitoring, hazardous substance control and exposure management.

Consultation, worker representation and issue resolution.

Incident reporting, investigation and corrective action.

Audit, inspection and assurance programme.

Interfaces with an operational asset, if the site adjoins one.

## 12.5  High-risk activities and permits

| High-risk activity | Control requirement | Permit required |
| --- | --- | --- |
| Work at height and on fragile surfaces | Safe work method statement; edge protection; fall arrest as last resort | Yes - height permit |
| Excavation and trenching | Ground support design; services location and proving; access and egress | Yes - excavation permit |
| Confined space entry | Atmospheric testing; standby person; rescue plan; communications | Yes - confined space permit |
| Hot works | Fire watch; combustible clearance; extinguishers; post-work monitoring | Yes - hot work permit |
| Live electrical work and energisation | Isolation and lock-out/tag-out; competent person; testing before touching | Yes - electrical permit |
| Lifting operations and craneage | Lift study; certified equipment and riggers; exclusion zones; wind limits | Yes - lift permit |
| Demolition and structural alteration | Engineered demolition plan; hazardous material clearance; exclusion zones | Yes |
| Asbestos and hazardous materials | Survey; licensed removal; clearance certificate | Yes |
| Work adjacent to live traffic or rail | Third-party approval; protection; competent controllers | Yes |
| Services isolation and shutdown | Isolation plan; stakeholder notification; proving dead | Yes - isolation permit |
| Temporary works | Independent design check; erection and dismantling supervision; load restriction | Yes - permit to load |
| Work over or near water | Rescue provision; personal flotation; exclusion | Yes |

## 12.6  Induction, competency and consultation

No person enters the site without completing the project induction, which is recorded and refreshed at the interval set in the safety plan.

Competency, licences and tickets for high-risk work are verified before the work begins and are held in a competency register.

Task-specific inductions are given before any worker undertakes a new high-risk activity or enters a new work area.

Health and safety representatives are elected in accordance with the requirements applicable in the jurisdiction, and issue resolution follows the prescribed procedure.

Every worker has, and is regularly reminded of, the authority to stop work they believe is unsafe, without any adverse consequence.

## 12.7  Incident reporting and investigation

| Event | Immediate action | Notify | Timeframe | Investigation |
| --- | --- | --- | --- | --- |
| Fatality or life-threatening injury | Make safe; preserve the scene; do not disturb | Regulator (as required in the jurisdiction), client executive, Sponsor | Immediately | Independent, with the regulator |
| Notifiable / serious incident | Make safe; preserve the scene | Regulator as required; Project Director; Sponsor | Immediately, and in writing within the prescribed period | Formal investigation within 48 hours |
| Lost time injury | Treat; secure the area | HSE Manager; Project Manager | Within 4 hours | Formal, within 5 working days |
| Medical treatment / first aid injury | Treat; secure the area | HSE Manager | Same day | Supervisor-level review |
| High-potential near miss | Make safe | HSE Manager; Project Manager | Same day | Investigated as if the harm had occurred |
| Environmental incident | Contain; stop the source | Environmental Lead; regulator as required | Immediately | Formal investigation |
| Property or plant damage | Make safe; isolate | HSE Manager | Same day | Proportionate to consequence |

Investigations use a structured root cause method and examine systemic and organisational factors, not only worker behaviour. Corrective actions are assigned, tracked to closure and verified for effectiveness. Lessons are shared across the project and with the client's wider portfolio within 10 working days.

## 12.8  Emergency preparedness

An emergency response plan is prepared before mobilisation and covers fire, medical emergency, rescue from height and confined space, structural collapse, services strike, hazardous release, severe weather and security threat.

Emergency arrangements are coordinated with the emergency services and, where the site adjoins an operating asset, with the asset operator.

Emergency drills are conducted at least quarterly and after any major change to the site layout, and are debriefed with actions recorded.

Emergency contact details, assembly points and rescue provisions are displayed at every site entrance and in every work area.

## 12.9  Safety performance indicators

| Type | Indicator | Definition | Target | Frequency |
| --- | --- | --- | --- | --- |
| Lead | Safety interactions / observations | Documented conversations per 100 workers per week | ≥10 | Weekly |
| Lead | Hazard reports closed | Hazards closed ÷ hazards raised | ≥95% within 10 days | Weekly |
| Lead | Inspection completion | Planned inspections completed ÷ planned | 100% | Monthly |
| Lead | SWMS / permit compliance | Audited activities compliant ÷ audited | ≥98% | Monthly |
| Lead | Training currency | Personnel with current required competencies | 100% | Monthly |
| Lead | Corrective action closure | HSE actions closed by due date | ≥95% | Monthly |
| Lag | Total recordable injury frequency rate (TRIFR) | Recordable injuries × 1,000,000 ÷ hours worked | Below the client portfolio benchmark | Monthly |
| Lag | Lost time injury frequency rate (LTIFR) | Lost time injuries × 1,000,000 ÷ hours worked | 0 | Monthly |
| Lag | Severity rate | Days lost × 1,000,000 ÷ hours worked | Downward trend | Monthly |
| Lag | High-potential incidents | Count of incidents with potential for serious harm | 0 | Monthly |
| Lag | Notifiable incidents | Count reportable to the regulator | 0 | Monthly |
| Lag | Enforcement actions | Notices issued by a regulator | 0 | Monthly |

## 12.10  Assurance and audit

Client-led HSE audits are conducted at least quarterly, and within one month of mobilisation of any new principal contractor.

Executive safety walks are undertaken monthly by the Project Director and at least quarterly by the Sponsor.

Findings are rated by consequence, assigned an owner and a due date, and tracked to verified closure.

Repeat or systemic findings trigger a formal review of the contractor's management system and, where necessary, a stop-work.

## 12.11  Wellbeing, mental health and fatigue

Mental health is managed as a project risk, not a welfare afterthought. Support arrangements, including confidential counselling access, are made available to all personnel including subcontractors.

Trained mental health first aiders are appointed in proportion to the workforce, and their identity is publicised on site.

Working hours, roster patterns and travel time are monitored against defined fatigue limits; extended shifts and consecutive days worked require documented approval and a fatigue risk assessment.

Fatigue is treated as a hazard in its own right and is considered in shift planning, night work, and after significant overtime or acceleration.

Welfare facilities - amenities, rest areas, drinking water, shade and climate protection - are provided in proportion to the workforce and the climate.

Bullying, harassment and discrimination are managed under a stated policy with a confidential reporting channel and defined consequences.

Wellbeing indicators - participation rates, absenteeism, turnover, and anonymous pulse surveys - are reported alongside safety indicators.

# 13.  Environmental, social and sustainability management

## 13.1  Approach

Guidance Set out the environmental management system, the approvals that constrain the works, and the sustainability outcomes the project has committed to. Every commitment must have a measurement method and an owner - an unmeasured target is a future audit finding.

Environmental management aligns to ISO 14001 principles. Sustainability outcomes are pursued through design, procurement and construction practice, and are measured and reported with the same discipline as cost and schedule.

## 13.2  Environmental management plan requirements

A construction environmental management plan is prepared by the contractor and accepted before site mobilisation.

It addresses, as a minimum: consent and permit conditions; erosion and sediment control; water quality and discharge; noise and vibration; air quality and dust; contaminated land and acid sulphate soils; hazardous materials; waste and resource recovery; flora, fauna and habitat; heritage and cultural sites; and incident and emergency response.

Sub-plans are prepared where a consent condition or a specific risk requires them.

Environmental monitoring is conducted at the frequency and locations required by the consent conditions, with results reported and exceedances notified.

## 13.3  Approvals and permits register

| Ref | Approval / permit | Issuing authority | Application date | Granted | Expiry | Key conditions | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AP01 | Planning / development consent |  |  |  |  |  |  |
| AP02 | Building / construction permit |  |  |  |  |  |  |
| AP03 | Environmental licence or approval |  |  |  |  |  |  |
| AP04 | Vegetation removal / tree permit |  |  |  |  |  |  |
| AP05 | Heritage or cultural approval |  |  |  |  |  |  |
| AP06 | Water take, discharge or dewatering |  |  |  |  |  |  |
| AP07 | Road occupancy and traffic management |  |  |  |  |  |  |
| AP08 | Out-of-hours works approval |  |  |  |  |  |  |
| AP09 | Waste and contaminated soil disposal |  |  |  |  |  |  |
| AP10 | Utility connection approvals |  |  |  |  |  |  |
| AP11 | Occupation / operating certificate |  |  |  |  |  |  |

Each consent condition is decomposed into a discrete, assignable obligation in the compliance tracker, with an owner, an evidence requirement and a verification date. Compliance is reported monthly and audited quarterly.

## 13.4  Sustainability targets and rating

| Commitment | Scheme / standard | Target | Measurement | Owner |
| --- | --- | --- | --- | --- |
| Sustainability rating certification | [Insert applicable scheme] |  | Certified assessment | ESG Lead |
| Energy performance in operation |  |  | Modelled and metered | Design Manager |
| Embodied carbon reduction |  |  | Life cycle assessment against a baseline design | ESG Lead |
| Operational carbon reduction |  |  | Energy model and metered performance | Operations |
| Renewable energy generation or procurement |  |  | Installed capacity and supply contracts | Design Manager |
| Potable water reduction |  |  | Metered consumption | Design Manager |
| Construction waste diverted from landfill |  | ≥90% by mass | Weighbridge and waste contractor reporting | Contractor |
| Responsibly sourced timber and materials |  | 100% of specified products | Chain of custody certificates | Contractor |
| Indoor environment quality |  |  | Verified by commissioning and post-occupancy survey | Design Manager |
| Climate resilience assessment complete |  | Before stage 3 gate | Risk assessment report | Design Manager |

## 13.5  Carbon management

Carbon is managed across the whole life of the asset. Embodied carbon is assessed at each design stage using a recognised life cycle assessment method, against a defined baseline, and is reported alongside capital cost so that carbon and cost trade-offs are made visibly.

| Life cycle stage | Scope | Assessed at | Reduction lever |
| --- | --- | --- | --- |
| A1-A3 Product | Extraction, transport and manufacture of materials | Stages 2, 3 and 4 | Material selection, low-carbon concrete and steel, reuse |
| A4-A5 Construction | Transport to site and construction process | Stage 4 and during construction | Local sourcing, plant electrification, site energy |
| B1-B7 Use | Operational energy, water, maintenance and replacement | Stages 3 and 4 | Passive design, system efficiency, durability |
| C1-C4 End of life | Deconstruction, transport, processing, disposal | Stage 3 | Design for disassembly, material passports |
| D Beyond life cycle | Reuse, recovery and recycling potential | Stage 3 | Circular design and take-back arrangements |

A carbon baseline is fixed at the end of concept design; all subsequent reduction is measured against it.

Carbon reduction options are assessed in the same value management process as cost, with the cost per tonne abated recorded.

Construction-stage carbon - fuel, electricity, transport and waste - is measured monthly from contractor data.

Offsets are used only for genuinely residual emissions after reduction, and only from a source accepted by the client's policy.

## 13.6  Waste and circular economy

| Stream | Target diversion | Method | Evidence |
| --- | --- | --- | --- |
| Excavated material | ≥95% | Reuse on site; cut-fill balance; beneficial reuse off site | Volume records and disposal dockets |
| Concrete and masonry | ≥95% | Crushing and reuse as sub-base | Weighbridge records |
| Metals | ≥98% | Segregation and recycling | Recycler receipts |
| Timber | ≥80% | Reuse, mulching or recycling | Waste contractor reporting |
| Plasterboard | ≥70% | Manufacturer take-back or recycling | Take-back receipts |
| Packaging | ≥90% | Supplier take-back and segregated recycling | Waste contractor reporting |
| General / mixed waste | ≥60% | Off-site sorting | Facility reporting |
| Hazardous waste | 0% to landfill without treatment | Licensed treatment and disposal | Consignment notes |

## 13.7  Environmental controls

| Aspect | Control | Monitoring | Limit / trigger |
| --- | --- | --- | --- |
| Noise | Plant selection, screening, restricted hours, respite periods | Attended and continuous monitoring at sensitive receivers | As set by the consent conditions |
| Vibration | Method selection, exclusion zones, condition surveys of adjacent structures | Continuous monitoring with alarms | Cosmetic damage and human comfort criteria |
| Dust and air quality | Water suppression, wheel wash, covered loads, stabilised surfaces | Visual assessment and deposition monitoring | No visible dust beyond the boundary |
| Water quality and sediment | Sediment basins, silt fences, stabilised entry, treatment before discharge | Discharge sampling and rainfall-triggered inspection | Consent discharge criteria |
| Contaminated land | Validated excavation, classification, licensed disposal, unexpected finds protocol | Validation sampling | Land use criteria applicable in the jurisdiction |
| Flora, fauna and habitat | Protection zones, supervised clearing, fauna spotter, nesting checks | Ecologist inspection | No clearing outside the approved footprint |
| Heritage and cultural | Exclusion zones, unexpected finds protocol, monitoring where required | Inspection and, where required, monitoring by a nominated party | Stop work on any find and notify |
| Light spill | Directional lighting, curfews, shielding | Complaint-triggered assessment | Consent conditions |

## 13.8  Social value and community benefit

| Commitment | Measure | Target | Reporting | Owner |
| --- | --- | --- | --- | --- |
| Local employment | Percentage of workforce hours from the defined local area |  | Monthly | Contractor |
| Apprentices and trainees | Percentage of total labour hours |  | Monthly | Contractor |
| Local and small business spend | Percentage of contract value |  | Monthly | Commercial Manager |
| Social enterprise and diverse supplier spend | Value and percentage |  | Quarterly | Commercial Manager |
| Indigenous / first nations participation | Employment and business spend, per the applicable jurisdiction |  | Quarterly | Contractor |
| Workforce diversity | Representation across the workforce |  | Quarterly | Contractor |
| Community investment | Hours or value contributed to community initiatives |  | Quarterly | Comms Lead |
| Skills and education engagement | Site visits, work experience and school programmes delivered |  | Quarterly | Comms Lead |

## 13.9  Modern slavery and ethical sourcing

Supply chain due diligence is undertaken proportionate to the risk profile of the product and its country of origin, in accordance with the modern slavery and ethical sourcing obligations applicable in the relevant jurisdiction.

High-risk product categories - including stone, brick, glass, solar components, electronics, textiles and some metals - receive enhanced scrutiny and traceability evidence.

Contractual obligations require flow-down of ethical sourcing requirements, a right of audit, and a duty to report suspected exploitation.

A confidential grievance channel is available to all workers in the supply chain, in languages the workforce understands.

## 13.10  Climate resilience and adaptation

A climate risk assessment is undertaken at concept design, considering the asset's design life and plausible warming scenarios.

Physical climate hazards assessed include extreme heat, flooding and stormwater capacity, drought, wind, bushfire or wildfire, coastal inundation and ground movement.

Adaptation measures are incorporated into the design where the whole-of-life case supports them, and residual climate risk is documented and transferred to the operator at handover.

Construction-phase weather risk is separately assessed and reflected in the schedule allowances and the risk register.

# 14.  Information and digital management

## 14.1  Information management strategy

Guidance Align to ISO 19650: the appointing party states what information it needs and why, and the delivery team produces exactly that - no more. The most common failure is specifying a model standard without specifying the asset information the operator will actually use. Start from the operator's requirements and work backwards.

Information is managed as a project asset. The information requirements are defined by the purpose to which the information will be put - design decisions, construction, statutory compliance, asset operation and maintenance - and the level of information need is set no higher than that purpose requires.

## 14.2  Information requirements

| Requirement | Defines | Owner | Issued to |
| --- | --- | --- | --- |
| Organisational information requirements (OIR) | What the organisation needs to manage its portfolio | Client asset management | Project |
| Asset information requirements (AIR) | What the operator needs to operate and maintain the asset | Operations Representative | Project and supply chain |
| Project information requirements (PIR) | What the client needs to make project decisions | Sponsor | Delivery team |
| Exchange information requirements (EIR) | What each appointed party must deliver, when, and in what format | Information Manager | Every appointed party |
| BIM execution plan (BEP) | How the appointed parties will meet the EIR | Lead appointed party | Information Manager for acceptance |
| Master information delivery plan (MIDP) | The consolidated schedule of every information deliverable | Information Manager | Delivery team |
| Task information delivery plan (TIDP) | Each task team's contribution to the MIDP | Task team leads | Information Manager |

## 14.3  BIM execution and levels of information need

| Stage | Purpose of information | Geometrical detail | Alphanumerical / data | Documentation |
| --- | --- | --- | --- | --- |
| Concept | Option comparison and area validation | Massing, indicative elements | Area, use, indicative performance | Concept report, cost plan |
| Developed | Coordination and consent | Systems located and sized, generic products | Performance parameters, system classification | Specification, calculations |
| Technical | Construction and procurement | Specific products, connections, tolerances | Product data, compliance references | Full specification and schedules |
| Construction | Fabrication and installation | Fabrication-level where required by the trade | Manufacturer data, serial and batch identifiers | Shop drawings, certificates |
| Handover | Operation and maintenance | As-built geometry to the agreed tolerance | Asset register data, warranty, maintenance regime, spares | O&M manuals, certificates, as-builts |

Model authoring, federation and coordination responsibilities are assigned in the BIM execution plan and reflected in every appointment.

The level of information need is defined per element and per exchange, not as a single project-wide 'level'.

Model content is validated automatically against the information standard before acceptance; non-conforming information is rejected, not corrected by the receiving party.

The client's right to use, modify and share project information for asset management purposes is secured in every appointment.

## 14.4  Common data environment

| State | Meaning | Who can edit | Approval to advance |
| --- | --- | --- | --- |
| Work in progress | Information being developed by a single task team | Originating task team only | Task team lead check |
| Shared | Coordinated and available to other task teams for reference and coordination | Originating task team | Task team lead authorisation |
| Published | Authorised and suitable for its stated purpose, including construction | No one - reissue as a new revision | Lead appointed party and client acceptance |
| Archive | Superseded or historical records retained for audit | No one | Automatic on supersession |

There is one common data environment for the project. Information exchanged outside it - by email attachment, file transfer or portable media - has no contractual status.

Every container carries a status code and a revision; superseded information is visibly marked and cannot be downloaded as current.

Access is role-based and reviewed quarterly; access is revoked within one working day of a person leaving the project.

The CDE audit trail is preserved and is exportable at closeout.

## 14.5  Naming, classification and metadata

All information containers follow a single naming convention agreed before the first exchange. The convention is recorded in Appendix H and is enforced automatically by the CDE. Classification uses a recognised system appropriate to the jurisdiction and asset type, applied consistently across models, documents and the asset register.

## 14.6  Model federation and coordination

Discipline models are federated on a fixed cycle - typically fortnightly in design and weekly during construction documentation.

Each federation produces a clash report classified per Section 7.8, with owners and due dates.

A shared coordinate system, project base point and units are fixed at the outset and never changed.

Model health metrics - file size, element count, warnings, unplaced elements, naming compliance - are reported with each federation.

## 14.7  Data security and access control

A security-minded approach is applied proportionate to the sensitivity of the asset; where the asset is sensitive, a security strategy and information-handling protocol are prepared before any information is shared.

Access is granted on the principle of least privilege and is logged.

Personal data is handled in accordance with the privacy obligations applicable in the relevant jurisdiction.

Backup, retention and disaster recovery arrangements for the CDE are confirmed contractually, including the position on the provider's insolvency.

Cyber incident response responsibilities are defined and tested.

## 14.8  Document control

Every document has a unique number, a revision, a status and an owner.

Revisions are alphabetic during development and numeric from the first issue for construction, or as the convention in Appendix H provides.

Transmittals record what was issued, to whom, when, in what status and for what purpose.

Distribution matrices define who receives each document class automatically.

Registers are maintained for drawings, specifications, models, RFIs, transmittals, correspondence, samples, ITPs, NCRs, certificates and warranties.

Superseded documents are withdrawn from circulation and marked superseded; retention follows the client's records policy and any statutory retention period applicable in the jurisdiction.

## 14.9  Digital tools and systems register

| System | Purpose | Owner | Users | Integration | Data exported at closeout |
| --- | --- | --- | --- | --- | --- |
| Common data environment | Single source of information |  | All parties | Model and document authoring tools | Full archive |
| Project controls / cost system | Budget, commitment, actual and forecast |  | Client and commercial team | Client finance ledger | Cost history and final account |
| Scheduling software | Baseline and progress |  | Planner and package managers | Cost system, reporting | All schedule versions |
| Risk register system | Risk and opportunity |  | Delivery team | Reporting and cost | Full register history |
| Model authoring and federation | Design production and coordination |  | Design team | CDE | Native and open-format models |
| Field / site management app | Inspections, ITPs, NCRs, defects |  | Site teams | CDE and quality records | Complete quality record set |
| HSE management system | Incidents, permits, inductions |  | All site personnel | Reporting | Incident and training history |
| Asset information system | Operational asset data |  | Operations | CDE handover export | Populated asset register |
| Reporting and analytics | Dashboards and performance reporting |  | Client and delivery team | All of the above | Report archive |

## 14.10  Reporting and analytics

Wherever possible, reports are generated from the source systems rather than re-keyed. Each reported metric has a single authoritative source system, a defined calculation, and a nominated data owner accountable for its accuracy. Manual data entry into reports is identified as such so that its reliability is understood.

# 15.  Interface and integration management

## 15.1  Approach

Guidance Interfaces are where projects fail. Every scope boundary, every handover between contractors, every connection to a third-party asset is an interface, and each one needs a named owner on both sides and an agreed date. Treat an unowned interface as an open risk, because it is.

An interface exists wherever a deliverable, decision or physical connection must pass between two parties. Interfaces are identified at the point the packaging strategy is set, are recorded in the interface register, and are reviewed monthly at the interface forum.

## 15.2  Interface classification

| Class | Definition | Typical examples | Owner |
| --- | --- | --- | --- |
| Physical | A tangible connection between elements or packages | Structure to façade; services penetrations; slab-to-fit-out tolerances | Design Manager |
| Functional / systems | Systems that must operate together | Fire detection to smoke control; BMS to plant; security to access control | Commissioning Manager |
| Contractual | A boundary of responsibility between contracts | Package scope splits; free-issue items; attendance obligations | Commercial Manager |
| Organisational | A dependency between teams or organisations | Client decision inputs; operator resourcing; consultant novation | Project Manager |
| Spatial / temporal | Shared access to space or time | Site access sequencing; craneage sharing; possession windows | Project Manager |
| External / third party | A dependency on a party outside the contract | Utility connections; authority approvals; adjacent landowners | Project Manager |
| Operational | A boundary with an existing operating asset | Live services tie-ins; shutdowns; migration of users | Operations Representative |
| Information | A dependency for data or model content | Model exchange; asset data population; as-built handover | Information Manager |

## 15.3  Internal interfaces

| Ref | Interface | Party A | Party B | Deliverable required | Required by | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IF-01 | Substructure to superstructure | Civil contractor | Structure contractor | Survey-verified setting out and levels |  |  | Open |
| IF-02 | Structure to façade | Structure contractor | Façade contractor | As-built tolerances and fixing zones |  |  | Open |
| IF-03 | Services to structure | Services contractor | Structure contractor | Penetration and cast-in schedule |  |  | Open |
| IF-04 | Base build to fit-out | Main contractor | Fit-out contractor | Serviced, weathertight shell to agreed condition |  |  | Open |
| IF-05 | Fit-out to equipment installation | Fit-out contractor | Equipment supplier | Room readiness certificate |  |  | Open |
| IF-06 | Construction to commissioning | Main contractor | Commissioning Manager | System completion certificates |  |  | Open |
| IF-07 | Design to construction | Lead designer | Main contractor | AFC documentation with no open mandatory comments |  |  | Open |

## 15.4  External and third-party interfaces

| Ref | Third party | Interface | Lead time | Risk if late | Owner |
| --- | --- | --- | --- | --- | --- |
| EX-01 | Electricity network operator | Supply capacity, connection and energisation | Typically 6-18 months | Cannot energise; commissioning stops |  |
| EX-02 | Water and wastewater authority | Connection, capacity and diversion | 6-12 months | Cannot commission or occupy |  |
| EX-03 | Telecommunications providers | Lead-in and service provision | 3-9 months | Systems cannot be commissioned |  |
| EX-04 | Gas network operator | Connection and purging | 6-12 months | Heating systems incomplete |  |
| EX-05 | Road / transport authority | Occupancy, closures, works within the road reserve | 3-6 months | Access and deliveries constrained |  |
| EX-06 | Planning / consent authority | Condition discharge and modifications | Variable | Cannot proceed or occupy |  |
| EX-07 | Building certifier / regulator | Inspections and occupation certification | Per approval | Cannot occupy |  |
| EX-08 | Adjacent landowners | Access, party wall, dilapidation, protection works | 3-12 months | Access denied; claims |  |
| EX-09 | Emergency services | Access, hydrants, brigade interface | Per approval | Cannot obtain occupation approval |  |
| EX-10 | Adjacent projects and programme | Shared access, sequencing and services | Ongoing | Clashing possession and rework |  |

## 15.5  Utilities and services diversions

Existing services are identified by records search, non-destructive location and physical proving before any ground disturbance.

Diversion design, approval and construction lead times are placed on the critical path from the outset - they are routinely the longest lead item on a project.

Asset owners' own works are contracted, programmed and monitored as though they were a delivery package, with named contacts and escalation routes on both sides.

Shutdowns and outages are planned with the asset owner and affected users, with contingency and reversion plans, and are notified in accordance with Section 5.

## 15.6  Operational interfaces with the existing asset

Where the works adjoin or affect an operating asset, a joint interface protocol is agreed with the operator covering access, permits, noise, isolation, infection or contamination control, security and emergency response.

Live tie-ins are planned in detail, rehearsed where the consequence warrants it, executed in agreed windows, and always with a documented reversion plan.

Operational continuity requirements are treated as constraints in the schedule, not as preferences.

## 15.7  Interface resolution process

Identify - any party may raise an interface; it is registered within 2 working days with both parties named.

Define - the parties agree what must pass across the interface, in what form, to what standard and by when.

Assign - a single owner on each side is named; the register never records a team as an owner.

Agree - the interface agreement is documented and signed by both parties.

Monitor - status is reviewed monthly at the interface forum and reported with the schedule.

Escalate - an interface unresolved 20 working days before it is required is escalated per Section 4.7.

Close - closure requires evidence that the deliverable passed and was accepted, not merely that the date arrived.

# 16.  Resource and people management

## 16.1  Resourcing plan and mobilisation

Guidance Under-resourcing the client side is the cheapest false economy in capital delivery. Set out the roles, the effort in full-time equivalents by phase, and the date each role must be in place. Show vacancies honestly - a plan that assumes a full team from day one is already behind.

| Role | FTE - design | FTE - procurement | FTE - construction | FTE - handover | Mobilise by | Source | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Director | 0.3 | 0.5 | 0.5 | 0.3 |  | Client |  |
| Project Manager | 1.0 | 1.0 | 1.0 | 1.0 |  | Client / consultant |  |
| Design Manager | 1.0 | 0.5 | 0.5 | 0.2 |  | Consultant |  |
| Commercial Manager | 0.5 | 1.0 | 1.0 | 0.5 |  | Client / consultant |  |
| Cost Manager / QS | 0.5 | 1.0 | 1.0 | 0.5 |  | Consultant |  |
| Planner | 0.5 | 0.5 | 1.0 | 0.5 |  | Consultant |  |
| HSE Manager | 0.3 | 0.3 | 1.0 | 0.5 |  | Client |  |
| Quality Manager | 0.2 | 0.3 | 1.0 | 1.0 |  | Client / consultant |  |
| Information Manager | 1.0 | 0.5 | 0.5 | 1.0 |  | Consultant |  |
| Environmental / ESG Lead | 0.5 | 0.3 | 0.5 | 0.3 |  | Client |  |
| Risk Manager | 0.3 | 0.3 | 0.3 | 0.2 |  | Client |  |
| Stakeholder / Comms Lead | 0.5 | 0.3 | 0.8 | 0.5 |  | Client |  |
| Commissioning Manager | 0.2 | 0.2 | 0.5 | 1.0 |  | Consultant |  |
| Operations Representative | 0.3 | 0.2 | 0.5 | 1.0 |  | Operator |  |
| Document Controller | 0.5 | 0.5 | 1.0 | 1.0 |  | Consultant |  |
| Package Managers (n) |  |  |  |  |  |  |  |
| Site supervision / clerk of works | 0 | 0 |  |  |  | Client / consultant |  |

## 16.2  Competency and capability

Each role has a defined competency profile covering qualifications, licences, experience on comparable projects and behavioural requirements.

Competency is verified before appointment, not assumed from a job title, and evidence is retained.

A capability gap analysis is undertaken at mobilisation and at each stage gate; gaps are closed by training, mentoring, secondment or external appointment.

Roles with statutory or contractual competency requirements applicable in the jurisdiction - safety, certification, temporary works, high-risk licences - are identified and tracked in the competency register.

## 16.3  Training and development

| Training | Audience | Frequency | Owner |
| --- | --- | --- | --- |
| Project induction | Every person on the project | On mobilisation | Project Manager |
| Site safety induction | Every person entering the site | On first entry, refreshed per the safety plan | HSE Manager |
| Systems training - CDE, cost, controls | All users | On mobilisation and on system change | Information Manager |
| Contract and commercial awareness | Delivery leads | Post-award and annually | Commercial Manager |
| Risk facilitation and assessment | Risk owners | Annually | Risk Manager |
| Mental health first aid | Nominated personnel | On appointment, refreshed per certification | HSE Manager |
| Cultural awareness | All personnel | On mobilisation | Comms Lead |
| Operational readiness and asset familiarisation | Operations and maintenance staff | Before handover | Commissioning Manager |

## 16.4  Onboarding and offboarding

New team members complete a structured onboarding within their first week covering this plan, the governance, the systems, the current position and their specific accountabilities.

Access to systems and the CDE is provisioned on the first day and revoked within one working day of departure.

Departing personnel complete a documented handover of their accountabilities, open actions, registers and relationships, and are debriefed for lessons.

## 16.5  Performance management

Individual objectives are aligned to the project objectives in Section 2.4 and are reviewed at least six-monthly.

Consultant and contractor performance is assessed formally against defined criteria at each stage gate and at completion, and the assessment is recorded for use in future procurement.

Poor performance is addressed early, in writing, with a defined improvement period and consequence.

## 16.6  Key person dependencies

Guidance Identify the small number of people whose sudden absence would genuinely damage the project, and do something about it now - document their knowledge, name a deputy, and where the contract allows, name them as key personnel who cannot be replaced without consent.

| Role / person | Why critical | Deputy | Mitigation | Contractual key person? |
| --- | --- | --- | --- | --- |

## 16.7  Industrial relations

Applicable industrial instruments, site agreements and consultation obligations are identified before mobilisation.

A single point of contact manages industrial relations; site-level commitments outside the agreed framework are not made.

Disputes follow the resolution procedure in the applicable instrument and are escalated in accordance with Section 4.7.

Industrial risk - including the effect of enterprise agreement expiry dates falling within the construction period - is carried in the risk register with a schedule allowance.

## 16.8  Team charter and ways of working

We raise problems early. An early warning is never punished; a concealed problem always is.

We make decisions at the lowest level that has the authority and the information.

We put decisions in writing on the day they are made.

We challenge the work, not the person, and we disagree openly rather than privately.

We do not accept information we know to be wrong in order to keep a meeting short.

We finish what we start: actions have an owner and a date, and we close them.

We look after each other's safety and wellbeing without exception.

## 16.9  Co-location and accommodation

| Facility | Requirement | Provided by | In place by |
| --- | --- | --- | --- |
| Project office / co-location space | Desks, meeting rooms, collaboration wall, video conferencing |  |  |
| Site accommodation | Site office, meeting room, first aid, amenities |  |  |
| Site welfare facilities | Sized to peak workforce with climate protection |  |  |
| Site security and access control | Access system, CCTV, visitor management |  |  |
| IT and connectivity | Network, systems access, site Wi-Fi, mobile coverage |  |  |
| Visitor and viewing arrangements | Safe viewing point and visitor PPE |  |  |

# 17.  Commercial and contract management

## 17.1  Contract administration framework

Guidance Contract administration is a discipline of dates and records. Most entitlement is won or lost on whether a notice was served in time and whether contemporaneous records exist. Build the notice timetable into the project calendar on the day the contract is executed.

The contract is administered by the person named in it. This plan does not vary the contract in any respect. Where the roles described here differ from the roles named in the contract, the contract prevails and this plan is corrected.

A contract summary - key dates, notice periods, liquidated damages, caps, securities, insurance obligations and the payment regime - is prepared within 10 working days of execution and briefed to the whole team.

Every obligation with a time limit is entered into the project calendar with an advance reminder.

All formal communication uses the method the contract prescribes; email is used only where the contract permits it.

Contemporaneous records - daily diaries, labour and plant returns, weather, progress photographs, delay events, instructions - are kept from day one by both parties.

## 17.2  Contractual notices register

| Notice type | Given by | Trigger | Time limit | Consequence of late or no notice |
| --- | --- | --- | --- | --- |
| Early warning | Either party | Awareness of any matter that could affect cost, time, quality or safety | As soon as aware, typically within days | Loss of collaborative mitigation; possible reduction of entitlement |
| Notice of delay / claim for extension of time | Contractor | Awareness of a delay event | Typically 10-28 days from awareness | Entitlement may be barred entirely |
| Detailed claim submission | Contractor | Following the initial notice | Typically 28 days from the notice | Claim may not be assessed |
| Notice of variation / change | Client Representative | Instruction of a change | On instruction | Work may be carried out without authority to pay |
| Notice of intention to claim additional cost | Contractor | Awareness of the cost event | Per contract | Entitlement may be barred |
| Payment claim | Contractor | Reference date under the contract | Per contract and any statutory regime in the jurisdiction | Payment cycle deferred |
| Payment schedule / certificate | Client Representative | Receipt of a payment claim | Per contract and any statutory regime | Client may become liable for the full claimed amount |
| Notice of defect | Client Representative | Identification of a defect | Per contract | Rectification may be at the client's cost |
| Notice of practical completion / taking over | Contractor | Achievement of completion | Per contract | Completion date disputed |
| Notice to show cause / default | Either party | Substantial breach | Per contract | Termination rights may be lost |
| Notice of dispute | Either party | Failure to resolve | Per contract | Dispute process cannot be commenced |
| Notice of suspension | Either party | Non-payment or breach | Per contract and any statutory regime | Suspension may be a breach |

Insert the actual periods from the executed contract. The periods shown are indicative only and vary substantially between contract families and jurisdictions.

## 17.3  Instructions and directions

Only the person named in the contract may issue instructions. No other person - including the Project Manager, designers or client staff - may direct the contractor.

Instructions are issued in writing on the numbered instruction form and recorded in the instruction register.

Verbal directions in an emergency are confirmed in writing within 1 working day.

Site instructions that constitute a change must be identified as such and priced before, not after, the work is carried out wherever practicable.

Design team comments, RFI responses and shop drawing reviews are not instructions and must not vary the works.

## 17.4  Claims management

Claims are assessed on entitlement first, then quantum. A claim without established entitlement is not negotiated on value.

Assessment is documented against the contract clause relied on, the facts, the causation and the substantiation provided.

Global claims are rejected in principle; the claimant is required to establish the causal link between each event and its consequence.

The client maintains its own delay analysis and cost records so that any claim can be tested independently.

Claims are assessed and determined within the contractual timeframe. Silence is not a defence and may create entitlement.

A claims position statement is maintained and reported monthly showing claimed, assessed, agreed and disputed values.

| Ref | Event | Notice date | Clause relied on | Claimed (time) | Claimed (cost) | Assessed | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CL-01 |  |  |  |  |  |  |  |
| CL-02 |  |  |  |  |  |  |  |
| CL-03 |  |  |  |  |  |  |  |
| CL-04 |  |  |  |  |  |  |  |
| CL-05 |  |  |  |  |  |  |  |

## 17.5  Dispute avoidance and resolution

| Step | Mechanism | Timeframe | Decision-maker |
| --- | --- | --- | --- |
| 0 | Early warning and joint mitigation at working level | Continuous | Project Manager and contractor PM |
| 1 | Escalation to senior representatives of each party | Within 10 working days of the issue being raised | Project Director and contractor management |
| 2 | Executive negotiation between senior executives | Within 20 working days | Sponsor and contractor executive |
| 3 | Independent expert determination, dispute avoidance board or adjudication as the contract provides | Per contract | Appointed independent |
| 4 | Mediation or other structured negotiation | Per contract | Appointed mediator |
| 5 | Arbitration or litigation as the contract provides | Per contract and the applicable jurisdiction | Tribunal or court |

Escalation is time-bound at every step: a dispute that stalls at one level moves to the next automatically. Work continues while a dispute is being resolved unless the contract expressly permits suspension.

## 17.6  Securities, bonds and guarantees

| Instrument | Purpose | Value | Provided by | Held until | Release authority |
| --- | --- | --- | --- | --- | --- |
| Performance security / bond | Secures performance of the contract | Typically 5-10% of contract value | Contractor | Practical completion (partial) and end of defects (balance) | Commercial Manager |
| Retention | Secures completion and defect rectification | Typically 5% to a cap | Withheld from payments | Half at completion, half at end of defects | Client Representative |
| Parent company guarantee | Secures the obligations of a subsidiary | Full contract value | Contractor's parent | End of the liability period | Commercial Manager |
| Advance payment guarantee | Secures repayment of any advance | Value of the advance | Contractor | Full amortisation | Commercial Manager |
| Off-site materials bond | Secures payment for materials not on site | Value of the materials | Contractor | Delivery to site | Cost Manager |
| Collateral warranties / third-party rights | Provides recourse to funders, purchasers and tenants | n/a | Contractor and consultants | Statutory limitation period | Legal adviser |
| Design warranty | Secures the design obligation of a design sub-contractor | n/a | Designer | Limitation period | Commercial Manager |

## 17.7  Insurance administration

Certificates of currency are obtained before mobilisation and are re-verified before each renewal date; expiry dates are diarised.

The client verifies that the interests, sums insured, deductibles and periods match the contract requirements - not merely that a certificate exists.

Claims under project policies are notified within the policy timeframe; late notification can void cover.

Professional indemnity run-off cover is confirmed for the period required after completion.

Refer to the insurance summary table in Section 10.12.

## 17.8  Subcontractor management and flow-down

The contractor's proposed subcontractors for nominated critical packages are subject to client review before engagement.

Obligations relating to safety, quality, environment, information management, ethical sourcing, security, insurance and payment terms flow down to every tier.

Subcontract payment terms may not be less favourable than the head contract terms, and any statutory payment protection applicable in the jurisdiction is complied with.

The client maintains visibility of the subcontractor supply chain through a subcontractor register, including value, scope and financial standing where the exposure is material.

Step-in rights and novation arrangements for critical subcontracts are secured where the consequence of a subcontractor failure would be severe.

## 17.9  Contract close-out obligations

| Obligation | Evidence required | Owner | Complete by |
| --- | --- | --- | --- |
| Final account agreed and signed | Signed final account statement | Commercial Manager | Per contract |
| All claims resolved or expressly reserved | Settlement record | Commercial Manager | Before final certificate |
| Retention and securities released | Release instruction and confirmation | Commercial Manager | Per contract |
| Warranties and guarantees delivered | Executed warranty documents | Commercial Manager | At practical completion |
| Insurance run-off confirmed | Certificates of currency | Commercial Manager | At final certificate |
| Statutory declarations and payment confirmations received | Declarations as required in the jurisdiction | Commercial Manager | With each payment and at final |
| Defects rectified and final certificate issued | Final defects certificate | Client Representative | End of defects period |
| Contract records archived | Complete contract file in the CDE | Document Controller | Within 3 months of final certificate |

# 18.  Change control

## 18.1  Principles

Guidance Change control is not about preventing change - it is about making sure every change is visible, assessed, priced and authorised before it is built. The single most valuable rule is: no instruction without an approved budget source. Enforce it from the first week.

Any change to an approved baseline requires an approved change, regardless of value, including changes that are cost-neutral.

Change is assessed for cost, time, risk, safety, quality, sustainability, operational impact, benefits and interfaces - not cost alone.

No change is instructed without an identified and approved funding source.

Cumulative change is monitored: a series of individually minor changes can consume contingency and float without ever reaching a governance forum.

The change register is the single record of every change, whether approved, rejected, withdrawn or pending.

## 18.2  Change categories

| Category | Definition | Examples | Route |
| --- | --- | --- | --- |
| Client-initiated scope change | The client changes what it wants | Additional area, changed function, upgraded specification | Full change control with Sponsor approval |
| Design development | Design detail evolving within the approved brief and budget | Detailing, coordination resolution, buildability | No change; managed by the Design Manager unless cost or time is affected |
| Design change beyond the brief | Design that alters the approved requirement | Changed system selection, performance change | Full change control |
| Latent or site condition | Conditions differing from those assumed | Ground conditions, unrecorded services, contamination | Full change control with risk register linkage |
| Statutory or regulatory change | External change in requirements | Code change, new consent condition | Full change control; compliance is mandatory |
| Contractor-initiated | Proposed alternative or value engineering | Alternative method, product substitution | Full change control with designer concurrence |
| Correction of error or omission | Rectification of a documentation error | Missing scope, conflicting documents | Full change control; cause recorded for lessons |
| Risk realisation | A registered risk occurring | Weather event beyond the allowance, supplier failure | Contingency drawdown per Section 9.12 |

## 18.3  Change control process

Step 1 - Raise. Any party raises a change request describing the change, the reason, the originator and the date. It is entered in the change register within 2 working days and given a unique number.

Step 2 - Screen. The Project Manager confirms within 3 working days whether it is a genuine change to the baseline, a clarification, or a contractor risk already priced.

Step 3 - Assess. Discipline leads assess the impact: cost (Cost Manager), time (Planner), risk (Risk Manager), safety (HSE Manager), quality (Quality Manager), operations (Operations Representative), benefits (Sponsor's representative), interfaces (Project Manager). Target 10 working days.

Step 4 - Price. The commercial impact is established under the contract mechanism, with a quotation obtained where the contract provides for one.

Step 5 - Recommend. The Project Manager consolidates the assessment into a change recommendation with options, including the option of not proceeding.

Step 6 - Authorise. The change is approved, rejected or deferred at the level set in Section 18.4. The decision and its rationale are recorded.

Step 7 - Instruct. Approved changes are instructed formally under the contract by the person authorised to do so.

Step 8 - Implement and verify. The change is executed and its implementation is verified.

Step 9 - Baseline. Cost, schedule and scope baselines and all affected documents, models and registers are updated at the next control cycle.

Step 10 - Communicate. Every affected party - including designers, contractors, the operator and the information manager - is notified in writing.

## 18.4  Change authority matrix

| Change type and value | Assessed by | Recommended by | Approved by | Baseline updated by |
| --- | --- | --- | --- | --- |
| Clarification with no cost or time impact | Package Manager | - | Project Manager | Document Controller |
| Cost impact up to [X], no milestone impact | Cost Manager | Project Manager | Project Manager | Cost Manager and Planner |
| Cost impact up to [Y], or float consumption within tolerance | Cost Manager and Planner | Project Manager | Project Director | Cost Manager and Planner |
| Cost impact up to [Z], or any change to a contractual milestone | Commercial Manager and Planner | Project Director | Sponsor | Project Controls |
| Cost impact above [Z], any change to the funding envelope, benefits or scope of the business case | Commercial Manager | Sponsor | Project Board / investment authority | Project Controls |
| Any change affecting statutory compliance, safety in design or consent conditions | HSE Manager and Planning Lead | Project Manager | Project Director with HSE endorsement | Project Controls |
| Any change affecting the operator's ability to accept or run the asset | Operations Representative | Project Manager | Sponsor | Project Controls |

## 18.5  Change request content

Unique reference, title, originator and date raised.

Description of the change and the reason it is required.

Category per Section 18.2 and the baseline element affected.

Options considered, including the do-nothing option and its consequence.

Cost impact - capital, whole-of-life and the proposed funding source.

Time impact - activities affected, float consumed, milestone effect.

Risk impact - risks created, removed or changed, with register references.

Safety, quality, environmental and sustainability impact.

Operational and benefits impact.

Interface and stakeholder impact.

Documents, drawings, models and registers requiring update.

Recommendation, decision, decision-maker and date.

## 18.6  Baseline change management

Baselines are changed only by approved change, never by an update or a correction.

Each baseline version is retained; the current and original baselines are both reported.

Baseline changes are applied at a defined control point each month so that reporting is stable within a period.

A baseline change log records what changed, by how much, on whose authority and when it took effect.

## 18.7  Change register

| Ref | Title | Category | Raised | Cost impact | Time impact | Status | Approved by | Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CR-01 |  |  |  |  |  |  |  |  |
| CR-02 |  |  |  |  |  |  |  |  |
| CR-03 |  |  |  |  |  |  |  |  |
| CR-04 |  |  |  |  |  |  |  |  |
| CR-05 |  |  |  |  |  |  |  |  |
| CR-06 |  |  |  |  |  |  |  |  |

## 18.8  Communication of approved changes

An approved change is not complete until every party who must act on it has been told, in writing, what has changed and what they must do differently. The Project Manager confirms distribution and records it against the change in the register. Where a change affects information already issued for construction, the affected documents are reissued at a new revision - never marked up in isolation.

# 19.  Reporting and performance management

## 19.1  Reporting framework

Guidance Design reporting around decisions. For each report ask: who reads it, what will they decide, and what would they do differently if the number moved? Reports that survive that test get read. Everything else becomes a monthly ritual that consumes the team's best week.

One set of numbers: every report draws from the same source systems, so the Board and the site team see the same position.

Report by exception against tolerance, with the detail available but not compulsory.

Every report states the data date, so no reader compares figures from different periods.

Forecasts are reported alongside actuals; a report of the past alone is not a management report.

Bad news travels at the same speed as good news.

## 19.2  Report suite

| Report | Purpose | Audience | Author | Frequency | Due |
| --- | --- | --- | --- | --- | --- |
| Weekly delivery report | Short-term progress, blockers and look-ahead | Delivery team | Project Manager | Weekly | Monday close |
| Weekly HSE report | Incidents, lead indicators, actions | Delivery team and client | HSE Manager | Weekly | Monday close |
| Monthly project report | Full performance position against baseline | Sponsor and Control Group | Project Manager | Monthly | Working day 8 |
| Monthly cost report | Budget, commitment, actual, forecast, change, contingency | Control Group | Cost Manager | Monthly | Working day 6 |
| Monthly schedule report | Milestones, critical path, float, SPI | Control Group | Planner | Monthly | Working day 5 |
| Monthly risk report | Top risks, movement, treatment status, exposure vs contingency | Control Group | Risk Manager | Monthly | Working day 5 |
| Monthly quality report | NCRs, ITP status, audit findings | Control Group | Quality Manager | Monthly | Working day 5 |
| Monthly ESG report | Environmental compliance, sustainability and social value | Control Group | ESG Lead | Monthly | Working day 6 |
| Board pack | Decisions required, exceptions, assurance | Project Board | Project Manager | Monthly | 5 days before Board |
| Executive dashboard | One-page portfolio view | Executive | PMO | Monthly | Working day 10 |
| Quarterly assurance report | Independent view of control effectiveness | Sponsor and Board | Assurance Lead | Quarterly | +15 working days |
| Stage gate report | Readiness to proceed | Board and investment authority | Project Manager | At each gate | Per gate schedule |
| Exception report | Any breach of tolerance | Sponsor | Project Manager | On trigger | Within 2 working days |
| Closeout report | Outcome, performance and lessons | Sponsor | Project Manager | At closeout | Within 3 months of completion |

## 19.3  Key performance indicators

Guidance Twenty well-chosen indicators beat sixty. Each must have a formula that two people would calculate identically, a target, an escalation threshold and an owner. If nobody can state the formula, the indicator is decoration.

| # | KPI | Definition / formula | Target | Threshold | Frequency | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | TRIFR | Recordable injuries × 1,000,000 ÷ hours worked | Below benchmark | Any increase over 3 months | Monthly | HSE |
| 2 | LTIFR | Lost time injuries × 1,000,000 ÷ hours worked | 0 | Any occurrence | Monthly | HSE |
| 3 | High-potential incidents | Count of incidents with potential for serious harm | 0 | Any occurrence | Monthly | HSE |
| 4 | Safety lead indicator compliance | Completed HSE inspections and interactions ÷ planned | 100% | <90% | Monthly | HSE |
| 5 | SPI | Earned value ÷ planned value | ≥0.95 | <0.90 | Monthly | Planner |
| 6 | Milestone achievement | Milestones achieved on or before the planned date ÷ milestones due | ≥90% | <80% | Monthly | Planner |
| 7 | Critical path float | Total float on the critical path | ≥0 days | Negative | Monthly | Planner |
| 8 | Percent plan complete | Look-ahead activities completed as promised ÷ promised | ≥80% | <70% | Weekly | PM |
| 9 | CPI | Earned value ÷ actual cost | ≥0.95 | <0.90 | Monthly | Cost Manager |
| 10 | Forecast variance at completion | (BAC − EAC) ÷ BAC × 100 | ≥0% | <−2% | Monthly | Cost Manager |
| 11 | Contingency drawdown ratio | Contingency drawn ÷ contingency budget, compared with percent complete | ≤ percent complete | 10 points above | Monthly | Commercial |
| 12 | Change value | Approved change value ÷ original contract sum | ≤5% | >10% | Monthly | Commercial |
| 13 | Change assessment cycle time | Average working days from raised to decided | ≤15 days | >25 days | Monthly | PM |
| 14 | Commitment coverage | Value committed ÷ value budgeted | Aligned to plan | ±10% of plan | Monthly | Cost Manager |
| 15 | First-time inspection pass rate | Inspections passed first time ÷ inspections carried out | ≥95% | <90% | Monthly | Quality |
| 16 | Open NCRs beyond 20 days | Count of NCRs open more than 20 working days | 0 | >3 | Monthly | Quality |
| 17 | Design comment closure | Comments closed ÷ comments raised, by due date | ≥95% | <85% | Monthly | Design Manager |
| 18 | RFI response time | Average working days to respond to an RFI | ≤7 days | >14 days | Monthly | Design Manager |
| 19 | Clash closure rate | Class 1 clashes closed ÷ raised per federation cycle | ≥95% | <85% | Fortnightly | Information Manager |
| 20 | Environmental incidents | Count of reportable environmental incidents | 0 | Any occurrence | Monthly | ESG Lead |
| 21 | Waste diversion | Waste diverted from landfill ÷ total waste by mass | ≥90% | <80% | Monthly | Contractor |
| 22 | Embodied carbon vs baseline | Assessed embodied carbon ÷ baseline design carbon | ≤ target | >baseline | At each design stage | ESG Lead |
| 23 | Consent condition compliance | Conditions verified compliant ÷ conditions due | 100% | <100% | Monthly | Planning Lead |
| 24 | Local employment | Local workforce hours ÷ total workforce hours | ≥ target | <target | Monthly | Contractor |
| 25 | Complaint response | Complaints substantively answered within 5 working days ÷ complaints received | 100% | <95% | Monthly | Comms Lead |
| 26 | Stakeholder commitments closed | Commitments met by due date ÷ commitments due | 100% | <90% | Monthly | Comms Lead |
| 27 | Action closure | Governance actions closed by due date ÷ due | ≥90% | <80% | Monthly | PM |
| 28 | Decision latency | Average working days from decision request to recorded decision | ≤10 days | >20 days | Monthly | PM |
| 29 | Information delivery | Deliverables issued on or before the MIDP date ÷ due | ≥95% | <85% | Monthly | Information Manager |
| 30 | Operational readiness completion | Readiness checklist items complete ÷ due | 100% by handover | <90% at 3 months out | Monthly | Operations Rep |

## 19.4  Dashboard content

Header: project name, data date, overall status, and the Project Manager's one-sentence assessment.

Safety: TRIFR and LTIFR trend, high-potential incidents, lead indicator compliance.

Schedule: milestone tracker with planned, forecast and actual dates; critical path float trend; SPI.

Cost: budget, commitment, actual, forecast and variance; S-curve against plan; contingency drawdown against percent complete.

Change: approved, pending and rejected change with cumulative value.

Risk: top ten risks by residual exposure with movement arrows; exposure against remaining contingency.

Quality: open NCRs, ageing, first-time pass rate.

ESG: incidents, waste diversion, carbon against baseline, social value.

Decisions required this period, with the date each is needed by.

## 19.5  Data sources and integrity

| Metric group | Source system | Data owner | Validation |
| --- | --- | --- | --- |
| Safety | HSE management system | HSE Manager | Reconciled to contractor returns monthly |
| Schedule | Scheduling software | Planner | Progress verified on site before acceptance |
| Cost | Project cost system | Cost Manager | Reconciled to the corporate ledger monthly |
| Change | Change register | Project Manager | Reconciled to cost and schedule baselines |
| Risk | Risk register | Risk Manager | Quarterly quality audit of the register |
| Quality | Field management system | Quality Manager | Sampled against physical records |
| Environment and social | Contractor returns and monitoring data | ESG Lead | Verified against weighbridge and monitoring records |
| Information | Common data environment | Information Manager | Automated validation reporting |

## 19.6  Exception reporting

An exception report is issued to the Sponsor within 2 working days whenever a tolerance in Section 2.4 is forecast to be breached, a risk rated Extreme emerges, a notifiable incident occurs, a contractual milestone is forecast to be missed, or the forecast cost at completion exceeds the approved budget. The report states what happened, the forecast impact, the options, the recommendation and the decision required.

## 19.7  Lessons capture

Lessons are captured continuously in the lessons register, not retrospectively at closeout.

A facilitated lessons session is held at every stage gate, after every significant incident or claim, and at completion of every major package.

Each lesson records the situation, what happened, the root cause, the recommendation and the owner of the change to practice.

Lessons relevant to the wider portfolio are transmitted to the PMO within 20 working days and are actively fed into future project plans.

# 20.  Testing, commissioning, handover and closeout

## 20.1  Commissioning strategy

Guidance Commissioning is where projects run out of time, because it is planned last and starts late. Build the commissioning programme backwards from the required operational date, and protect it - every day of construction overrun consumes a day of commissioning unless the completion date moves with it.

Commissioning is planned from design stage, with the commissioning manager appointed no later than the end of developed design. The commissioning programme is a distinct section of the master schedule with its own milestones, resources and float.

| Stage | Activity | Responsible | Evidence |
| --- | --- | --- | --- |
| Design | Commissionability review; specification of testing regimes, access and metering | Commissioning Manager | Commissioning strategy and specification |
| Pre-construction | Commissioning programme, method statements and witnessing schedule agreed | Commissioning Manager | Accepted commissioning plan |
| Installation | Installation checks and quality verification against ITPs | Contractor | Signed ITPs and installation checksheets |
| Static commissioning | Pre-commissioning checks, cleaning, flushing, pressure and continuity testing, energisation readiness | Contractor | Static completion certificates |
| Dynamic commissioning | Individual system setting to work, balancing, control verification | Contractor and specialists | System commissioning records |
| Integrated systems testing | Cause-and-effect testing across interacting systems | Commissioning Manager | Witnessed IST results |
| Performance verification | Testing against specified performance under representative conditions | Independent commissioning agent | Performance test report |
| Regulatory testing | Statutory tests and certification required in the jurisdiction | Certifier / authority | Statutory certificates |
| Seasonal commissioning | Verification under opposite seasonal conditions | Commissioning Manager | Seasonal test report |
| Fine tuning and aftercare | Optimisation in use during the first period of operation | Contractor and operator | Aftercare records |

## 20.2  Integrated systems testing

Integrated systems testing verifies that systems behave correctly together - typically fire detection and alarm with smoke control, lifts, access control, door release, public address and emergency power.

A cause-and-effect matrix is prepared at design stage, agreed with the authority and the operator, and forms the test script.

Testing is witnessed by the client, the operator, the certifier and the insurer where required, and every result is recorded against the matrix.

Failed tests are rectified and the affected sequence is re-tested in full, not in part.

Integrated testing cannot begin until every contributing system has passed its own commissioning.

## 20.3  Training and familiarisation

A training needs analysis is completed at least six months before planned completion, covering operations, maintenance, security, cleaning and end users.

Training is delivered on the installed systems, on site, by the installers, before handover - not by video afterwards.

Training is recorded, and recordings and materials are provided as part of the handover documentation for future staff.

Familiarisation walkthroughs are undertaken with the operator during construction so that concealed services and access routes are understood.

## 20.4  Soft landings and aftercare

The design and construction teams remain engaged after handover for a defined aftercare period - commonly 12 months, extending through a full seasonal cycle.

An aftercare team, resident on site initially and then on call, resolves operational issues and tunes system performance.

Performance in use is measured against the design intent, and the gap is analysed and acted on rather than explained away.

A post-occupancy evaluation is undertaken and its findings feed both the asset's operation and the client's future briefs.

## 20.5  Documentation and asset data handover

| Deliverable | Content | Required by | Accepted by |
| --- | --- | --- | --- |
| As-built drawings and models | Verified record of the works as constructed, to the agreed tolerance | Practical completion | Information Manager |
| Operation and maintenance manuals | System descriptions, operating procedures, maintenance regimes, spares | 4 weeks before practical completion (draft), final at PC | Operations |
| Asset register data | Populated to the asset information requirements with unique asset identifiers, location, classification and maintenance attributes | Practical completion | Operations |
| Test and commissioning records | All ITPs, test certificates, commissioning results and IST records | Practical completion | Commissioning Manager |
| Statutory certificates and approvals | All certificates required in the jurisdiction for occupation and operation | Before occupation | Client Representative |
| Warranties and guarantees | Executed warranties with commencement dates and claim procedures | Practical completion | Commercial Manager |
| Spares, special tools and consumables | As specified, delivered and receipted | Practical completion | Operations |
| Health and safety file / residual risk information | Residual risks for operation, maintenance, alteration and demolition | Practical completion | Operations |
| Training records and materials | Attendance records, materials, recordings | Practical completion | Operations |
| Building tuning and seasonal plan | Programme for post-handover optimisation | Practical completion | Operations |

## 20.6  Practical completion and taking over

The criteria for practical completion are defined in the contract and are restated in a completion criteria schedule agreed at least three months before the forecast date, so that there is no argument at the moment it matters.

Pre-completion inspections are staged by area and by system, so that defects are found and fixed progressively rather than in a single overwhelming list.

Defects are categorised - Category A prevents completion, Category B must be rectified within a defined period, Category C is minor and tracked to closure.

Practical completion is certified only when the criteria are met, including the statutory approvals required for occupation and the operational readiness confirmation in Section 20.8.

Insurance, security, risk of loss, utilities accounts and maintenance responsibility transfer on the date recorded in the certificate; the transfer is confirmed in writing to all parties.

## 20.7  Defects liability administration

A single defects register is maintained from the first pre-completion inspection through to the end of the defects liability period.

The operator reports defects through one defined channel with a defined response and rectification time by severity.

Latent and recurring defects are escalated and investigated for root cause; a repeated defect is a system failure, not a maintenance item.

The final defects certificate is issued only when every notified defect is verified closed, and it triggers release of the remaining security.

| Category | Definition | Response time | Rectification time |
| --- | --- | --- | --- |
| Category A - critical | Prevents safe or lawful occupation or operation | Immediate | Before practical completion |
| Category B - major | Materially affects use, performance or appearance | 1 working day | Within 20 working days |
| Category C - minor | Does not affect use | 5 working days | Within the defects liability period |
| Emergency during DLP | Loss of an essential service or a safety hazard | Within 2 hours | Make safe immediately; rectify within 24 hours |

## 20.8  Operational readiness

Operational readiness runs in parallel with construction, not after it, and is owned by the operator with support from the project.

Readiness activities include: recruitment and rostering; operating procedures; maintenance contracts and strategy; spares and consumables; IT and communications; security and access; cleaning and waste; signage and wayfinding; supply arrangements; insurance; licences to operate; and the migration or decant plan.

A readiness checklist is maintained with an owner and a due date for every item, reported monthly and weekly from six months out.

Go / no-go readiness reviews are held at three months, one month and two weeks before the planned operational date.

Refer to the Handover Checklist for the detailed item-by-item requirement.

## 20.9  Benefits realisation handover

Accountability for realising the benefits transfers from the project to the business owner at handover. The transfer is formal: the benefits register, the measurement baseline, the data sources and the review schedule are handed over and accepted, and the date of the post-implementation review is set. See Section 21.

## 20.10  Project closeout

| Closeout activity | Owner | Evidence | Complete by |
| --- | --- | --- | --- |
| Final account agreed and paid | Commercial Manager | Signed final account | Per contract |
| All claims and disputes resolved | Commercial Manager | Settlement records | Before final certificate |
| Securities and retention released | Commercial Manager | Release confirmations | Per contract |
| All defects closed and final certificate issued | Client Representative | Final defects certificate | End of DLP |
| Asset capitalised and entered into the asset register | Client finance | Capitalisation record | Within 3 months of PC |
| Project records archived | Document Controller | Complete CDE archive with retention applied | Within 3 months of PC |
| Team demobilised and resources released | Project Manager | Demobilisation record | Per plan |
| Contracts and appointments formally closed | Commercial Manager | Closure letters | At final certificate |
| Lessons learned finalised and transmitted | Project Manager | Lessons register and PMO submission | Within 1 month of PC |
| Closeout report approved | Project Manager | Sponsor approval | Within 3 months of PC |
| Post-implementation review completed | Sponsor | Review report | 6-12 months after handover |

Refer to the Closeout Checklist for the detailed item-by-item requirement.

# 21.  Benefits realisation

## 21.1  Approach

Guidance The project does not exist to produce an asset; it exists to produce a benefit. Name the person in the business who is accountable for each benefit, and confirm they accept it - a benefit owned by the project team is a benefit that will never be measured, because the project team will have moved on.

Benefits are defined in the business case, refined during delivery, and measured after the asset is in use. The project is accountable for creating the capability; the business owner is accountable for converting that capability into benefit.

## 21.2  Benefits map

The benefits map traces the logic from project outputs through capabilities and business changes to measurable outcomes and, ultimately, to strategic objectives. Insert the map below and test every link: if a step cannot be explained, the benefit is not real.

[Insert benefits map - outputs → capabilities → business change → outcomes → strategic objectives]

## 21.3  Benefits register

| Ref | Benefit | Type | Measure | Baseline | Target | Realisation date | Owner | Dependency |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B01 |  | Financial - cost saving |  |  |  |  |  |  |
| B02 |  | Financial - revenue |  |  |  |  |  |  |
| B03 |  | Service - capacity |  |  |  |  |  |  |
| B04 |  | Service - quality |  |  |  |  |  |  |
| B05 |  | Compliance / risk reduction |  |  |  |  |  |  |
| B06 |  | Safety |  |  |  |  |  |  |
| B07 |  | Environmental / carbon |  |  |  |  |  |  |
| B08 |  | Social / community |  |  |  |  |  |  |
| B09 |  | Staff / user experience |  |  |  |  |  |  |
| B10 |  | Whole-of-life cost |  |  |  |  |  |  |

## 21.4  Measurement approach

Every benefit has a baseline measured before the change; a benefit without a baseline cannot be evidenced.

The measurement method, data source, frequency and responsible party are agreed before handover.

Double counting across benefits and across projects in the same programme is explicitly checked and eliminated.

Disbenefits - the things that get worse - are recorded and reported alongside benefits.

Benefit forecasts are updated whenever scope changes materially; the change control process in Section 18 requires a benefits impact assessment.

## 21.5  Post-implementation review

| Review | Timing | Focus | Owner | Reported to |
| --- | --- | --- | --- | --- |
| Handover review | At practical completion | Delivery performance, outstanding items, readiness | Project Manager | Sponsor |
| Early benefits review | 3-6 months after handover | Asset performance in use, early benefit indicators, defects | Business owner | Sponsor |
| Post-implementation review | 12 months after handover | Benefits realised against target, cost and schedule outturn, lessons | Sponsor | Investment authority |
| Benefits sustainment review | 24-36 months after handover | Whether benefits are being sustained and the asset performs as designed | Business owner | Investment authority |

## 21.6  Transition to business as usual

The business change required to realise the benefits - new processes, roles, ways of working - is planned and resourced alongside the physical works, not after them.

The transition plan names what changes, who changes it, when, and how it will be sustained.

Ongoing operating and maintenance budget is confirmed before handover; an asset handed over without a funded operating budget will degrade.

Whole-of-life asset management responsibilities transfer in accordance with ISO 55000 principles and the client's asset management framework.

# 22.  Plan maintenance and continuous improvement

## 22.1  Review and update

This plan is reviewed against the triggers in Section 1.5. Each review confirms that the plan still describes how the project is actually run, that the organisation and authorities are current, and that the controls remain proportionate to the risk.

| Review | Scope | Owner | Approval |
| --- | --- | --- | --- |
| Stage gate review | Full document | Project Manager | Sponsor |
| Periodic review | Full document | Project Manager | Project Director |
| Targeted revision | Affected sections only | Section owner | Project Manager or above per Section 4.6 |
| Administrative update | Names, contacts, dates only | Document Controller | Project Manager |

## 22.2  Lessons learned process

Capture - anyone may raise a lesson at any time through the lessons register.

Facilitate - structured sessions at each stage gate, after each major package, and after any significant incident, claim or dispute.

Analyse - identify the root cause and whether the lesson is specific to this project or applicable to the portfolio.

Act - convert each accepted lesson into a specific change: to this plan, to a process, to a template, to a specification or to a procurement requirement.

Share - transmit portfolio-relevant lessons to the PMO within 20 working days.

Verify - confirm at the next gate that the change was actually made. A lesson that changes nothing has not been learned.

| Ref | Lesson | Category | Root cause | Recommendation | Change made to | Owner | Verified |
| --- | --- | --- | --- | --- | --- | --- | --- |
| LL-01 |  |  |  |  |  |  |  |
| LL-02 |  |  |  |  |  |  |  |
| LL-03 |  |  |  |  |  |  |  |
| LL-04 |  |  |  |  |  |  |  |
| LL-05 |  |  |  |  |  |  |  |

## 22.3  Knowledge management

Project knowledge - decisions, rationale, precedents and data - is captured in the common data environment as it is created, so that it survives personnel change.

Decision rationale is recorded at the time; reconstructing why a decision was made two years later is unreliable and expensive.

Benchmark data - rates, durations, productivity, carbon intensity - is captured in a form the organisation can reuse on the next project.

Key documents are handed to the PMO at closeout in a reusable form, not merely archived.

## 22.4  Continuous improvement register

| Ref | Improvement opportunity | Source | Benefit | Owner | Target date | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CI-01 |  |  |  |  |  |  |
| CI-02 |  |  |  |  |  |  |
| CI-03 |  |  |  |  |  |  |
| CI-04 |  |  |  |  |  |  |
| CI-05 |  |  |  |  |  |  |

# Appendix A - Milestone schedule

Guidance Reproduce the approved milestone set from Section 8.5, adding the baseline date on approval. Forecast and actual dates are updated each month; variance is the difference between forecast and baseline, and is the number the Board reads first.

| Ref | Milestone | Predecessor | Baseline date | Forecast date | Actual date | Variance (days) | Tolerance | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M01 |  |  |  |  |  |  |  |  |  |
| M02 |  |  |  |  |  |  |  |  |  |
| M03 |  |  |  |  |  |  |  |  |  |
| M04 |  |  |  |  |  |  |  |  |  |
| M05 |  |  |  |  |  |  |  |  |  |
| M06 |  |  |  |  |  |  |  |  |  |
| M07 |  |  |  |  |  |  |  |  |  |
| M08 |  |  |  |  |  |  |  |  |  |
| M09 |  |  |  |  |  |  |  |  |  |
| M10 |  |  |  |  |  |  |  |  |  |
| M11 |  |  |  |  |  |  |  |  |  |
| M12 |  |  |  |  |  |  |  |  |  |
| M13 |  |  |  |  |  |  |  |  |  |
| M14 |  |  |  |  |  |  |  |  |  |

# Appendix B - RACI matrix

Guidance Complete one row per delivery activity. Exactly one A per row. Add columns for project-specific roles and delete those that do not apply. Review at every stage gate - responsibilities that were right in design are rarely right in construction.

| Activity | SPO | PD | PM | CM | DM | PL | HSE | QM | IM | ESG | OPS | CON |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approve the business case and funding |  |  |  |  |  |  |  |  |  |  |  |  |
| Approve this PEP |  |  |  |  |  |  |  |  |  |  |  |  |
| Maintain this PEP |  |  |  |  |  |  |  |  |  |  |  |  |
| Define the design brief |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage design delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| Approve design deliverables |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake safety in design |  |  |  |  |  |  |  |  |  |  |  |  |
| Obtain statutory approvals |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop the procurement strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| Prequalify tenderers |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluate tenders |  |  |  |  |  |  |  |  |  |  |  |  |
| Award contracts |  |  |  |  |  |  |  |  |  |  |  |  |
| Administer the contract |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and baseline the schedule |  |  |  |  |  |  |  |  |  |  |  |  |
| Update and report the schedule |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess extensions of time |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepare and maintain the cost plan |  |  |  |  |  |  |  |  |  |  |  |  |
| Value work and certify payment |  |  |  |  |  |  |  |  |  |  |  |  |
| Forecast cost at completion |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage the risk register |  |  |  |  |  |  |  |  |  |  |  |  |
| Approve contingency drawdown |  |  |  |  |  |  |  |  |  |  |  |  |
| Raise and assess change |  |  |  |  |  |  |  |  |  |  |  |  |
| Authorise change |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage the quality system |  |  |  |  |  |  |  |  |  |  |  |  |
| Release hold points |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage site HSE performance |  |  |  |  |  |  |  |  |  |  |  |  |
| Investigate incidents |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage environmental compliance |  |  |  |  |  |  |  |  |  |  |  |  |
| Report sustainability performance |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage stakeholders and communications |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage interfaces |  |  |  |  |  |  |  |  |  |  |  |  |
| Set the information standard |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage the CDE |  |  |  |  |  |  |  |  |  |  |  |  |
| Plan and manage commissioning |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliver training |  |  |  |  |  |  |  |  |  |  |  |  |
| Confirm operational readiness |  |  |  |  |  |  |  |  |  |  |  |  |
| Accept handover |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage defects |  |  |  |  |  |  |  |  |  |  |  |  |
| Agree the final account |  |  |  |  |  |  |  |  |  |  |  |  |
| Close out contracts |  |  |  |  |  |  |  |  |  |  |  |  |
| Capture lessons learned |  |  |  |  |  |  |  |  |  |  |  |  |
| Report benefits realisation |  |  |  |  |  |  |  |  |  |  |  |  |

SPO Sponsor · PD Project Director · PM Project Manager · CM Commercial Manager · DM Design Manager · PL Planner · HSE HSE Manager · QM Quality Manager · IM Information Manager · ESG Environmental and Sustainability Lead · OPS Operations Representative · CON Contractor

# Appendix C - Risk register template

Guidance Write each risk as cause → event → consequence. Rate inherent risk first, then residual after planned treatment. Every treatment needs an owner and a date; every risk needs a proximity so the team knows when to worry about it.

| ID | Category | Risk (cause → event → consequence) | Owner | Existing controls | Inh. L | Inh. C | Inh. rating | Treatment | Action owner | Due | Res. L | Res. C | Res. rating | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R02 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R03 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R07 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R08 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R09 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Appendix D - Interface register template

Guidance Every interface has two named owners - one on each side - and one date. If either is missing, the interface is not managed.

| ID | Class | Interface description | Party A | Party A owner | Party B | Party B owner | Deliverable required | Required by | Status | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IF-01 |  |  |  |  |  |  |  |  |  |  |
| IF-02 |  |  |  |  |  |  |  |  |  |  |
| IF-03 |  |  |  |  |  |  |  |  |  |  |
| IF-04 |  |  |  |  |  |  |  |  |  |  |
| IF-05 |  |  |  |  |  |  |  |  |  |  |
| IF-06 |  |  |  |  |  |  |  |  |  |  |
| IF-07 |  |  |  |  |  |  |  |  |  |  |
| IF-08 |  |  |  |  |  |  |  |  |  |  |
| IF-09 |  |  |  |  |  |  |  |  |  |  |
| IF-10 |  |  |  |  |  |  |  |  |  |  |

# Appendix E - Change register template

Guidance Record every change, including those rejected and withdrawn - the rejected ones are the evidence that the process is working. Track the cumulative approved value against the original contract sum.

| ID | Title | Category | Originator | Date raised | Cost impact | Time impact (days) | Risk impact | Funding source | Assessed by | Approved by | Decision date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CR-01 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-02 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-03 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-04 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-05 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-06 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-07 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-08 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-09 |  |  |  |  |  |  |  |  |  |  |  |  |
| CR-10 |  |  |  |  |  |  |  |  |  |  |  |  |

# Appendix F - KPI reporting template

Guidance Report actual against target every period and record the trend arrow. Any indicator breaching its threshold requires a written action with an owner and a date - an amber KPI with no action is a reporting failure, not a performance one.

| # | KPI | Formula | Target | Threshold | This period | Last period | Trend | Status | Action required | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 01 |  |  |  |  |  |  |  |  |  |  |
| 02 |  |  |  |  |  |  |  |  |  |  |
| 03 |  |  |  |  |  |  |  |  |  |  |
| 04 |  |  |  |  |  |  |  |  |  |  |
| 05 |  |  |  |  |  |  |  |  |  |  |
| 06 |  |  |  |  |  |  |  |  |  |  |
| 07 |  |  |  |  |  |  |  |  |  |  |
| 08 |  |  |  |  |  |  |  |  |  |  |
| 09 |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |

# Appendix G - Meeting and reporting calendar

Guidance Publish the calendar at the start of each year and hold to it. Reporting cut-offs must fall before the meetings that consume them, and Board papers must be issued far enough ahead to be read.

| Working day | Activity | Type | Owner | Input required from | Output |
| --- | --- | --- | --- | --- | --- |
| WD -3 (25th) | Schedule and payment claim cut-off | Cut-off | Contractor | Site records | Progress claim and updated programme |
| Last working day | Cost and commitment cut-off | Cut-off | Cost Manager | Finance system | Cost ledger position |
| WD 1 | Site progress verification | Activity | Project Manager | Contractor | Verified progress |
| WD 2 | Schedule update and analysis | Activity | Planner | Verified progress | Updated schedule |
| WD 3 | Risk register update | Activity | Risk Manager | Risk owners | Updated register |
| WD 4 | Cost report drafted | Report | Cost Manager | Commitments, accruals, forecasts | Draft cost report |
| WD 5 | Schedule, risk and quality reports issued | Report | Discipline leads | Updated registers | Discipline reports |
| WD 5 | Project Control Group meeting | Meeting | Project Director | Discipline reports | Actions and decisions |
| WD 7 | Monthly project report drafted | Report | Project Manager | All discipline reports | Draft report |
| WD 8 | Monthly project report issued | Report | Project Manager | Reviewed draft | Issued report |
| WD 10 | Board pack issued | Report | Project Manager | Monthly report and decision papers | Board pack |
| WD 15 | Project Board meeting | Meeting | Sponsor | Board pack | Minutes and decisions |
| Weekly - Monday | Delivery team meeting | Meeting | Project Manager | Look-aheads | Actions |
| Weekly - Tuesday | Design coordination meeting | Meeting | Design Manager | Clash and RFI status | Design actions |
| Weekly - Wednesday | Site progress meeting | Meeting | Project Manager | Contractor report | Minutes |
| Weekly - Thursday | HSE walk and toolbox review | Activity | HSE Manager | Site inspection | HSE actions |
| Monthly | Risk workshop | Meeting | Risk Manager | Register | Updated register |
| Monthly | HSE committee | Meeting | HSE Manager | HSE report | HSE actions |
| Monthly | Interface forum | Meeting | Project Manager | Interface register | Updated register |
| Monthly | Operational readiness group | Meeting | Operations Rep | Readiness checklist | Readiness status |
| Quarterly | Assurance review | Assurance | Assurance Lead | All registers and reports | Assurance report |
| At each gate | Gateway review and lessons session | Assurance | Independent reviewer | Gate submission | Gate report and lessons |

# Appendix H - Document numbering convention

Guidance Agree the convention before the first document is issued and enforce it in the CDE. Changing a numbering convention mid-project is one of the most expensive administrative mistakes a project can make.

Format:  PROJECT - ORIGINATOR - VOLUME/SYSTEM - LEVEL/LOCATION - TYPE - DISCIPLINE - NUMBER  [ - REVISION - STATUS ]

| Field | Length | Description | Examples |
| --- | --- | --- | --- |
| Project | 2-6 | Fixed project code | ABC1 |
| Originator | 3-6 | Organisation producing the information | MST, ARC, STR, MEP, CON |
| Volume / system | 2 | Building, zone or system | ZZ (all), 01, 02 |
| Level / location | 2 | Floor or location | ZZ, GF, 01, B1, XX |
| Type | 2 | Information type | DR drawing, MO model, SP specification, RP report, SH schedule, CA calculation, PP presentation, PH photograph |
| Discipline | 1-2 | Originating discipline | A architectural, S structural, C civil, M mechanical, E electrical, P public health, F fire, L landscape, Q quantity surveying, Z general |
| Number | 4-6 | Sequential within the preceding fields | 0001 |
| Revision | 2-3 | Alphabetic in development, numeric from first issue for construction | P01, C01, A, B, 0, 1 |
| Status | 2 | Suitability code | S0 WIP, S1 coordination, S2 information, S3 review and comment, S4 stage approval, A1 authorised for construction, B1 authorised with comments |

Example: ABC1-MST-ZZ-GF-DR-A-0101-C02-A1 - project ABC1, originated by MST, all volumes, ground floor, drawing, architectural, number 0101, revision C02, authorised for construction.

Numbers are never reused, even after a document is withdrawn.

The number is fixed for the life of the document; only the revision and status change.

Every register - drawings, models, specifications, RFIs, NCRs, ITPs, certificates - uses the same project and originator codes.

The convention applies equally to models, documents and containers in the CDE.

# Appendix I - PEP completeness checklist

Guidance Work through this before issuing any revision of the plan. An incomplete PEP that has been signed is worse than a draft that hasn't - it creates the appearance of control without the substance.

| Section | Check | Complete (Y/N) | Evidence / reference | Checked by | Date |
| --- | --- | --- | --- | --- | --- |
| Front matter | Revision history complete and the current revision recorded |  |  |  |  |
| Front matter | Distribution list current, with copy types assigned |  |  |  |  |
| Front matter | Related documents register complete with versions relied on |  |  |  |  |
| Front matter | Approval block signed by all required signatories |  |  |  |  |
| Front matter | Table of contents updated |  |  |  |  |
| Front matter | Glossary reviewed; project-specific terms added |  |  |  |  |
| 1 Introduction | Purpose written specifically for this project |  |  |  |  |
| 1 Introduction | Review triggers and deviation process understood by the team |  |  |  |  |
| 2 Overview | Objectives have measures, targets, tolerances and owners |  |  |  |  |
| 2 Overview | Project characteristics table complete |  |  |  |  |
| 3 Scope | In-scope and out-of-scope tables complete and reconciled |  |  |  |  |
| 3 Scope | Assumptions have validation dates and owners |  |  |  |  |
| 3 Scope | Change authority thresholds inserted and reconciled with Sections 4 and 9 |  |  |  |  |
| 4 Governance | Organisation chart inserted and current |  |  |  |  |
| 4 Governance | All roles filled or shown as vacant with a mobilisation date |  |  |  |  |
| 4 Governance | RACI complete with exactly one A per row |  |  |  |  |
| 4 Governance | Delegation thresholds copied from the client's delegation instrument |  |  |  |  |
| 4 Governance | Gateway dates included in the baseline schedule |  |  |  |  |
| 5 Stakeholders | Stakeholder register complete with relationship owners |  |  |  |  |
| 5 Stakeholders | Communications matrix agreed with the client's communications function |  |  |  |  |
| 6 Procurement | Delivery model selected, justified and approved |  |  |  |  |
| 6 Procurement | Procurement plan dates reconciled with the baseline schedule |  |  |  |  |
| 6 Procurement | Probity arrangements confirmed |  |  |  |  |
| 7 Design | Design responsibility matrix complete |  |  |  |  |
| 7 Design | Design freeze points agreed with the procurement programme |  |  |  |  |
| 7 Design | Independent verification scope defined |  |  |  |  |
| 8 Schedule | Baseline schedule approved and archived |  |  |  |  |
| 8 Schedule | Milestones have definitions of achievement and tolerances |  |  |  |  |
| 8 Schedule | Schedule risk analysis completed |  |  |  |  |
| 9 Cost | Control accounts established and reconciled to the WBS |  |  |  |  |
| 9 Cost | Contingency basis documented and drawdown authority set |  |  |  |  |
| 9 Cost | Cash flow forecast issued to the client's finance function |  |  |  |  |
| 10 Risk | Risk register populated with owners and treatments |  |  |  |  |
| 10 Risk | Likelihood and consequence scales calibrated to this project |  |  |  |  |
| 10 Risk | Insurance summary complete with periods of cover |  |  |  |  |
| 11 Quality | Quality objectives and targets agreed |  |  |  |  |
| 11 Quality | ITP regime and hold points defined |  |  |  |  |
| 12 HSE | Duties assigned and safety plan acceptance process defined |  |  |  |  |
| 12 HSE | Emergency response arrangements in place and tested |  |  |  |  |
| 13 ESG | Approvals register complete with condition tracking |  |  |  |  |
| 13 ESG | Sustainability targets have measurement methods and owners |  |  |  |  |
| 14 Information | EIR issued and BEP accepted |  |  |  |  |
| 14 Information | CDE established and access controlled |  |  |  |  |
| 14 Information | Numbering convention agreed and enforced |  |  |  |  |
| 15 Interfaces | Interface register populated with owners on both sides |  |  |  |  |
| 15 Interfaces | Utility and authority lead times reflected in the schedule |  |  |  |  |
| 16 Resources | Resourcing plan funded and mobilisation dates set |  |  |  |  |
| 16 Resources | Key person dependencies identified and mitigated |  |  |  |  |
| 17 Commercial | Contract summary prepared and notice dates diarised |  |  |  |  |
| 17 Commercial | Securities and insurances verified |  |  |  |  |
| 18 Change | Change register established and thresholds set |  |  |  |  |
| 19 Reporting | Report suite agreed and data sources confirmed |  |  |  |  |
| 19 Reporting | KPIs selected with formulas, targets and owners |  |  |  |  |
| 20 Handover | Commissioning manager appointed and programme integrated |  |  |  |  |
| 20 Handover | Operational readiness owner confirmed and checklist started |  |  |  |  |
| 21 Benefits | Benefits register complete with baselines and owners |  |  |  |  |
| 22 Improvement | Lessons register established and review cadence set |  |  |  |  |
| Overall | Plan reviewed against the contract for inconsistency |  |  |  |  |
| Overall | Plan issued to everyone on the distribution list |  |  |  |  |
| Overall | Superseded revision withdrawn from circulation |  |  |  |  |

# About this template

Mastt builds software for capital project owners - planning, tracking and reporting cost, schedule, risk and delivery performance across a portfolio of projects. This template is one of a series covering the documents a capital delivery team needs from initiation to closeout.

Visit mastt.com

This template is provided by Mastt as general guidance for capital project delivery. It is not legal, financial or professional advice. Users must adapt it to the contract, jurisdiction, statutory regime and organisational policies applicable to their project, and should obtain independent professional advice where appropriate. Mastt accepts no liability arising from use of this template.