## Cover
Cost Benefit Analysis Template
Capital project economic appraisal - global edition
Purpose
A complete, formula-driven cost benefit analysis model for capital projects. It discounts whole-of-life costs and monetised benefits over an appraisal period, applies optimism bias and risk adjustment, and reports NPV, BCR, IRR and payback with full sensitivity, switching-value, options, risk and distributional analysis. Built to the common core of international appraisal practice and shipped with a worked example you can replace.
How to use this template
• Start on the Instructions sheet, then set every driver on the Inputs & Assumptions sheet - the whole model runs from there.
• Set the real discount rate mandated by your jurisdiction or organisation. The 7% shown is a neutral placeholder only.
• Replace the example cost and benefit line items with your own. Year profiles, subtotals and the cash flow build themselves.
• Read the Results sheet for the headline appraisal, then the Sensitivity sheet for robustness and switching values.
• Record non-monetised and distributional impacts - a monetised NPV alone is not a business case.
• White cells are your inputs, tinted blue cells are assumptions to evidence, off-white cells are calculated - do not overtype them.
Scope, standards and jurisdiction
• Jurisdiction-neutral. Aligned to the common core of HM Treasury's Green Book, Infrastructure Australia's assessment framework, the European Commission's CBA Guide, and World Bank and ADB economic appraisal practice.
• No jurisdiction's mandated discount rate, optimism bias uplift or carbon value is asserted. Every such parameter is an editable assumption you must set from your own policy source.
• Covers social and economic CBA and financial CBA. Keep the two separate in reporting - transfer payments belong in the distributional table, not the economic NPV.
• All values are incremental: with-project minus the Base Case (do-minimum). Analysis is in real (constant) prices by default, with a nominal option.
• Every example figure in this workbook is illustrative and must be replaced before the model is relied on.
Document control
Field | Detail | Field | Detail
Template name | Cost Benefit Analysis Template | Template version | 1.0
Project name |  | Project number
Client / asset owner |  | Prepared by
Date prepared |  | Reviewed by
Revision |  | Approved by
Disclaimer
This template is provided by Mastt as general guidance for capital project delivery. It is not legal, financial or professional advice. Users must adapt it to the contract, jurisdiction, statutory regime and organisational policies applicable to their project, and should obtain independent professional advice where appropriate. Mastt accepts no liability arising from use of this template.
Built for capital project teams - plan, track and report with Mastt. |  |  |  | Visit mastt.com ↗

## Instructions
Instructions
How to use this model, what to change, and how to read the outputs.
What this model does
This is a discounted cash flow cost benefit analysis for a capital project. It compares a with-project option against a Base Case (do-minimum) on an incremental basis, discounts the resulting cost and benefit streams over an appraisal period, and reports NPV, BCR, IRR and payback together with sensitivity, switching values, options comparison, quantified risk and distributional analysis. The structure is jurisdiction-neutral and follows the common core of international appraisal practice - HM Treasury's Green Book, Infrastructure Australia's assessment framework, the European Commission's CBA Guide, and World Bank and ADB economic analysis guidance. It does not assert any single jurisdiction's mandated parameters. You must set the discount rate, optimism bias uplift, carbon price and appraisal period required by your own jurisdiction or organisation.
Cell colour convention
Appearance | Meaning | What you should do
White cell with a thin border | User input | Type your own value here. These are the raw data of your appraisal.
Tinted blue | Assumption | A judgement or policy parameter. Review every one, evidence it, and record the source.
Off-white tint | Calculated - do not edit | Contains a live formula. Overtyping breaks the model. Change the driver on the Inputs sheet instead.
Order of operations
Step | Sheet | What to do
1 | Inputs & Assumptions | Set the project name, currency label, price base year and analysis start year. Then set the appraisal period, construction period and - most importantly - the real discount rate mandated by your jurisdiction or organisation. The 7% default is a neutral placeholder, not a recommendation.
2 | Inputs & Assumptions | Set the optimism bias uplift and contingency percentage, the residual value method and asset life, the benefit ramp-up period and the carbon price. Decide whether you are working in real or nominal terms.
3 | Cost Inputs | Replace the example cost lines with your own. For each line set the Type (Capital, Operating or Lifecycle), the Profile, the Amount, the Start year index and the Duration or interval. The year columns fill themselves.
4 | Benefit Inputs | Replace the example benefit lines. Enter the annual value at full realisation, the valuation basis and the source of evidence. The ramp-up factor is applied automatically from the Inputs sheet.
5 | Cash Flow | Read only. Check that the spend and benefit profiles look right year by year. Do not type on this sheet.
6 | Results & Appraisal Summary | Read the headline NPV, BCR, IRR and payback. Record the non-monetised impacts - they are part of the decision, not an afterthought.
7 | Sensitivity Analysis | Check which drivers move the result and how far each has to move before the recommendation changes.
8 | Risk & Optimism Bias | Build the quantified risk register and test whether your contingency covers the residual risk.
9 | Scenario & Options Comparison | Bring in the results of each option's own model run and compare them side by side.
10 | Distributional Impacts | Allocate the costs and benefits across stakeholder groups and record the equity implications.
What to change and what to leave alone
Change freely | Every white input cell, every tinted-blue assumption, and the line items on the Cost Inputs and Benefit Inputs sheets. Add or delete rows within the existing item blocks.
Change with care | The category and profile labels - they feed SUMIF subtotals and the dropdown lists on the Lists sheet. If you add a new Type or Profile, add it to the Lists sheet too.
Do not change | Anything on the Cash Flow sheet, the calculated cells on the Results and Sensitivity sheets, the year index rows on the Cost and Benefit Inputs sheets, or the defined names.
Adding options | This workbook models one option at a time. To appraise a second option, save a copy of the whole workbook, change the option name and the cost and benefit lines, then paste the resulting PV of costs, PV of benefits, IRR and payback into the Option 2 and Option 3 columns on the Scenario & Options Comparison sheet.
Extending the horizon | The model is built with 40 year columns. The appraisal period must not exceed that. To go further, insert additional year columns on the Cost Inputs, Benefit Inputs and Cash Flow sheets and copy the formulas across.
How to read the sensitivity outputs
• The one-way table re-derives NPV and BCR with one driver moved at a time. Everything else is held at its base value.
• The tornado ranks the drivers by how much the NPV moves across the outer sensitivity band. Rank 1 is the driver that matters most - put your estimating and assurance effort there.
• A switching value is the change that drives NPV to exactly zero. A benefits switching value of -30% means benefits could fall by 30% before the case fails. Small switching values mean a fragile case.
• The switching discount rate is the IRR. If it sits close to your mandated discount rate, the case is marginal.
• Negative NPV cells are shaded red and positive cells green throughout the sensitivity sheet.
• Sensitivity is not risk analysis. Use it alongside the quantified risk register, not instead of it.
Glossary of appraisal concepts
Term | Definition
Present value (PV) | The value today of a future cash flow, obtained by multiplying it by the discount factor for the year in which it occurs.
Net present value (NPV) | PV of benefits less PV of costs. The primary decision measure: an option is economically worthwhile when NPV is positive at the mandated discount rate.
Benefit cost ratio (BCR) | PV of benefits divided by PV of costs. Useful for ranking under capital rationing. It should not be used to choose between mutually exclusive options - use incremental NPV.
Net BCR | Net benefits (benefits less recurrent costs) divided by the PV of capital invested. Shows the return on the capital rather than on the whole cost stream.
Internal rate of return (IRR) | The discount rate at which NPV equals zero. Reported for information only: it is undefined or ambiguous when the net cash flow changes sign more than once, and it ignores project scale.
Payback period | The elapsed time until cumulative net benefits turn positive. Reported here both discounted and undiscounted. It ignores everything that happens after payback, so it is a liquidity measure, not a value measure.
Discount rate | The rate used to convert future values to present values. It reflects social time preference and the opportunity cost of capital. It is set by policy in most jurisdictions - never invent one.
Real vs nominal | Real analysis uses constant prices and a real discount rate. Nominal analysis escalates cash flows for inflation and uses a nominal discount rate. NPV is the same either way provided the two are used consistently - mixing them is the most common error in appraisal.
Incremental analysis | All costs and benefits are measured as the difference between the with-project case and the Base Case (do-minimum). Anything that happens in both cases is excluded.
Base Case / do-minimum | The realistic counterfactual - what actually happens if the project does not proceed, including the minimum works needed to keep the asset safe, legal and operating. It is not 'do nothing'.
Residual value | The value of the asset remaining at the end of the appraisal period, recognised as a benefit in the final year. Methods here are a percentage of capital cost or the unexpired share of economic life.
Optimism bias | The demonstrated systematic tendency for appraisers to be too optimistic about capital cost, duration and benefits. Corrected by an explicit uplift drawn from reference-class outturn evidence.
Contingency | A cost allowance for identified risks within the defined scope. It is not the same as optimism bias - contingency covers known risk, optimism bias covers systematic appraisal error. Do not double count.
Switching value | The change in a single input required to drive NPV to zero. It expresses how much headroom the case has before the decision flips.
Sensitivity analysis | Recalculating the result with one or more inputs moved, to show how robust the conclusion is.
Ramp-up | The period over which benefits build from zero to full realisation once the asset is operational. Assuming instant full benefits is a common source of overstatement.
Distributional analysis | Identification of which groups bear the costs and which receive the benefits, and whether the pattern is equitable. Some jurisdictions apply explicit welfare weights.
Non-monetised impacts | Effects that are real and material but cannot be reliably valued in money. They are recorded qualitatively and must be weighed alongside the NPV, not ignored because they lack a number.
PERT expected value | A three-point estimate weighting: (minimum + 4 x most likely + maximum) / 6. Used on the Risk sheet, then multiplied by likelihood to give the expected cost of each risk.
Equivalent annual value | The NPV expressed as a constant annual amount over the appraisal period. Use the equivalent annual cost to compare options with different asset lives.
ILLUSTRATIVE WORKED EXAMPLE - every value shown is example data for a mid-size community health and aquatic centre. Replace all example figures with your own project data before use. The worked example is a mid-size community health and aquatic centre with roughly 45 million of base capital cost, a three-year delivery programme and a 30-year appraisal period.

## Inputs & Assumptions
Inputs & Assumptions
The single control sheet - every calculation in this workbook is driven from here.
ILLUSTRATIVE WORKED EXAMPLE - every value shown is example data for a mid-size community health and aquatic centre. Replace all example figures with your own project data before use.
A. Project identification
Input | Value | Unit | Guidance / source
Project name | Riverside Community Health & Aquatic Centre | text | Free text. Appears on the Results sheet.
Option / scenario name | Option 1 - New integrated facility | text | The with-project option being appraised against the Base Case (do-minimum).
Base Case description | Do-minimum - continue operating the existing 1974 facility with reactive repairs | text | All costs and benefits in this workbook are INCREMENTAL: with-project minus Base Case.
Currency label | USD | text | Purely a label. All money cells are formatted #,##0 in this unit - no FX conversion is applied.
Price base year | 2026 | year | The year in which real prices are expressed. Keep costs and benefits on the same price base.
Analysis start year (Year 0) | 2026 | year | Year index 0. Drives every calendar year label in the model.
B. Appraisal period and discounting
Input | Value | Unit | Guidance / source
Appraisal period | 30 | years | Length of the evaluation horizon. Must not exceed the model horizon below.
Model horizon (maximum periods built) | 40 | years | Fixed structural limit - the number of year columns built into this workbook. To go beyond it, extend the year columns on the Cost Inputs, Benefit Inputs and Cash Flow sheets.
Construction / delivery period | 3 | years | Year indices 0 to n-1 are the delivery phase; operations and benefits begin at year index n.
Real discount rate (social / economic) | 7% | % p.a. | SET THE RATE MANDATED BY YOUR JURISDICTION OR ORGANISATION. 7% is a neutral placeholder only. Practice varies widely - HM Treasury Green Book uses a 3.5% social time preference rate, Infrastructure Australia has used 7% real with 4% and 10% sensitivities, the EU CBA Guide suggests 3-5% social / 4% financial, and World Bank and ADB appraisals commonly use 6-12%.
Apply declining long-run discount rate? | No | Yes / No | If Yes, the rate steps down for distant years (x1.000 to year 30, x0.857 to year 75, x0.714 beyond) in the style of the Green Book declining schedule. Has no effect on a 30-year appraisal.
Price basis | Real | Real / Nominal | Real = constant prices, real discount rate. Nominal = cash flows escalated at the inflation rate below and discounted at the Fisher-adjusted nominal rate. NPV is invariant between the two - a useful integrity check.
Inflation / escalation rate | 2.5% | % p.a. | Used only when Price basis = Nominal. Applied to all cash flows and to the discount rate.
Effective discount rate applied | 7% | % p.a. | Calculated. Fisher relation: (1+real)(1+inflation)-1 when working in nominal terms.
C. Risk, optimism bias and contingency
Input | Value | Unit | Guidance / source
Optimism bias uplift on capital cost | 15% | % | Systematic appraisal optimism correction applied to total capital cost in the Cash Flow. Set from your reference-class evidence - see the reference table on the Risk & Optimism Bias sheet.
Contingency allowance | 12% | % | Drives the contingency line item on the Cost Inputs sheet (a percentage of base capital cost). Compare against the quantified risk register on the Risk & Optimism Bias sheet.
D. Residual value
Input | Value | Unit | Guidance / source
Residual value method | Straight-line remaining life | method | '% of capex' applies the percentage below. 'Straight-line remaining life' values the unexpired portion of the asset's economic life. 'None' sets residual value to zero.
Asset economic life | 50 | years | Used by the straight-line remaining life method.
Residual value as % of capital cost | 15% | % | Used only when the method above is '% of capex'.
Total capital cost from Cost Inputs (incl. contingency, excl. optimism bias) | 50500800 | amount | Calculated from the Cost Inputs sheet - the sum of every line item typed as Capital, including the contingency line.
Residual value (recognised in the final appraisal year) | 20200320 | amount | Calculated. Recognised as a benefit in year index (Appraisal period - 1).
E. Benefit realisation and valuation
Input | Value | Unit | Guidance / source
Benefit ramp-up period | 3 | years | Years from the start of operations to full benefit realisation. A linear ramp is applied on the Benefit Inputs sheet.
Carbon price | 75 | per tonne CO2-e | Used to value the energy and carbon benefit line. Use the shadow carbon price mandated by your jurisdiction.
Annual carbon abatement | 4200 | tCO2-e p.a. | Tonnes of CO2-e avoided each year once the asset is operational.
F. Sensitivity settings
Input | Value | Unit | Guidance / source
Sensitivity step 1 | 10% | % | Inner sensitivity band applied to every driver on the Sensitivity Analysis sheet.
Sensitivity step 2 | 20% | % | Outer sensitivity band. Also drives the tornado swing ranking.
Discount rate sensitivity point - low | 3.5% | % p.a. | Explicit discount rate test point (e.g. a social time preference rate).
Discount rate sensitivity point - central | 7% | % p.a. | Explicit discount rate test point.
Discount rate sensitivity point - high | 10% | % p.a. | Explicit discount rate test point.
Cell colour convention
White with a thin border | User input - type over these
Tinted blue | Assumption - a judgement or policy parameter you should review
Off-white | Calculated - contains a formula, do not overtype
Named drivers available in formulas: ApprYears, AssetLife, BaseCaseDesc, CapexTotal, CarbonPrice, CarbonTonnes, ConstrYears, ContPct, CurrLabel, DRHigh, DRLow, DRMid, DeclineDR, DiscRate, EffDiscRate, InflRate, MaxYears, OptBias, OptName, PriceBase, PriceBasis, ProjName, RampYears, ResidMethod, ResidPct, ResidVal, SensA, SensB, StartYear

## Cost Inputs
Cost Inputs
Whole-of-life incremental costs by line item, spread across the appraisal horizon by formula.
ILLUSTRATIVE WORKED EXAMPLE - every value shown is example data for a mid-size community health and aquatic centre. Replace all example figures with your own project data before use.
Cost line items - incremental (with-project minus Base Case) | [5 empty] | Amount, start year and duration drive the year profile.
[10 empty] | Year index → | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Ref | Category | Cost item | Type | Profile | Amount | Start year (idx) | Duration / interval (yrs) | Basis of estimate | Confidence | Total (undiscounted) | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065
C-01 | Land and acquisition | Site acquisition | Capital | Spread | 3200000 | 0 | 1 | Independent market valuation | Medium | 3200000 | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-02 | Land and acquisition | Site remediation and services relocation | Capital | Spread | 1150000 | 0 | 2 | Contractor budget quotation | Low | 1150000 | 575000 | 575000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-03 | Design and professional fees | Design, engineering and technical advisory | Capital | Spread | 3600000 | 0 | 3 | Percentage of construction value | Medium | 3600000 | 1200000 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-04 | Design and professional fees | Planning, approvals and statutory fees | Capital | Spread | 640000 | 0 | 2 | Published schedule of fees | High | 640000 | 320000 | 320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-05 | Construction | Main works - health and aquatic facility | Capital | Spread | 24800000 | 1 | 2 | Elemental cost plan, P50 | Medium | 24800000 | 0 | 12400000 | 12400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-06 | Construction | Site establishment and preliminaries | Capital | Spread | 2150000 | 1 | 2 | Elemental cost plan, P50 | Medium | 2150000 | 0 | 1075000 | 1075000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-07 | Construction | External works, landscaping and car parking | Capital | Spread | 2900000 | 2 | 1 | Rate per square metre benchmark | Medium | 2900000 | 0 | 0 | 2900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-08 | Client-side costs | Client project management and superintendence | Capital | Spread | 1450000 | 0 | 3 | Resource plan x day rates | High | 1450000 | 483333.3333 | 483333.3333 | 483333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-09 | Client-side costs | Legal, insurances and financing costs | Capital | Spread | 520000 | 0 | 3 | Advisor fee proposals | High | 520000 | 173333.3333 | 173333.3333 | 173333.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-10 | ICT and FF&E | ICT, audio-visual and security systems | Capital | Spread | 1380000 | 2 | 1 | Vendor budget pricing | Medium | 1380000 | 0 | 0 | 1380000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-11 | ICT and FF&E | Furniture, fittings and equipment | Capital | Spread | 1620000 | 2 | 1 | Room data sheets x unit rates | Medium | 1620000 | 0 | 0 | 1620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-12 | Decant and enabling works | Temporary facilities and service decant | Capital | Spread | 780000 | 0 | 2 | Comparable project benchmark | Low | 780000 | 390000 | 390000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-13 | Decant and enabling works | Enabling works and early utilities | Capital | Spread | 900000 | 0 | 1 | Utility authority estimate | Medium | 900000 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-14 | Risk allowance | Contingency allowance (driven by Inputs) | Capital | Spread | 5410800 | 0 | 3 | Percentage of base capital cost from Inputs | Medium | 5410800 | 1803600 | 1803600 | 1803600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-15 | Operating costs | Facility operations and management | Operating | Annual | 1250000 | 3 | 0 | Operating model, FTE and service contracts | Medium | 46250000 | 0 | 0 | 0 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000
C-16 | Staffing | Incremental staffing and workforce costs | Operating | Annual | 1850000 | 3 | 0 | Establishment schedule x award rates | Medium | 68450000 | 0 | 0 | 0 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000 | 1850000
C-17 | Energy and utilities | Energy, water and utilities | Operating | Annual | 520000 | 3 | 0 | Modelled consumption x tariff | Medium | 19240000 | 0 | 0 | 0 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000 | 520000
C-18 | Maintenance | Routine and planned maintenance | Operating | Annual | 430000 | 3 | 0 | Percentage of asset replacement value | Medium | 15910000 | 0 | 0 | 0 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000
C-19 | Operating costs | Insurance, rates and corporate overhead | Operating | Annual | 240000 | 3 | 0 | Corporate policy allocation | High | 8880000 | 0 | 0 | 0 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000 | 240000
C-20 | Maintenance and lifecycle | Plant and equipment renewal (cyclical) | Lifecycle | Periodic | 1400000 | 10 | 10 | Lifecycle model, 10-year cycle | Medium | 4200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-21 | Maintenance and lifecycle | Building fabric and finishes refresh | Lifecycle | Periodic | 950000 | 15 | 15 | Lifecycle model, 15-year cycle | Low | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C-22 | ICT and FF&E | ICT and FF&E replacement cycle | Lifecycle | Periodic | 820000 | 7 | 7 | Asset register replacement cycle | Medium | 4100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 0 | 0
C-23 | Decommissioning | Decommissioning and disposal provision | Lifecycle | Spread | 1200000 | 29 | 1 | Provisional allowance | Low | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | Capital costs - total by year (undiscounted) | [8 empty] | 50500800 | 9045266.6667 | 18420266.6667 | 23035266.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | Operating costs - total by year (undiscounted) | [8 empty] | 158730000 | 0 | 0 | 0 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000
TOTAL | Lifecycle costs - total by year (undiscounted) | [8 empty] | 11400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 1400000 | 0 | 0 | 0 | 820000 | 950000 | 0 | 0 | 0 | 0 | 1400000 | 820000 | 0 | 0 | 0 | 0 | 0 | 0 | 820000 | 1200000 | 2350000 | 0 | 0 | 0 | 0 | 820000 | 0 | 0 | 0 | 0
TOTAL | All costs - total by year (undiscounted) | [8 empty] | 220630800 | 9045266.6667 | 18420266.6667 | 23035266.6667 | 4290000 | 4290000 | 4290000 | 4290000 | 5110000 | 4290000 | 4290000 | 5690000 | 4290000 | 4290000 | 4290000 | 5110000 | 5240000 | 4290000 | 4290000 | 4290000 | 4290000 | 5690000 | 5110000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 4290000 | 5110000 | 5490000 | 6640000 | 4290000 | 4290000 | 4290000 | 4290000 | 5110000 | 4290000 | 4290000 | 4290000 | 4290000
Subtotal by category (SUMIF over the whole appraisal horizon)
Ref | Category | [8 empty] | Total (undiscounted)
S-01 | Land and acquisition | [8 empty] | 4350000
S-02 | Design and professional fees | [8 empty] | 4240000
S-03 | Construction | [8 empty] | 29850000
S-04 | Client-side costs | [8 empty] | 1970000
S-05 | ICT and FF&E | [8 empty] | 7100000
S-06 | Decant and enabling works | [8 empty] | 1680000
S-07 | Risk allowance | [8 empty] | 5410800
S-08 | Operating costs | [8 empty] | 55130000
S-09 | Staffing | [8 empty] | 68450000
S-10 | Energy and utilities | [8 empty] | 19240000
S-11 | Maintenance | [8 empty] | 15910000
S-12 | Maintenance and lifecycle | [8 empty] | 6100000
S-13 | Decommissioning | [8 empty] | 1200000
TOTAL | All categories | [8 empty] | 220630800
Profile key: Spread = amount divided evenly across 'Duration' years from 'Start year'. Annual = amount recurs every year from 'Start year' (duration 0 = to the end of the model horizon). Periodic = amount recurs every 'Interval' years from 'Start year'.

## Benefit Inputs
Benefit Inputs
Monetised incremental benefits, with the ramp-up profile applied by formula from the Inputs sheet.
ILLUSTRATIVE WORKED EXAMPLE - every value shown is example data for a mid-size community health and aquatic centre. Replace all example figures with your own project data before use.
Monetised benefit line items - incremental (with-project minus Base Case) | [5 empty] | Ramped items follow the ramp-up factor row below.
[10 empty] | Year index → | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
[10 empty] | Ramp-up factor → | 0 | 0 | 0 | 0.33333 | 0.66667 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Ref | Category | Benefit item | Profile | Annual value at full realisation | Start year (idx) | Duration (yrs) | Valuation basis | Source of evidence | Confidence | Total (undiscounted) | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065
B-01 | Avoided cost | Avoided operating cost of the legacy facility | Ramped | 2600000 | 3 | 0 | Resource cost saving - avoided expenditure | Legacy facility actual costs, 3-year average | High | 93600000 | 0 | 0 | 0 | 866666.6667 | 1733333.3333 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000
B-02 | Avoided cost | Avoided renewal and deferred maintenance backlog | Ramped | 1450000 | 3 | 0 | Avoided capital renewal, annualised | Condition audit and backlog register | Medium | 52200000 | 0 | 0 | 0 | 483333.3333 | 966666.6667 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000 | 1450000
B-03 | Productivity | Service delivery productivity gains | Ramped | 1150000 | 3 | 0 | Staff hours released x fully loaded hourly cost | Time and motion study, comparable sites | Medium | 41400000 | 0 | 0 | 0 | 383333.3333 | 766666.6667 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000 | 1150000
B-04 | Capacity and throughput | Additional service episodes delivered | Ramped | 2900000 | 3 | 0 | Incremental throughput x unit value of service | Demand model and unit cost benchmarks | Medium | 104400000 | 0 | 0 | 0 | 966666.6667 | 1933333.3333 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000
B-05 | User time savings | User and carer travel time savings | Ramped | 890000 | 3 | 0 | Hours saved x value of travel time savings | Catchment travel model, national VTTS values | Medium | 32040000 | 0 | 0 | 0 | 296666.6667 | 593333.3333 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000 | 890000
B-06 | Energy and carbon | Energy efficiency and carbon abatement | Ramped | 315000 | 3 | 0 | tCO2-e abated x shadow carbon price (from Inputs) | Energy model and jurisdictional carbon values | Medium | 11340000 | 0 | 0 | 0 | 105000 | 210000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000 | 315000
B-07 | Safety | Reduced incidents, injuries and slips | Ramped | 620000 | 3 | 0 | Incidents avoided x value of prevented injury | Incident register and national safety values | Low | 22320000 | 0 | 0 | 0 | 206666.6667 | 413333.3333 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000
B-08 | Revenue and commercial | Memberships, programme fees and commercial hire | Ramped | 2300000 | 3 | 0 | Net incremental revenue (financial CBA line) | Business plan and comparable facility yields | Medium | 82800000 | 0 | 0 | 0 | 766666.6667 | 1533333.3333 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000
B-09 | Wider economic | Wider economic and agglomeration effects | Ramped | 620000 | 3 | 0 | Wider economic impact uplift, capped | Regional economic model | Low | 22320000 | 0 | 0 | 0 | 206666.6667 | 413333.3333 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000 | 620000
B-10 | Compliance | Avoided compliance and regulatory penalties | Ramped | 340000 | 3 | 0 | Expected penalty x probability avoided | Regulator correspondence and notices | Low | 12240000 | 0 | 0 | 0 | 113333.3333 | 226666.6667 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000
B-11 | Disposal | Disposal receipts - legacy site divestment | One-off | 4500000 | 3 | 1 | Net realisable value at disposal | Independent valuation | Medium | 4500000 | 0 | 0 | 0 | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | All monetised benefits - total by year (undiscounted) | [8 empty] | 479160000 | 0 | 0 | 0 | 8895000 | 8790000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000 | 13185000
Subtotal by benefit category (SUMIF over the whole appraisal horizon)
Ref | Category | [8 empty] | Total (undiscounted)
S-01 | Avoided cost | [8 empty] | 145800000
S-02 | Productivity | [8 empty] | 41400000
S-03 | Capacity and throughput | [8 empty] | 104400000
S-04 | User time savings | [8 empty] | 32040000
S-05 | Energy and carbon | [8 empty] | 11340000
S-06 | Safety | [8 empty] | 22320000
S-07 | Revenue and commercial | [8 empty] | 82800000
S-08 | Wider economic | [8 empty] | 22320000
S-09 | Compliance | [8 empty] | 12240000
S-10 | Disposal | [8 empty] | 4500000
TOTAL | All categories | [8 empty] | 479160000
Profile key: Ramped = annual value multiplied by the ramp-up factor row above, from 'Start year' (duration 0 = to the end of the model horizon). One-off = single amount in 'Start year'. Periodic = amount recurs every 'Duration' years. Residual value is NOT entered here - it is derived on the Inputs sheet and recognised in the Cash Flow.

## Cash Flow
Cash Flow & Discounting
The calculation engine - one row per year. Every cell is a formula. This sheet is the source of truth for all results.
Do not overtype anything on this sheet. Change the drivers on the Inputs & Assumptions sheet instead. Rows beyond the appraisal period are switched off by the 'In appraisal period' flag.
Discounted cash flow | [9 empty] | Discount factor = 1 / (1 + effective discount rate) ^ year index
Year index | Calendar year | Capital costs | Operating costs | Lifecycle costs | Optimism bias adjustment | Total costs | Monetised benefits | Residual value | Total benefits | Net cash flow | Discount factor | PV of costs | PV of benefits | PV net | Cumulative PV net | Escalation factor | In appraisal period | Cumulative net cash flow (undiscounted)
0 | 2026 | 9045266.6667 | 0 | 0 | 1356790 | 10402056.6667 | 0 | 0 | 0 | -10402056.6667 | 1 | 10402056.6667 | 0 | -10402056.6667 | -10402056.6667 | 1 | 1 | -10402056.6667
1 | 2027 | 18420266.6667 | 0 | 0 | 2763040 | 21183306.6667 | 0 | 0 | 0 | -21183306.6667 | 0.93458 | 19797482.866 | 0 | -19797482.866 | -30199539.5327 | 1 | 1 | -31585363.3333
2 | 2028 | 23035266.6667 | 0 | 0 | 3455290 | 26490556.6667 | 0 | 0 | 0 | -26490556.6667 | 0.87344 | 23137878.1262 | 0 | -23137878.1262 | -53337417.6589 | 1 | 1 | -58075920
3 | 2029 | 0 | 4290000 | 0 | 0 | 4290000 | 8895000 | 0 | 8895000 | 4605000 | 0.8163 | 3501917.8919 | 7260969.6149 | 3759051.7231 | -49578365.9358 | 1 | 1 | -53470920
4 | 2030 | 0 | 4290000 | 0 | 0 | 4290000 | 8790000 | 0 | 8790000 | 4500000 | 0.7629 | 3272820.4597 | 6705848.9139 | 3433028.4542 | -46145337.4816 | 1 | 1 | -48970920
5 | 2031 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.71299 | 3058710.71 | 9400722.7765 | 6342012.0665 | -39803325.4151 | 1 | 1 | -40075920
6 | 2032 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.66634 | 2858608.1402 | 8785722.221 | 5927114.0808 | -33876211.3342 | 1 | 1 | -31180920
7 | 2033 | 0 | 4290000 | 820000 | 0 | 5110000 | 13185000 | 0 | 13185000 | 8075000 | 0.62275 | 3182251.181 | 8210955.3467 | 5028704.1657 | -28847507.1685 | 1 | 1 | -23105920
8 | 2034 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.58201 | 2496819.0586 | 7673790.0437 | 5176970.9851 | -23670536.1834 | 1 | 1 | -14210920
9 | 2035 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.54393 | 2333475.7557 | 7171766.396 | 4838290.6403 | -18832245.5431 | 1 | 1 | -5315920
10 | 2036 | 0 | 4290000 | 1400000 | 0 | 5690000 | 13185000 | 0 | 13185000 | 7495000 | 0.50835 | 2892507.4722 | 6702585.4168 | 3810077.9445 | -15022167.5986 | 1 | 1 | 2179080
11 | 2037 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.47509 | 2038148.0965 | 6264098.5204 | 4225950.4239 | -10796217.1747 | 1 | 1 | 11074080
12 | 2038 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.44401 | 1904811.3051 | 5854297.6826 | 3949486.3774 | -6846730.7973 | 1 | 1 | 19969080
13 | 2039 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.41496 | 1780197.4814 | 5471306.2454 | 3691108.764 | -3155622.0333 | 1 | 1 | 28864080
14 | 2040 | 0 | 4290000 | 820000 | 0 | 5110000 | 13185000 | 0 | 13185000 | 8075000 | 0.38782 | 1981746.1016 | 5113370.3228 | 3131624.2212 | -23997.8121 | 1 | 1 | 36939080
15 | 2041 | 0 | 4290000 | 950000 | 0 | 5240000 | 13185000 | 0 | 13185000 | 7945000 | 0.36245 | 1899217.1429 | 4778850.769 | 2879633.6261 | 2855635.814 | 1 | 1 | 44884080
16 | 2042 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.33873 | 1453171.4245 | 4466215.6719 | 3013044.2474 | 5868680.0614 | 1 | 1 | 53779080
17 | 2043 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.31657 | 1358104.1351 | 4174033.3383 | 2815929.2032 | 8684609.2646 | 1 | 1 | 62674080
18 | 2044 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.29586 | 1269256.201 | 3900965.7367 | 2631709.5357 | 11316318.8002 | 1 | 1 | 71569080
19 | 2045 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.27651 | 1186220.7486 | 3645762.3707 | 2459541.6221 | 13775860.4224 | 1 | 1 | 80464080
20 | 2046 | 0 | 4290000 | 1400000 | 0 | 5690000 | 13185000 | 0 | 13185000 | 7495000 | 0.25842 | 1470404.126 | 3407254.5521 | 1936850.4261 | 15712710.8485 | 1 | 1 | 87959080
21 | 2047 | 0 | 4290000 | 820000 | 0 | 5110000 | 13185000 | 0 | 13185000 | 8075000 | 0.24151 | 1234131.8733 | 3184350.0487 | 1950218.1754 | 17662929.0239 | 1 | 1 | 96034080
22 | 2048 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.22571 | 968309.4786 | 2976028.0829 | 2007718.6043 | 19670647.6282 | 1 | 1 | 104929080
23 | 2049 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.21095 | 904962.1296 | 2781334.6569 | 1876372.5274 | 21547020.1555 | 1 | 1 | 113824080
24 | 2050 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.19715 | 845758.9996 | 2599378.184 | 1753619.1844 | 23300639.34 | 1 | 1 | 122719080
25 | 2051 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.18425 | 790428.9716 | 2429325.4056 | 1638896.4341 | 24939535.774 | 1 | 1 | 131614080
26 | 2052 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.1722 | 738718.665 | 2270397.5754 | 1531678.9103 | 26471214.6844 | 1 | 1 | 140509080
27 | 2053 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 8895000 | 0.16093 | 690391.2757 | 2121866.8929 | 1431475.6171 | 27902690.3015 | 1 | 1 | 149404080
28 | 2054 | 0 | 4290000 | 820000 | 0 | 5110000 | 13185000 | 0 | 13185000 | 8075000 | 0.1504 | 768555.3055 | 1983053.1709 | 1214497.8654 | 29117188.1669 | 1 | 1 | 157479080
29 | 2055 | 0 | 4290000 | 1200000 | 0 | 5490000 | 13185000 | 20200320 | 33385320 | 27895320 | 0.14056 | 771689.8563 | 4692734.5707 | 3921044.7144 | 33038232.8813 | 1 | 1 | 185374400
30 | 2056 | 0 | 4290000 | 2350000 | 0 | 6640000 | 13185000 | 0 | 13185000 | 0 | 0.13137 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
31 | 2057 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.12277 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
32 | 2058 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.11474 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
33 | 2059 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.10723 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
34 | 2060 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.10022 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
35 | 2061 | 0 | 4290000 | 820000 | 0 | 5110000 | 13185000 | 0 | 13185000 | 0 | 0.093663 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
36 | 2062 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.087535 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
37 | 2063 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.081809 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
38 | 2064 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.076457 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
39 | 2065 | 0 | 4290000 | 0 | 0 | 4290000 | 13185000 | 0 | 13185000 | 0 | 0.071455 | 0 | 0 | 0 | 33038232.8813 | 1 | 0 | 185374400
TOTAL |  | 50500800 | 115830000 | 8230000 | 7575120 | 182135920 | 347310000 | 20200320 | 367510320 | 185374400 |  | 100988751.6462 | 134026984.5275 | 33038232.8813

## Results & Appraisal Summary
Results & Appraisal Summary
Headline appraisal metrics - every figure is calculated from the Cash Flow sheet.
Riverside Community Health & Aquatic Centre - Option 1 - New integrated facility ¦ All values in USD, real (constant) prices, base year 2026, discounted at 7.00% over 30 years
Headline result
NET PRESENT VALUE |  | BENEFIT COST RATIO |  | INTERNAL RATE OF RETURN |  | DISCOUNTED PAYBACK (YEARS)
33038232.8813 |  | 1.3271 |  | 11.85% |  | 15
PV OF BENEFITS |  | PV OF COSTS |  | EQUIVALENT ANNUAL VALUE |  | PV OF CAPITAL INVESTED
134026984.5275 |  | 100988751.6462 |  | 2662432.3663 |  | 53337417.6589
Appraisal results |  |  |  |  | All figures are present values unless stated.
Measure | Value | Unit | Basis
Present value of costs (PVC) | 100988751.6462 | amount | Sum of discounted total costs, including the optimism bias adjustment.
Present value of benefits (PVB) | 134026984.5275 | amount | Sum of discounted monetised benefits plus residual value.
Net present value (NPV) | 33038232.8813 | amount | NPV = PVB - PVC. The primary decision measure.
Benefit cost ratio (BCR) | 1.3271 | ratio | PVB / PVC. A BCR above 1.0 indicates monetised benefits exceed monetised costs.
PV of capital cost (incl. optimism bias) | 53337417.6589 | amount | Discounted capital expenditure plus the optimism bias uplift.
PV of operating and lifecycle cost | 47651333.9873 | amount | Discounted recurrent and lifecycle renewal cost.
PV of monetised benefits (excl. residual value) | 131187570.6772 | amount | Discounted benefit stream from the Benefit Inputs sheet.
PV of residual value | 2839413.8503 | amount | Discounted residual value recognised in the final appraisal year.
Net benefit cost ratio (net BCR) | 1.6194 | ratio | Net benefits (benefits less recurrent cost) divided by PV of capital invested.
Internal rate of return (IRR) | 11.85% | % p.a. | Discount rate at which NPV = 0, on the undiscounted net cash flow.
Discounted payback - calendar year | 2041 | year | First year in which cumulative PV net turns positive.
Discounted payback - years from start | 15 | years | Year index at which cumulative PV net turns positive.
Simple payback - years from start (undiscounted) | 10 | years | Year index at which cumulative undiscounted net cash flow turns positive.
NPV per unit of capital invested | 0.61942 | ratio | NPV divided by the PV of capital cost - a capital-rationing measure.
Equivalent annual value (annualised NPV) | 2662432.3663 | amount p.a. | NPV converted to a constant annual equivalent over the appraisal period.
Equivalent annual cost | 8138320.2902 | amount p.a. | PV of costs converted to a constant annual equivalent - use to compare options of unequal life.
Appraisal verdict (monetised terms only) | Value for money on monetised terms - proceed to the next assurance gate
Decision rules applied
• NPV is the primary decision measure. An option is economically worthwhile when NPV > 0 at the mandated discount rate.
• BCR is used to rank options under capital rationing, not to select between mutually exclusive options - use incremental NPV for that.
• A BCR between 1.0 and 1.2 is treated here as marginal: the result is within the plausible error band of most appraisals and should not be relied on without sensitivity and switching-value evidence.
• IRR is reported for information. It is unreliable where the net cash flow changes sign more than once and must not override NPV.
• Non-monetised and distributional impacts are material to the decision and are recorded below and on the Distributional Impacts sheet.
Non-monetised impacts |  |  |  |  | Impacts that cannot be reliably valued but must inform the decision.
Impact | Direction | Significance | Evidence / basis |  |  | Who is affected
Health and wellbeing outcomes for the catchment population | Positive | Major | Public health evidence review; comparable facility outcome data |  |  | Catchment residents, particularly older adults and families
Social inclusion and community cohesion | Positive | Moderate | Community consultation; participation survey |  |  | Low-income households, culturally diverse communities
Accessibility for people with disability | Positive | Major | Universal design compliance report |  |  | People with disability and their carers
Heritage and townscape character | Negative | Minor | Heritage impact statement |  |  | Local residents, heritage bodies
Construction-phase amenity, noise and traffic disruption | Negative | Moderate | Construction environmental management plan |  |  | Adjacent residents and businesses
Climate resilience and adaptation capability | Positive | Moderate | Climate risk assessment |  |  | Whole catchment, emergency services
Workforce attraction and retention in the region | Positive | Minor | Workforce strategy; vacancy data |  |  | Health and leisure sector employees
Biodiversity and open-space quality | Neutral | Minor | Ecological assessment; offset plan |  |  | Local environment groups
Qualitative impacts must be weighed alongside the monetised result. Where a non-monetised impact is assessed as Major, record explicitly in the business case how it was taken into account in the recommendation.

## Sensitivity Analysis
Sensitivity Analysis
One-way sensitivity, switching values and a tornado ranking - all recomputed live from the Cash Flow.
Each cell re-derives the present values from the Cash Flow sheet with the named driver scaled. No Excel data tables are used, so the results recalculate anywhere.
Base present value components
Component | Value | [7 empty] | Note
PV of total costs | 100988751.6462 | From the Results sheet.
PV of total benefits | 134026984.5275 | Includes residual value.
PV of capital cost (incl. optimism bias) | 53337417.6589 | Scales with the capital cost driver.
PV of operating and lifecycle cost | 47651333.9873 | Scales with the operating cost driver.
PV of monetised benefits (excl. residual) | 131187570.6772 | Scales with the benefits driver.
Base NPV | 33038232.8813 | Reference point for every sensitivity below.
Annual value of ramped benefits at full realisation | 13185000 | Used to re-derive the benefit stream under a different ramp-up period.
PV of ramped benefits at the base ramp-up period | 127514230.2312 | Cross-check: this plus the PV of one-off and periodic benefit lines equals the PV of monetised benefits above.
One-way sensitivity - NPV and BCR at each driver setting | [5 empty] | Sensitivity steps are set on the Inputs sheet.
Driver | Measure | -20% | -10% | Base | +10% | +20% | Downside NPV swing | Upside NPV swing | How the driver is applied
Capital cost (incl. optimism bias) | NPV | 43705716.4131 | 38371974.6472 | 33038232.8813 | 27704491.1154 | 22370749.3495 | -10667483.5318 | 10667483.5318 | PV of capital cost scaled by the percentage shown; benefits held constant.
| BCR | 1.4839 | 1.4011 | 1.3271 | 1.2606 | 1.2004
Operating and lifecycle cost | NPV | 42568499.6788 | 37803366.28 | 33038232.8813 | 28273099.4826 | 23507966.0839 | -9530266.7975 | 9530266.7975 | PV of recurrent and renewal cost scaled by the percentage shown.
| BCR | 1.4654 | 1.3929 | 1.3271 | 1.2673 | 1.2127
Monetised benefits | NPV | 6800718.7459 | 19919475.8136 | 33038232.8813 | 46156989.949 | 59275747.0168 | -26237514.1354 | 26237514.1354 | PV of the benefit stream scaled by the percentage shown; residual value held constant.
| BCR | 1.0673 | 1.1972 | 1.3271 | 1.4571 | 1.587
Discount rate | NPV | 49161702.9676 | 40575840.8234 | 33038232.8813 | 26402652.4567 | 20545483.6124 | -12492749.2689 | 16123470.0863 | Effective discount rate scaled by the percentage shown; the whole cash flow is re-discounted.
| BCR | 1.445 | 1.3847 | 1.3271 | 1.2723 | 1.2202
Appraisal period | NPV | 21547020.1555 | 26471214.6844 | 33038232.8813 | 36010718.8889 | 38612350.8382 | -11491212.7258 | 5574117.9569 | Appraisal period scaled and rounded to whole years; the cash flow is re-summed over the new horizon.
| BCR | 1.2236 | 1.268 | 1.3271 | 1.35 | 1.3704
Benefit ramp-up period | NPV | 35611602.402 | 34181952.6683 | 33038232.8813 | 31247850.985 | 29755866.0714 | -3282366.8099 | 2573369.5207 | Ramp-up period scaled by the percentage shown; a longer ramp delays benefit realisation.
| BCR | 1.3526 | 1.3385 | 1.3271 | 1.3094 | 1.2946
Explicit discount rate test points | [5 empty] | Set the three rates on the Inputs sheet.
Discount rate | Rate | PV of costs | PV of benefits | NPV | BCR |  |  |  | Note
Low test rate | 3.5% | 129389830.5354 | 212503626.8177 | 83113796.2824 | 1.6424 | Whole cash flow re-discounted at the rate shown.
Central test rate | 7% | 100988751.6462 | 134026984.5275 | 33038232.8813 | 1.3271 | Whole cash flow re-discounted at the rate shown.
High test rate | 10% | 86158106.3666 | 95703627.7155 | 9545521.3489 | 1.1108 | Whole cash flow re-discounted at the rate shown.
Model rate in use | 7% | 100988751.6462 | 134026984.5275 | 33038232.8813 | 1.3271 | Whole cash flow re-discounted at the rate shown.
Switching values - the change that drives NPV to zero
Driver | Switching value | Unit | Interpretation | [5 empty] | Headroom assessment
Monetised benefits | -25.18% | % change | The percentage change in monetised benefits at which NPV = 0. A large negative number means the case is robust to benefit shortfall. | [5 empty] | Moderate headroom
Capital cost (incl. optimism bias) | 61.94% | % change | The percentage capital cost overrun at which NPV = 0. | [5 empty] | Robust
Operating and lifecycle cost | 69.33% | % change | The percentage increase in recurrent cost at which NPV = 0. | [5 empty] | Robust
Discount rate (switching rate = IRR) | 11.85% | % p.a. | The discount rate at which NPV = 0 - this is the internal rate of return. Headroom is measured as the margin over the discount rate in use. | [5 empty] | Robust
Proof: applying the benefits switching value above to the monetised benefit stream returns an NPV of zero - see the check cell below.
Check - NPV at the benefits switching value | 0 | Must be zero (to rounding).
Tornado - drivers ranked by NPV swing | [5 empty] | Swing measured across the outer sensitivity band.
Driver | NPV at low setting | NPV at high setting | NPV swing (absolute) | Rank | Share of total swing |  |  |  | Materiality
Capital cost (incl. optimism bias) | 43705716.4131 | 22370749.3495 | 21334967.0636 | 3 | 14.77% | Secondary |  |  | Low
Operating and lifecycle cost | 42568499.6788 | 23507966.0839 | 19060533.5949 | 4 | 13.2% | Secondary |  |  | Low
Monetised benefits | 6800718.7459 | 59275747.0168 | 52475028.2709 | 1 | 36.34% | Primary driver - quantify and control |  |  | High
Discount rate | 49161702.9676 | 20545483.6124 | 28616219.3552 | 2 | 19.82% | Primary driver - quantify and control |  |  | Moderate
Appraisal period | 21547020.1555 | 38612350.8382 | 17065330.6827 | 5 | 11.82% | Secondary |  |  | Low
Benefit ramp-up period | 35611602.402 | 29755866.0714 | 5855736.3306 | 6 | 4.055% | Secondary |  |  | Low
Read the tornado top-down: the driver with rank 1 has the largest influence on NPV and should receive the greatest estimating, assurance and risk-management effort. Switching values above tell you how far each driver has to move before the recommendation changes.

## Scenario & Options Comparison
Scenario & Options Comparison
Side-by-side comparison of the Base Case and up to three options, with formula-driven ranking.
Option 1 is linked live to this workbook's model. For Options 2 and 3, enter the present value figures produced by a separate run of this template (save one copy per option) - the derived metrics below calculate automatically.
Options comparison
Measure | Unit | Base Case (do-minimum) | Option 1 - New integrated facility | Option 2 | Option 3 | Note
Option description | text | Do-minimum - continue operating the existing 1974 facility with reactive repairs | Option 1 - New integrated facility | Option 2 - Refurbish and extend the existing facility | Option 3 - Two smaller distributed facilities | Base Case is the counterfactual against which all options are measured.
Capital cost (undiscounted, incl. optimism bias) | amount | 0 | 58075920 | 34500000 | 61200000 | Base Case has no incremental capital cost by definition.
PV of costs | amount | 0 | 100988751.6462 | 76500000 | 129400000 | Incremental PV of whole-of-life cost against the Base Case.
PV of benefits | amount | 0 | 134026984.5275 | 88200000 | 151000000 | Incremental PV of monetised benefits including residual value.
NPV | amount | 0 | 33038232.8813 | 11700000 | 21600000 | NPV = PV of benefits less PV of costs.
BCR | ratio | n/a | 1.3271 | 1.1529 | 1.1669 | Benefit cost ratio.
IRR | % p.a. | n/a | 11.85% | 9.4% | 8.1% | Enter the IRR reported by each option's own model run.
Discounted payback | years | n/a | 15 | 14 | 18 | Years from analysis start until cumulative PV net turns positive.
Risk rating | rating | High | Medium | Medium | High | Overall delivery and benefit-realisation risk.
Non-monetised score (1 low - 5 high) | score | 1 | 4 | 3 | 4 | Weighted assessment of the non-monetised impacts recorded on the Results sheet.
Rank by NPV | rank | 4 | 1 | 3 | 2 | 1 = highest NPV.
Rank by BCR | rank | n/a | 1 | 3 | 2 | 1 = highest BCR. Use for capital rationing, not for choosing between mutually exclusive options.
Recommended option (highest NPV) | Option 1 - New integrated facility
Incremental NPV of the recommended option over the next best | 11438232.8813
Where options are mutually exclusive, select on the highest NPV, not the highest BCR. Where the incremental NPV between the top two options is small relative to the switching values on the Sensitivity Analysis sheet, the ranking is not robust and the non-monetised and distributional evidence should decide the outcome.

## Risk & Optimism Bias
Risk & Optimism Bias
Quantified risk register with PERT-weighted expected values, tested against the contingency allowance.
ILLUSTRATIVE WORKED EXAMPLE - every value shown is example data for a mid-size community health and aquatic centre. Replace all example figures with your own project data before use.
Quantified risk register | [6 empty] | Expected value = PERT mean x likelihood.
Ref | Risk | Category | Likelihood (%) | Cost impact - min | Cost impact - most likely | Cost impact - max | PERT expected cost | Expected value | Mitigation | Owner | Mitigation effectiveness (%) | Post-mitigation EV
R-01 | Ground conditions worse than assumed | Construction | 35% | 400000 | 1200000 | 3400000 | 1433333.3333 | 501666.6667 | Additional geotechnical investigation before tender; provisional sum in contract | Design Manager | 40% | 301000
R-02 | Market escalation above allowance | Market | 50% | 600000 | 1900000 | 4800000 | 2166666.6667 | 1083333.3333 | Early contractor involvement; fixed-price subcontracts; indexation cap | Commercial Lead | 30% | 758333.3333
R-03 | Planning or approvals delay | Approvals | 30% | 250000 | 900000 | 2600000 | 1075000 | 322500 | Pre-lodgement engagement; approvals tracker with float | Planning Lead | 45% | 177375
R-04 | Scope growth from stakeholder change | Governance | 40% | 300000 | 1100000 | 2900000 | 1266666.6667 | 506666.6667 | Frozen design baseline; change control board | Project Director | 50% | 253333.3333
R-05 | Contractor insolvency or performance failure | Delivery | 12% | 800000 | 2600000 | 7500000 | 3116666.6667 | 374000 | Financial capacity testing; performance security; step-in rights | Commercial Lead | 35% | 243100
R-06 | Latent contamination on site | Environment | 25% | 350000 | 1000000 | 3100000 | 1241666.6667 | 310416.6667 | Intrusive site investigation; remediation action plan | Environment Lead | 40% | 186250
R-07 | Utility diversion complexity | Construction | 45% | 180000 | 620000 | 1700000 | 726666.6667 | 327000 | Early utility authority agreements; survey validation | Design Manager | 50% | 163500
R-08 | Benefit realisation shortfall (demand below forecast) | Benefits | 35% | 0 | 1500000 | 4200000 | 1700000 | 595000 | Demand validation; phased service ramp; benefits realisation plan | Service Director | 35% | 386750
R-09 | Industrial relations disruption | Delivery | 20% | 150000 | 700000 | 2200000 | 858333.3333 | 171666.6667 | Project labour agreement; contingency programme float | Delivery Manager | 30% | 120166.6667
R-10 | Interface with operating facility during construction | Operations | 40% | 120000 | 480000 | 1400000 | 573333.3333 | 229333.3333 | Staged handover plan; decant strategy; operations liaison | Operations Manager | 55% | 103200
R-11 | Regulatory or code change during delivery | Compliance | 15% | 200000 | 800000 | 2500000 | 983333.3333 | 147500 | Compliance watch; design flexibility allowance | Design Manager | 25% | 110625
R-12 | Cyber or ICT integration failure | ICT | 18% | 150000 | 550000 | 1900000 | 708333.3333 | 127500 | Early integration testing; vendor performance regime | ICT Lead | 45% | 70125
TOTAL | [6 empty] | 15850000 | 4696583.3333 |  |  |  | 2873758.3333
Contingency adequacy test
Measure | Value | [7 empty] | Assessment
Total pre-mitigation expected risk cost | 4696583.3333
Total post-mitigation expected risk cost | 2873758.3333
Contingency allowance from the Inputs sheet | 5410800 | Contingency percentage applied to the base capital cost.
Contingency coverage of post-mitigation risk | 188.3% | [7 empty] | Adequate - contingency covers quantified residual risk
Optimism bias uplift applied in the model | 7575120 | The optimism bias adjustment carried in the Cash Flow.
Combined risk allowance as a share of base capital | 25.71%
Optimism bias reference values by project type | [6 empty] | Commonly cited international reference-class values - validate against your own outturn data.
Project type | Capital cost - upper bound (%) | Capital cost - lower bound (%) | Works duration - upper bound (%) | Works duration - lower bound (%) |  |  |  | Typical drivers of bias
Standard buildings | 24% | 2% | 4% | 1% |  |  |  | Repeatable design, known site conditions
Non-standard buildings | 51% | 4% | 39% | 2% |  |  |  | Bespoke design, complex services, occupied sites
Standard civil engineering | 44% | 3% | 20% | 1% |  |  |  | Linear works, known ground conditions
Non-standard civil engineering | 66% | 6% | 25% | 3% |  |  |  | Tunnelling, marine, deep excavation, interfaces
Equipment and development | 200% | 10% | 54% | 10% |  |  |  | Technology novelty, first-of-a-kind, integration risk
Outsourcing and service transformation | 41% | 0% | 0% | 0% |  |  |  | Benefit optimism, transition complexity
Optimism bias is applied here to the total capital cost including the contingency line item. If your organisation applies the uplift to the base estimate only, set the contingency percentage on the Inputs sheet to zero and carry all risk in the optimism bias uplift, or vice versa - do not double count. The upper bound is the appropriate starting point at strategic outline case; the uplift may be reduced as risk is actively mitigated and the estimate matures, with the reduction evidenced.

## Distributional Impacts
Distributional & Qualitative Impacts
Who bears the costs and who receives the benefits - monetised split and qualitative significance.
Enter the share of PV costs and PV benefits attributable to each group. The monetised amounts are calculated from the Results sheet. Shares in each column should sum to 100%.
Distributional analysis by stakeholder group
Stakeholder group | Share of PV costs | Share of PV benefits | PV costs borne | PV benefits received | Net position | Significance | Commentary
General taxpayers / national budget | 42% | 5% | 42415275.6914 | 6701349.2264 | -35713926.465 | Major | Bears the majority of capital funding; receives limited direct benefit.
Local government / asset owner | 28% | 12% | 28276850.4609 | 16083238.1433 | -12193612.3176 | Major | Funds recurrent operations; receives avoided legacy cost and disposal receipts.
Catchment residents - general | 5% | 31% | 5049437.5823 | 41548365.2035 | 36498927.6212 | Major | Principal beneficiary through access, time savings and health outcomes.
Low-income and vulnerable households | 2% | 19% | 2019775.0329 | 25465127.0602 | 23445352.0273 | Major | Disproportionate benefit from subsidised access and proximity; distributional weight may apply.
Older adults and people with disability | 1% | 14% | 1009887.5165 | 18763777.8338 | 17753890.3174 | Major | Accessibility and health-service benefits concentrated in this group.
Local businesses and employers | 6% | 9% | 6059325.0988 | 12062428.6075 | 6003103.5087 | Moderate | Construction-phase disruption offset by workforce and trade benefits.
Facility users paying fees | 14% | 6% | 14138425.2305 | 8041619.0716 | -6096806.1588 | Moderate | Pays membership and programme fees; receives service quality improvement.
Environment and future generations | 2% | 4% | 2019775.0329 | 5361079.3811 | 3341304.3482 | Moderate | Carbon abatement and climate resilience accrue beyond the appraisal period.
TOTAL | 100% | 100% | 100988751.6462 | 134026984.5275 | 33038232.8813
Allocation check | Shares balance to 100%
Net position check (total must equal NPV) | 0 | Must be zero when the shares sum to 100% - the distributional split reallocates the NPV, it does not change it.
Qualitative and equity considerations
• Distributional weighting: where your jurisdiction applies income-based welfare weights, apply them to the benefits received by lower-income groups and report both the unweighted and weighted NPV.
• Transfer payments (taxes, subsidies, fees) redistribute between groups but do not create economic value - exclude them from the economic NPV while showing them in this distributional table.
• Where a group bears a net cost, record the mitigation or compensation measure and who is accountable for delivering it.
• Impacts on future generations extend beyond the appraisal period. Test them through the residual value and, where your jurisdiction permits, the declining long-run discount rate toggle on the Inputs sheet.
• Report the distributional result alongside the headline NPV. An option with a strong NPV but a regressive distribution may not be the right decision.

## Lists
Lists
Dropdown sources - edit with care; these feed data validation across the workbook.
Dropdown source lists |  |  |  |  | Add items by extending a column, then widen the named range.
Cost type | Cost profile | Benefit profile | Confidence | Yes / No | Price basis | Residual value method | Risk rating | Impact direction | Significance
Capital | Spread | Ramped | High | Yes | Real | % of capex | Low | Positive | Major
Operating | Annual | One-off | Medium | No | Nominal | Straight-line remaining life | Medium | Negative | Moderate
Lifecycle | Periodic | Periodic | Low |  |  | None | High | Neutral | Minor
[7 empty] | Very high |  | Negligible