## Cover
Construction Estimate
A construction estimate that shows its working. Price the works line by line against your own cost codes, type every line as firm or risk money, and let the summary apply contingency, escalation, overhead, profit, bonds and tax in a visible cascade - each step on its stated base. Built for contractors pricing work and owners checking it.
HOW TO USE IT
1 | Set the project up once | Setup holds the project, the estimate class, the pricing date and the markup rates. The register, the summary and the alternates all read from it.
2 | Price the works line by line | One row per work item on the Estimate sheet, coded to a section. Enter quantity, unit and the rates that apply - material, labour, equipment, subcontract. The line total builds itself. Use burdened labour rates - the all-in cost of an hour, not the wage.
3 | Type every line honestly | Firm, Allowance, PC sum or Provisional sum. The Summary shows how much of the estimate is risk money rather than measured work - that number decides how far to trust the total.
4 | Record where every number came from | Quantity source and rate source on each line, the drawing set on Basis of Estimate, and every assumption on its log. Months later this is what makes the estimate defensible.
5 | Read the cascade, not just the total | The Summary applies contingency, escalation, overhead, profit, bonds and tax in a visible order, each on the running subtotal. Every step shows its base, its rate and its amount.
6 | Keep alternates out of the base | Price additions and deductions on the Alternates sheet. They carry the same markups pro-rata but never touch the base estimate until you move them in deliberately.
WHAT IS IN THE WORKBOOK
| Sheet | What it is for
| Setup | Project, estimate class, pricing date, tax and the markup rates. Everything else reads from it.
| Estimate | The register. One row per work item - quantity, unit, rates and the calculated line total, with the source of every number.
| Summary | Direct cost by section, the markup cascade to the estimate total, and how much of the price is not yet firm.
| Alternates | Additions and deductions priced outside the base estimate, carrying the same markups pro-rata.
| Assumptions & Exclusions | The numbered log of what the price does and does not include.
| Basis of Estimate | Method, the drawing set priced from, and the estimate revision log.
| Reference | Every dropdown source - editable section list, item types, estimate classes and the section map across US, UK and AU conventions.
WHAT MOST ESTIMATE TEMPLATES GET WRONG
| One flat markup hides the build-up | A single 'margin' line cannot be checked, negotiated or defended. This estimate applies each markup on a stated base, in a stated order, so a reviewer can follow every dollar from direct cost to the total - and challenge the step they disagree with.
| No record of where the numbers came from | An estimate is only defensible if it states its basis - the drawing revisions priced from, the source of each quantity and rate, the pricing date and how long it holds. That is what the Basis of Estimate sheet and the source columns are for.
| Risk money mixed in with measured work | Allowances, PC sums and provisional sums are guesses with a currency sign. Typing every line lets the summary show how much of the total is firm - the single most useful thing a reviewer can know.
IMPORTANT
This workbook is an estimating tool, not advice. The markup rates are placeholders - no standard overhead, profit or contingency percentage exists, and the right figures come from your business and your market. Pricing is valid only for the period stated on Setup. Confirm quantities, rates and tax treatment for your project before relying on the total.
Built for teams delivering capital projects, programs and portfolios · mastt.com

## Setup
CONSTRUCTION ESTIMATE · SETUP
EXAMPLE DATA - the priced rows are a worked example. Delete them and this banner clears.
Fill this in once. The register, the summary, the alternates and the basis of estimate all read from here.
1 · PROJECT AND CLIENT
Project name | EXAMPLE - Level 3 Office Fitout, 45 Harbour Street
Project number | PRJ-2141
Site address | 45 Harbour Street
Owner / Client | Meridian Property Group
Estimate prepared by (company) | Fitwell Interiors Pty Ltd
Prepared by (name and role) | T. Okafor, Senior Estimator
2 · THE ESTIMATE
Estimate class | Class 2 - control or bid | How defined the scope is. Reference explains each class and how far to trust the number.
Pricing date | 13 Aug 2026 | The date the rates were current. An estimate without one cannot be defended later.
Validity (days) | 60 | How long the pricing holds. Beyond it, escalation and requotes apply.
Currency | $ - contract currency | Label only. Enter values in whatever currency the contract uses.
Tax label | GST | GST, VAT or Sales tax - whatever applies where the project is.
Tax rate | 10% | Applied once, as the last line of the cascade.
3 · MARKUP RATES - THERE IS NO STANDARD, SET YOUR OWN
Contingency | 5% | Known-unknowns inside the defined scope. Expect to spend it. Set it from the risk register, not habit.
Escalation | 0% | Cost growth between pricing date and construction. Zero is a statement - it says the program starts now.
Overhead (home office) | 6% | The cost of running the business, spread across jobs. Site supervision belongs in the register, not here.
Profit | 8% | Set from your market and your appetite - no authority specifies it.
Bonds and insurances | 1.5% | Premiums are charged on the contract value, so this sits near the end of the cascade.
4 · WHERE THE ESTIMATE STANDS
Direct cost of the works | 493003.6
Estimate total excluding tax | 601498.6
Estimate total including tax | 661648.6
Priced lines on the register | 20
Risk money - not yet firm | 28000
Setup completeness | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
For scale only: US industry surveys put operating overhead near 12% of revenue, with net margin before tax around 8-9% for homebuilders and nearer 4-6% on non-residential work. Those are survey medians from one market, not rules, and the non-residential figure is well below what most people assume. The only defensible markup is the one your own accounts support.

## Estimate
CONSTRUCTION ESTIMATE · REGISTER
EXAMPLE DATA - the priced rows are a worked example. Delete them and this banner clears.
One row per work item. Blue cells are yours; grey columns calculate. Unit cost = material + labour hours x rate + equipment + subcontract; the line total multiplies it by the quantity. Prints A3 landscape.
Ref | Section / trade | Description of the work | Item type | Qty | Unit | Material $/unit | Labour hrs/unit | Labour rate $/hr | Equipment $/unit | Subcontract $/unit | Unit cost | Line total | Quantity source | Rate source | Notes
1 | 01 General Requirements | Site management and supervision - 12 week program | Firm | 12 | wk |  | 24 | 95 |  |  | 2280 | 27360 | Historical data | Historical data | EXAMPLE - part-time senior supervisor
2 | 01 General Requirements | Site establishment, hoardings and facilities | Firm | 1 | item |  |  |  | 6800 |  | 6800 | 6800 | Historical data | Historical data | EXAMPLE
3 | 01 General Requirements | Waste removal and bins | Firm | 12 | wk |  |  |  | 240 |  | 240 | 2880 | Historical data | Historical data | EXAMPLE
4 | 01 General Requirements | Progressive and final clean | Firm | 1 | item |  |  |  |  | 4900 | 4900 | 4900 | Historical data | Trade quote | EXAMPLE
5 | 02 Existing Conditions | Demolition and strip-out of existing fitout | Firm | 650 | m2 |  |  |  |  | 25 | 25 | 16250 | Drawing take-off | Trade quote | EXAMPLE - includes making good
6 | 06 Wood, Plastics, and Composites | Reception desk and feature joinery | Firm | 1 | item |  |  |  |  | 18000 | 18000 | 18000 | Drawing take-off | Trade quote | EXAMPLE - joiner's quote ref JQ-114
7 | 08 Openings | Solid-core doors, frames and hardware | Firm | 14 | no. | 950 | 4.5 | 88 |  |  | 1346 | 18844 | Drawing take-off | Supplier quote | EXAMPLE
8 | 09 Finishes | Steel-stud plasterboard partitions, insulated | Firm | 380 | m2 | 42 | 0.6 | 88 |  |  | 94.8 | 36024 | Drawing take-off | Historical data | EXAMPLE
9 | 09 Finishes | Full-height glazed partitions and doors | Firm | 45 | m2 |  |  |  |  | 520 | 520 | 23400 | Drawing take-off | Trade quote | EXAMPLE
10 | 09 Finishes | Suspended ceiling grid and tile | Firm | 600 | m2 | 30 | 0.42 | 90 |  |  | 67.8 | 40680 | Drawing take-off | Historical data | EXAMPLE
11 | 09 Finishes | Carpet tile to open plan and offices | Firm | 520 | m2 | 48 | 0.25 | 96 |  |  | 72 | 37440 | Drawing take-off | Supplier quote | EXAMPLE
12 | 09 Finishes | Vinyl safety flooring to wet areas | Firm | 80 | m2 | 52 | 0.36 | 92 |  |  | 85.12 | 6809.6 | Drawing take-off | Supplier quote | EXAMPLE
13 | 09 Finishes | Preparation and two-coat paint system | Firm | 1100 | m2 | 3.5 | 0.12 | 88 |  |  | 14.06 | 15466 | Drawing take-off | Historical data | EXAMPLE - walls and ceilings
14 | 12 Furnishings | Kitchenette joinery, benchtops and appliances | Firm | 2 | no. | 9800 | 30 | 90 |  |  | 12500 | 25000 | Drawing take-off | Trade quote | EXAMPLE
15 | 21 Fire Suppression | Fire sprinkler modifications | Firm | 600 | m2 |  |  |  |  | 22 | 22 | 13200 | Drawing take-off | Trade quote | EXAMPLE
16 | 22 Plumbing | Hydraulic services to kitchenettes and accessible WC | Allowance | 1 | sum |  |  |  |  | 28000 | 28000 | 28000 | Allowance | Allowance | EXAMPLE - design not yet issued
17 | 23 Heating, Ventilating, and Air Conditioning (HVAC) | Mechanical modifications - VAV rezoning and flues | Firm | 650 | m2 |  |  |  |  | 95 | 95 | 61750 | Drawing take-off | Trade quote | EXAMPLE
18 | 26 Electrical | Electrical services, lighting and switchboard works | Firm | 650 | m2 |  |  |  |  | 110 | 110 | 71500 | Drawing take-off | Trade quote | EXAMPLE
19 | 27 Communications | Structured data cabling - outlets | Firm | 120 | no. |  |  |  |  | 185 | 185 | 22200 | Site measure | Trade quote | EXAMPLE
20 | 28 Electronic Safety and Security | Security and access control | Firm | 1 | item |  |  |  |  | 16500 | 16500 | 16500 | Drawing take-off | Trade quote | EXAMPLE
Use burdened labour rates - the all-in cost of an hour, not the wage. Price site supervision, facilities and clean-up as General Requirements lines, not as a percentage. The print area covers the first 60 rows - extend it under Page Layout if your estimate runs longer.

## Summary
CONSTRUCTION ESTIMATE · SUMMARY
EXAMPLE DATA - the priced rows are a worked example. Delete them and this banner clears.
Every figure is a formula over the register. The cascade shows its working - each step states its base, its rate and its amount.
DIRECT COST BY SECTION
Section / trade | Direct cost | Share
01 General Requirements | 41940 | 8.507% | ¦¦¦
02 Existing Conditions | 16250 | 3.296% | ¦
03 Concrete | 0 | 0%
04 Masonry | 0 | 0%
05 Metals | 0 | 0%
06 Wood, Plastics, and Composites | 18000 | 3.651% | ¦
07 Thermal and Moisture Protection | 0 | 0%
08 Openings | 18844 | 3.822% | ¦¦
09 Finishes | 159819.6 | 32.42% | ¦¦¦¦¦¦¦¦¦¦¦¦¦
10 Specialties | 0 | 0%
11 Equipment | 0 | 0%
12 Furnishings | 25000 | 5.071% | ¦¦
13 Special Construction | 0 | 0%
14 Conveying Equipment | 0 | 0%
21 Fire Suppression | 13200 | 2.677% | ¦
22 Plumbing | 28000 | 5.679% | ¦¦
23 Heating, Ventilating, and Air Conditioning (HVAC) | 61750 | 12.53% | ¦¦¦¦¦
25 Integrated Automation | 0 | 0%
26 Electrical | 71500 | 14.5% | ¦¦¦¦¦¦
27 Communications | 22200 | 4.503% | ¦¦
28 Electronic Safety and Security | 16500 | 3.347% | ¦
31 Earthwork | 0 | 0%
32 Exterior Improvements | 0 | 0%
33 Utilities | 0 | 0%
Direct cost of the works | 493003.6
FROM DIRECT COST TO THE ESTIMATE TOTAL
Step | Base | Rate | Amount | Running total
Direct cost of the works |  |  |  | 493003.6
Contingency | 493003.6 | 5% | 24650 | 517653.6
Escalation | 517653.6 | 0% | 0 | 517653.6
Net cost of the works |  |  |  | 517653.6
Overhead (home office) | 517653.6 | 6% | 31059 | 548712.6
Profit | 548712.6 | 8% | 43897 | 592609.6
Bonds and insurances | 592609.6 | 1.5% | 8889 | 601498.6
ESTIMATE TOTAL excluding tax |  |  |  | 601498.6
GST | 601498.6 | 10% | 60150 | 661648.6
ESTIMATE TOTAL including tax |  |  |  | 661648.6
This is a contractor's tender build-up: contingency and escalation are costs the works will consume, so they sit before overhead and profit and are marked up like any other cost. Bonds and insurance premiums are charged on the contract value, so they sit last before tax. A client-side cost plan under the standard UK rules orders it differently - overhead and profit inside the base cost, risk allowances on top - and some contractors deliberately keep contingency out of the marked-up base so it can be released without surrendering margin. Set the order you use; the cascade shows its working either way.
RISK CARRIED IN THE ESTIMATE
Allowances, PC and provisional sums |  | 28000
Share of direct cost not yet firm |  | 5.679%
Contingency carried |  | 24650
Lines priced from allowances |  | 1
Above about 15% not-yet-firm, the estimate is a forecast, not a price - say so when you present it.
ALTERNATES CARRIED - NOT IN THE TOTAL ABOVE
Additions offered (with markups) |  | 46973
Deductions offered (with markups) |  | -5710

## Alternates
CONSTRUCTION ESTIMATE · ALTERNATES
EXAMPLE DATA - the priced rows are a worked example. Delete them and this banner clears.
Additions and deductions priced but not in the base estimate. Each carries the estimate's markups pro-rata, so an accepted alternate adjusts the total honestly.
Ref | Description | Add / Deduct | Qty | Unit | Material $/unit | Labour hrs/unit | Labour rate $/hr | Equipment $/unit | Subcontract $/unit | Direct cost | With markups | Notes
A-01 | Operable wall to boardroom in lieu of fixed partition | Add | 1 | item |  |  |  |  | 38500 | 38500 | 46973 | EXAMPLE - supplier budget
A-02 | Substitute carpet tile to specification grade B | Deduct | 520 | m2 | 9 |  |  |  |  | 4680 | 5710 | EXAMPLE - supply saving
With markups = direct cost x the ratio of the estimate total excluding tax to the direct cost of the works, so every alternate carries contingency, overhead, profit and bonds at the same effective rate as the base estimate.

## Assumptions & Exclusions
CONSTRUCTION ESTIMATE · ASSUMPTIONS
The numbered log that travels with the price. In a dispute, what you excluded matters as much as what you priced.
No. | Type | Statement | Raised by | Date
1 | Assumption | Access is available during normal site hours for the full program (Program/Schedule) without interruption.
2 | Assumption | Existing services are adequate at the point of connection shown on the drawings.
3 | Exclusion | Structural alterations and slab penetrations beyond those shown.
4 | Exclusion | Rectification of base building defects or latent conditions.
5 | Exclusion | Authority, permit and utility connection fees - by the Owner / Client.
6 | Exclusion | Loose furniture, workstations and equipment (FF&E) - by the Owner / Client.
7 | Exclusion | Out-of-hours or staged working beyond the stated assumption.
8 | Exclusion | Cost escalation beyond the validity period stated on Setup.
9 | Clarification | Allowances and PC sums are carried at the values stated and will be adjusted to actual cost when the scope is fixed.
10 | Qualification | Tax is shown as a single line at the rate on Setup; confirm the treatment that applies to your contract.
11 | Clarification | Provisional sums are expended only on instruction and adjusted to the value of the work executed.
The first ten rows are a starter set - edit them to match what you have actually assumed and excluded on this project. An exclusions list nobody read is still binding; put it in the tender letter as well.

## Basis of Estimate
CONSTRUCTION ESTIMATE · BASIS OF ESTIMATE
What the estimate was built from. This page is what separates a defensible estimate from a number in a spreadsheet.
1 · METHOD
How quantities were measured | Measured from the drawing set below; site verified on 28 Jul 2026.
How rates were built | Subcontract quotes for services trades; current project data for finishes; supplier quotes for joinery.
Site visit | Yes - 28 Jul 2026, accompanied by building manager.
Estimate reviewed by | M. Reyes, Commercial Manager, 11 Aug 2026.
2 · DESIGN BASIS - THE DOCUMENTS THE PRICE RELIES ON
Document number | Title | Rev | Dated | Received
A-100 series | Architectural fitout plans, L3 | C
A-500 series | Joinery details | B
M-01 to M-04 | Mechanical services layouts | B
E-01 to E-03 | Electrical and lighting layouts | C
FS-01 | Fire services sketch | A
3 · ESTIMATE REVISION LOG
Revision | What changed |  | By | Date
0 | Issued for tender
Keep one row per issued revision. If the drawing set changes, the estimate has changed - reprice or requalify before reissuing.

## Reference
CONSTRUCTION ESTIMATE · REFERENCE
Every dropdown in the workbook is sourced from this sheet. Rename the sections to suit your own cost codes - the dropdowns follow whatever is written here.
Section / trade |  | Quantity source | Rate source | Unit
01 General Requirements |  | Drawing take-off | Supplier quote | m2
02 Existing Conditions |  | Site measure | Trade quote | m3
03 Concrete |  | Supplier advice | Historical data | m
04 Masonry |  | Allowance | Published data | lm
05 Metals |  | Historical data | Allowance | no.
06 Wood, Plastics, and Composites |  |  |  | item
07 Thermal and Moisture Protection |  |  |  | sum
08 Openings |  |  |  | hr
09 Finishes |  |  |  | day
10 Specialties |  |  |  | wk
11 Equipment |  |  |  | t
12 Furnishings |  |  |  | kg
13 Special Construction |  |  |  | L
14 Conveying Equipment |  |  |  | sf
21 Fire Suppression |  |  |  | sy
22 Plumbing |  |  |  | lf
23 Heating, Ventilating, and Air Conditioning (HVAC) |  |  |  | cy
25 Integrated Automation |  |  |  | ea
26 Electrical |  |  |  | ls
27 Communications
28 Electronic Safety and Security
31 Earthwork
32 Exterior Improvements
33 Utilities
Item type |  | Tax label | Estimate class | Add / Deduct
Firm |  | GST | Class 5 - concept screening | Add
Allowance |  | VAT | Class 4 - schematic design | Deduct
PC sum |  | Sales tax | Class 3 - budget authorisation
Provisional sum (defined) |  | None | Class 2 - control or bid
Provisional sum (undefined) |  |  | Class 1 - check estimate
Entry type
Assumption
Exclusion
Clarification
Qualification
ITEM TYPES - what each one means
Firm | Priced from a measured quantity and a real rate - a quote, current project data or a published source. The bulk of a bid-stage estimate should be Firm.
Allowance | Money carried for scope that exists but is not yet designed or measurable. State the basis in the notes. Allowances are where estimates go wrong - watch the total.
PC sum | Prime cost sum - a supply item whose quality is not yet settled (tapware, door furniture, finishes). Supply only: fixing, ancillary materials, preliminaries, overhead and profit are priced in the line it belongs to, not inside the sum.
Provisional sum (defined) | Work that IS expected but cannot yet be described and quantified - a service connection, undesigned joinery. Defined means you have stated its nature, where it fixes, its scope and any limitations, so the Contractor is deemed to have allowed for it in the program and the preliminaries.
Provisional sum (undefined) | The same, but without that description. The Contractor is deemed NOT to have allowed for it in the program or the preliminaries - so instructing it can carry time and preliminaries cost as well as the work. Define them wherever you can.
ESTIMATE CLASS - how far to trust the number
Class 5 - concept screening | 0 - 2% of design defined. Capacity factors and gross unit rates. Typical accuracy for building works: low -20% to -30%, high +30% to +50%.
Class 4 - schematic design | 1 - 15% defined. Parametric and elemental rates. Low -10% to -20%, high +20% to +30%.
Class 3 - design development and budget authorisation | 10 - 40% defined. Semi-detailed unit costs against a defined scope. The usual basis for funding approval and the point feasibility is normally settled. Low -5% to -15%, high +10% to +20%.
Class 2 - control or bid / tender | 30 - 75% defined. Detailed take-off with firm rates and quotes for the major trades. Low -5% to -10%, high +5% to +15%.
Class 1 - check estimate or bid check | 65 - 100% defined. Full detail, used to check tenders or negotiate. Low -3% to -5%, high +3% to +10%.
These follow the recognised cost estimate classification for building and general construction - not the process-industry version, whose ranges are roughly twice as wide and are widely misquoted for buildings. Each class carries a range of ranges, not one number: the low and high bands above bracket what is typical. They describe the CLASS, not your estimate. A defensible range for a specific project comes from risk analysis of that project, not from a table.
SECTION MAP - the same work under three naming conventions
This workbook (MasterFormat-style) |  | UK elemental (NRM-style) | Common AU trade package
01 General Requirements |  | Preliminaries | Preliminaries / site establishment
02 Existing Conditions |  | Facilitating works | Demolition / make-good
03 - 05 Concrete, Masonry, Metals |  | Substructure / frame | Structure trades
06 Wood, Plastics, and Composites |  | Internal finishes / fittings | Carpentry / joinery
07 Thermal and Moisture Protection |  | External envelope | Roofing / waterproofing
08 Openings |  | Windows and doors | Doors / glazing
09 Finishes |  | Internal finishes | Partitions / ceilings / floor finishes / painting
10 - 14 Specialties to Conveying |  | Fittings and equipment | Specialist packages / lifts
21 - 28 Fire to Electronic Safety |  | Services | Mechanical / electrical / fire / comms
31 - 33 Earthwork to Utilities |  | External works | Civil / siteworks / services
The section list is editable - overwrite it with your own cost codes if your business uses NAHB codes, NRM elements or trade packages. The register and the summary follow whatever the list says.
CELL CONVENTIONS
You complete this | Pale blue fill, blue text.
Calculated | Grey fill. A formula - do not type over it.
Subtotal or total | Light grey with a rule above.
Section band | Marks the start of a section.
TERMINOLOGY - this estimate is written for a global audience
Estimate / Cost plan / Tender build-up | Related but NOT the same artefact. This workbook is a contractor's tender build-up: overhead and profit sit on top of risk. A client-side cost plan under the standard UK rules does the opposite - overhead and profit are inside the base cost, and risk allowances sit on top of that. If you are producing a cost plan rather than a price, invert those two steps.
Overhead | Home-office overhead - the cost of running the business, spread across jobs. Site-specific supervision and facilities are General Requirements lines in the register, priced as real costs, not a percentage.
Burdened labour rate | The all-in cost of an hour - wage plus payroll taxes or on-costs, insurance, leave, small tools and non-productive time. Commonly 1.4 to 1.7 times the base wage. US construction averages about 1.44 times on statutory costs and benefits alone, before tools, PPE or travel - so anything near 1.3 is almost certainly missing something.
Contingency | Money for known-unknowns inside the defined scope - expect to spend it. Scope the client might add is not contingency; it belongs on Alternates.
PC sums and provisional sums | Standard-form terms in the UK, Australia and New Zealand. US practice carries the same money as allowances - if that is your convention, use the Allowance type and ignore the other two.
Variation / Change Order | Both mean an instructed change to the contract scope after award.