## Cover
Toolbox Talk
A printable talk record, and the register that makes it worth keeping. It ties each briefing to the safe work method statement, risk assessment or permit it supports, records the language it was delivered in and how you checked the message landed, and carries every open action onto the next talk until someone closes it with evidence. Thirty-seven topics, grouped by what actually hurts people.
HOW TO USE IT
1 | Set the project up once | Setup holds the project, the parties, how often you brief and how long a talk stays current. Every other sheet reads from it.
2 | Pick the topic from the work about to happen | Not from the top of the list. The Topic Library shows what you have never covered and what has gone stale, so the choice is informed rather than alphabetical.
3 | Print the Talk Record and take it out with you | One page. It carries the open actions from previous talks at the top, so last week's unfinished business is the first thing discussed rather than the thing everyone forgot.
4 | Record who was there and in what language | A signature proves attendance, not understanding. Note the language it was delivered in and how you checked the message landed - that is the part an investigator asks about.
5 | Log the talk and its actions | Copy the header into the Register and any actions into the Actions sheet. An action raised and never closed is worse than no action at all - it proves you saw the hazard.
6 | Close actions out and keep the evidence | Name what proves it was done. Photo, permit, inspection reference. Months later that is the only thing that distinguishes a real record from a tidy one.
WHAT IS IN THE WORKBOOK
| Sheet | What it is for
| Setup | Project, parties, how often you brief and how long a talk stays current. Everything else reads from it.
| Talk Record | The printable page. One talk, its hazards and controls, the open actions carried forward, and who was there.
| Register | Every talk given, with attendance against signatures and how many actions are still open.
| Actions | Every action raised, until it is closed with evidence. This is the sheet that free templates do not have.
| Topic Library | Thirty-seven topics with what you have covered, when, and what you have never covered at all.
| Reference | Every dropdown source, the terminology map and the cell conventions.
WHAT MOST TOOLBOX TALK TEMPLATES GET WRONG
| They record the talk and lose the actions | Every free template has somewhere to write an action. None of them carries it into the next talk. So the action is raised, the sheet is filed, and the hazard stays. That is not a neutral omission - it is documentary proof that you identified a problem and did nothing about it. This workbook pulls every open action onto the next Talk Record and will not let it disappear until someone closes it with evidence.
| The topic has nothing to do with today's work | A talk on ladder safety while the crew digs a trench proves nothing about the trench. The Talk Record ties the briefing to the specific SWMS, risk assessment, method statement or permit it supports, and the Topic Library shows coverage against the work actually in front of you.
| A signature is treated as proof of understanding | It proves someone was standing there. Where the workforce does not share a first language it may not even prove that much. This record captures the language it was delivered in, and how you verified the message landed - a question answered, a control demonstrated, the method explained back.
IMPORTANT
This workbook is a record-keeping tool, not advice. What you must brief, how often, who may deliver it and how long you keep the record are set by the law where you work, your contract and your own safety management system - read them and set this workbook to match. Requirements differ sharply between jurisdictions, so do not treat any figure in this file as a minimum standard. A briefing does not replace the risk assessment, the safe work method statement or the permit it refers to.
Built for teams delivering capital projects, programs and portfolios · mastt.com

## Setup
TOOLBOX TALK · SETUP
EXAMPLE DATA - the register, actions and talk record hold a worked example. Delete those rows and this banner clears.
Fill this in once. The talk record, the register and the topic library all read from here.
1 · PROJECT AND PARTIES
Project name | EXAMPLE - Riverside Commerce Centre
Project number | PRJ-0870
Site address | 12 Wharf Road, Riverside
Principal contractor | Askern Construction
Owner / Client | Harbourline Developments
Safety representative | S. Whitcombe, HSE Manager
2 · HOW YOU BRIEF ON THIS PROJECT
Briefing frequency | Weekly | What your own system, your contract or the law where you work requires. There is no universal figure - some jurisdictions set an interval, most set none.
A talk goes stale after (days) | 90 | How long you would still rely on a briefing. The topic library flags anything older.
Record retention (months) | 24 | How long you keep these records. Set it from your contract and the law where you work, not from habit.
Current data date | 2026-08-13 | Today's date for the overdue and staleness flags. Move it when you open the file.
3 · WHERE THE PROGRAM STANDS
Talks recorded | 5
Talks in the last 30 days | 5
Most recent talk | 11 Aug 2026
Attendances recorded | 102
Open actions | 2
Overdue actions | 0
Topics never covered | 32
An action raised and never closed is worse than no action at all - it is a record that you saw the hazard. Overdue actions appear at the top of the next Talk Record automatically and stay there until someone closes them with evidence.

## Talk Record
TOOLBOX TALK · TALK RECORD
EXAMPLE DATA - the register, actions and talk record hold a worked example. Delete those rows and this banner clears.
Print this page and take it out with you. Open actions from earlier talks appear automatically - work through them first.
THE TALK
Talk reference | TT-014 |  | Date | 2026-08-11
Topic | Excavations - support, access and inspection
Topic group | D - Ground and structure
Delivery type | SWMS briefing |  | Trade or crew | Civil / earthworks
Related document | SWMS |  | Reference | SWMS-041 Rev B - Bulk excavation and shoring
The related document is what turns this from a note that a conversation happened into evidence that a specific control was briefed. Name it and its revision.
WHO DELIVERED IT
Presenter | D. Nkemelu |  | Role | Site supervisor
Delivered in | English + interpreter |  | Location | Zone C laydown
Started | 6:45 | Finished | 7:05 | Minutes | 20
Recording start and finish is what makes the duration provable and a back-filled record obvious.
WHY THIS TOPIC, TODAY
Bulk excavation to the lift pit starts today, 2.4 m deep in mixed fill next to the site boundary.
HAZARDS DISCUSSED
Collapse of unsupported face in fill. Water main on the north side within the zone of influence. Spoil stockpiled too close to the edge yesterday. Access ladder not tied off.
CONTROLS AGREED
Shoring boxes in before anyone enters below 1.5 m. Service located and marked this morning, hand dig within 500 mm. Spoil kept back a full metre. Ladder tied and extending a metre above the edge. Daily inspection by the supervisor before first entry and after any rain.
OPEN ACTIONS FROM EARLIER TALKS - COVER THESE FIRST
Ref | Action |  |  | Owner | Due
A-002 | Confirm the water main location by potholing before the machine works the north face |  |  | M. Silva | 2026-08-14
A-003 | Install the second pedestrian gate at the east boundary so walkers stop crossing the haul route |  |  | D. Nkemelu | 2026-08-15
Pulled from the Actions sheet - the four oldest still open. Red means past its due date. Close them there and they drop off this list.
NEW ACTIONS RAISED TODAY
Action |  |  |  | Owner | Due
Copy these into the Actions sheet before you file the record - that is what makes them carry forward.
ATTENDANCE
Name |  | Company | Trade | Understood? | Signature
D. Nkemelu |  | Askern Construction | Civil / earthworks | Yes
R. Oyelaran |  | Askern Construction | Civil / earthworks | Yes
M. Silva |  | Trenchline Civil | Civil / earthworks | Yes
T. Pham |  | Trenchline Civil | Civil / earthworks | Yes
J. Kowalski |  | Trenchline Civil | Civil / earthworks | Yes
A. Bekele |  | Askern Construction | Traffic control | Yes
S. Whitcombe |  | Askern Construction | All trades | No
Attended | 7 | Confirmed understanding |  | 6 | 85.71%
HOW THE MESSAGE WAS CHECKED, AND WHO VERIFIED THE RECORD
Understanding checked | Worker explained it back
Verified by |  |  |  | Date
A signature proves someone was present. It does not prove they understood, and where the crew does not share a first language it may not prove much at all. Say how you checked - a question answered, a control demonstrated, the method explained back.

## Register
TOOLBOX TALK · REGISTER
EXAMPLE DATA - the register, actions and talk record hold a worked example. Delete those rows and this banner clears.
One row per talk. This is what survives a two-year project - a stack of loose forms does not. Actions raised and still open are counted from the Actions sheet.
No. | Talk ref | Date | Topic | Group | Delivery type | Related doc | Document reference | Presenter | Presenter role | Attended | Signed | Language | Minutes | Understanding checked | Actions raised | Actions open | Status
1 | TT-010 | 2026-07-14 | PPE - selection, fit and inspection | H - Site systems | Toolbox talk | None - general talk |  | S. Whitcombe | HSE advisor or manager | 22 | 22 | English | 12 | Questions asked and answered | 0 | 0 | Complete
2 | TT-011 | 2026-07-21 | Silica dust and respirable dust controls | F - Occupational health | Toolbox talk | Risk assessment | RA-022 Concrete cutting | S. Whitcombe | HSE advisor or manager | 24 | 24 | English + interpreter | 18 | Worker demonstrated the control | 0 | 0 | Complete
3 | TT-012 | 2026-07-28 | Reversing, spotters and blind spots | B - Vehicles, plant and traffic | Pre-start briefing | SWMS | SWMS-033 Rev A - Plant movements | D. Nkemelu | Site supervisor | 26 | 26 | English + interpreter | 15 | Questions asked and answered | 0 | 0 | Complete
4 | TT-013 | 2026-08-04 | Site traffic management and pedestrian segregation | B - Vehicles, plant and traffic | Toolbox talk | None - general talk |  | D. Nkemelu | Site supervisor | 25 | 24 | English | 14 | Questions asked and answered | 1 | 1 | Actions open
5 | TT-014 | 2026-08-11 | Excavations - support, access and inspection | D - Ground and structure | SWMS briefing | SWMS | SWMS-041 Rev B - Bulk excavation and shoring | D. Nkemelu | Site supervisor | 7 | 6 | English + interpreter | 20 | Worker explained it back | 2 | 1 | Actions open
Attended is the headcount; Signed is how many signatures you actually have. A gap between them is the first thing anyone reviewing this will notice, so the status column says so. The print area covers the first 40 rows - extend it under Page Layout if your register runs longer.

## Actions
TOOLBOX TALK · ACTIONS
EXAMPLE DATA - the register, actions and talk record hold a worked example. Delete those rows and this banner clears.
Every action raised at a talk, until it is closed with evidence. The four oldest open actions appear on the Talk Record automatically.
Ref | From talk | Raised | Topic | Action | Hazard it addresses | Owner | Due | Priority | Status | Rank | Days open | Closed | Evidence it was done
A-001 | TT-014 | 2026-08-11 | Excavations - support, access and inspection | Move the spoil stockpile back a full metre from the excavation edge and mark the line |  | R. Oyelaran | 2026-08-11 | Before next shift | Closed |  | 0 | 2026-08-11 | Photo on daily report 11 Aug
A-002 | TT-014 | 2026-08-11 | Excavations - support, access and inspection | Confirm the water main location by potholing before the machine works the north face |  | M. Silva | 2026-08-14 | Stop work | Open | 1 | 2
A-003 | TT-013 | 2026-08-04 | Site traffic management and pedestrian segregation | Install the second pedestrian gate at the east boundary so walkers stop crossing the haul route |  | D. Nkemelu | 2026-08-15 | This week | In progress | 2 | 9
Rank orders the open actions by due date and is what the Talk Record reads - leave it alone. Evidence should name something that exists: a photo on the daily report, a permit number, an inspection reference. 'Done' is not evidence.

## Topic Library
TOOLBOX TALK · TOPIC LIBRARY
EXAMPLE DATA - the register, actions and talk record hold a worked example. Delete those rows and this banner clears.
What you have covered, when, and what you have never covered at all. Pick the next topic from the work in front of you - this sheet tells you where the gaps are.
No. | Topic | Group | Last delivered | Times given | Coverage
1 | Working at height - planning and edge protection | A - Working at height |  | 0 | Never covered
2 | Ladders and stepladders | A - Working at height |  | 0 | Never covered
3 | Mobile access towers, podiums and hop-ups | A - Working at height |  | 0 | Never covered
4 | Scaffolding - use, alteration and tags | A - Working at height |  | 0 | Never covered
5 | MEWPs and fragile surfaces | A - Working at height |  | 0 | Never covered
6 | Site traffic management and pedestrian segregation | B - Vehicles, plant and traffic | 04 Aug 2026 | 1 | Current
7 | Reversing, spotters and blind spots | B - Vehicles, plant and traffic | 28 Jul 2026 | 1 | Current
8 | Mobile plant - excavators and quick hitches | B - Vehicles, plant and traffic |  | 0 | Never covered
9 | Driving for work and journey management | B - Vehicles, plant and traffic |  | 0 | Never covered
10 | Lifting operations, cranes and slinging | B - Vehicles, plant and traffic |  | 0 | Never covered
11 | Falling objects and exclusion zones | C - Struck-by and falling objects |  | 0 | Never covered
12 | Dropped tools, tethering and toe boards | C - Struck-by and falling objects |  | 0 | Never covered
13 | Material handling, storage and stacking | C - Struck-by and falling objects |  | 0 | Never covered
14 | Excavations - support, access and inspection | D - Ground and structure | 11 Aug 2026 | 1 | Current
15 | Underground services | D - Ground and structure |  | 0 | Never covered
16 | Overhead services and powerlines | D - Ground and structure |  | 0 | Never covered
17 | Temporary works and structural stability | D - Ground and structure |  | 0 | Never covered
18 | Electrical safety and temporary supplies | E - Energy and confined environments |  | 0 | Never covered
19 | Isolation, lock-out and permits to work | E - Energy and confined environments |  | 0 | Never covered
20 | Confined spaces | E - Energy and confined environments |  | 0 | Never covered
21 | Hot works and fire prevention | E - Energy and confined environments |  | 0 | Never covered
22 | Silica dust and respirable dust controls | F - Occupational health | 21 Jul 2026 | 1 | Current
23 | Asbestos - awareness and what to do on discovery | F - Occupational health |  | 0 | Never covered
24 | Noise and hearing protection | F - Occupational health |  | 0 | Never covered
25 | Hand-arm vibration | F - Occupational health |  | 0 | Never covered
26 | Manual handling and musculoskeletal injury | F - Occupational health |  | 0 | Never covered
27 | Heat stress, cold and sun exposure | F - Occupational health |  | 0 | Never covered
28 | Hazardous substances, safety data sheets and skin protection | F - Occupational health |  | 0 | Never covered
29 | Mental health and wellbeing | G - People and behaviour |  | 0 | Never covered
30 | Fatigue and shift work | G - People and behaviour |  | 0 | Never covered
31 | Drugs and alcohol | G - People and behaviour |  | 0 | Never covered
32 | New starters, young workers and language barriers | G - People and behaviour |  | 0 | Never covered
33 | Stop-work authority and speaking up | G - People and behaviour |  | 0 | Never covered
34 | Emergency arrangements, first aid and rescue | H - Site systems |  | 0 | Never covered
35 | Housekeeping, slips and trips | H - Site systems |  | 0 | Never covered
36 | PPE - selection, fit and inspection | H - Site systems | 14 Jul 2026 | 1 | Current
37 | Incident and near-miss reporting | H - Site systems |  | 0 | Never covered
Edit the topic list on the Reference sheet and this follows it. Stale means older than the period you set on Setup - no jurisdiction agrees on what that period should be, which is exactly why you set it rather than the template.

## Reference
TOOLBOX TALK · REFERENCE
Every dropdown in the workbook is sourced from this sheet. Add your own values inside the ranges, not below them.
Topic |  | Language | Trade or crew | Related document type
Working at height - planning and edge protection |  | English | All trades | SWMS
Ladders and stepladders |  | English + interpreter | Civil / earthworks | RAMS
Mobile access towers, podiums and hop-ups |  | Spanish | Concrete / formwork | Risk assessment
Scaffolding - use, alteration and tags |  | Mandarin | Steel / structure | Method statement
MEWPs and fragile surfaces |  | Cantonese | Carpentry | JHA
Site traffic management and pedestrian segregation |  | Vietnamese | Bricklaying | JSA
Reversing, spotters and blind spots |  | Korean | Roofing | Permit to work
Mobile plant - excavators and quick hitches |  | Polish | Scaffolding | Pre-start plan
Driving for work and journey management |  | Romanian | Mechanical | Safe work procedure
Lifting operations, cranes and slinging |  | Portuguese | Electrical | None - general talk
Falling objects and exclusion zones |  | Arabic | Hydraulic / plumbing
Dropped tools, tethering and toe boards |  | Punjabi | Fire services
Material handling, storage and stacking |  | Nepali | Finishes / fitout
Excavations - support, access and inspection |  | Tagalog | Landscaping
Underground services |  | Other - state in notes | Demolition
Overhead services and powerlines |  |  | Traffic control
Temporary works and structural stability |  |  | Crane / rigging
Electrical safety and temporary supplies
Isolation, lock-out and permits to work |  | Delivery type | Presenter role | Topic group
Confined spaces |  | Toolbox talk | Site supervisor | A - Working at height
Hot works and fire prevention |  | Pre-start briefing | Foreman or leading hand | B - Vehicles, plant and traffic
Silica dust and respirable dust controls |  | SWMS briefing | HSE advisor or manager | C - Struck-by and falling objects
Asbestos - awareness and what to do on discovery |  | Induction top-up | Project manager | D - Ground and structure
Noise and hearing protection |  | Post-incident stand-down | Specialist or trainer | E - Energy and confined environments
Hand-arm vibration |  | Demonstration or practical | Subcontractor supervisor | F - Occupational health
Manual handling and musculoskeletal injury |  |  | Manufacturer or supplier representative | G - People and behaviour
Heat stress, cold and sun exposure |  |  |  | H - Site systems
Hazardous substances, safety data sheets and skin protection
Mental health and wellbeing |  | How understanding was checked | Action priority | Action status
Fatigue and shift work |  | Questions asked and answered | Stop work | Open
Drugs and alcohol |  | Worker demonstrated the control | Before next shift | In progress
New starters, young workers and language barriers |  | Worker explained it back | This week | Closed
Stop-work authority and speaking up |  | Not verified | Routine | Escalated
Emergency arrangements, first aid and rescue
Housekeeping, slips and trips |  | Briefing frequency | Yes / No | Yes / No / N/A
PPE - selection, fit and inspection |  | Daily | Yes | Yes
Incident and near-miss reporting |  | Weekly | No | No
|  | Fortnightly |  | N/A
Monthly
Per shift
Per task
Per phase
TOPIC GROUPS - WHY THEY ARE WEIGHTED THIS WAY
The library is grouped by what actually kills and injures construction workers, not by what is easiest to write about. Falls from height remain the single largest cause of death on building sites in the United Kingdom and the United States. Vehicles and mobile plant are the largest cause in Australia and the largest category of work-related death in the United States overall - and they are the group most under-represented in free topic libraries, which tend to lead with PPE and housekeeping. Occupational health sits here as a full group because over time it kills more people than trauma does. No regulator publishes a definitive list, so treat this as a well-founded starting point and add your own.
TERMINOLOGY - this workbook is written for a global audience
Toolbox talk | A short briefing to the crew on one aspect of health and safety. Called a tailgate meeting or a safety talk in parts of the United States, and a toolbox meeting in much of Asia and the Middle East. The same artefact under several names.
Toolbox talk and pre-start | Not the same thing. A toolbox talk is topic-based and periodic. A pre-start, pre-task plan or morning huddle covers today's specific task and runs every shift. Sites commonly merge them, which is fine - the record should just say which it was, and the Delivery type field does that.
SWMS / RAMS / JHA / JSA | The written assessment of a task and its controls. Safe Work Method Statement, Risk Assessment and Method Statement, Job Hazard Analysis, Job Safety Analysis. Different names, and the detail differs, but the toolbox talk's job is the same in each case - to brief the crew on a document that already exists.
The talk does not create controls | It communicates controls decided elsewhere. That is why the related document reference matters more than anything else on the record: it is what turns a note that a conversation happened into evidence that a specific control was briefed to a named person on a stated date.
Stale | A talk delivered long enough ago that you would not rely on it today. You set the period on Setup, because no single figure applies everywhere - some jurisdictions set a briefing interval in law, most set none at all.
CELL CONVENTIONS
You complete this | Pale blue fill, blue text.
Calculated | Grey fill. A formula - do not type over it.
Summary tile | Reads the registers; nothing to type.
Section band | Marks the start of a section.