## Cover
Traffic Control Plan
The temporary traffic control plan for work on a road, and the registers that make it hold up afterwards. It records each layout by typical application or standard sheet number and by EDITION, the certification and expiration of everyone who prepares, approves or installs it, every inspection, every deficiency and every change with who approved it. It also plans the equipment movements inside the work space, which is where road workers are most often hurt.
HOW TO USE IT
1 | Set the project up once | Setup holds the project, the agency, the permit and its validity, the roadway environment and the speed limits. Every other sheet reads from it.
2 | Write the plan | The Plan sheet is the narrative - the scope, how traffic is handled through the four areas of the work zone, and what happens for pedestrians, bicyclists, transit, property access and emergency vehicles. The example text shows the level of detail expected.
3 | Reference the layouts, do not draw them | Record each layout by its typical application or standard sheet number, which document and EDITION it came from, and who prepared and approved it. The federal regulation lists referencing a standard layout ahead of designing a bespoke one, and no template should hand you a blank canvas to draw a work zone.
4 | Record the certifications, not just the names | Certification type, number and expiration for everyone who designs, installs, maintains or flags. The register turns amber 60 days out and red once expired.
5 | Log every inspection and every change | What was checked, by whom, what was found, and what changed and who approved it. The MUTCD requires changes to be approved by someone knowledgeable in temporary traffic control - the Change Log is where you prove that happened.
6 | Plan the traffic inside the work zone too | The Internal Traffic Control sheet covers equipment, deliveries and workers on foot inside the work space. That is a different problem from moving the public past it, and it is the one most likely to hurt your own crew.
WHAT IS IN THE WORKBOOK
| Sheet | What it is for
| Setup | Project, agency, the permit and its validity, the roadway environment and the dates. Everything else reads from it.
| Plan | The plan itself - scope, existing conditions, the four areas of the work zone, pedestrians and bicyclists, night work, responsibility and monitoring.
| Layout Register | Which layout is in effect, from which source document and edition, prepared by whom and approved by whom.
| Personnel | Certification type, number and expiration for everyone who prepares, approves, installs or flags. Amber at 60 days, red once expired.
| Inspection Log | Every inspection, what was found and what it raised.
| Deficiencies | What was wrong, who owns it, when it is due and what proves it was corrected.
| Change Log | Every change to a layout and who approved it.
| Internal Traffic Control | How equipment, deliveries and workers on foot move inside the work space.
| Notifications | Who was told, how, when, and whether they confirmed.
| Signs and Devices | Changeable message signs, arrow boards and portable devices - what they said, where, and when they came down.
| Reference | Every dropdown source, the terminology and what this workbook is not.
WHAT MOST TRAFFIC CONTROL PLAN TEMPLATES GET WRONG
| They cite sections of the MUTCD that no longer exist | The 11th Edition renumbered almost all of Part 6. Temporary traffic control elements moved from Chapter 6C to 6B. Typical applications moved from Chapter 6H to Chapter 6P and went from 46 figures to TA-1 through TA-54. The sign spacing table is now 6B-1, not 6C-1, and it has eight speed-banded rows where the old one had four. Templates built on the old numbering point at nothing - which is why this workbook records the edition of the source document alongside every layout number.
| They say a work zone has five areas | It has four: advance warning, transition, activity and termination. The buffer space is a component of the activity area, alongside the work space and the traffic space - not a fifth area. The five-area version is repeated widely enough that it now shows up in search results as though it were the answer.
| They hand you a blank drawing box and a signature line | A layout is engineering work, approved by the agency having jurisdiction and in many states sealed by a licensed engineer. Federal regulation lists referencing MUTCD elements or approved standard plans FIRST, ahead of designing something project-specific. This workbook records the typical application or standard sheet by number, its edition, and who prepared and approved it. It does not invite anyone to sketch a work zone.
| They manage the public and ignore the equipment inside the work zone | A traffic control plan moves the public safely past the work space. It does not govern the loader backing up inside it - and when a road worker is killed, it is usually a vehicle or piece of equipment on their own site that does it. The Internal Traffic Control sheet plans that separately, because the two problems have different answers, and no free template has it.
IMPORTANT
This workbook is a planning and record-keeping tool, not advice and not a design. A temporary traffic control layout is an engineering deliverable: it must be approved by the agency having jurisdiction, prepared by someone qualified in temporary traffic control, and in many states sealed by a licensed engineer. This file records which layout is in effect and who is responsible for it, and deliberately does not provide a drawing canvas. Sign spacing, taper lengths, buffer distances and device spacing come from the edition of the MUTCD your state has adopted and from your state supplement - they changed in the 11th Edition and they differ by state. Read them; do not infer them from any template.
Built for teams delivering capital projects, programs and portfolios · mastt.com

## Setup
TRAFFIC CONTROL PLAN · SETUP
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Fill this in once. The plan, the registers and every alert read from here.
1 · PROJECT AND PARTIES
Project name | EXAMPLE - Wharf Road curb and sidewalk reconstruction
Project number | PRJ-2266
Location | Wharf Road between Anderson Street and the rail overpass
Prime contractor | Askern Construction
Traffic control subcontractor | Wayline Traffic
Agency having jurisdiction | State DOT - district 4
Plan prepared by | K. Restrepo, TCDS, Wayline Traffic
Plan approved by | J. Halloran, PE - agency engineer
2 · PERMIT TO OCCUPY THE RIGHT-OF-WAY
Permit type | Lane closure permit | The agency's authorization. A permit, not a plan - you need both.
Permit number | ROW-2026-04417
Valid from | 2026-07-27
Valid to | 2026-09-06 | The workbook flags the expiration as it approaches. Work must not continue past it.
Permit conditions | No lane closure 7:30-9:00 AM or 4:00-6:00 PM weekdays. 48 hours notice before any night shift. | Copy the agency's conditions here so the crew can see them.
3 · THE ROADWAY ENVIRONMENT
Roadway type | Major arterial | With the speed limit and the duration, this drives which typical application applies and what qualifications the crew needs.
Posted speed limit | 45 mph
Speed limit through the work zone | 35 mph | A reduced work zone speed limit needs the agency's approval. In effect only while workers are present, unless the agency directs otherwise.
Type of operation | Long term stationary - over 3 days | The MUTCD duration category. It changes which devices are acceptable - a short duration operation and a long term stationary one are not the same problem.
Work start | 2026-07-29
Work complete | 2026-09-04
Current data date | 2026-08-13 | Today's date for the expiry and overdue flags. Move it when you open the file.
4 · WHERE THE PLAN STANDS
Permit expires in (days) | 24
Layouts in effect | 3
Inspections recorded | 5
Days since last inspection | 1
Open deficiencies | 1
Overdue deficiencies | 0
Certifications expiring within 60 days | 2
Certifications already expired | 0
Changes logged | 2
Notifications not confirmed | 0
An expired certification invalidates everything signed after it. Check the Personnel register before anyone designs, changes or installs a layout.

## Plan
TRAFFIC CONTROL PLAN · THE PLAN
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
The narrative document. Replace the example text with yours - the level of detail shown is what the agency and, later, an investigator will expect to see.
1 · SCOPE OF WORK
What the work is | EXAMPLE - Reconstruction of curb and gutter and sidewalk replacement on the northbound side of Wharf Road between Anderson Street and the rail overpass, including two new ADA curb ramps.
Why temporary traffic control is required | EXAMPLE - Work occupies the northbound curb lane and the sidewalk for the full duration. Pedestrian movement past the work space cannot be maintained on the existing alignment.
Limits of work | EXAMPLE - Wharf Road, STA 0+00 to 3+40, northbound side.
Duration and work hours | EXAMPLE - 6 weeks. 7:00 AM to 5:00 PM weekdays. Two night shifts for the asphalt overlay, dates confirmed with the agency 14 days in advance.
2 · EXISTING ROADWAY CONDITIONS
Existing conditions | EXAMPLE - Two lanes northbound, one southbound, separated by a painted median. Signalized intersection at the north end. On-street parking both sides. Sidewalk 6 ft wide on the work side.
Traffic volumes and peak periods | EXAMPLE - Approx. 11,000 ADT. Peaks 7:30-9:00 AM and 4:00-6:00 PM. Trucks approx. 6 percent.
Pedestrians, bicyclists and transit | EXAMPLE - Elementary school 600 ft north; children crossing 8:15-9:00 AM and 2:45-3:30 PM. Striped bike lane northbound. Bus route with two stops in the work area. Assisted living facility on the east side.
Adjacent or concurrent work | EXAMPLE - Water main replacement on Anderson Street beginning week 3. Coordination meeting every two weeks.
3 · TEMPORARY TRAFFIC CONTROL APPROACH
How traffic will be handled | EXAMPLE - Northbound curb lane closed for the full duration under a stationary layout. Two northbound lanes maintained by temporarily removing the painted median and restriping. Southbound unaffected.
The four areas of the work zone | EXAMPLE - Advance warning area begins at the Anderson Street approach. Transition area contains the merging taper. Activity area holds the work space, the traffic space and a longitudinal buffer ahead of the work space. Termination area returns traffic to the normal path past the overpass.
Staging | EXAMPLE - Stage 1 (weeks 1-3) STA 0+00 to 1+70. Stage 2 (weeks 4-6) STA 1+70 to 3+40. Each stage has its own layout - see the Layout Register.
Speed reduction and justification | EXAMPLE - Reduced to 35 mph through the work zone, approved by the agency, in effect only while workers are present. Reverts to the posted 45 mph outside work hours, which is why the layout uses a removable speed limit assembly.
Pedestrian accommodation | EXAMPLE - Sidewalk closed on the work side. Pedestrians diverted to the sidewalk opposite via the signalized crossings at both ends. A temporary pedestrian access route is maintained at 4 ft minimum clear width with a firm, stable, slip-resistant surface, curb ramps kept in service, and continuous detectable edging on both sides so a person using a long cane can follow it. The route is accessible for the full length - a closed sidewalk with no alternative is not an option.
Bicycle accommodation | EXAMPLE - Bike lane closed. Bicyclists share the travel lane under the reduced speed limit, with BICYCLES MAY USE FULL LANE signing 300 ft in advance of the taper on both approaches.
Property and business access | EXAMPLE - All driveways remain usable outside work hours. Where a driveway falls inside the active work space, 24 hours notice is given and alternative access is agreed with the occupant in writing.
Transit | EXAMPLE - Two bus stops relocated 200 ft south for the duration. Agency notified; temporary stop signing installed by the transit agency.
Emergency vehicle access | EXAMPLE - A passable width of not less than 12 ft is maintained through the work zone at all times. Equipment parked clear of the travel way. Crew briefed to clear the lane immediately for an approaching emergency vehicle.
Worker safety provisions | EXAMPLE - All workers within the right-of-way wear high-visibility safety apparel meeting ANSI/ISEA 107 Performance Class 2 or 3, day and night. Positive protection provided by a truck-mounted attenuator on the mobile operations. Access to the work space is from the closed lane only, never from the live lane.
4 · NIGHT WORK AND ADVERSE CONDITIONS
Night work provisions | EXAMPLE - Work zone and taper illuminated, luminaires aimed and shielded so they do not create glare for approaching drivers. All channelizing devices retroreflective and checked at the start of each night shift. Additional advance warning and an arrow board on the approach.
Rain, fog and reduced visibility | EXAMPLE - Work stands down in heavy rain or fog. Devices remain in place and are re-checked before restart. If the work zone is left unattended the reduced speed limit assembly is removed.
If the plan cannot be implemented as written | EXAMPLE - Work does not begin. The supervisor contacts the plan designer for a revised layout. No field modification without approval - every change is logged on the Change Log and approved by a person knowledgeable in temporary traffic control, as the MUTCD requires.
5 · RESPONSIBILITY AND QUALIFICATIONS
Who does what | EXAMPLE - Traffic control subcontractor installs, maintains and removes all devices and provides flaggers. Prime contractor's superintendent verifies the setup before first use each shift and holds the record. The agency engineer approves the plan and any change to it.
Qualifications required on this project | EXAMPLE - Flaggers hold current flagger certification. The person responsible for setup and maintenance holds TCT or higher. The plan is prepared by a TCDS and approved by the agency engineer. Certification cards sighted and recorded on the Personnel register.
Training and briefing | EXAMPLE - Orientation covers the plan, the layout in effect, the internal traffic control plan and the emergency procedures. Any change to the layout is briefed before the shift it applies to.
6 · MONITORING, INCIDENTS AND RECORDS
Inspection regime | EXAMPLE - Setup verified before first use of each layout. Daily check at the start of each shift and after any change. Weekly documented inspection. Night check on any shift running after dark. All recorded on the Inspection Log.
Incident and near miss | EXAMPLE - Any intrusion into the work space, any device struck, and any near miss involving a worker on foot is recorded, reported to the prime contractor the same day, and triggers a review of the layout before work resumes.
Records kept and for how long | EXAMPLE - This plan, every layout with its revision, the inspection log, the change log, the deficiency log and the personnel register are kept for the period the contract and the agency require, and a copy is kept on site whenever workers are present.
This plan does not contain scaled layouts and is not a substitute for one. The layouts in effect are listed on the Layout Register with the typical application or standard sheet each came from, its edition, and who prepared and approved it.

## Layout Register
TRAFFIC CONTROL PLAN · LAYOUT REGISTER
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Which layout is in effect, where it came from and who is responsible for it. Record the EDITION of the source document - the typical applications were renumbered in the 11th Edition and states adopted it at different times, so a TA number on its own will not tell you which drawing you actually used.
TCP ref | Rev | Stage or limits | Layout no. | Source document | Edition of source | Applies to | Prepared by | Certification | Approved by | Certification | Approved | Status | Installed | Removed | Superseded by
TCP-01 | B | Stage 1 - STA 0+00 to 1+70 | TA-10 | MUTCD typical application (Chapter 6P) | 11th Ed Rev 1 (2026) | Weekdays 7 AM - 5 PM, workers present | K. Restrepo | TCDS | J. Halloran | PE - Licensed Professional Engineer | 2026-07-24 | In effect | 2026-07-29
TCP-02 | A | Stage 1 - outside work hours | TA-9 | MUTCD typical application (Chapter 6P) | 11th Ed Rev 1 (2026) | Outside work hours, work zone unattended | K. Restrepo | TCDS | J. Halloran | PE - Licensed Professional Engineer | 2026-07-24 | In effect | 2026-07-29
TCP-03 | A | Stage 2 - STA 1+70 to 3+40 | TA-10 | MUTCD typical application (Chapter 6P) | 11th Ed Rev 1 (2026) | Weekdays 7 AM - 5 PM, workers present | K. Restrepo | TCDS | J. Halloran | PE - Licensed Professional Engineer | 2026-08-07 | Approved
TCP-04 | A | Night work - asphalt overlay | Sheet TC-04 | Project-specific TCP - engineer sealed | Sealed 11 Aug 2026 | Night shift only, dates TBC | K. Restrepo | TCDS | M. Ferreira | PE - Licensed Professional Engineer | 2026-08-11 | Approved
TCP-05 | A | Sidewalk detour - full duration | Std Dwg 704-02 | State DOT standard sheet | 2026 standard plans | Full duration, pedestrian route | K. Restrepo | TCDS | J. Halloran | PE - Licensed Professional Engineer | 2026-07-24 | In effect | 2026-07-29
A layout is engineering work, and the MUTCD requires the plan to be approved by the engineer or the engineer's designee of the agency having jurisdiction. This register is where you prove that happened - not with a name, but with the certification and, on the Personnel sheet, the number and its expiration. Referencing a typical application or a state standard sheet is the regulation's first-listed option, ahead of designing something project-specific; this workbook does not provide a canvas to draw one.

## Personnel
TRAFFIC CONTROL PLAN · PERSONNEL AND CERTIFICATION
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Everyone who designs, approves, installs, maintains or flags. The certificate number and its expiration are the point - a name on its own proves nothing.
Name | Company | Role on this project | Certification | Certificate no. | Issued | Expires | Days to expiry | Status | Verified by | Notes
K. Restrepo | Wayline Traffic | Plan designer | TCDS - Traffic Control Design Specialist (ATSSA) | TCDS-44182 |  | 2027-05-19 | 279 | Current | A. Kaur
J. Halloran | Northbank Engineering | Engineer of record | PE - Licensed Professional Engineer | PE-39007 |  | 2026-11-02 | 81 | Current | A. Kaur
M. Ferreira | Northbank Engineering | Engineer of record | PE - Licensed Professional Engineer | PE-41255 |  | 2028-02-14 | 550 | Current | A. Kaur
D. Onyema | Wayline Traffic | Setup and maintenance | TCS - Traffic Control Supervisor (ATSSA) | TCS-70441 |  | 2026-09-08 | 26 | Expiring | A. Kaur
S. Baptiste | Wayline Traffic | Flagger | Flagger certification (ATSSA) | FL-118203 |  | 2027-01-30 | 170 | Current | A. Kaur
L. Whitmore | Wayline Traffic | Flagger | Flagger certification (ATSSA) | FL-118477 |  | 2026-08-27 | 14 | Expiring | A. Kaur
A. Kaur | Askern Construction | Superintendent - verifier | TCT - Traffic Control Technician (ATSSA) | TCT-68812 |  | 2027-06-11 | 302 | Current | A. Kaur
Amber at 60 days, red once expired. An expired certification invalidates everything signed after that date, so check this before anyone designs, changes or installs a layout. ATSSA certifications run four years.

## Inspection Log
TRAFFIC CONTROL PLAN · INSPECTION LOG
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Every inspection, what was found and what it raised. Compliant is a finding too - record it, because a gap in the log reads as an inspection that never happened.
No. | Date | Time | Type | Layout | Result | What was found | Inspector | Deficiency ref | Days since previous
1 | 2026-07-29 |  | Setup verification | TCP-01 | Compliant | Setup checked against TCP-01 Rev B before first use. All devices in position, taper measured, reduced speed limit assembly in place. | A. Kaur
2 | 2026-08-03 |  | Weekly | TCP-01 | Minor defect - corrected on site | Two channelizing devices displaced in the taper, reset immediately. Advance warning sign rotated by wind, re-secured. | A. Kaur |  | 5
3 | 2026-08-07 |  | Daily | TCP-01 | Defect - action raised | Detectable edging missing over approximately 25 ft at the north end of the temporary pedestrian access route. | D. Onyema | D-002 | 4
4 | 2026-08-10 |  | After a change | TCP-01 | Compliant | Setup re-verified after the merging taper was lengthened. Change logged as C-002. | A. Kaur |  | 3
5 | 2026-08-12 |  | Night check | TCP-02 | Compliant | After-hours setup checked. Reduced speed limit assembly removed as required, all devices retroreflective and visible under headlights. | D. Onyema |  | 2
Days since previous turns orange above a week - adjust it to whatever your contract or the agency requires. Verify each setup before first use, then check daily, after any change and after any incident.

## Deficiencies
TRAFFIC CONTROL PLAN · DEFICIENCIES AND CORRECTIVE ACTIONS
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
What was wrong, who owns it, when it is due and what proves it was corrected. A deficiency raised and never closed is a record that you found the problem and left it.
Ref | Raised | Found by | What is wrong | Layout | Priority | Owner | Due | Status | Days open | Closed | Evidence it was corrected
D-001 | 2026-07-31 | Daily inspection | Advance warning sign obscured by vegetation on the approach |  | Immediate | D. Onyema | 2026-07-31 | Closed | 0 | 2026-07-31 | Vegetation cut back, photo on daily report
D-002 | 2026-08-07 | Daily inspection | Detectable edging missing over approx. 25 ft of the temporary pedestrian access route |  | Stop work | D. Onyema | 2026-08-08 | Closed | 1 | 2026-08-08 | Edging installed and re-inspected, photo on daily report 8 Aug
D-003 | 2026-08-12 | Public feedback | Residents report the detour signing at Anderson Street is unclear at night |  | Before next shift | K. Restrepo | 2026-08-15 | Open | 1
A deficiency in a live work zone is not paperwork. If it affects the safety of road users or the crew, the honest priority is stop work, and the log should show that is what happened.

## Change Log
TRAFFIC CONTROL PLAN · CHANGE LOG
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Every change to a layout, and who approved it. The MUTCD requires changes to be approved by someone knowledgeable in temporary traffic control - and after an incident, what was in place at the time and who authorized it is the first question.
Ref | Date | Layout affected | What changed | Why | Requested by | Approved by | Certification | Crew briefed | New revision issued
C-001 | 2026-08-04 | TCP-01 | Transit stop relocation moved 60 ft further south to clear the new work space | Field conditions changed | A. Kaur | J. Halloran | PE - Licensed Professional Engineer | Yes
C-002 | 2026-08-10 | TCP-01 | Merging taper lengthened after observed queuing in the morning peak | Inspection finding | D. Onyema | J. Halloran | PE - Licensed Professional Engineer | Yes
No field modification without approval. A change to a layout is approved by someone knowledgeable in temporary traffic control, logged here, and briefed to the crew before the shift it applies to. If the change is significant, it needs a new revision of the layout - not a note.

## Internal Traffic Control
TRAFFIC CONTROL PLAN · INTERNAL TRAFFIC CONTROL
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
How equipment, deliveries and workers on foot move INSIDE the work space. The plan on the other sheets moves the public safely past the work zone; this one separates equipment from workers on foot within it - and when a road worker is killed, it is usually a vehicle or machine on their own site that does it.
No. | Movement | Route | Where it conflicts with workers on foot | Control | Who controls it
1 | Equipment and truck entry | From the Wharf Rd south approach into the staging area at STA 0+40 | Entry crosses the temporary pedestrian access route | Spotter at the gate for every entry and exit. Pedestrian route held closed during the movement. No backing across the pedestrian route in any circumstances. | Flagger
2 | Equipment and truck exit | From the staging area onto Wharf Rd northbound | Sight distance at the exit restricted by the perimeter fence | Fence panel replaced with mesh for 20 ft either side of the gate. Spotter for every exit. Right turn out only. | Flagger
3 | Spoil and material haul | Excavation to the staging area stockpile, then out | Haul route runs alongside the crew working in the trench | Haul route separated from the work space by concrete barrier for its full length. Exclusion zone marked. No worker on foot inside the haul route without positive communication with the operator. | Superintendent
4 | Concrete and material delivery | Curbside standing in the closed lane at STA 1+20 | Delivery trucks back into the closed lane | Backing only with a dedicated spotter in continuous sight of the driver. Backing area cleared of workers on foot first. Delivery window outside the school peak. | Spotter
5 | Workers on foot | Staging area to the work space and back | Crossing the haul route and the live travel lane | One designated walking route, marked, crossing the haul route at a single controlled point. High-visibility apparel Class 2 or 3 at all times. No crossing the live lane on foot. | All personnel
6 | Equipment fueling and service | Within the staging area only | Fuel truck movements in a confined area with workers on foot | Fueling outside work hours where practicable. Area cleared before the fuel truck enters. Spotter for all movements in the staging area. | Superintendent
Backing, spotters and the point where a haul route crosses a walking route are where people get hurt. Separate them physically where you can, control them positively where you cannot, and make sure the crew has been told which is which. A plan that moves the public perfectly and leaves the equipment unmanaged has solved the wrong half of the problem.

## Notifications
TRAFFIC CONTROL PLAN · NOTIFICATIONS
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Who was told, how, when and whether they came back to you. The party you forgot is the one that stops the job.
Party | Contact | How notified | Notice required | Date notified | By | Confirmed | Notes
State DOT | District permits office | Permit application and email | 10 business days | 2026-07-10 | A. Kaur | Yes
City or county public works | Engineering division | Email | 10 business days | 2026-07-10 | A. Kaur | Yes
911 dispatch | Communications center | Email | 7 days | 2026-07-15 | A. Kaur | Yes
Fire department | Station 4 and battalion chief | Email and phone | 7 days | 2026-07-15 | A. Kaur | Yes
EMS | County EMS coordinator | Email | 7 days | 2026-07-15 | A. Kaur | Yes
Transit agency | Service planning | Email and phone | 14 days | 2026-07-12 | A. Kaur | Yes
School district | Riverside Elementary and transportation dept | Letter and phone | 7 days | 2026-07-18 | A. Kaur | Yes
Adjacent residents | Door hanger, 140 properties | Written notice | 7 days | 2026-07-20 | D. Onyema | Yes
Adjacent businesses | 12 businesses, in person | In person and letter | 7 days | 2026-07-20 | D. Onyema | Yes
Solid waste hauler | Contractor dispatch | Email | 7 days | 2026-07-22 | A. Kaur | Yes
911 dispatch, the transit agency, the school district and the waste hauler are the ones most often missed, and each of them can stop your work on the day. Add your own parties to the list on the Reference sheet.

## Signs and Devices
TRAFFIC CONTROL PLAN · SIGNS AND DEVICES
EXAMPLE DATA - a worked example runs through every sheet. Type your project name on Setup and this banner clears.
Changeable message signs, arrow boards and portable devices - what they said, where they were and when. A message left up after the work has moved on does more harm than no message at all.
Ref | Device | Location | Message or setting | In place from | Until | Set by | Removed on | Notes
V-01 | Portable changeable message sign | Wharf Rd, 1/4 mile south of work | ROAD WORK AHEAD / REDUCE SPEED | 2026-07-27 | 2026-09-06 | D. Onyema
V-02 | Portable changeable message sign | Anderson St, 600 ft east | SIDEWALK CLOSED / USE OTHER SIDE | 2026-07-29 | 2026-09-06 | D. Onyema
V-03 | Arrow board | Wharf Rd, at the merging taper | Right arrow - merge left | 2026-07-29 | 2026-09-06 | D. Onyema
V-04 | Portable changeable message sign | Wharf Rd, 1/4 mile south of work | NIGHT WORK / EXPECT DELAYS | 2026-08-24 | 2026-08-28 | D. Onyema
A row turns red when the device was due to come down and no removal date has been entered. Drivers stop believing a sign that is wrong, and they stop believing the next one too.

## Reference
TRAFFIC CONTROL PLAN · REFERENCE
Every dropdown in the workbook is sourced from this sheet. The certification list carries the national and common state credentials - use the ones your agency recognises.
Certification |  | Permit type | Layout source | Roadway type
PE - Licensed Professional Engineer |  | Right-of-way permit | MUTCD typical application (Chapter 6P) | Local street
TCS - Traffic Control Supervisor (ATSSA) |  | Lane closure permit | State MUTCD or supplement | Collector
TCT - Traffic Control Technician (ATSSA) |  | Encroachment permit | State DOT standard sheet | Minor arterial
TCDS - Traffic Control Design Specialist (ATSSA) |  | Street use permit | City or county standard detail | Major arterial
Flagger certification (ATSSA) |  | Road closure permit | Project-specific TCP - engineer sealed | Highway
CPSP - Certified Public Safety Professional (ATSSA) |  | Utility permit | Contractor standard layout | Expressway
State DOT Traffic Control Supervisor |  | Municipal work permit |  | Freeway or interstate
State DOT Traffic Control Technician |  | Other - state in notes |  | Parking lot or private road
State DOT flagger certification
Work zone safety - agency specific |  | Speed limit | Type of operation | Inspection type
Competent person - agency designated |  | 20 mph | Short duration - up to 1 hour | Setup verification
Other - state in notes |  | 25 mph | Short term - one daylight period or less | Daily
|  | 30 mph | Intermediate term - overnight to 3 days | Weekly
|  | 35 mph | Long term stationary - over 3 days | After a change
|  | 40 mph | Mobile operation | After an incident
|  | 45 mph | Night work | Removal and restoration
|  | 50 mph | Emergency operation | Night check
55 mph
60 mph
65 mph
70 mph
|  | Inspection result | Defect status | Defect priority
|  | Compliant | Open | Stop work
|  | Minor defect - corrected on site | In progress | Immediate
|  | Defect - action raised | Closed | Before next shift
|  | Non-compliant - work stopped | Escalated | This week
|  | Reason for change | Party to notify | Device type
|  | Field conditions changed | State DOT | Portable changeable message sign
|  | Staging change | City or county public works | Portable traffic signals
|  | Agency direction | Police department | Arrow board
|  | Inspection finding | Fire department | Speed display trailer
|  | Incident or near miss | EMS | Static advance notice sign
|  | Weather | 911 dispatch | Automated flagger assistance device
|  | Public or stakeholder feedback | Transit agency | Truck-mounted attenuator
|  | Design error corrected | School district
Solid waste hauler
|  | Yes / No | Adjacent residents | Yes / No / N/A
|  | Yes | Adjacent businesses | Yes
|  | No | Bicycle and pedestrian advocacy | No
|  |  | Utility owner | N/A
Traveler information
Impact on road users
Lane closure
Shoulder closure
Full road closure
Detour
Two-way traffic on one side
One-lane two-way operation
Sidewalk closure
Bike lane closure
Parking removal
Transit stop relocation
Driveway access affected
Ramp closure
WHAT THIS WORKBOOK IS, AND WHAT IT IS NOT
This workbook - the plan and its record | The narrative plan and the registers behind it. What the work is, how traffic is handled past it, who is responsible, what was inspected and what changed. It is the document you submit, keep on site and produce if anything goes wrong.
Not in this workbook - the layout drawing | The scaled drawing showing every sign, channelizing device, taper and dimension in position. It is engineering work: approved by the agency having jurisdiction and, in many states, sealed by a licensed engineer. This workbook records which layout is in effect, where it came from and who is responsible for it. Deliberately, it does not provide a blank canvas to draw one.
Not in this workbook - the permit | The agency's authorization to occupy the right-of-way. A separate instrument with its own number and validity period, recorded on Setup. Having a plan is not the same as having a permit.
WHY THERE ARE NO SPACING OR TAPER TABLES IN THIS FILE
Advance warning sign spacing, taper length, buffer space, device spacing and minimum lane width come from the edition of the MUTCD your state has adopted and from your state supplement. They changed in the 11th Edition - the sign spacing table went from four rows to eight, and the tables and chapters were renumbered - and states adopted at different times, so two projects in neighbouring states can be governed by different numbers on the same day. A figure reproduced in a template is a figure that is wrong somewhere, and the consequence of using the wrong one is not administrative. Take them from the document your project is governed by, and record which layout and which edition you used on the Layout Register so the record still makes sense in two years.
TERMINOLOGY
Traffic control plan (TCP) | What the MUTCD calls a temporary traffic control plan, or TTC plan. In parts of the southeast it is a maintenance of traffic or MOT plan. On federal-aid projects, note that a Transportation Management Plan is a different and larger thing: the TCP is one component of it, alongside transportation operations and public information.
The four areas of a work zone | Advance warning area, transition area, activity area, termination area. The activity area contains the work space, the traffic space and the buffer space - and the buffer has both a longitudinal and a lateral form. Neither work nor storage belongs in a buffer space.
The layout | The scaled drawing showing every sign, channelizing device, taper and dimension in position. Referenced here by number; prepared and approved elsewhere. It may be a MUTCD typical application, a state standard sheet, or a project-specific plan sealed by an engineer.
Permit | The agency's authorization to occupy the right-of-way. A permission, not a plan - you need both, and the names differ between agencies.
Internal traffic control plan (ITCP) | How equipment, deliveries and workers on foot move inside the work space. Its purpose is to separate equipment from workers on foot and prevent struck-by incidents. Separate from the TCP, and aimed at a different set of risks.
Temporary pedestrian access route | The accessible path provided when an existing pedestrian facility is closed or relocated. It has to be detectable and include accessibility features consistent with what it replaces - which in practice means a continuous detectable edge, a firm and stable surface, and usable curb ramps.
CELL CONVENTIONS
You complete this | Pale blue fill, blue text.
Calculated | Grey fill. A formula - do not type over it.
Summary tile | Reads the registers; nothing to type.
Section band | Marks the start of a section.