## Draw Schedule Template
DRAW SCHEDULE TEMPLATE
Project Name: |  | < Insert Project Name >
Project Number: |  | < Insert Project Number >
Project Address: |  | < Insert Project Address >
Client Name: |  | < Insert Client Organization Name >
Client Address: |  | < Insert Client Address >
Contractor Name: |  | < Insert Contractor Organization Name >
Contractor Address: |  | < Insert Contractor Address >
Contract Number: |  | < Insert Contract Number >
Date Prepared: |  | < Insert Date >
Draw # | Milestone Description |  | Estimated Completion Date |  | Contract Value % | Value of Draw | Work Verified | Inspector / Authority | Draw Release Date | Notes
1 | Site Preparation, Permits, Temporary Works |  | 2025-02-01 |  | 10% | 500000 | Yes | Lender's Inspector / Owner's Rep | 2025-03-15 | Paid 03/15/25. Site works and permits complete.
2 | Foundation / Slab Complete |  | 2025-03-01 |  | 10% | 500000 | Yes | Lender's Inspector / Owner's Rep | 2025-04-15 | Paid 04/15/25. Slab poured and inspected.
3 | Framing / Structural Skeleton Complete |  | 2025-07-31 |  | 15% | 750000 | No | Lender's Inspector / Owner's Rep | TBD | Framing underway. Inspection scheduled 08/20/2025.
4 | Roof Installed, External Envelope Closed |  | 2025-08-30 |  | 15% | 750000 | No | Lender's Inspector / Owner's Rep | TBD | Materials on site. Envelope to commence after framing.
5 | Rough-In Services (Plumbing, Electrical) |  | 2025-09-29 |  | 10% | 500000 | No | Lender's Inspector / Owner's Rep | TBD | MEP trades mobilizing. Rough-ins start mid-September.
6 | Insulation, Internal Wall Sheeting |  | 2025-10-29 |  | 10% | 500000 | No | Lender's Inspector / Owner's Rep | TBD | Pending prior inspections. Target completion: 10/15/2025.
7 | Interior Fit-Out Commenced |  | 2025-11-28 |  | 10% | 500000 | No | Lender's Inspector / Owner's Rep | TBD | On hold pending wall sheeting sign-off.
8 | Joinery, Fixtures, Equipment Installed |  | 2025-12-28 |  | 10% | 500000 | No | Lender's Inspector / Owner's Rep | TBD | Joinery lead times confirmed. Install forecast Q1 2026.
9 | Final Finishes, Painting, Flooring |  | 2025-01-27 |  | 5% | 250000 | No | Lender's Inspector / Owner's Rep | TBD | Not commenced. Scheduled Q2 2026.
10 | Practical Completion & Handover |  | 2025-02-26 |  | 5% | 250000 | No | Lender's Inspector / Owner's Rep | TBD | Final inspections and occupancy cert to precede draw.
11 | … |  | … |  | … | … | … | … | … | …
12 | … |  | … |  | … | … | … | … | … | …
13 | … |  | … |  | … | … | … | … | … | …
14 | … |  | … |  | … | … | … | … | … | …
15 | … |  | … |  | … | … | … | … | … | …
16 | … |  | … |  | … | … | … | … | … | …
17 | … |  | … |  | … | … | … | … | … | …
18 | … |  | … |  | … | … | … | … | … | …
19 | … |  | … |  | … | … | … | … | … | …
20 | < Insert Milestone Description > |  | < Insert Date > |  | < Insert % > | < Insert $ > | < Insert Y / N > | < Insert Name > | < Insert Date > | < Insert Notes >
|  |  |  | Total Contract Value |  | 5000000
|  |  |  | Total Draws to Date |  | 1000000
|  |  |  | Remaining |  | 4000000