## Issue Log Template
Project:
Date:
Issue Log Template
Issue # | Status | Priority | Issue Description | Issue Impact | Category | Assigned To | Reported By | Date Reported | Due Date | Date Resolved | Resolution | Comments
1 | Open | High | Delayed material delivery. | Schedule delay | Logistical | John Doe | Jane Smith | 2024-05-15 | 2024-05-20 |  |  | Awaiting confirmation from supplier
2 | In Progress | Medium | Incorrect installation of HVAC system. | Rework required | Technical | Sarah Lee | Tom Johnson | 2024-05-12 | 2024-05-18 |  |  | HVAC team to review installation manual
3 | Resolved | High | Safety hazard on site. | Potential injury risk | Safety | Michael Smith | Alice Cooper | 2024-05-10 | 2024-05-11 | 2024-05-10 | Installed safety barriers and provided additional training | Safety training conducted for all site workers
4 | Open | Low | Minor software glitch in project management tool. | Minor inconvenience | Technical | Emily Davis | Nancy Wilson | 2024-05-14 | 2024-05-16 |  |  | Glitch reported to software vendor
5 | Closed | Medium | Unapproved change in design. | Budget overrun | Administrative | Robert Brown | David Clark | 2024-05-08 | 2024-05-13 | 2024-05-09 | Reverted to approved design and documented the change process | Design change approved retrospectively
6
7
8
9
10

## Issue Log Parameters
these power the drop downs on the Issue Log Template - do not delete!
Status | Priority | Category
New | Low | Technical
Open | Medium | Logistical
In Progress | High | Administrative
Resolved |  | Financial
Closed |  | Safety
Quality
Environmental
Scheduling
Contractual
Communication
Stakeholder
Human Resources
Regulatory
Procurement
Technology