REQUEST FOR INFORMATION

One request. One question. One sheet.

| PART 1 · THE REQUEST |  |  |  |
| --- | --- | --- | --- |
| Request number |  | Date raised |  |
| Project |  | Date found |  |
| Project number |  |  |  |
| Priority | ☐ P1 work stopped ☐ P2 at risk ☐ P3 needed soon ☐ P4 routine |  |  |
| Subject |  |  |  |
| From |  |  |  |
| To - the role |  |  |  |
| Copies to |  |  |  |
| Discipline or trade |  | Location |  |
| WHICH DOCUMENT NEEDS CLARIFYING |  |  |  |
| Drawing and revision |  |  |  |
| Specification |  |  |  |
| DOCUMENTS YOU CHECKED BEFORE ASKING - AND ANYTHING ELSE THAT CARRIES THE REQUIREMENT |  |  |  |
| THE QUESTION |  |  |  |
| WHAT CLARIFICATION YOU WANT - ONE QUESTION PER REQUEST |  |  |  |
| WHAT YOU PROPOSE, AND WHAT IT DOES TO COST OR TIME |  |  |  |
| WHEN THE WORK NEEDS THE ANSWER |  |  |  |
| Date the work needs it |  | Float (days) |  |
| Programme activity |  |  |  |
| Period allowed |  | Reply due by |  |
| Attachments |  |  |  |
| How many |  | Issued by |  |

| Signed for the contractor |  |  | Date issued |  |
| --- | --- | --- | --- | --- |

| PART 2 · THE REPLY |  |  |  |
| --- | --- | --- | --- |
| This reply is not an authorisation to proceed with work involving additional cost, time or both. Where the reply changes what the contract documents require, the change has to be instructed under the contract - as a minor change, a direction, a variation or a change order - before the work is built. |  |  |  |
| Answered by |  | Their role |  |
| Date of the reply |  | Date reply received |  |
| THE REPLY |  |  |  |
| Did the reply change the work? | ☐ No - clarification only ☐ Yes - an instruction has been issued ☐ Yes - an instruction is still required ☐ Returned without action |  |  |
| What instructed it |  | Who instructed it |  |
| Instruction reference |  |  |  |
| Answering and instructing are not the same power, and they are not always the same role: under some forms a change touching cost or time needs the owner as well as the designer. Record who instructed it. |  |  |  |
| Already in the documents? | ☐ No ☐ Partly ☐ Yes - it was in the issued set |  |  |
| If returned, on what ground |  |  |  |
| PART 3 · WHAT IT COST AND WHAT HAS TO BE SERVED |  |  |  |
| Cost effect claimed |  | Time claimed (days) |  |
| Disruption claimed |  | Claim window closes |  |
| Contractual notice | ☐ Not required ☐ Required - not yet served ☐ Served |  |  |
| Notice reference and date served |  |  |  |
| The period for claiming usually runs from the event, or from when you became aware of it - not from the reply. Read yours. A line on this form is not a notice. |  |  |  |
| Closed out by |  | Date closed out |  |

| Contractor |  |  | Contract administrator |  |
| --- | --- | --- | --- | --- |

REQUEST FOR INFORMATION

WORKED EXAMPLE - the same form, filled in end to end

| PART 1 · THE REQUEST |  |  |  |
| --- | --- | --- | --- |
| Request number | RFI-042 | Date raised | 5 Aug 2026 |
| Project | Rowanbank Hospital | Date found | 28 Jul 2026 |
| Project number | RB-2214 |  |  |
| Priority | ☐ P1 work stopped ☒ P2 at risk ☐ P3 needed soon ☐ P4 routine |  |  |
| Subject | Sanitary stack clashes with the PT band beam at grid F4 |  |  |
| From | D. Okonjo, Site Engineer, Merrivale Construction |  |  |
| To - the role | Contract administrator |  |  |
| Copies to | L. Aturu (PM), structural and hydraulic consultants, Level 2 foreman |  |  |
| Discipline or trade | Hydraulic / structural | Location | Level 2, grid F4, west riser |
| WHICH DOCUMENT NEEDS CLARIFYING |  |  |  |
| Drawing and revision | S-2104 Rev C, Level 2 slab penetration plan |  |  |
| Specification | Concrete reinforcing, post-tensioning - the clause on penetrations |  |  |
| DOCUMENTS YOU CHECKED BEFORE ASKING - AND ANYTHING ELSE THAT CARRIES THE REQUIREMENT |  |  |  |
| S-2104 Rev C, H-3202 Rev B, the structural specification, and the clash report issued with the June coordination model. |  |  |  |
| THE QUESTION |  |  |  |
| WHAT CLARIFICATION YOU WANT - ONE QUESTION PER REQUEST |  |  |  |
| H-3202 Rev B runs the 150 dia sanitary stack through the post-tensioned band beam at grid F4. S-2104 Rev C shows no penetration there and the specification does not permit coring a band beam. Which document governs, and which service or member is to move? |  |  |  |
| WHAT YOU PROPOSE, AND WHAT IT DOES TO COST OR TIME |  |  |  |
| Move the stack 600 mm east into the band-free zone of the slab, keeping the fixture set and the pipe grade as drawn. |  |  |  |
| WHEN THE WORK NEEDS THE ANSWER |  |  |  |
| Date the work needs it | 11 Aug 2026 | Float (days) | 2 |
| Programme activity | Level 2 deck - reinforcement fix and PT layout |  |  |
| Period allowed | 5 working days | Reply due by | 12 Aug 2026 |
| Attachments | Marked-up S-2104 Rev C, photograph at grid F4, clash report extract |  |  |
| How many | 3 | Issued by | D. Okonjo, Site Engineer |

| Signed for the contractor |  |  | Date issued |  |
| --- | --- | --- | --- | --- |

| PART 2 · THE REPLY |  |  |  |
| --- | --- | --- | --- |
| This reply is not an authorisation to proceed with work involving additional cost, time or both. Where the reply changes what the contract documents require, the change has to be instructed under the contract - as a minor change, a direction, a variation or a change order - before the work is built. |  |  |  |
| Answered by | R. Vance, Hydraulic Consultant | Their role | Sub-consultant |
| Date of the reply | 12 Aug 2026 | Date reply received | 13 Aug 2026 |
| THE REPLY |  |  |  |
| The stack is to move, not the beam. Relocate 600 mm east as proposed and set out to the revised hydraulic layout issued with this reply. The band beam is not to be penetrated at any point in its depth. |  |  |  |
| Did the reply change the work? | ☐ No - clarification only ☒ Yes - an instruction has been issued ☐ Yes - an instruction is still required ☐ Returned without action |  |  |
| What instructed it | Revised drawing issued with the reply | Who instructed it | Contract administrator |
| Instruction reference | CA instruction 018, revised layout H-3202 Rev C |  |  |
| CHECK - the reply came direct from a sub-consultant, who is not the role this contract empowers to change anything. The change was instructed separately by the contract administrator, which is what makes it safe to build. Without that instruction the work is being built to nothing. |  |  |  |
| Already in the documents? | ☒ No ☐ Partly ☐ Yes - it was in the issued set |  |  |
| If returned, on what ground | Not returned - answered |  |  |
| PART 3 · WHAT IT COST AND WHAT HAS TO BE SERVED |  |  |  |
| Cost effect claimed | $4,200 | Time claimed (days) | 1 day |
| Disruption claimed | No | Claim window closes | 10 Sep 2026 |
| Contractual notice | ☐ Not required ☒ Required - not yet served ☐ Served |  |  |
| Notice reference and date served |  |  |  |
| The period for claiming usually runs from the event, or from when you became aware of it - not from the reply. Read yours. A line on this form is not a notice. |  |  |  |
| Closed out by |  | Date closed out |  |

| Contractor |  |  | Contract administrator |  |
| --- | --- | --- | --- | --- |

| HOW TO USE IT |  |  |  |
| --- | --- | --- | --- |

1.   Copy the form for each request and number it in sequence. One request, one question - project specifications commonly require one subject per request. Withdrawn? Mark it void and keep the number.

2.   Name the drawing or specification that needs clarifying, and say what clarification you want. Those two are the minimum a standard owner-architect agreement sets.

3.   List what you had already read - the standard objection is that the answer was already in the documents issued to you.

4.   Give the date the work needs the answer, off the programme, and name the activity. Information that is not tied to an activity cannot be shown to have delayed anything.

5.   Record the date the reply was received, not just the date on it - different fact, and it is the one you will be asked for. If the reply changes what the documents require, get it instructed before the work is built; under some forms that needs the owner as well as the designer.

6.   Diarise the claim window. It usually runs from the event or from when you became aware of it, not from the reply, and the period differs by contract form.

7.   Keep every issued form on one numbered list - Mastt has an RFI register template for that.

| WHAT GETS SENT BACK UNANSWERED |  |  |  |
| --- | --- | --- | --- |
| From the coordination specifications, not the contract conditions. Most also require the request to come from the contractor. |  |  |  |
| Information already in the contract documents · Approval of a submittal · Approval of a substitution · Approval of the contractor's means and methods · An adjustment to the contract time or sum · An interpretation of the designer's action on a submittal · An incomplete or inaccurately prepared request |  |

| WHAT BELONGS HERE AND WHAT BELONGS SOMEWHERE ELSE |  |  |  |
| --- | --- | --- | --- |
| If it is | It goes in |
| A question about what the contract documents mean or require | Here |
| The same question across forty requests, and the turnaround on all of them | RFI register |
| A matter that has gone wrong and needs a decision above the project manager | Issue register |
| Work that does not comply with the documents | Non-conformance register |
| A change, once it has been instructed | Variation or change register |
| A drawing, sample or product data awaiting review | Submittal register |
| A defect found at completion | Defects or punch list |
| A formal contractual notice | Wherever your contract says - a form is not a notice |
| A question to a vendor before you have a contract | Not here - that is a procurement RFI |

IMPORTANT This is a template, not advice. It creates no entitlement on its own, and contract forms differ on who may answer, who may instruct a change, what periods apply and what notice has to be served - read yours and set the form to match it.

Built for teams delivering capital projects, programs and portfolios  ·  mastt.com