## Multiple Project Schedule
MULTIPLE PROJECT SCHEDULE REGISTER
[9 empty] | Phase 01 - Initiation |  |  |  | Phase 02 - Planning |  |  |  | Phase 03 - Design |  |  |  | Phase 04 - Construction |  |  |  | Phase 05 - Close
Program Name: |  | <Insert Program Name>
Program Number: |  | <Insert Program Number> | [6 empty] | Project Feasibility Study | Stakeholder Identification & Engagement | Project Charter Development | Initial Budget Approval | Detailed Scope Definition | Schedule Development | Resource Allocation & Procurement Plan | Risk Management Planning | Conceptual Design Approval | Detailed Design & Specifications | Permits & Approvals | Design Review & Finalization | Site Preparation & Mobilization | Foundation & Structural Work | Systems Installation (HVAC, Electrical, Plumbing) | Practical / Substantial Completion | Final Inspection & Testing | Punch List Completion | Project Handover & Client Acceptance | Project Review & Lessons Learned Documentation
Date: |  | 2024-11-14
Project No. | Project Name |  | Project Phase | Point of Contact | Project Start Date | Baseline Completion Date | Project Completion Date | Delay
1 | Project A - New Commercial Building |  | Close | Clark Kent | 2023-07-26 | 2025-01-10 | 2025-01-02 | 8 | 2023-08-15 | 2023-09-10 | 2023-10-07 | 2023-11-02 | 2023-11-29 | 2023-12-26 | 2024-01-21 | 2024-02-17 | 2024-03-15 | 2024-04-10 | 2024-05-07 | 2024-06-02 | 2024-06-29 | 2024-07-26 | 2024-08-21 | 2024-09-17 | 2024-10-14 | 2024-11-09 | 2024-12-06 | 2025-01-02
2 | Project B - Airport Redevelopment |  | Completed | Peter Parker | 2023-11-11 | 2024-08-15 | 2024-10-07 | -53 | 2023-12-01 | 2023-12-17 | 2024-01-02 | 2024-01-19 | 2024-02-04 | 2024-02-20 | 2024-03-08 | 2024-03-24 | 2024-04-09 | 2024-04-26 | 2024-05-12 | 2024-05-29 | 2024-06-14 | 2024-06-30 | 2024-07-17 | 2024-08-02 | 2024-08-18 | 2024-09-04 | 2024-09-20 | 2024-10-07
3 | Project C - Road Upgrade |  | Planning | Bruce Wayne | 2024-05-12 | 2026-12-01 | 2026-12-15 | -14 | 2024-06-01 | 2024-07-19 | 2024-09-06 | 2024-10-25 | 2024-12-13 | 2025-01-30 | 2025-03-20 | 2025-05-08 | 2025-06-26 | 2025-08-14 | 2025-10-01 | 2025-11-19 | 2026-01-07 | 2026-02-25 | 2026-04-15 | 2026-06-02 | 2026-07-21 | 2026-09-08 | 2026-10-27 | 2026-12-15
4 | Project D - New School Building |  | Initiation | Diana Prince | 2024-09-25 | 2026-11-10 | 2026-10-30 | 11 | 2024-10-15 | 2024-11-23 | 2025-01-01 | 2025-02-09 | 2025-03-20 | 2025-04-29 | 2025-06-07 | 2025-07-16 | 2025-08-24 | 2025-10-02 | 2025-11-11 | 2025-12-20 | 2026-01-28 | 2026-03-08 | 2026-04-16 | 2026-05-26 | 2026-07-04 | 2026-08-12 | 2026-09-20 | 2026-10-30
5 | Project E - High Speed Rail Development |  | Not Started | Tony Stark | 2024-11-11 | 2025-12-01 | 2025-12-01 | 0 | 2024-12-01 | 2024-12-20 | 2025-01-08 | 2025-01-27 | 2025-02-15 | 2025-03-07 | 2025-03-26 | 2025-04-14 | 2025-05-03 | 2025-05-22 | 2025-06-11 | 2025-06-30 | 2025-07-19 | 2025-08-07 | 2025-08-26 | 2025-09-15 | 2025-10-04 | 2025-10-23 | 2025-11-11 | 2025-12-01
6 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
7 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
8 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
9 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
10 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
11 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
12 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
13 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
14 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
15 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
16 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
17 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
18 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
19 | … |  | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | … | …
20 | <Insert Project Name> |  | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert> | <Insert>

## Settings
Project Phase
Not Started
Initiation
Planning
Design
Construction
Close
Completed