## Cover
Construction Project List
For teams delivering capital projects, programs and portfolios
Every project you are delivering, on one page, with the two things a portfolio register normally leaves out: a forecast beside the approved budget so a variance exists at all, and two delivery confidence ratings so the reviewer and the owner can visibly disagree. The contractor list is not a contact list - it sums what you have committed with each contractor across the whole register and sets it against the capacity they were assessed at.
HOW TO USE IT
1 | Fill in Setup, including the variance threshold and the slip tolerance. | Two numbers do most of the work. The variance threshold decides when a cost movement has to be explained in writing rather than just reported, and the slip tolerance decides when a late project stops being a slip and becomes a problem. Both are yours to set, and every flag in the workbook derives from them.
2 | List the projects, and name somebody accountable for each one. | Not the project manager - the person answerable for whether the thing was worth doing. The published government portfolio names an accountable owner for its major projects in a list of its own, and a portfolio register that only names delivery staff cannot answer the question a board asks.
3 | Record two delivery confidence ratings, not one. | What an independent review says, and what the owner says. The published national portfolio carries one rating per project and states whose it is - an independent one where the project has had assurance or active support recently, the owner's own otherwise - so where the two disagree, the published number has already chosen between them. Keeping both is the only way to see the gap, and the row where the owner is the more confident of the two is the most useful row in the register.
4 | Baseline the finish date and then leave it alone. | The baseline is what you promised. The forecast is what you now think. Slip is the difference, and it only means anything if the baseline stops moving. Re-baseline deliberately, at a gate, and say so.
5 | Let the sheet find the cost movements that need explaining. | Enter approved budget and current forecast and it works out the variance, the percentage, and whether that percentage has crossed your threshold. If it has and the narrative cell is empty, the row goes red. Nobody has to remember the rule.
6 | Keep the contractor list current, because the register reads from it. | Contract values are summed by contractor across the whole portfolio, spread over the average contract length you set, and compared against the capacity their prequalification was assessed at - which the civil scheme states as a year of cash flow, so the comparison has to be annual to mean anything. It also checks whether a licence or an insurance certificate expires before the last project that contractor is on finishes.
7 | Use the gates your framework actually uses. | Gate names and counts differ - one national framework runs six gates ending at benefit realisation, a state one runs seven. The names shipped here are plain-language placeholders, not any framework's published titles. The list on Reference is editable and everything follows it. Do not adopt somebody else's numbering because a template shipped with it.
WHAT IS IN THE WORKBOOK
| Sheet | What it is for
| Setup | The organisation, the reporting period and the thresholds. The variance threshold and the slip tolerance are the two fields every flag in the workbook derives from.
| Portfolio Summary | The board read. What is late, where the two confidence ratings disagree, what has moved without an explanation, and which contractors are carrying more than they were assessed for.
| Project List | One row per project: who owns it, which gate it has passed, who is building it, and whether the finish date has moved.
| Cost & Benefits | Approved against forecast, the variance and whether it needs explaining, whole-life cost, benefits, and how the movement compares with the published allowance for that kind of asset.
| Assurance | The independent rating against the owner's own rating, when the last review was, when the next one is due, and what is still open from the last one.
| Contractor List | Who is building what, what they were prequalified for, what they are carrying across your whole portfolio, and whether their licences and cover outlast the work.
| Reference | The colour key, what the confidence ratings actually mean, where the cost allowance percentages come from and how old they are, definitions and every dropdown source.
THE COLOUR KEY
| Done | Complete, or within every threshold you set.
| On track | Under way and forecast to land on its baseline.
| Watch | Inside a warning window, or over a threshold and explained.
| Needs a decision | Something has to be settled above the project.
| Blocking | Late beyond tolerance, moved without an explanation, or a contractor carrying more than they were assessed for.
| Not applicable | On hold, withdrawn, or out of scope for this row.
WHAT MOST PROJECT LISTS GET WRONG
| One delivery confidence rating | A single rating is the owner's rating whatever it is labelled. The published national portfolio prints one per project and swaps in the independent rating where there has been a recent review, so the disagreement between the two is settled before anybody outside sees it. A project the reviewer calls amber and the owner calls green is the one to look at first, and it only exists as a visible row if you keep both.
| A baseline that moves whenever the forecast does | If the baseline finish is updated every time the forecast slips, slip is permanently zero and the register cannot tell you anything. The baseline is a commitment. Change it at a gate, deliberately, and record that you did. There is a published word for the severe case - a reset, meaning a programme with no credible route to what it promised - and it is worth keeping that word for that case rather than using it for every re-baseline.
| Approved budget with no forecast beside it | Most project lists on the market carry an approved or estimated budget and nothing to compare it with, which means no variance can be computed and the register reports intentions rather than performance. Two columns and a subtraction is the whole fix.
| A variance threshold nobody wrote down | Reporting a movement is not the same as explaining one. A published national portfolio return carries a departmental narrative field that applies wherever the in-year budget to forecast variance is more than five per cent - a real published rule rather than a colour somebody chose. Set your own number and let the sheet enforce it, so the explanation arrives with the number rather than after the meeting.
| Inventing a contingency rule | There is a published table of cost uplifts by asset class, issued by a treasury, and it is the nearest thing to an authority on how wrong early estimates usually are. It is also based on fifty projects reviewed in 2002, has never been revised since, and other government bodies now publish their own newer uplifts on newer evidence - which is exactly why the workbook shows it as a starting point on an editable field rather than a rule.
| Treating the contractor list as a contact list | Names, phones and addresses are the least useful thing you can hold. What matters is what they were prequalified for, what capacity that assessment was based on, what they are already carrying across your portfolio, and whether their cover and licences outlast the work. The civil prequalification scheme assesses capacity as an aggregate cash flow commitment across concurrent work over twelve months, and one national procurement rule requires the ability to perform to be judged against everything the contractor already holds.
| A portfolio register that stops at delivery | The published portfolio return carries a benefits field and a benefits narrative against every project, and the published gateway frameworks end at benefit realisation rather than handover. A register that closes a row at practical completion has stopped one gate early.
WHY IT IS BUILT THIS WAY
| Two ratings, because the published one has already chosen | The independent assurance rating and the owner's own, in separate columns, with the sheet saying which way the gap runs. The published portfolio prints one number and replaces the owner's with an independent one where there has been a recent review, so the disagreement never reaches the page. Here it does.
| The variance threshold is a field, and it has a precedent | A published portfolio return carries a narrative field that applies above five per cent in-year variance. Yours may differ; the point is that it is written down and the sheet enforces it rather than leaving it to whoever is presenting.
| The contractor sheet is a join, not a list | Contract values summed by contractor across every project in the register, spread over the contract length you set, and put beside the capacity their prequalification was assessed at. The civil scheme states that capacity as a year of aggregate cash flow, so the sheet annualises before it compares - which is the comparison the scheme intended.
| Cover that lapses before the work ends | The sheet takes the latest forecast finish of every project a contractor is on and checks it against their licence, insurance and prequalification expiry dates. An expiry date on its own tells you nothing; an expiry date against the work it has to cover tells you everything.
| Baseline and forecast kept apart | Slip is a subtraction, and it is only honest if the baseline is a commitment rather than a rolling estimate. Both columns, both visible, and a reset recorded as an event.
| Cost allowances shown with their age | The uplift percentages on Reference are a treasury's published indicative starting values for early estimates. They come from a review of fifty projects published in 2002 and have never been revised. Reference says so, and the field is editable.
| Gates you can change | Six gates in one national framework, seven in a state one, none at all in plenty of private portfolios. The gate list is a dropdown source on Reference and every count follows it.
IMPORTANT
This is a reporting and record-keeping artefact, not advice. Assurance frameworks, gate definitions, confidence rating scales, prequalification schemes, licensing and insurance requirements and any obligation to report a project publicly are specific to your jurisdiction, your organisation and your contracts - take your own legal, procurement and probity advice. Where the workbook names a scheme, a rating or a gate it is naming the concept, not asserting what applies to you. A prequalification level is an assessment made at a point in time, not a contractual ceiling, and nothing here is a compliance determination.
Built for teams delivering capital projects, programs and portfolios · mastt.com

## Setup
PROJECT LIST · SETUP
EXAMPLE DATA - type your own organisation name on Setup to clear this.
The organisation, the reporting period and the thresholds. The two numbers in section 2 are what every flag in the workbook derives from - set them once and nothing has to be remembered again.
1 · THE PORTFOLIO
Organisation | EXAMPLE - Carrowbrook Shire Council
Portfolio or programme | 2026-27 capital programme
Portfolio owner | Chief Operating Officer
Register maintained by | H. Nakamura, PMO
Reporting period | Quarter ending 30 September 2026
Today | 2026-08-18 | Every countdown, overdue flag and expiry check is measured against this.
2 · THE TWO THRESHOLDS EVERYTHING DERIVES FROM
Reporting a movement is not the same as explaining one. A published national portfolio return carries a narrative field that applies wherever the in-year budget to forecast variance is more than five per cent - a real threshold rather than a colour somebody chose. Set yours here. Slip tolerance does the same job for time: below it a project is slipping, above it the register calls it late.
Explain a cost movement above this (%) | 5% | Five per cent has a published precedent. Yours may differ; write it down either way.
Slip tolerance before a project is late (days) | 21 | Below this the register says slipping. Above it, late.
Warn me this many days before a date | 30 | Applies to review dates, finish dates, and every licence, insurance and prequalification expiry on the contractor list.
3 · THE CONTRACTOR CHECK
The contractor list sums what you have committed with each contractor across every project in this register and sets it against the capacity their prequalification was assessed at. The civil scheme states that capacity as a year of aggregate cash flow, so a multi-year commitment has to be spread over its length before the two can be compared - which is what the field below does. You can only see your own work, and the level is an assessment at a point in time rather than a contractual ceiling. Reference sets out all three cautions.
Spread committed value over this many months | 24 | The assessed level is a twelve-month cash flow figure, so committed value is divided over this many months before it is compared. Set it to your average contract length. Twelve compares totals instead, which overstates every multi-year contractor.
Flag a contractor at this share of their assessed level (%) | 90% | Below the level but close enough to matter before the next award.
IS THE SHEET READY?
Setup complete | 100% | Everything above filled in.
Visit mastt.com

## Portfolio Summary
PROJECT LIST · PORTFOLIO SUMMARY
EXAMPLE DATA - type your own organisation name on Setup to clear this.
The board read. Every figure counts itself from the sheets behind it - none of it is typed.
WHERE THE PORTFOLIO STANDS
Projects in the portfolio |  | Late beyond tolerance |  | Owner rating ahead of the review |  | Moved without an explanation
16 |  | 2 |  | 3 |  | 1
Approved budget |  | Current forecast |  | Variance |  | Variance %
168150000 |  | 193135000 |  | 24985000 |  | 14.86%
Contractors over the assessed level |  | Cover that lapses before the work ends |  | Assurance reviews overdue |  | Assurance actions overdue
1 |  | 1 |  | 1 |  | 15
Red independent ratings | 1 |  | The reviewer's view, not the owner's. Read it beside the tile above - a portfolio with no reds and three owner-ahead rows is telling you something.
Whole-life cost of the portfolio | 343100000 |  | Capital plus the cost of owning and running the assets. It often exceeds the capital figure over the life of the asset, and it is the number a decision should turn on.
Benefits claimed against these projects | 342200000 |  | The published portfolio return carries a benefits field and a narrative against every project, and the published gateway frameworks end at benefit realisation, not handover.
Committed with contractors | 172535000 |  | Total value summed from the project register by contractor - not annualised, unlike the capacity check. The gap between this and the forecast total is the work that has no contractor against it yet.
Projects with no contractor recorded | 2 |  | Correct at an early gate and worth seeing at a late one.
Rows pointing at a project not on the list | 0 |  | Anything other than nought and the money above is wrong. A cost row whose reference no longer matches a project still adds its budget to these totals. Fix the reference or delete the row - the row itself is flagged red on the sheet it sits on.
Projects on the list with no cost row | 0 |  | Those projects contribute nothing to the budget, forecast and benefits totals above. Early in a programme that is honest; at a delivery gate it means the totals understate the portfolio.
WHERE THE PROJECTS STAND
Status | Projects |  | Share |  | What it means
On programme | 6 |  | 37.5% |  | Under way and forecast to land on its baseline finish.
Finishing soon | 1 |  | 6.25% |  | Inside the warning window set on Setup.
Slipping | 5 |  | 31.25% |  | Forecast later than baseline, but inside the slip tolerance.
LATE - beyond tolerance | 2 |  | 12.5% |  | Slip past the tolerance on Setup. This is the list a board should be given.
Overdue - not closed out | 0 |  | 0% |  | The forecast finish has passed and nothing has been recorded against it.
Complete | 1 |  | 6.25% |  | At the benefits gate, not at handover.
On hold | 1 |  | 6.25% |  | Kept in the register so the count stays honest.
No forecast finish | 0 |  | 0% |  | Nothing to measure slip against yet.
BY GATE
Gate | Projects |  | Approved | Forecast | Variance | Late | Owner ahead
Gate 0 - business need | 1 |  | 18000000 | 18000000 | 0 | 0 | 0
Gate 1 - business case | 2 |  | 8800000 | 9790000 | 990000 | 1 | 1
Gate 2 - delivery strategy | 2 |  | 44500000 | 59650000 | 15150000 | 0 | 1
Gate 3 - investment decision | 4 |  | 63100000 | 71490000 | 8390000 | 1 | 1
Gate 4 - readiness for service | 5 |  | 29300000 | 29810000 | 510000 | 0 | 0
Gate 5 - benefits realised | 1 |  | 1850000 | 1795000 | -55000 | 0 | 0
Not gated | 0 |  | 0 | 0 | 0 | 0 | 0
On hold | 1 |  | 2600000 | 2600000 | 0 | 0 | 0
BY PORTFOLIO
Portfolio | Projects |  | Approved | Forecast | Variance | Variance % | Whole-life
Buildings | 4 |  | 35900000 | 43658000 | 7758000 | 21.61% | 68700000
Roads and bridges | 2 |  | 51100000 | 58810000 | 7710000 | 15.09% | 83100000
Water and wastewater | 3 |  | 58400000 | 66650000 | 8250000 | 14.13% | 143900000
Open space and recreation | 3 |  | 7350000 | 7585000 | 235000 | 3.197% | 13500000
Fleet and plant | 1 |  | 4200000 | 4500000 | 300000 | 7.143% | 9800000
Digital and technology | 1 |  | 4600000 | 5290000 | 690000 | 15% | 12400000
Renewals programme | 2 |  | 6600000 | 6642000 | 42000 | 0.6364% | 11700000
THE TWO RATINGS, SIDE BY SIDE
Rating | Independent |  | Owner's own |  | What the gap says
Green | 6 |  | 8 |  | Delivery on time, budget and quality appears highly likely.
Amber | 7 |  | 6 |  | Feasible, but significant issues already exist and need attention.
Red | 1 |  | 0 |  | Delivery appears unachievable as things stand.
Reset | 1 |  | 1 |  | The baseline is being changed and a business case refreshed.
Not rated | 1 |  | 1 |  | No review has been done yet.
Owner more confident than the reviewer | 3
Reviewer more confident than the owner | 0
The two agree | 11
BY CONTRACTOR
Contractor | Projects |  | Committed | Assessed level | Headroom | Where they stand
Merrivale Construction | 2 |  | 21790000 | 25000000 | 14105000 | Current
Halverson Civil | 3 |  | 100060000 | 25000000 | -25030000 | OVER THE ASSESSED LEVEL
Orne Pipeline Services | 1 |  | 7400000 | 10000000 | 6300000 | Expiring soon
Bellhaven Mechanical | 3 |  | 9485000 | 5000000 | 257500 | Near the assessed level
Ardley Fitout Group | 1 |  | 3468000 | 5000000 | 3266000 | COVER LAPSES BEFORE THE WORK ENDS
Vasari Heritage Works | 1 |  | 18400000 | 25000000 | 15800000 | Current
Southgate Technology | 1 |  | 5290000 | 0 |  | Current
Tamarind Surfacing | 2 |  | 6642000 | 5000000 | 1679000 | SUSPENDED - DO NOT AWARD
Kestrel Demolition | 0 |  | 0 | 2000000 | 2000000 | Prequalified, carrying nothing
Visit mastt.com

## Project List
PROJECT LIST
EXAMPLE DATA - type your own organisation name on Setup to clear this.
One row per project, present tense. The baseline finish is what you committed to and it should only move at a gate; the forecast is what you now think. Slip is the difference, and it is the only reason to keep both columns.
Ref | Project | Portfolio | Asset class | Gate passed | Accountable owner | Project manager | Contractor | Baseline finish | Forecast finish | Slip (days) | Status | Note
P001 | Riverton Library replacement | Buildings | Standard building | Gate 4 - readiness for service | Director Community | T. Awuah | Merrivale Construction | 2026-10-17 | 2026-10-17 | 0 | On programme | On its baseline at the last gate.
P002 | Depot workshop rebuild | Buildings | Standard building | Gate 3 - investment decision | Director Operations | T. Awuah | Merrivale Construction | 2027-03-16 | 2027-04-03 | 18 | Slipping | Slipping, but inside tolerance. Reported as a slip.
P003 | Kalinda Road duplication | Roads and bridges | Standard civil engineering | Gate 3 - investment decision | Director Infrastructure | P. Sundaram | Halverson Civil | 2027-07-04 | 2027-10-03 | 91 | LATE - beyond tolerance | Late, and the two ratings do not agree either.
P004 | Bridge 214 strengthening | Roads and bridges | Non-standard civil engineering | Gate 3 - investment decision | Director Infrastructure | P. Sundaram | Halverson Civil | 2027-01-15 | 2027-02-02 | 18 | Slipping
P005 | Wastewater treatment upgrade, stage 2 | Water and wastewater | Non-standard civil engineering | Gate 2 - delivery strategy | Director Utilities | L. Beaumont | Halverson Civil | 2028-02-09 | 2028-02-09 | 0 | On programme | Cost has moved and nobody wrote down why.
P006 | Trunk main renewal, northern sector | Water and wastewater | Standard civil engineering | Gate 4 - readiness for service | Director Utilities | L. Beaumont | Orne Pipeline Services | 2026-11-16 | 2026-11-23 | 7 | Slipping
P007 | Aquatic centre plant replacement | Open space and recreation | Equipment or development | Gate 4 - readiness for service | Director Community | T. Awuah | Bellhaven Mechanical | 2026-09-12 | 2026-09-12 | 0 | Finishing soon
P008 | Sportsfield lighting, three reserves | Open space and recreation | Standard building | Gate 5 - benefits realised | Director Community | R. Okafor | Bellhaven Mechanical | 2026-07-09 | 2026-07-09 | 0 | Complete | Closed at the benefits gate.
P009 | Civic centre accessibility works | Buildings | Standard building | Gate 4 - readiness for service | Director Community | R. Okafor | Ardley Fitout Group | 2026-12-16 | 2026-12-30 | 14 | Slipping | The fitout contractor's cover runs out first.
P010 | Heritage town hall restoration | Buildings | Non-standard building | Gate 2 - delivery strategy | Director Community | R. Okafor | Vasari Heritage Works | 2027-10-12 | 2027-10-12 | 0 | On programme | Sixty per cent over, past the published allowance.
P011 | Fleet depot fuel system | Fleet and plant | Equipment or development | Gate 1 - business case | Director Operations | L. Beaumont | Bellhaven Mechanical | 2027-06-14 | 2027-06-14 | 0 | On programme
P012 | Asset management system replacement | Digital and technology | Equipment or development | Gate 1 - business case | Director Corporate | M. Ferreira | Southgate Technology | 2027-05-15 | 2027-06-14 | 30 | LATE - beyond tolerance
P013 | Depot yard resurfacing | Renewals programme | Standard civil engineering | Gate 4 - readiness for service | Director Operations | P. Sundaram | Tamarind Surfacing | 2026-09-17 | 2026-10-05 | 18 | Slipping | This contractor is suspended under their scheme.
P014 | Footpath renewals, 2026-27 programme | Renewals programme | Standard civil engineering | Gate 3 - investment decision | Director Infrastructure | P. Sundaram | Tamarind Surfacing | 2027-04-15 | 2027-04-15 | 0 | On programme
P015 | Stormwater harvesting scheme | Water and wastewater | Non-standard civil engineering | Gate 0 - business need | Director Utilities |  |  | 2027-09-12 | 2027-09-12 | 0 | On programme | No manager and no contractor yet. Correct this early.
P016 | Library forecourt upgrade | Open space and recreation | Standard building | On hold | Director Community | R. Okafor |  | 2027-02-14 | 2027-02-14 | 0 | On hold | On hold. Kept in the register so the count is honest.
A project at the benefits gate reads as complete, and one on hold reads as on hold, because neither is usefully described as late. Everything else is measured against the slip tolerance on Setup. Keep a project on hold in the register rather than deleting it - a portfolio count that quietly drops the awkward ones is not a portfolio count.
Visit mastt.com

## Cost & Benefits
PROJECT LIST · COST & BENEFITS
EXAMPLE DATA - type your own organisation name on Setup to clear this.
Approved against forecast, so a variance exists at all. Above the threshold on Setup the movement has to be explained in writing, and the row stays red until it is. The allowance is a published starting point for this asset class - see Reference for what it is and how old.
Ref | Project | Contractor | Approved budget | Forecast cost | Variance | Variance % | Explain? | Why it moved | Whole-life cost | Benefits | Allowance % | Indicated allowance | Check
P001 | Riverton Library replacement | Merrivale Construction | 14200000 | 14310000 | 110000 | 0.7746% | No |  | 24800000 | 31000000 | 24% | 3408000 | Over budget, inside the allowance
P002 | Depot workshop rebuild | Merrivale Construction | 6800000 | 7480000 | 680000 | 10% | Yes | Structural steel repriced after the tender period lapsed. | 11200000 | 8900000 | 24% | 1632000 | Over threshold - explained
P003 | Kalinda Road duplication | Halverson Civil | 41500000 | 48970000 | 7470000 | 18% | Yes | Two service relocations were not in the reference design. | 68000000 | 74000000 | 44% | 18260000 | Over threshold - explained
P004 | Bridge 214 strengthening | Halverson Civil | 9600000 | 9840000 | 240000 | 2.5% | No |  | 15100000 | 12400000 | 66% | 6336000 | Over budget, inside the allowance
P005 | Wastewater treatment upgrade, ... | Halverson Civil | 33000000 | 41250000 | 8250000 | 25% | Yes |  | 88000000 | 96000000 | 66% | 21780000 | OVER THRESHOLD - NO EXPLANATION
P006 | Trunk main renewal, northern s... | Orne Pipeline Services | 7400000 | 7400000 | 0 | 0% | No |  | 13900000 | 9100000 | 44% | 3256000 | On budget
P007 | Aquatic centre plant replaceme... | Bellhaven Mechanical | 2900000 | 3190000 | 290000 | 10% | Yes | Chiller selection changed after the energy review. | 6100000 | 4200000 | 200% | 5800000 | Over threshold - explained
P008 | Sportsfield lighting, three re... | Bellhaven Mechanical | 1850000 | 1795000 | -55000 | -2.973% | No |  | 3300000 | 2600000 | 24% | 444000 | Under budget
P009 | Civic centre accessibility wor... | Ardley Fitout Group | 3400000 | 3468000 | 68000 | 2% | No |  | 5200000 | 6800000 | 24% | 816000 | Over budget, inside the allowance
P010 | Heritage town hall restoration | Vasari Heritage Works | 11500000 | 18400000 | 6900000 | 60% | Yes | Structure worse than the condition survey found. | 27500000 | 14200000 | 51% | 5865000 | BEYOND THE INDICATED ALLOWANCE
P011 | Fleet depot fuel system | Bellhaven Mechanical | 4200000 | 4500000 | 300000 | 7.143% | Yes | Bunded tank required after the environmental review. | 9800000 | 5400000 | 200% | 8400000 | Over threshold - explained
P012 | Asset management system replac... | Southgate Technology | 4600000 | 5290000 | 690000 | 15% | Yes | Integration scope grew after the discovery workshops. | 12400000 | 15000000 | 200% | 9200000 | Over threshold - explained
P013 | Depot yard resurfacing | Tamarind Surfacing | 1400000 | 1442000 | 42000 | 3% | No |  | 2600000 | 1900000 | 44% | 616000 | Over budget, inside the allowance
P014 | Footpath renewals, 2026-27 pro... | Tamarind Surfacing | 5200000 | 5200000 | 0 | 0% | No |  | 9100000 | 6400000 | 44% | 2288000 | On budget
P015 | Stormwater harvesting scheme | 0 | 18000000 | 18000000 | 0 | 0% | No |  | 42000000 | 51000000 | 66% | 11880000 | On budget
P016 | Library forecourt upgrade | 0 | 2600000 | 2600000 | 0 | 0% | No |  | 4100000 | 3300000 | 24% | 624000 | On budget
The indicated allowance is the approved budget times a published upper-bound uplift for that asset class. It is not a target and it is not a contingency you hold - it is a treasury's own indicative figure for how wrong early estimates of that kind of asset turn out to be. The treasury applies it at appraisal and expects it to have fallen to the lower bound by contract award, so on an approved budget read it as a sanity check on how far an early estimate could move rather than as a live allowance - and the table itself dates from 2002.
Visit mastt.com

## Assurance
PROJECT LIST · ASSURANCE
EXAMPLE DATA - type your own organisation name on Setup to clear this.
Two delivery confidence ratings, because they can disagree. The published national portfolio prints one per project - an independent rating where there has been a recent review, the senior owner's own otherwise - so it has already chosen between them. Keep both, and the row where the owner is the more confident is the row to read first.
Ref | Project | Gate passed | Independent rating | Owner's own rating | Which way the gap runs | Last review | Next review due | Days until | Actions open | Actions overdue | Check | Note
P001 | Riverton Library replacement | Gate 4 - readiness for service | Green | Green | Aligned | 2026-06-17 | 2026-12-14 | 118 | 1 | 0 | Current
P002 | Depot workshop rebuild | Gate 3 - investment decision | Amber | Amber | Aligned | 2026-05-15 | 2026-11-11 | 85 | 4 | 1 | Actions overdue
P003 | Kalinda Road duplication | Gate 3 - investment decision | Amber | Green | Owner more confident | 2026-07-01 | 2026-12-28 | 132 | 7 | 3 | OWNER AHEAD OF THE REVIEW | Reviewer amber, owner green. Start here.
P004 | Bridge 214 strengthening | Gate 3 - investment decision | Green | Green | Aligned | 2026-04-20 | 2026-10-17 | 60 | 0 | 0 | Current
P005 | Wastewater treatment upgrade, ... | Gate 2 - delivery strategy | Red | Amber | Owner more confident | 2026-07-19 | 2027-01-15 | 150 | 9 | 5 | OWNER AHEAD OF THE REVIEW | Reviewer red, owner amber. Same direction.
P006 | Trunk main renewal, northern s... | Gate 4 - readiness for service | Green | Green | Aligned | 2026-03-21 | 2026-09-17 | 30 | 2 | 0 | Review due soon
P007 | Aquatic centre plant replaceme... | Gate 4 - readiness for service | Amber | Amber | Aligned | 2026-06-05 | 2026-12-02 | 106 | 3 | 0 | Current
P008 | Sportsfield lighting, three re... | Gate 5 - benefits realised | Green | Green | Aligned | 2026-01-30 | 2026-07-29 | -20 | 0 | 0 | Closed | Complete. The overdue review is housekeeping, not risk.
P009 | Civic centre accessibility wor... | Gate 4 - readiness for service | Amber | Amber | Aligned | 2026-04-30 | 2026-08-06 | -12 | 5 | 2 | REVIEW OVERDUE | Review overdue, actions still open.
P010 | Heritage town hall restoration | Gate 2 - delivery strategy | Reset | Reset | - | 2026-06-24 | 2026-12-21 | 125 | 6 | 1 | Baseline being reset | Business case refreshed, so the baseline resets.
P011 | Fleet depot fuel system | Gate 1 - business case | Green | Green | Aligned | 2026-05-30 | 2026-11-26 | 100 | 1 | 0 | Current
P012 | Asset management system replac... | Gate 1 - business case | Amber | Green | Owner more confident | 2026-06-13 | 2026-12-10 | 114 | 5 | 2 | OWNER AHEAD OF THE REVIEW | Third row where the owner is the more confident.
P013 | Depot yard resurfacing | Gate 4 - readiness for service | Amber | Amber | Aligned | 2026-07-09 | 2027-01-05 | 140 | 2 | 1 | Actions overdue
P014 | Footpath renewals, 2026-27 pro... | Gate 3 - investment decision | Green | Green | Aligned | 2026-05-10 | 2026-11-06 | 80 | 0 | 0 | Current
P015 | Stormwater harvesting scheme | Gate 0 - business need | Not rated | Not rated | - | [5 empty] | Not yet reviewed | Not yet reviewed. Correct this early.
P016 | Library forecourt upgrade | On hold | Amber | Amber | Aligned | 2026-07-29 | 2027-01-25 | 160 | 3 | 0 | Current | On hold, so it reports as on hold rather than late.
A single rating is the owner's rating whatever it is labelled - which is why the published return substitutes an independent one where a recent review exists, and why the disagreement never appears in it. Recording both, and the direction of the gap, is the one thing a single-column RAG can never say. An owner rating ahead of the reviewer is not misconduct - the owner knows things the reviewer does not - but it is the conversation worth having before the board reads the green light.
Visit mastt.com
Formulas:
Days until = IF(OR([Ref]="",[Next review due]=""),"",[Next review due]-TODAY())

## Contractor List
PROJECT LIST · CONTRACTOR LIST
EXAMPLE DATA - type your own organisation name on Setup to clear this.
Who is building what, and whether they can carry it. Committed value is summed from the project register, not typed - so it moves when the portfolio does - and it is spread over the contract length on Setup before it is set against a level that was assessed as a year's cash flow. An expiry date on its own tells you nothing; an expiry date against the work it has to cover tells you everything.
Ref | Contractor | Prequal scheme | Category | Financial level | Capacity a year | Committed here | Headroom for a year | Projects | Licence expires | Insurance expires | Prequal expires | Status | Check | Note
C001 | Merrivale Construction | National prequal - building | Design and construct | F25 | 25000000 | 21790000 | 14105000 | 2 | 2027-09-22 | 2027-05-05 | 2028-01-20 | Current | Current
C002 | Halverson Civil | National prequal - civil | R4 | F25 | 25000000 | 100060000 | -25030000 | 3 | 2028-04-29 | 2028-04-09 | 2028-03-20 | Current | OVER THE ASSESSED LEVEL | A year of their work is twice the level.
C003 | Orne Pipeline Services | National prequal - civil | R3 | F10 | 10000000 | 7400000 | 6300000 | 1 | 2027-06-14 | 2027-03-16 | 2026-09-12 | Current | Expiring soon | Prequalification expires soon.
C004 | Bellhaven Mechanical | Agency panel | Panel | F5 | 5000000 | 9485000 | 257500 | 3 | 2027-08-13 | 2027-07-24 | 2027-07-04 | Current | Near the assessed level | A year of their work is near the level.
C005 | Ardley Fitout Group | Agency panel | Panel | F5 | 5000000 | 3468000 | 3266000 | 1 | 2027-05-25 | 2026-11-22 | 2027-07-24 | Current | COVER LAPSES BEFORE THE WORK ENDS | Cover runs out before the work does.
C006 | Vasari Heritage Works | National prequal - building | Construct only | F25 | 25000000 | 18400000 | 15800000 | 1 | 2027-11-11 | 2027-10-22 | 2027-12-01 | Current | Current
C007 | Southgate Technology | Assessed in-house | Not set | Not assessed |  | 5290000 |  | 1 | 2027-12-31 | 2027-07-04 |  | Current | Current | No assessed capacity, so no check runs.
C008 | Tamarind Surfacing | National prequal - civil | R2 | F5 | 5000000 | 6642000 | 1679000 | 2 | 2026-08-03 | 2027-02-14 | 2027-04-15 | Suspended | SUSPENDED - DO NOT AWARD | Suspended, and the licence has expired.
C009 | Kestrel Demolition | National prequal - civil | R2 | F2 | 2000000 | 0 | 2000000 | 0 | 2027-07-14 | 2027-06-04 | 2027-10-02 | Current | Prequalified, carrying nothing | Prequalified and carrying nothing.
Committed here is the total value of your work, and headroom is what is left of a year's capacity once that total is spread over the contract length on Setup. It is your work only: whatever this contractor is doing for everybody else is invisible to you, so a row inside its level is not proof of capacity - and a row over it is a conversation to have rather than a breach, because the level is an assessment made at a point in time. Where no capacity is recorded the check simply does not run, which is honest rather than silent.
Visit mastt.com

## Reference
PROJECT LIST · REFERENCE
The colour key, what the delivery confidence ratings actually mean, where the cost allowance percentages come from and how old they are, what belongs here and what belongs somewhere else, definitions and every dropdown source.
THE COLOUR KEY - THE SAME SIX MEANINGS ON EVERY SHEET
Colour | It means |  |  |  | When you will see it
DONE | Done |  |  |  | Complete, or within every threshold you set.
ON TRACK | On track |  |  |  | Under way and forecast to land on its baseline.
WATCH | Watch |  |  |  | Inside a warning window, or over a threshold and explained.
NEEDS A DECISION | Needs a decision |  |  |  | Something has to be settled above the project.
BLOCKING | Blocking |  |  |  | Late beyond tolerance, moved without an explanation, or a contractor carrying more than they were assessed for.
NOT APPLICABLE | Not applicable |  |  |  | On hold, withdrawn, or out of scope for this row.
WHAT THE DELIVERY CONFIDENCE RATINGS MEAN
Delivery confidence is a published rating and it is worth using the published wording. One national portfolio moved from a five-point scale to three points in 2021, deleting the two hybrid rungs. It publishes one rating per project and says whose it is: an independent rating where the project has had independent assurance or active support in the last six months, and the senior owner's own rating otherwise. The published wording runs like this. Green: successful delivery of the project on time, budget and quality appears highly likely and there are no major outstanding issues that at this stage appear to threaten delivery significantly. Amber: successful delivery appears feasible but significant issues already exist, requiring management attention - these appear resolvable at this stage and, if addressed promptly, should not present a cost or schedule overrun. Red: successful delivery of the project appears to be unachievable, with major issues of project definition, schedule, budget, quality or benefits delivery which at this stage do not appear to be manageable or resolvable, and the project may need re-scoping or its overall viability reassessed. Reset is the published term for a programme with no credible route to delivering what it promised, needing fundamental change to its objectives, approach, schedule or whole-life cost and ending in a new business case - it is not the word for a routine re-baseline at a gate. The scale is a dropdown source you can change. What matters is that both ratings are recorded and that the difference between them is visible, because the published return shows you only one of them.
WHERE THE COST ALLOWANCE PERCENTAGES COME FROM
There is a published table of cost uplifts by asset class, issued by a treasury as indicative starting values for early estimates, and the guidance that carries it says to start at the upper bound and reduce it as the causes are dealt with, ideally reaching the lower bound before contract award. The percentages below are those upper bounds for capital expenditure. Three things you should know before quoting them. They come from a review of fifty public projects over about twenty years, published in 2002, and the table has never been revised since, though the treasury still publishes it. The current edition of the main appraisal guidance requires the adjustment but publishes no numbers at all, while other government bodies - a transport department's own scheme appraisal guidance is the obvious one - now publish their own uplifts on newer evidence, so this is not the only or the latest table. And because the uplift is meant to have fallen to the lower bound by contract award, applying the upper bound to a budget that is already approved is a sanity check on how far an early estimate could move, not an allowance you hold. Use it as a starting point on an editable field, say where it came from, and do not present it as an estimate of your project.
WHAT AN ASSESSED CAPACITY ACTUALLY MEASURES
A prequalification financial level is not a limit on one contract, and it is not a stock of contract value either. The national civil scheme that publishes these levels describes the assessed capacity as the maximum additional aggregate contract cash flow commitment over a twelve-month period, assuming a relatively even spread of cash flow over that period. That is a rate, not a total: a three-year contract worth ninety million is roughly thirty million a year against the level, not ninety. So this sheet spreads your committed value over the average contract length you set on Setup before it compares - leave that field at twelve months and it compares totals instead, which overstates every contractor you use. A national procurement rule in another jurisdiction comes at the same idea from the other direction: the ability to perform must be judged taking into account all existing commercial and government commitments. Three cautions. The scheme documents themselves say the financial level is only indicative, reflecting capacity at a point in time, and the assessment already considers inter-company arrangements and existing commitments you cannot see. You can only sum what is in your own register - work they are doing for everybody else is invisible to you. And the category codes in the dropdown belong to that civil scheme, where R is roadworks and B is bridgeworks rather than building; the national building scheme works differently again, setting a limit on contract value from turnover and working capital and categorising by contract type, so if that is your scheme put its own values in the list and read the comparison as total exposure rather than a year's cash flow. Treat a flag here as a conversation to have, never as a breach.
THE PUBLISHED COST ALLOWANCES, BY ASSET CLASS
Asset class | Start here | By contract award |  |  | What it is
Standard building | 24% | 2% |  |  | The published upper bound for this class, and the value the guidance says to work down to as the causes are dealt with.
Non-standard building | 51% | 4%
Standard civil engineering | 44% | 3%
Non-standard civil engineering | 66% | 6%
Equipment or development | 200% | 10%
Not classified
The pale blue column is editable. If your organisation publishes its own contingency guidance, put it here and every allowance in the workbook follows it.
WHAT BELONGS HERE, AND WHAT BELONGS SOMEWHERE ELSE
If it is... | It goes in |  |  | Why
A list of the projects you are delivering, with delivery status and confidence | Here |  |  | This is the artefact. One row per project, present tense.
What you intend to fund over the next five to ten years, and where the money comes from | Capital improvement plan |  |  | Forward-looking, multi-year, dollars by financial year. This register is present tense and asks whether what was approved is landing.
The tasks inside one project | A programme or a task list |  |  | One row per project here, not one row per activity. A register that mixes the two can report neither.
A month-by-month narrative on one project | Monthly project report |  |  | This register is the roll-up that report feeds, not a replacement for it.
Every contract and its variations | Contract register |  |  | One row per contractor here, not one row per contract.
What each contractor has been paid | Payment register |  |  | Committed value here, certified and paid elsewhere.
Your list of projects delivered, for a tender submission or a CV | Not this |  |  | That is a credentials document. It shares the name and nothing else - it looks backwards at completed work and carries no forecast, no rating and no accountability.
DEFINITIONS
Portfolio | The collection of projects and programmes managed together to meet an organisation's objectives. Grouped to be managed, not just to be counted.
Gate | A decision point where a project needs approval to continue. Frameworks differ on how many there are and what they are called - set yours on Reference.
Baseline | The date or cost you committed to. It changes at a gate, deliberately, and the change is recorded. If it moves whenever the forecast does, it is not a baseline.
Forecast | What you now expect. The difference between it and the baseline is the whole point of the register.
Slip | Forecast finish less baseline finish, in days. Positive means later.
Slip tolerance | How much slip you are prepared to absorb before a project stops being on programme and starts being late. Yours to set.
Variance threshold | The cost movement above which a written explanation is required rather than optional. A published portfolio return uses five per cent in-year; yours may differ.
Delivery confidence | A published rating of how likely successful delivery looks. See the block above for what each rating means and why this register keeps two of them.
Reset | The published term for a programme with no credible route to delivering what it promised: fundamental change to objectives, approach, schedule or whole-life cost, ending in a new business case. Bigger than a re-baseline at a gate.
Accountable owner | The person answerable for whether the project was worth doing, as distinct from the person delivering it. The published portfolio names one for its major projects in a list of its own.
Whole-life cost | Capital plus the cost of owning and operating the asset. It often exceeds the capital cost over the life of the asset, and it is the number a decision should turn on.
Benefits | The value the project is meant to produce, and the last gate in the published frameworks. A register that closes at handover has stopped a gate early.
Prequalification | An assessment that a contractor is capable of work of a given type and size. It has a category for the kind of work and a level for the financial capacity, it expires, and it can be suspended.
Assessed capacity | The value the financial level was set against. The civil scheme describes it as an aggregate cash flow commitment across concurrent work over twelve months, not a cap on a single contract.
Committed value | What you have with a contractor across this register. It is not what they are carrying in total, because their other clients are invisible to you.
Certificate of currency | Evidence that an insurance policy is in force now. A policy number is not evidence; a certificate with a date is.
THE SAME THING, CALLED SOMETHING ELSE
Used here | Also called |  |  | Note
Project list | Project register, portfolio register, project tracker, master project list |  |  | Register and tracker are the same artefact. Note that a project list can also mean a credentials document for a CV or a tender - a different thing entirely.
Accountable owner | Senior responsible owner, SRO, project sponsor, executive sponsor |  |  | One named person, answerable for the investment rather than the delivery.
Delivery confidence | DCA, delivery confidence assessment, RAG rating, health rating |  |  | A published rating with published definitions, not a colour somebody chose.
Gate | Stage gate, gateway review, tollgate, decision point |  |  | Numbering differs by framework. Six gates in one, seven in another.
Prequalification | Prequal, panel, approved list, vendor list, capability assessment |  |  | An assessment with a category, a level, an expiry and a status.
Contractor | Head contractor, main contractor, principal contractor, builder |  |  | One row per organisation here, whatever your contracts call them.
HOW TO READ A CELL
Pale blue | You type here.
Off white | Worked out for you. Do not type over it.
Pale cyan | Column heading.
Grey | Reference, or something that does not apply.
DROPDOWN SOURCES - EDIT THESE AND EVERY LIST IN THE WORKBOOK FOLLOWS
|  | Portfolio | Rating | Yes or no | Gate | Asset class
|  | Buildings | Green | Yes | Gate 0 - business need | Standard building
|  | Roads and bridges | Amber | No | Gate 1 - business case | Non-standard building
|  | Water and wastewater | Red |  | Gate 2 - delivery strategy | Standard civil engineering
|  | Open space and recreation | Reset |  | Gate 3 - investment decision | Non-standard civil engineering
|  | Fleet and plant | Not rated |  | Gate 4 - readiness for service | Equipment or development
|  | Digital and technology |  |  | Gate 5 - benefits realised | Not classified
|  | Renewals programme |  |  | Not gated
On hold
|  |  | Prequal status | Financial level | Category | Scheme
|  |  | Current | F0.25 | R1 | National prequal - building
|  |  | Under review | F1 | R2 | National prequal - civil
|  |  | Suspended | F2 | R3 | Agency panel
|  |  | Cancelled | F5 | R4 | Common assessment standard
|  |  | Not prequalified | F10 | R5 | Assessed in-house
|  |  |  | F15 | B1 | Not prequalified
|  |  |  | F20 | B2
|  |  |  | F25 | B3
|  |  |  | F50 | B4
|  |  |  | F75 | Construct only
|  |  |  | F100 | Design and construct
|  |  |  | F150 | Managing contractor
|  |  |  | F150 PLUS | Relationship
|  |  |  | Not assessed | Panel
Not set
Visit mastt.com