## WBS Template
WORK BREAKDOWN STRUCTURE TEMPLATE
Project Name: | < Insert Project Name >
Project Number: | < Insert Project Number >
Date: | < Insert Date Issued >
Level | WBS Code | Name | Description | Owner | Duration | Dependencies
1 | 1 | Project Initiation | Initial project planning and setup | Project Manager | 5 Days | -
2 | 1.1 | Define project scope | Identify overall scope and deliverables | Project Manager | 2 Days | -
3 | 1.1.1 | Conduct needs assessment | Determine project requirements | Project Manager | 1 Day | 1.1
3 | 1.1.2 | Create project charter | Formalize project goals and deliverables | Project Manager | 1 Day | 1.1.1
2 | 1.2 | Identify stakeholders | Compile a list of project stakeholders | PMO | 2 Days | 1.1
3 | 1.2.1 | Meet with key stakeholders | Discuss project expectations | Project Manager | 1 Day | 1.2
3 | 1.2.2 | Document stakeholder interests | Define roles and communication plans | PMO | 1 Day | 1.2.1
2 | 1.3 | Budget allocation | Set project budget and funding sources | Finance | 1 Day | 1.1
3 | 1.3.1 | Create preliminary budget | Estimate high-level project costs | Finance | 1 Day | 1.3
3 | 1.3.2 | Review budget with stakeholders | Confirm and finalize budget | Finance | 1 Day | 1.3.1
1 | 2 | Design Phase | Planning the design of the construction | Design Team | 10 Days | 1
2 | 2.1 | Create conceptual design | Develop initial project designs | Architects | 5 Days | 2
3 | 2.1.1 | Conduct site surveys | Survey site to assess design feasibility | Surveyor | 2 Days | 2.1
3 | 2.1.2 | Develop architectural layouts | Initial drafts of building layout | Architects | 3 Days | 2.1.1
2 | 2.2 | Review and approve designs | Client/Stakeholder design approval | Client | 3 Days | 2.1
3 | 2.2.1 | Stakeholder design review | Present design for client feedback | Architects | 2 Days | 2.1.2
3 | 2.2.2 | Incorporate feedback | Adjust designs based on feedback | Design Team | 1 Day | 2.2.1
1 | 3 | Construction Planning | Develop detailed plans for construction | Construction Team | 15 Days | 2
2 | 3.1 | Define work packages | Break down tasks into work packages | Site Manager | 3 Days | 3
3 | 3.1.1 | Create task breakdown | List of specific construction tasks | Site Manager | 2 Days | 3.1
3 | 3.1.2 | Assign work package leaders | Assign roles to sub-contractors | Site Manager | 1 Day | 3.1.1
2 | 3.2 | Schedule resources | Allocate workforce and equipment | Resource Manager | 5 Days | 3.1
3 | 3.2.1 | Estimate manpower needs | Assess and schedule labor requirements | Resource Manager | 2 Days | 3.1.1
3 | 3.2.2 | Book equipment | Reserve necessary construction equipment | Equipment Manager | 3 Days | 3.2.1
2 | 3.3 | Set up construction site | Prepare site for construction | Site Manager | 7 Days | 3.2
3 | 3.3.1 | Secure site | Install fencing, security, and signage | Safety Officer | 3 Days | 3.3
3 | 3.3.2 | Install temporary facilities | Set up temporary offices and restrooms | Site Manager | 2 Days | 3.3.1
3 | 3.3.3 | Site utility connection | Ensure water, electricity, and internet | Utility Manager | 2 Days | 3.3.2
1 | 4 | Construction Execution | Actual construction work starts | Construction Team | 120 Days | 3
2 | 4.1 | Site excavation | Dig and prepare foundation | Excavation Team | 15 Days | 3.3
3 | 4.1.1 | Conduct soil testing | Ensure soil stability for construction | Geotechnical Team | 3 Days | 4.1
3 | 4.1.2 | Excavate foundation trenches | Dig trenches for foundation | Excavation Team | 12 Days | 4.1.1
2 | 4.2 | Lay foundation | Concrete pouring and foundation setup | Concrete Team | 10 Days | 4.1.2
3 | 4.2.1 | Prepare rebar and formwork | Setup rebar and molds for foundation | Concrete Team | 5 Days | 4.1.2
3 | 4.2.2 | Pour concrete | Pour and cure foundation concrete | Concrete Team | 5 Days | 4.2.1
2 | 4.3 | Structural framing | Erect structural framework | Framing Team | 25 Days | 4.2
3 | 4.3.1 | Steel frame erection | Assemble and secure steel frame | Framing Team | 15 Days | 4.2.2
3 | 4.3.2 | Roof installation | Install roofing materials | Roofing Team | 10 Days | 4.3.1
2 | 4.4 | Electrical and plumbing | Install electrical systems and plumbing | Electrical Team | 20 Days | 4.3
3 | 4.4.1 | Electrical rough-in | Run electrical wiring through structure | Electricians | 10 Days | 4.3.2
3 | 4.4.2 | Plumbing rough-in | Install plumbing pipes and fixtures | Plumbers | 10 Days | 4.4.1
2 | 4.5 | Drywall and insulation | Insulation and drywall work | Interior Team | 15 Days | 4.4
3 | 4.5.1 | Install insulation | Place insulation between wall studs | Insulation Team | 5 Days | 4.4.2
3 | 4.5.2 | Hang drywall | Install drywall panels | Drywall Team | 10 Days | 4.5.1
2 | 4.6 | Finishing work | Painting, flooring, and finishing touches | Finishing Team | 25 Days | 4.5
3 | 4.6.1 | Paint interior and exterior | Paint all rooms and building exterior | Painting Team | 10 Days | 4.5.2
3 | 4.6.2 | Install flooring | Lay down hardwood, tile, or carpet | Flooring Team | 10 Days | 4.6.1
3 | 4.6.3 | Final trim and fixtures | Install fixtures like lighting and handles | Finishing Team | 5 Days | 4.6.2
1 | 5 | Project Closure | Final steps to close out the project | Project Manager | 10 Days | 4
2 | 5.1 | Final inspection and handover | Final review with stakeholders | QA Team | 5 Days | 5
3 | 5.1.1 | Conduct final walkthrough | Walkthrough with client to ensure quality | Project Manager | 2 Days | 5.1
3 | 5.1.2 | Address punch list items | Fix any outstanding issues | Construction Team | 3 Days | 5.1.1
2 | 5.2 | Project documentation and close | Close out and archive project files | PMO | 5 Days | 5.1
3 | 5.2.1 | Prepare final reports | Final cost, schedule, and performance report | PMO | 3 Days | 5.2
3 | 5.2.2 | Archive project documentation | Store all project documents for future reference | PMO | 2 Days | 5.2.1
1 | 6 | … | … | … | … | …
2 | 6.1 | … | … | … | … | …
3 | 6.1.1 | … | … | … | … | …
3 | 6.1.2 | … | … | … | … | …
2 | 6.2 | … | … | … | … | …
3 | 6.2.1 | … | … | … | … | …
3 | 6.2.2 | … | … | … | … | …
2 | 6.3 | … | … | … | … | …
3 | 6.3.1 | … | … | … | … | …
3 | 6.3.2 | … | … | … | … | …
1 | 7 | … | … | … | … | …
2 | 7.1 | … | … | … | … | …
3 | 7.1.1 | … | … | … | … | …
3 | 7.1.2 | … | … | … | … | …
2 | 7.2 | … | … | … | … | …
3 | 7.2.1 | … | … | … | … | …
3 | 7.2.2 | … | … | … | … | …
2 | 7.3 | … | … | … | … | …
3 | 7.3.1 | … | … | … | … | …
3 | 7.3.2 | … | … | … | … | …
1 | 8 | < Insert Phase > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
2 | 8.1 | < Insert Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
3 | 8.1.1 | < Insert Sub-Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
3 | 8.1.2 | < Insert Sub-Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
2 | 8.2 | < Insert Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
3 | 8.2.1 | < Insert Sub-Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
3 | 8.2.2 | < Insert Sub-Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
2 | 8.3 | < Insert Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
3 | 8.3.1 | < Insert Sub-Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >
3 | 8.3.2 | < Insert Sub-Task > | < Insert Description > | < Insert Owner > | < Insert Duration > | < Insert Dependency >