## Cover
PERT Chart
Three estimates, a calculated network, and the arithmetic nobody else does
Give every activity a best, most likely and worst case and say what it comes after. This works out the early and late dates, both floats, the critical path, and the chance of hitting a date - and draws the network from START to FINISH as you type.
HOW TO USE IT
1. Fill in Setup |  | Project, start date, calendar, estimating convention, required finish date.
2. List the activities |  | Three estimates and the IDs it comes after. It must sit BELOW those rows.
3. Clear the Check column |  | It names the fault in words and colours the row until you deal with it.
4. Read the Network Diagram |  | It draws itself from what you typed. Red boxes are the critical path.
5. Read the Summary |  | Duration, finish date, how much is critical, and the chance of a date.
WHAT IS IN THE WORKBOOK
Setup |  | Project, start date, calendar, estimating convention and the two thresholds.
Summary |  | Duration, finish date, how much of the work is critical, and the chance of a target date.
Network |  | One row per activity. Three estimates in; every date, both floats and the critical flag out.
Network Diagram |  | The network drawn - a box per activity, a line per dependency, START to FINISH, red on the critical path.
Reference |  | The colour key and every dropdown source. Edit a list here and every list in the workbook follows.
The colour key, what each cell colour means and every dropdown source are on the Reference sheet.
IMPORTANT | A planning aid, not a scheduling tool. It models finish-to-start links on one calendar with no lags, no leads and no resource levelling - real programmes have all three, and any of them can move the critical path. The probability follows one path, so it is optimistic wherever paths converge; the Summary counts those merge points beside it. Take your own scheduling advice before relying on a date contractually.
Built for teams delivering capital projects, programs and portfolios · mastt.com

## Setup
PERT CHART · SETUP
The project, the start date and the calendar everything is counted from, which estimating formula to use, and the two thresholds the flags derive from.
1 · THE PROJECT
Project | EXAMPLE - Northgate Depot refurbishment
Project number | EX-2026-114
Client or business unit | Facilities and Assets
Programme prepared by | H. Nakamura, PMO
Project start date | 2026-08-19 | Day 1 of the network. Every date in the workbook counts forward from here.
Calendar | 5-day working week | Durations are entered in this unit. A 5-day week skips weekends.
2 · HOW THE THREE ESTIMATES ARE COMBINED
Two weightings are in common use and neither is a law. The weighted form pulls the answer towards the most likely value; the triangular form treats the three equally and is more pessimistic wherever the worst case sits a long way out. Reference sets out both.
Estimating method | PERT weighted | Weighted: best plus four times most likely plus worst, over six. Triangular: the plain average of the three.
3 · THE TWO THRESHOLDS EVERYTHING DERIVES FROM
Treat float at or under this as nearly critical (days) | 5 | The least float in the network is the critical path. This is the band just above it - the activities nobody watches, and the ones that become critical first.
Confidence level for the date question (%) | 80% | The Summary works out the finish date that carries this confidence. Yours to set.
4 · DATES YOU ARE MEASURED AGAINST (OPTIONAL)
Required finish date |  | Blank measures float against the calculated finish. Fill it in and a date that cannot be met shows NEGATIVE float - the amount to recover.
Test the chance of finishing by | 2027-03-12 | Any date. The Summary works out how likely it is, and why that is optimistic.
CALCULATED FROM THE NETWORK - DO NOT TYPE HERE
Calculated duration (days) | 143.1667 | The longest path through the network.
Required finish, as a day number |  | Converted so the network can measure float against it.
The backward pass runs from | 143.1667 | The required date if you set one, otherwise the calculated finish.
Least float in the network (days) | 0 | Critical is read off this rather than off zero, so the longest path is still identified when an imposed date makes every float positive or every float negative.
Variance along the critical path | 54.6944 | Added along the one longest chain, not across every low-float row.
Target date, as a day number | 148 | Used for the probability question on the Summary.
IS THE SHEET READY?
Setup complete | 100% | Everything above the optional dates filled in.
Visit mastt.com

## Summary
PERT CHART · SUMMARY
EXAMPLE DATA - type your own project name on Setup to clear this.
The board read. Every figure counts itself from the Network - none of it is typed. Read the probability with the caution beside it.
WHERE THE PROGRAMME STANDS
Activities in the network |  | Expected duration (days) |  | Expected finish |  | On the critical path
15 |  | 143.1667 |  | 2027-03-08 |  | 11
Nearly critical |  | Behind the required date |  | Rows the sheet cannot calculate |  | Merge points
3 |  | 0 |  | 0 |  | 4
HOW LIKELY IS THE DATE
Three estimates give a spread as well as an average, and the spread along the critical path is what makes these two questions answerable at all. Both figures below are OPTIMISTIC wherever chains merge - see the tile above for how many merge points this network has, and Reference for why. Read them as a best case, not as a forecast.
Standard deviation of the critical path (days) | 7.3956 |  | Added along the longest chain, from the spread between your best and worst cases. A big number here is a schedule nobody should be quoting a single date for.
Chance of finishing by the target date | 74.33% |  | Set the target on Setup. Blank means no target set, or the estimates leave no spread to work with.
Finish date you would need for that confidence | 2027-03-16 |  | The date that carries the confidence level set on Setup. The gap between this and the expected finish is what a contingency allowance on time is actually for.
Days of contingency that implies | 7 |  | The difference between the two dates above, in whichever unit your calendar uses.
Widest spread on any one activity (days) | 22 |  | Best case to worst case on the single most uncertain activity. Compare it with the standard deviation above: if one activity carries most of the uncertainty in the network, the normal-curve arithmetic is on thinner ice than usual.
THE CRITICAL PATH - IN ORDER
Activity |  |  |  | Expected | Starts | Finishes
1 Site establishment and hoarding |  |  |  | 5.3333 | 2026-08-19 | 2026-08-26
2 Demolition and strip-out |  |  |  | 11 | 2026-08-27 | 2026-09-10
3 Asbestos clearance certificate |  |  |  | 6.3333 | 2026-09-11 | 2026-09-18
4 Structural steel - shop drawings |  |  |  | 12.6667 | 2026-09-21 | 2026-10-07
5 Structural steel - fabrication |  |  |  | 26.6667 | 2026-10-08 | 2026-11-12
6 Structural steel - erection |  |  |  | 14.6667 | 2026-11-13 | 2026-12-03
9 Mechanical services - rough-in |  |  |  | 19.6667 | 2026-12-04 | 2026-12-31
11 Services - coordination and testing |  |  |  | 10.3333 | 2027-01-01 | 2027-01-14
12 Internal linings and finishes |  |  |  | 20.8333 | 2027-01-15 | 2027-02-12
13 Joinery and fixed furniture |  |  |  | 12.3333 | 2027-02-15 | 2027-03-02
15 Practical completion inspection |  |  |  | 3.3333 | 2027-03-03 | 2027-03-08
The longest path through the network. Shows the first 12 - if the count in the tile above is larger than that, the rest are on the Network sheet with CRITICAL against them.
NEARLY CRITICAL - THE ONES NOBODY WATCHES
Activity |  |  |  | Float | Expected | Finishes
8 Facade - installation |  |  |  | 4.3333 | 25.6667 | 2027-01-08
10 Electrical services - rough-in |  |  |  | 3 | 16.6667 | 2026-12-28
14 Commissioning and witness testing |  |  |  | 1.1667 | 11.1667 | 2027-03-01
Float above zero but inside the threshold on Setup. A near-critical chain with a wide spread of estimates is more dangerous than a critical chain everybody is already watching, and it becomes the critical path the first time it slips.
Visit mastt.com

## Network
PERT CHART · NETWORK
EXAMPLE DATA - type your own project name on Setup to clear this.
One row per activity, and every column from Expected rightwards is calculated. An activity has to sit BELOW everything it comes after - a spreadsheet cannot resolve links that point upwards - and the Check column says so by name when one does not.
ID | Activity | After 1 | After 2 | After 3 | Best case (o) | Most likely (m) | Worst case (p) | Expected | Variance | Early start | Early finish | Late start | Late finish | Total float | Free float | Starts | Finishes | Status | Owner | Check
1 | Site establishment and hoarding |  |  |  | 4 | 5 | 8 | 5.3333 | 0.44444 | 1 | 5.3333 | 1 | 5.3333 | 0 | 0 | 2026-08-19 | 2026-08-26 | Complete | M. Okonkwo | CRITICAL | 143.1667 | 1 | 1 | 1 | 1 |  | 4 | 54.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Demolition and strip-out | 1 |  |  | 8 | 10 | 18 | 11 | 2.7778 | 6.3333 | 16.3333 | 6.3333 | 16.3333 | 0 | 0 | 2026-08-27 | 2026-09-10 | Complete | M. Okonkwo | CRITICAL | 137.8333 | 2 | 1 | 2 | 2 |  | 10 | 54.25 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0
3 | Asbestos clearance certificate | 2 |  |  | 3 | 5 | 15 | 6.3333 | 4 | 17.3333 | 22.6667 | 17.3333 | 22.6667 | 0 | 0 | 2026-09-11 | 2026-09-18 | Complete | R. Adeyemi | CRITICAL | 126.8333 | 3 | 1 | 3 | 3 |  | 12 | 51.4722 | 2 | 0 | 0 | 1 | 0 | 0 | 1 | 0
4 | Structural steel - shop drawings | 3 |  |  | 8 | 12 | 20 | 12.6667 | 4 | 23.6667 | 35.3333 | 23.6667 | 35.3333 | 0 | 0 | 2026-09-21 | 2026-10-07 | In progress | L. Brandt | CRITICAL | 120.5 | 4 | 1 | 4 | 4 |  | 12 | 47.4722 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0
5 | Structural steel - fabrication | 4 |  |  | 20 | 25 | 40 | 26.6667 | 11.1111 | 36.3333 | 62 | 36.3333 | 62 | 0 | 0 | 2026-10-08 | 2026-11-12 | Not started | L. Brandt | CRITICAL | 107.8333 | 5 | 1 | 5 | 5 |  | 20 | 43.4722 | 4 | 0 | 0 | 1 | 0 | 0 | 1 | 0
6 | Structural steel - erection | 5 |  |  | 10 | 14 | 22 | 14.6667 | 4 | 63 | 76.6667 | 63 | 76.6667 | 0 | 0 | 2026-11-13 | 2026-12-03 | Not started | L. Brandt | CRITICAL | 81.1667 | 6 | 1 | 6 | 6 |  | 12 | 32.3611 | 5 | 0 | 0 | 1 | 0 | 0 | 1 | 0
7 | Facade - procurement | 3 |  |  | 15 | 20 | 35 | 21.6667 | 11.1111 | 23.6667 | 44.3333 | 60.3333 | 81 | 36.6667 | 32.3333 | 2026-09-21 | 2026-10-20 | Not started | P. Nakamura | Has float | 83.8333 | 4 | 2 | 7 |  |  | 20 | 34.0278 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0
8 | Facade - installation | 6 | 7 |  | 18 | 24 | 40 | 25.6667 | 13.4444 | 77.6667 | 102.3333 | 82 | 106.6667 | 4.3333 | 4.3333 | 2026-12-04 | 2027-01-08 | Not started | P. Nakamura | Nearly critical | 62.1667 | 7 | 1 | 8 |  | 1 | 22 | 22.9167 | 6 | 4 | 0 | 1 | 2 | 0 | 1 | 0
9 | Mechanical services - rough-in | 6 |  |  | 12 | 18 | 34 | 19.6667 | 13.4444 | 77.6667 | 96.3333 | 77.6667 | 96.3333 | 0 | 0 | 2026-12-04 | 2026-12-31 | Not started | S. Villalobos | CRITICAL | 66.5 | 7 | 2 | 9 | 7 |  | 22 | 28.3611 | 6 | 0 | 0 | 1 | 0 | 0 | 1 | 0
10 | Electrical services - rough-in | 6 |  |  | 10 | 15 | 30 | 16.6667 | 11.1111 | 77.6667 | 93.3333 | 80.6667 | 96.3333 | 3 | 3 | 2026-12-04 | 2026-12-28 | Not started | S. Villalobos | Nearly critical | 63.5 | 7 | 3 | 10 |  | 2 | 20 | 26.0278 | 6 | 0 | 0 | 1 | 0 | 0 | 1 | 0
11 | Services - coordination and testing | 9 | 10 |  | 6 | 9 | 20 | 10.3333 | 5.4444 | 97.3333 | 106.6667 | 97.3333 | 106.6667 | 0 | 0 | 2027-01-01 | 2027-01-14 | Not started | S. Villalobos | CRITICAL | 46.8333 | 8 | 2 | 11 | 8 |  | 14 | 14.9167 | 7 | 7 | 0 | 2 | 3 | 0 | 2 | 0
12 | Internal linings and finishes | 8 | 11 |  | 15 | 20 | 30 | 20.8333 | 6.25 | 107.6667 | 127.5 | 107.6667 | 127.5 | 0 | 0 | 2027-01-15 | 2027-02-12 | Not started | K. Osei | CRITICAL | 36.5 | 9 | 2 | 12 | 9 |  | 15 | 9.4722 | 7 | 8 | 0 | 1 | 2 | 0 | 2 | 0
13 | Joinery and fixed furniture | 12 |  |  | 8 | 12 | 18 | 12.3333 | 2.7778 | 128.5 | 139.8333 | 128.5 | 139.8333 | 0 | 0 | 2027-02-15 | 2027-03-02 | Not started | K. Osei | CRITICAL | 15.6667 | 10 | 2 | 13 | 10 |  | 10 | 3.2222 | 9 | 0 | 0 | 2 | 0 | 0 | 2 | 0
14 | Commissioning and witness testing | 12 |  |  | 7 | 10 | 20 | 11.1667 | 4.6944 | 128.5 | 138.6667 | 129.6667 | 139.8333 | 1.1667 | 1.1667 | 2027-02-15 | 2027-03-01 | Not started | S. Villalobos | Nearly critical | 14.5 | 10 | 1 | 14 |  | 3 | 13 | 5.1389 | 9 | 0 | 0 | 2 | 0 | 0 | 2 | 0
15 | Practical completion inspection | 13 | 14 |  | 2 | 3 | 6 | 3.3333 | 0.44444 | 140.8333 | 143.1667 | 140.8333 | 143.1667 | 0 | 0 | 2027-03-03 | 2027-03-08 | Not started | R. Adeyemi | CRITICAL | 3.3333 | 11 | 2 | 15 | 11 |  | 4 | 0.44444 | 10 | 10 | 0 | 2 | 1 | 0 | 2 | 1
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 19 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | 0 | 0 | [9 empty] | 0 | 0 | 0 | 22 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Expected duration, both floats and the critical flag are calculated from the three estimates and the comes-after columns. Nothing about the path is typed, so a changed estimate moves every date that depends on it. Total float is late start less early start; free float is how long this activity can slip before the next one has to move, which is the smaller and more useful of the two.
Visit mastt.com
Formulas:
Starts = IF([Early start]=0,"",IF(Setup!$D12="5-day working week",WORKDAY(Setup!$D11-1,ROUNDUP([Early start],0)),Setup!$D11+ROUNDUP([Early start],0)-1))
Finishes = IF([Early finish]=0,"",IF(Setup!$D12="5-day working week",WORKDAY(Setup!$D11-1,ROUNDUP([Early finish],0)),Setup!$D11+ROUNDUP([Early finish],0)-1))

## Network Diagram
PERT CHART · NETWORK DIAGRAM
EXAMPLE DATA - type your own project name on Setup to clear this.
Every box and every line here is generated from the comes-after columns on the Network sheet. One continuous run, START to FINISH, left to right - a column is one step deeper into the network, so nothing in a column waits for anything else in it. Red is critical.
HOW TO READ A BOX | Early start | Duration | Early finish | Top row of a box: the earliest the activity can start and finish. Bottom row: the latest it can start and finish without moving the end date, and the float between the two. A RED box is on the critical path - it carries the least float in the network, so any delay to it is a delay to the project. Orange is nearly critical, blue has float, grey is missing its estimates. The thin navy line is a dependency: it leaves the right of one box and enters the left of the next, stepping up or down the vertical rule where the two are not in the same lane. Anything nothing waits for is fed from START; anything nothing waits on runs to FINISH. | [32 empty] | 1 | 0 | 1 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 1 | 4 | 0 | 1 | 1 | 0 | 0 | 5 | 0 | 1 | 1 | 0 | 0 | 6 | 0 | 3 | 2 | 0 | 3 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 14 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity name | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 9 | 0 | 1 | 2 | 0 | 1 | 11 | 0 | 1 | 2 | 0 | 0 | 12 | 0 | 2 | 1 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 0 | 15 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
[37 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Late start | Float | Late finish | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ID · comes after | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
THE NETWORK · START TO FINISH · 12 LEVELS, 5 LANES
| Level 1 |  |  | Level 2 |  |  |  | Level 3 |  |  | Level 4 |  |  | Level 5 |  |  | Level 6 |  |  | Level 7 |  |  | Level 8 |  |  | Level 9 |  |  | Level 10 |  |  | Level 11 |  |  | Level 12
START | 1 | 5.3333 | 5.3333 | 6.3333 | 11 | 16.3333 |  | 17.3333 | 6.3333 | 22.6667 | 23.6667 | 12.6667 | 35.3333 | 36.3333 | 26.6667 | 62 | 63 | 14.6667 | 76.6667 | 77.6667 | 25.6667 | 102.3333 | [6 empty] | 128.5 | 11.1667 | 138.6667 |  |  |  |  | FINISH
| Site establishment and hoarding |  |  | Demolition and strip-out |  |  |  | Asbestos clearance certificate |  |  | Structural steel - shop drawings |  |  | Structural steel - fabrication |  |  | Structural steel - erection |  |  | Facade - installation | [8 empty] | Commissioning and witness testing
| 1 | 0 | 5.3333 | 6.3333 | 0 | 16.3333 |  | 17.3333 | 0 | 22.6667 | 23.6667 | 0 | 35.3333 | 36.3333 | 0 | 62 | 63 | 0 | 76.6667 | 82 | 4.3333 | 106.6667 | [6 empty] | 129.6667 | 1.1667 | 139.8333
| 1 |  |  | 2 · after 1 |  |  |  | 3 · after 2 |  |  | 4 · after 3 |  |  | 5 · after 4 |  |  | 6 · after 5 |  |  | 8 · after 6, 7 | [8 empty] | 14 · after 12
[11 empty] | 23.6667 | 21.6667 | 44.3333 | [6 empty] | 77.6667 | 19.6667 | 96.3333 | 97.3333 | 10.3333 | 106.6667 | 107.6667 | 20.8333 | 127.5 | 128.5 | 12.3333 | 139.8333 | 140.8333 | 3.3333 | 143.1667
[11 empty] | Facade - procurement | [8 empty] | Mechanical services - rough-in |  |  | Services - coordination and testing |  |  | Internal linings and finishes |  |  | Joinery and fixed furniture |  |  | Practical completion inspection
[11 empty] | 60.3333 | 36.6667 | 81 | [6 empty] | 77.6667 | 0 | 96.3333 | 97.3333 | 0 | 106.6667 | 107.6667 | 0 | 127.5 | 128.5 | 0 | 139.8333 | 140.8333 | 0 | 143.1667
[11 empty] | 7 · after 3 | [8 empty] | 9 · after 6 |  |  | 11 · after 9, 10 |  |  | 12 · after 8, 11 |  |  | 13 · after 12 |  |  | 15 · after 13, 14
[20 empty] | 77.6667 | 16.6667 | 93.3333
Electrical services - rough-in
[20 empty] | 80.6667 | 3 | 96.3333
10 · after 6
Activities with no room on this diagram |  |  |  | 0 |  |  | The diagram holds 12 levels of 5 lanes. Anything past that is counted here rather than quietly dropped - it is still in the Network and still in every total.
Links that could not be drawn |  |  |  | 0 |  |  | A link skipping levels holds its lane across them. If a box lands in that lane the box wins and the line breaks - counted here, and still named in that box's own after line.
A column is a network level, not a phase: everything in one column has the same number of activities in front of it, so nothing in a column waits for anything else in it. This is an activity-on-node view - boxes for activities, lines for the links between them - which is the form modern scheduling uses and the form most people now mean by a PERT chart. Add an activity on the Network sheet and it appears here, in a lane, wired to what it comes after. The sheet is deliberately long: it prints across two A3 landscape pages side by side, and reads as one continuous run on screen.
Visit mastt.com

## Reference
PERT CHART · REFERENCE
The colour key and every dropdown source. Edit a list here and every list in the workbook follows it.
THE COLOUR KEY - THE SAME SIX MEANINGS ON EVERY SHEET
Colour | It means |  |  |  | When you will see it
CRITICAL | Critical |  |  |  | Least float in the network. Any delay here moves the finish.
NEARLY CRITICAL | Nearly critical |  |  |  | Within your near-critical threshold of the least float. Where schedules usually fail.
WATCH | Watch |  |  |  | Something needs a decision - an estimate missing, or a wide spread.
HAS FLOAT | Has float |  |  |  | Comfortable float. It can slip without moving the finish.
COMPLETE | Complete |  |  |  | Recorded as done.
NOT APPLICABLE | Not applicable |  |  |  | Not started, out of scope, or nothing to calculate yet.
HOW TO READ A CELL
Pale blue | You type in it.
Off-white | Calculated. Typing in it breaks the network.
Red row | Critical. No float.
Orange row | Near-critical. Inside the threshold on Setup.
A dash | Nothing to calculate yet - usually a missing estimate or a missing link.
DROPDOWN SOURCES - EDIT THESE AND EVERY LIST IN THE WORKBOOK FOLLOWS
|  | Estimating method | Status | Yes or no | Phase | Calendar
|  | PERT weighted | Not started | Yes | Enabling | 5-day working week
|  | Triangular | In progress | No | Substructure | 7-day calendar week
|  |  | Complete |  | Structure
|  |  | On hold |  | Envelope
Services
Fit-out
Commissioning
Handover
Not set
Visit mastt.com