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	Construction Traffic Management Plan

	One plan, two approvals - what goes to the authority, and what stays on site

	


	EXAMPLE CONTENT - this plan is filled in for a worked project so you can see what each field wants. Replace every entry with your own, and delete this banner, before you issue it.



	1.  PROJECT AND PLAN

	Project
	EXAMPLE - Halden Street Apartments
	Plan revision
	Rev C

	Site address
	22-30 Halden Street, Wrenford NSW
	Date of this revision
	12 August 2026

	Client
	Halden Street Developments Pty Ltd
	Principal contractor
	Marlow Constructions Pty Ltd

	Consent or approval this plan discharges
	DA2025/0418, condition 27
	Authority that approves it
	Wrenford City Council

	Prepared by
	J. Okonkwo, Traffic Engineer, Verrall Traffic
	Approved by
	Wrenford City Council, as roads authority

	Accreditation held by the preparer
	Prepare a work zone traffic management plan - card 88214, expires 4 May 2028



	2.  WHERE EACH PART OF THIS PLAN GOES

	Part of this plan
	Who it goes to
	When

	Two different documents share the name traffic management plan. One is approved by the authority and is about the public road; the other is held on site and is about people and plant inside the fence. They go to different approvers, and overlap most at the site gate.

	Sections 1 to 9 and 11
	The authority that approves this plan, and the roads authority for any road it does not control
	Before any work starts on or beside the public road, and again whenever a stage changes

	Section 10
	Held on site. Part of the work health and safety management plan if this is a construction project as defined by the work health and safety regulations
	Before work starts, and reviewed on the triggers in section 12

	Section 12, the review triggers
	Both. A revision goes back to whoever approved the part that changed
	On any trigger in section 12

	The traffic control plans listed in section 8
	Not in this document. Prepared and signed separately by the accredited person named in section 8, and issued with this plan
	Before the work each plan covers



	3.  WHICH RULES APPLY HERE - FILL THIS IN FIRST

	Left blank on purpose. Every one of these differs by state, and most of them changed in the two years to August 2026. Fill them in from the authority's own material, not from another project's plan.

	Authority that approves this plan - your consent, responsible or relevant authority, or assessment manager
	Wrenford City Council

	Roads authority for every road you will occupy, where that is a different body
	

	Temporary traffic management document you are working to, and its version
	

	Date you last checked that version is current
	

	Accreditation your traffic guidance scheme preparer holds, and its expiry
	Prepare a work zone traffic management plan - card 88214, expires 4 May 2028

	Is this a construction project requiring a written work health and safety management plan? On what basis?
	



	Where the work is
	The document temporary traffic management is done to
	Who may prepare a traffic guidance scheme

	Find your row and copy it into the two fields above. Named, not dated - these are reissued periodically, so record the version you are working to and the date you checked it.

	New South Wales
	The state road authority's technical standard for traffic control at work sites, which takes precedence over both the Australian Standard and the national guide where they differ
	A work zone traffic management plan card issued by the state work health and safety regulator

	Victoria
	The state code of practice for worksite safety - traffic management, made by the roads minister under state road law, which incorporates the national guide
	A traffic management company accredited by the state transport department in the design role. Mandatory on department-managed roads - confirm what the council requires on its own

	Queensland
	The national guide, with the state's own guide to temporary traffic management and the state manual of uniform traffic control devices, both of which carry only the state's departures
	The traffic management design course prescribed by the state road authority

	Western Australia
	The state road authority's code of practice for traffic management for works on roads
	Advanced worksite traffic management accreditation issued by the state road authority

	South Australia
	The national guide, with the state workzone traffic management standards and the state supplement to the Australian Standard, which carry the state's own requirements
	The traffic management designer role under the national framework, which is still in transition here - check which design categories your designer is approved for

	Tasmania
	The national guide to temporary traffic management, adopted by the state, with the state's own guide alongside it
	The traffic management designer role under the national temporary traffic management framework

	Northern Territory
	The national guide to temporary traffic management, adopted with Territory variations
	A Territory temporary traffic management card in the design role

	Australian Capital Territory
	The Australian Standard and the national guide to temporary traffic management
	The Territory's municipal infrastructure specification calls for a competent person and names no scheme. Confirm what the roads authority will accept before you commission the plan



	4.  THE WORKS, STAGE BY STAGE

	
	Stage
	Starts
	For
	Main activities
	Largest vehicle
	Movements

	One row per stage, because the largest vehicle, the movement count and the road occupation all change between them. A plan written for one stage is the most common reason a plan comes back.

	1
	Site establishment and hoarding
	Sep 2026
	3 weeks
	Fencing, hoarding, site shed, temporary power
	8.8 m rigid
	4 a day

	2
	Demolition
	Oct 2026
	5 weeks
	Structure demolition, materials removal
	12.5 m heavy rigid
	12 a day

	3
	Bulk excavation and shoring
	Nov 2026
	9 weeks
	Piling, shoring, spoil cartage
	19 m semi-trailer
	26 a day

	4
	Structure
	Feb 2027
	22 weeks
	Concrete pours, crane erection, formwork
	19 m semi-trailer, concrete agitators
	18 a day

	5
	Facade and fitout
	Jul 2027
	20 weeks
	Facade panels, services, internal fitout
	12.5 m heavy rigid
	9 a day

	6
	Landscaping and completion
	Dec 2027
	6 weeks
	Paving, landscaping, hoarding removal
	8.8 m rigid
	4 a day



	5.  CONSTRUCTION VEHICLES, ROUTES AND ACCESS

	Approved route in
	West on Wrenford Road, left into Halden Street, arrive at the site frontage. Drivers are issued the route plan with every delivery docket and are not to use any other local street.

	Approved route out
	North on Halden Street, right into Beckett Street, east to Wrenford Road.

	Site entry and exit points
	One combined entry and exit at 26 Halden Street, gate width 6.4 m, controlled by a traffic controller during all vehicle movements.

	Vehicles enter and leave in a forward direction
	Yes in every stage except stage 3, where the spoil bins have to be reversed in. That exception is applied for separately - see section 7 - and stage 3 does not start until it is granted. The movement is controlled by a traffic controller and a spotter. Recorded here because the authority asks the question directly, and a no needs an approval and a control against it.

	Swept path assessment
	Prepared for the 19 m semi-trailer at the site access and at the Halden Street / Wrenford Road intersection. Issued as drawing SP-01 and SP-02 with this plan.

	Where vehicles wait if the site is not ready
	On site behind the gate. No queuing or marshalling on any street. If the site cannot receive, the delivery is turned back from the holding point at the Wrenford Road industrial estate.

	Oversize or over-mass vehicles
	None planned. If one becomes necessary it is notified to the regulator and the roads authority at the notice period they require, and this plan is revised before it arrives.

	Worker parking
	No worker parking on Halden Street or Beckett Street. Six spaces on site for site management; all other workers use the Wrenford station car park and the shuttle at shift change.

	Deliveries outside site hours
	Not permitted. Any exception is applied for separately and this plan is revised first.



	6.  OCCUPYING THE PUBLIC ROAD

	What is occupied
	Stages
	When
	What it needs before it can happen
	Status

	Works zone, 22 m, north side of Halden Street
	Stages 2 to 5
	Oct 2026 - Nov 2027
	Works zone approval and signage from the roads authority
	Applied 14 Jul 2026

	Type B overhead hoarding, full site frontage
	Stages 1 to 6
	Sep 2026 - Jan 2028
	Hoarding permit from the roads authority
	Granted 2 Aug 2026

	Concrete pump standing, one travel lane, Halden Street
	Stage 4, pour days only
	Feb - Jul 2027, 14 days total
	Standing plant approval and a traffic control plan for each occasion
	Not yet applied

	Mobile crane standing for crane erection and dismantle
	Stage 4
	2 days at each end
	Standing plant approval, full road closure application
	Not yet applied

	Footpath closure, north side, with a signed diversion to the south side
	Stages 2 to 5
	Oct 2026 - Nov 2027
	Footpath occupation approval from the roads authority, and a pedestrian diversion plan
	Applied 14 Jul 2026

	Road opening for the stormwater connection
	Stage 3
	3 days, Dec 2026
	Road opening permit and restoration bond
	Not yet applied



	7.  APPROVALS AND PERMITS

	Approval
	Authority
	Who applies
	Applied
	Granted
	Expires
	Reference

	Approving this plan is not any of these approvals. Each is a separate application with its own lead time, and the lead time belongs on the programme.

	This plan, approved
	Approving authority
	Principal contractor
	14 Jul 2026
	Under assessment
	-
	DA2025/0418 cond. 27

	Hoarding permit
	Roads authority (council)
	Principal contractor
	20 Jun 2026
	Granted 2 Aug 2026
	31 Jan 2028
	HP26-0912

	Works zone approval and signage
	Roads authority (council)
	Principal contractor
	14 Jul 2026
	Under assessment
	-
	WZ26-0455

	Footpath occupation and pedestrian diversion
	Roads authority (council)
	Principal contractor
	14 Jul 2026
	Under assessment
	-
	FO26-0455

	Approval to reverse into the site, stage 3 only
	Roads authority (council)
	Principal contractor
	14 Jul 2026
	Under assessment
	-
	RV26-0455

	Road opening permit, stormwater connection
	Roads authority (council)
	Hydraulic subcontractor
	Not yet applied
	-
	-
	-

	Standing plant approval, concrete pump
	Roads authority (council)
	Concrete subcontractor
	Not yet applied
	-
	-
	-

	Full road closure, crane erection and dismantle
	Roads authority (council)
	Crane subcontractor
	Not yet applied
	-
	-
	-

	Bus stop relocation
	Transport operator and roads authority
	Principal contractor
	Not required - stop is outside the works zone
	-
	-
	-

	Put an approval in this table the day you identify it, not the day you apply for it. Authorities call these different things - match each row to the application your own authority publishes.



	8.  TRAFFIC GUIDANCE SCHEMES (TRAFFIC CONTROL PLANS)

	Ref
	What it covers
	Prepared by
	Accreditation held, and expiry
	Approved

	These are not in this document and must not be drawn into it. They are prepared and signed by the accredited person named here, to the roads authority's own document, and issued alongside this plan.

	TCP-01
	Site access, all stages, Halden Street
	J. Okonkwo, Verrall Traffic
	Card 88214, expires 4 May 2028
	Council, 2 Aug 2026

	TCP-02
	Footpath closure and pedestrian diversion, stages 2 to 5
	J. Okonkwo, Verrall Traffic
	Card 88214, expires 4 May 2028
	Council, 2 Aug 2026

	TCP-03
	Concrete pump standing, one lane closed, stage 4
	Not yet prepared
	-
	-

	TCP-04
	Full road closure, crane erection and dismantle, stage 4
	Not yet prepared
	-
	-

	Sign spacing, taper lengths, speed zones and how long a pedestrian may be held belong in those plans. They differ by state and they change.



	9.  PEOPLE AFFECTED, AND HOW

	Who
	What changes for them
	How it is managed
	Who checks, and when

	Residents of Halden Street
	Loss of 22 m of kerbside parking, noise and vehicle movements from 7 am
	Letterbox notification 7 days before each stage; site contact on the hoarding; parking permits unaffected outside the works zone
	Site manager, before each stage

	Pedestrians on the north side
	Footpath closed for the duration of stages 2 to 5
	Signed diversion to the south side at both ends of the block, kerb ramps checked for accessible width, lighting maintained overnight
	Site manager, daily

	People with reduced mobility or vision
	The diversion adds distance and two road crossings
	The diversion is checked for a continuous accessible path and tactile indicators at each crossing before the closure opens, and after any change
	Traffic engineer, at each change

	Cyclists on Halden Street
	The works zone removes the shoulder cyclists currently use
	Advance warning signage; cyclists share the travel lane past the site at the posted speed
	Site manager, daily

	Bus passengers, Wrenford Road route
	No change - the stop is outside the works zone
	Confirmed with the operator 4 Jul 2026. If a stage requires the stop to move, the operator and the roads authority approve the relocation before the stage starts
	Site manager, at each stage

	Emergency services
	One travel lane remains open at all times except during the two crane days
	Fire and rescue, ambulance and police notified of the crane days at least the notice period they require; a traffic controller holds an unobstructed path on request at all times
	Site manager, before each closure

	Wrenford Public School, 180 m north
	Construction vehicles on the route during school zone hours
	No construction vehicle movements between 8.00 and 9.30 am or 2.30 and 4.00 pm on school days
	Site manager, daily

	Adjoining businesses at 32-36 Halden Street
	Loading bay access affected during stage 3
	Loading bay kept open; deliveries to the neighbour scheduled outside spoil cartage windows by agreement recorded in the site diary
	Site manager, weekly



	10.  ON SITE - PEOPLE AND PLANT

	This section stays on site. It is the part work health and safety law asks for, and it is not what the approving authority approves.

	Keeping people and plant apart
	A fenced pedestrian walkway from the site gate to the site office, physically separated from the plant route, with a single controlled crossing point.

	Where the two have to cross
	One crossing point, at the site gate. Traffic controller present for every vehicle movement. Plant gives way to people on foot at the crossing.

	Exclusion zones
	Marked around the excavator, the piling rig and under the crane arc. Nobody on foot enters without the operator acknowledging them first.

	Reversing
	Avoided by the site layout wherever possible. Where it cannot be, a spotter in direct sight of the operator, in high visibility clothing, with an agreed stop signal.

	Delivery and unloading areas
	Inside the hoarding line at the north end of the site. No unloading from the travel lane at any time.

	Site speed
	10 km/h everywhere inside the gate, and 5 km/h within 3 m of the pedestrian walkway. Signed at the gate and enforced by the site manager.

	Visibility
	High visibility clothing on everyone past the gate line. Lighting to the walkway and the crossing point for any work before sunrise or after sunset.

	Who was consulted, and when
	Site walk with the health and safety representative and the subcontractor supervisors on 4 Aug 2026. Changes made: the walkway was moved to the east boundary and the crossing was relocated away from the excavator swing.



	11.  COMMUNICATION AND COMPLAINTS

	Who residents and businesses hear from, and when
	Letterbox notification at least 7 days before each stage starts, and before any change to access, parking or the pedestrian route. A copy of every notification goes to the consent authority.

	Site contact for complaints
	Site manager, name and mobile number displayed on the hoarding at both ends of the frontage and printed in every notification. Answered during site hours and diverted outside them.

	How a complaint is recorded and closed out
	Logged with date, time, who raised it, what about, what was done and when it was closed. Anything about traffic or pedestrian safety also triggers a review under section 12.

	Who tells the authority, and when
	The site manager notifies the approving authority of any incident on the public road, and of any change that affects an approval, within the period that approval sets.

	What is displayed on the hoarding
	Project name, principal contractor, site contact and hours, and the consent reference.



	12.  MONITORING AND REVIEW

	What triggers a review
	By when
	Who does it

	A stage starts or its dates move
	Before the stage starts
	Traffic engineer and site manager

	The largest vehicle, the route, or the number of movements changes
	Before the change takes effect
	Traffic engineer

	An approval is granted, refused, or granted with conditions that differ from this plan
	Within the time the authority sets, and before the work it covers
	Site manager

	A near miss, a collision, or a complaint about traffic or pedestrian safety
	Immediately, and the plan is revised before work resumes if the cause sits in it
	Site manager and health and safety representative

	The roads authority or the approving authority changes what it requires
	At the next revision, and immediately if the change affects work under way
	Traffic engineer

	No trigger has occurred
	Every 6 months in any case
	Site manager

	Reissue the whole plan, not a page, and send it back to whoever approved the part that changed.



	13.  SIGN-OFF



	Prepared by
	
	
	Date
	



	Accepted for the principal contractor
	
	
	Date
	



	Approved by the approving authority
	
	
	Date
	



	HOW TO USE IT



1.   Fill in section 3 first. Which roads authority, which approving authority, which temporary traffic management document, and what accreditation the person preparing your traffic control plans holds. Nothing else in this plan means anything until those four are right, and all four differ by state.
2.   Read the consent condition itself before you fill in anything else. What a construction traffic management plan has to contain is set by the individual authority, and neighbouring councils ask for different things.
3.   Work through sections 4 to 9 stage by stage. Most refusals are a stage the plan did not cover, not a control the authority disagreed with.
4.   Put every approval into section 7 the day you identify it, not the day you apply. The lead time is the risk, and it belongs on the programme.
5.   Section 10 stays on site. Do not send it to the council and do not leave it out - it is the half of this that work health and safety law asks for.
6.   Reissue the whole plan, not a page. Section 12 says when.

	WHAT GETS THESE PLANS SENT BACK



One plan for the whole job
A plan written for the structure stage says nothing useful about demolition or the spoil cartage before it. Every stage has its own largest vehicle, its own movement count and often its own road occupation. Section 4 is per stage for that reason.
Treating the plan as the approval
Approving this document does not let you occupy the road, stand a pump in a lane, put up a hoarding or open the pavement. Every one of those is a separate application, often to a different part of the same authority, with its own lead time. That is what section 7 is for.
Drawing the traffic control plan yourself
In most of Australia the person who prepares one has to hold a named accreditation, and the work area has to be signed to the roads authority's own document. This plan records who prepared yours and what they hold. It does not contain a canvas for you to draw on, and no template should.
Confusing the two documents
The plan the authority approves is about the public road. The plan work health and safety law asks for is about people and plant inside the fence. They go to different approvers on different timelines and overlap most heavily at the site gate, which is why the gate turns up in both halves. Section 2 says which part of this file goes where.
Copying numbers out of another project's plan
Sign spacing, taper lengths, speed zones and how long a pedestrian may be held are all set by the roads authority and differ between states. They belong in the traffic control plan, drawn by the person accredited to draw it.

	IMPORTANT
This is a planning and record-keeping template, not traffic engineering advice and not an approval. It does not contain traffic control plans and is not a substitute for one. In most Australian jurisdictions the person who prepares a traffic control plan must hold a specific accreditation, the document it is prepared to differs by state, and both are revised periodically - so confirm what applies to your roads authority and approving authority before you rely on anything here. Where this file states a period, a threshold or a notice, it is a field for you to fill in from your own approval, not a figure this template sets.
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