## Cover
Earned Value Analysis (EVM)
Global template · jurisdiction-neutral · aligned to PMI Practice Standard for EVM / ISO 21508
PROJECT DETAILS
| PROJECT NAME | e.g. Northbank Health Precinct — Stage 2 |  | ROLE | Project Controls Manager
| PROJECT NUMBER |  |  | DATA DATE | 2026-07-31
| CLIENT |  |  | REVISION | A
| CONTRACTOR |  |  | CURRENCY | AUD
| PACKAGE / TRADE |  |  | EV TECHNIQUE | % Complete
PREPARED BY
HOW TO USE THIS TEMPLATE
1. Set the DATA DATE and CURRENCY on this page. Every calculation in the workbook keys off the data date — nothing is hard-coded, and no currency symbol is used anywhere, only the code you enter here.
2. Open the Lists sheet and set the workbook settings: the EAC method that feeds the register and dashboard, the bottom-up ETC (if you use method 4), and the SPI / CPI thresholds that drive the Red-Amber-Green status.
3. Load your WBS into the EV Register — one row per control account or WBS element, with its Budget at Completion (BAC), the responsible control account manager, the contract or package reference, and the earned value technique you will use to measure it.
4. Enter the time-phased baseline on the Time-Phased Data sheet: one row per period, planned value in the period it is planned to be earned. Cumulative PV, the S-curve and every trend index build from this. Do not change it again without a formal rebaseline.
5. Each period, update three things only: Actual % Complete and Actual Cost on the EV Register, and the period Earned Value and Actual Cost on the Time-Phased Data sheet. Everything else calculates.
6. Read the Dashboard. SPI and CPI tell you where you are; the four EAC methods on Forecast & Scenarios tell you where you will end up. Explain every element that is amber or red in the Variance Explanation and Corrective Action columns of the register — the numbers are the prompt, not the answer.
7. Reconcile before you issue. The Time-Phased Data sheet carries a tie-out block that compares its cumulative PV, EV and AC at the data date to the EV Register totals. They must agree before the report goes out.
8. Delete the EXAMPLE rows (shown in grey italic and flagged in the Notes column) before you use this workbook on a live project. Read Notes & Assumptions first — it defines every term, states the formulas, and lists the traps that make earned value data misleading.
REVISION HISTORY
| Rev | Date | Description of Change |  | Prepared By | Approved By
| A |  | Initial issue for project use
Earned value is only as good as the baseline behind it. This workbook assumes a scoped WBS, an approved time-phased baseline and disciplined actual-cost capture — see Notes & Assumptions.
Visit mastt.com

## Dashboard
Earned Value Analysis (EVM)
Dashboard · every figure is calculated — the EV Register and the Time-Phased Data sheet are the inputs
All figures at the Data Date set on the Cover. Read-only — nothing on this sheet is typed.
PERFORMANCE AT A GLANCE · cumulative to the data date
VARIANCE SUMMARY · this period against cumulative to date
| Measure |  | This Period |  | Cumulative to Date | How it is derived
| Planned Value (PV / BCWS) |  |  |  |  | Period PV from the Time-Phased Data sheet; cumulative PV from the EV Register (BAC x Planned % Complete).
| Earned Value (EV / BCWP) |  |  |  |  | Budgeted cost of the work actually completed. Cumulative EV = sum of BAC x Actual % Complete across the register.
| Actual Cost (AC / ACWP) |  |  |  |  | Cost incurred for that work, on the same cut-off basis as the EV. Cumulative AC is the register total.
| Schedule Variance (SV = EV − PV) |  |  |  |  | Negative = behind the baseline in cost terms. SV is not time — read it with the programme, not instead of it.
| Cost Variance (CV = EV − AC) |  |  |  |  | Negative = the completed work cost more than it was budgeted to cost. The hardest variance to recover.
| Schedule Performance Index (SPI = EV / PV) |  |  |  |  | Rate of progress against plan. 1.00 = on plan. Loses meaning near completion because PV converges on BAC.
| Cost Performance Index (CPI = EV / AC) |  |  |  |  | Value returned per unit of cost. Research consistently shows cumulative CPI stabilises after ~20% complete.
FORECAST COMPARISON · the four standard EAC methods side by side
| Method |  | Formula |  |  |  |  | Implied overrun % |  | Use when
| 1 — Remaining work at budget |  | AC + (BAC − EV) | [6 empty] | The overruns to date are one-off and will not repeat.
| 2 — Current cost performance continues |  | BAC / CPI | [6 empty] | Performance to date is representative. The default for most live projects.
| 3 — Cost and schedule performance continue |  | AC + (BAC − EV) / (CPI x SPI) | [6 empty] | Schedule pressure is driving cost. The most conservative of the three.
| 4 — Bottom-up estimate to complete |  | AC + bottom-up ETC | [6 empty] | The baseline no longer reflects the work. Blank until a bottom-up ETC is entered on Lists.
Change the method on Lists
INTERPRETATION · what the indices are telling you
| Question |  |  | Answer |  |  | Basis
Are we spending more than the work is worth?
Are we earning work as fast as we planned to?
Where will this project finish?
Can we still deliver the remaining work to budget?
Does the workbook reconcile?
TOP 5 WORST-PERFORMING WBS ELEMENTS · ranked by cost variance (most negative first)
| Rank | WBS Code | Control Account / Element |  |  |  | CPI |  | SPI | Status | CAM
Ties are broken by the first matching register row. Rows with no actual cost recorded carry no cost variance and are excluded. "Status" is the worse of the element's SPI and CPI against the thresholds on Lists.
Visit mastt.com

## EV Register
Earned Value Analysis (EVM)
EV Register · one row per WBS element / control account · the source of truth for BAC, EV and AC at the data date
Shaded cells = your input. Tinted cells = auto-calculated, do not type over them.
WBS Code | Level | Parent WBS | Control Account / Element | Responsible (CAM) | Contract / Package Ref |  | % of Total BAC | EV Technique | Planned Start | Planned Finish | Planned % Complete | Actual % Complete |  | SV % | CV % | SPI | CPI |  | TCPI | Status | Variance Explanation | Corrective Action | Notes
CB-01.01 | 2 | CB-01 | Preliminaries, Site Establishment & Management | R. Okafor | MC-001 | 3850000 |  | Level of Effort | 2025-07-01 | 2028-06-30 |  | 36% | 1510000 | [7 empty] | Site management team held at full strength through the wet-season delay; LOE burns to plan so the variance is pure cost. | Re-forecast prelims to the revised programme; test whether two supervisory roles can demobilise from month 18. | EXAMPLE — delete before use
CB-01.02 | 2 | CB-01 | Demolition & Site Clearance | R. Okafor | SC-101 | 620000 |  | 0/100 | 2025-07-01 | 2025-09-30 |  | 100% | 598000 | [9 empty] | EXAMPLE — delete before use
CB-01.03 | 2 | CB-01 | Bulk Excavation & Earthworks | L. Fernandes | SC-102 | 1480000 |  | Units Complete | 2025-09-01 | 2025-12-31 |  | 100% | 1655000 | [7 empty] | Rock encountered below RL 12.4 over roughly 30% of the footprint — hammer and cart rates well above the tendered assumption. | Variation VO-004 submitted for latent condition; recover 60% of the overrun if approved. Treat as a BAC change only once approved. | EXAMPLE — delete before use
CB-01.04 | 2 | CB-01 | Piling & Ground Improvement | L. Fernandes | SC-103 | 2950000 |  | Units Complete | 2025-11-01 | 2026-03-31 |  | 100% | 3120000 | [7 empty] | Rig standing time during the rock delay plus 14 additional CFA piles from the revised geotechnical model. | Close out standing-time claim; lock the pile schedule before the next release. | EXAMPLE — delete before use
CB-01.05 | 2 | CB-01 | Substructure, Basement & Ground Slab | L. Fernandes | SC-104 | 4320000 |  | % Complete | 2026-02-01 | 2026-08-31 |  | 78% | 3480000 | [7 empty] | Basement slab pour sequence slipped two weeks behind the baseline; cost performance broadly holding. | Add a second pour crew for the remaining three pours to recover float before frame handover. | EXAMPLE — delete before use
CB-01.06 | 2 | CB-01 | Superstructure — Concrete Frame & Cores | M. Haddad | SC-201 | 9600000 |  | % Complete | 2026-06-01 | 2027-06-30 |  | 11% | 1090000 | [7 empty] | Frame start delayed by the substructure slip; only two levels of columns poured against four in the baseline. | Confirm crane and formwork availability for a compressed cycle; re-test the frame completion date at the next update. | EXAMPLE — delete before use
CB-01.07 | 2 | CB-01 | Façade & Cladding | M. Haddad | SC-301 | 6750000 |  | Milestone Weighted | 2027-01-01 | 2027-12-31 |  | 0% | [10 empty] | EXAMPLE — delete before use
CB-01.08 | 2 | CB-01 | Roofing & Waterproofing | M. Haddad | SC-302 | 1240000 |  | 50/50 | 2027-05-01 | 2027-10-31 |  | 0% | [10 empty] | EXAMPLE — delete before use
CB-01.09 | 2 | CB-01 | Internal Fitout & Finishes | S. Nguyen | SC-401 | 5900000 |  | % Complete | 2027-08-01 | 2028-04-30 |  | 0% | [10 empty] | EXAMPLE — delete before use
CB-01.10 | 2 | CB-01 | Building Services — Mech, Elec, Hydraulic, Fire | S. Nguyen | SC-501 | 8450000 |  | % Complete | 2026-10-01 | 2028-05-31 |  | 2% | 205000 | [7 empty] | Early procurement and off-site fabrication costs incurred ahead of any installed measurable work — classic front-loaded AC with no EV credit yet. | Do not claim EV for materials until installed or a milestone is met; verify the cut-off treatment with the cost team. | EXAMPLE — delete before use
CB-01.11 | 2 | CB-01 | External Works, Carpark & Landscaping | R. Okafor | SC-601 | 1680000 |  | % Complete | 2027-11-01 | 2028-05-31 |  | 0% | [10 empty] | EXAMPLE — delete before use
CB-01.12 | 2 | CB-01 | Testing, Commissioning & Handover | S. Nguyen | MC-001 | 1160000 |  | Milestone Weighted | 2028-03-01 | 2028-06-30 |  | 0% | [10 empty] | EXAMPLE — delete before use
PROJECT TOTAL | [20 empty] | Project-level EAC uses project totals — see the note below.
Column L (Planned % Complete) is pre-filled with a straight-line calculation between the planned dates at the data date. If your programme gives you a proper time-phased planned percentage, type it straight over the formula — that is the better number.
Element-level EAC applies the selected method to each row. For methods 2 and 3 the sum of the element EACs will not equal the project EAC, because CPI and SPI are weighted averages — the total row and the Dashboard compute the project EAC from project totals, and that is the figure to report. Method 4 distributes the bottom-up ETC across remaining work pro-rata, so it does tie. A row with no Actual Cost recorded has no basis for a forecast and returns a blank EAC — enter 0 if the element has genuinely cost nothing yet.
Visit mastt.com

## Time-Phased Data
Earned Value Analysis (EVM)
Time-Phased Data · the performance measurement baseline and the period-by-period actuals · 36 periods
Shaded cells = your input. Tinted cells = auto-calculated, do not type over them.
Period No. | Period End Date | Working Days | [5 empty] | SPI cum. | CPI cum. | Cum. % Planned | Cum. % Earned | Cum. % Spent | Notes
1 | 2025-07-31 | 23 | 309875 | 309465 | 310234 | [7 empty] | EXAMPLE baseline — replace rows 9-44 with your own time-phased PMB.
2 | 2025-08-31 | 21 | 320204 | 318416 | 321243
3 | 2025-09-30 | 22 | 664586 | 658817 | 667251
4 | 2025-10-31 | 23 | 488169 | 479723 | 491107
5 | 2025-11-30 | 20 | 1042755 | 1023617 | 1048738
6 | 2025-12-31 | 23 | 1097836 | 1069668 | 1105053
7 | 2026-01-31 | 22 | 718662 | 688832 | 724432
8 | 2026-02-28 | 20 | 1201910 | 1153480 | 1210636
9 | 2026-03-31 | 22 | 1353354 | 1289127 | 1363136
10 | 2026-04-30 | 22 | 719698 | 663027 | 725303
11 | 2026-05-31 | 21 | 743687 | 677944 | 748846
12 | 2026-06-30 | 22 | 1426296 | 1322595 | 1434997
13 | 2026-07-31 | 23 | 1499018 | 1375889 | 1507024 | [7 empty] | Data date period. Actuals stop here; later periods are baseline only.
14 | 2026-08-31 | 21 | 1499017 | [9 empty] | Forecast periods — leave EV and AC blank until each period closes.
15 | 2026-09-30 | 22 | 836444
16 | 2026-10-31 | 22 | 1281266
17 | 2026-11-30 | 21 | 1253385
18 | 2026-12-31 | 23 | 1295164
19 | 2027-01-31 | 21 | 1851483
20 | 2027-02-28 | 20 | 1689056
21 | 2027-03-31 | 23 | 1870027
22 | 2027-04-30 | 22 | 1809704
23 | 2027-05-31 | 21 | 2073305
24 | 2027-06-30 | 22 | 2012982
25 | 2027-07-31 | 22 | 1324752
26 | 2027-08-31 | 22 | 1973103
27 | 2027-09-30 | 22 | 1930369
28 | 2027-10-31 | 21 | 1994715
29 | 2027-11-30 | 22 | 1956902
30 | 2027-12-31 | 23 | 2030321
31 | 2028-01-31 | 21 | 1455458
32 | 2028-02-29 | 21 | 1361557
33 | 2028-03-31 | 23 | 1743061
34 | 2028-04-30 | 20 | 1696112
35 | 2028-05-31 | 23 | 1082684
36 | 2028-06-30 | 22 | 393083
TOTAL
POSITION AT THE DATA DATE · tie-out to the EV Register
| Measure |  | This sheet — cumulative at data date | EV Register total | Difference | Check
Planned Value (PV)
Earned Value (EV)
Actual Cost (AC)
THIS PERIOD · the period ending on or before the data date
| Measure |  | Value | Notes
| Period number at the data date |  |  | The last period whose end date falls on or before the data date set on the Cover.
| Planned Value this period |  |  | Baseline PV for the period — the plan, not the forecast.
| Earned Value this period |  |  | Budgeted cost of the work completed in the period.
| Actual Cost this period |  |  | Cost incurred in the period, on the same cut-off as the EV.
SOURCE OF TRUTH — this sheet owns the shape of the baseline over time (the S-curve, the trend indices and the period splits). The EV Register owns the position at the data date (BAC, EV and AC by control account). The two must reconcile in the block above every period before the report is issued; a persistent difference means either the register or the phasing is out of date.
Visit mastt.com

## S-Curve
Earned Value Analysis (EVM)
S-Curve · cumulative PV, EV and AC, and the SPI / CPI trend · plotted from Time-Phased Data
Charts refresh automatically. The EV and AC lines stop at the last period you have entered.
HOW TO READ THE S-CURVE
The grey dashed line is the baseline (PV). It is the only line you should not be able to move without a formal rebaseline.
EV below PV means you have earned less work than you planned to by now. The horizontal gap between the two curves is roughly the schedule slip in time.
AC above EV means the work you have completed cost more than it was budgeted to cost. The vertical gap is the cost variance.
AC above PV on its own means nothing. Spending faster than plan is only a problem if you are not earning at the same rate — which is why EV sits between them.
The EV and AC lines stop at the last period you have entered. Everything beyond that is baseline only.
HOW TO READ THE INDEX TREND
A flat line at 1.00 is on plan. What matters is the direction of travel, not a single month.
Cumulative CPI is remarkably stable — once a project is about 20% complete it rarely improves by more than a few points. Treat a recovery plan that assumes otherwise with scepticism.
SPI drifts back towards 1.00 as the project finishes, because PV converges on BAC whether or not the work is late. Near completion, read the programme, not the SPI.
A widening gap between the two indices tells you which lever is moving: cost, schedule, or both.
Visit mastt.com

## Forecast & Scenarios
Earned Value Analysis (EVM)
Forecast & Scenarios · the four standard EAC methods, TCPI and a CPI sensitivity
Choose the method that feeds the register and the dashboard on the Lists sheet.
INPUTS AT THE DATA DATE · all taken from the EV Register total row
| Input | Value | What it is
| BAC — Budget at Completion |  | Sum of the BAC column on the EV Register. Excludes management reserve.
| PV — Planned Value to date |  | Budgeted cost of the work scheduled to be done by the data date.
| EV — Earned Value to date |  | Budgeted cost of the work actually done by the data date.
| AC — Actual Cost to date |  | Cost incurred for that work, on a consistent cut-off.
| CPI — cumulative |  | EV / AC. The single best predictor of the final cost outturn.
| SPI — cumulative |  | EV / PV. Use with care in the last third of the project.
| Work remaining (BAC − EV) |  | The budget value of the scope still to be earned.
| Budget remaining (BAC − AC) |  | The money still available inside the BAC. If this is smaller than the work remaining you are already forecasting an overrun.
THE FOUR STANDARD EAC METHODS
| Method | Formula |  |  |  | vs BAC | When this is the right method
| 1 — Remaining work at the budgeted rate | EAC = AC + (BAC − EV) |  |  |  |  | Use when the cost overruns to date are demonstrably one-off — a latent condition, a single failed pour, a one-time rate correction — and the remaining work will be done at the budgeted rate. The most optimistic of the four; be able to name the reason.
| 2 — Current cost performance continues | EAC = BAC / CPI |  |  |  |  | The default for a project past about 20% complete. It assumes what has driven the overrun so far — productivity, rates, rework — carries on. Simple, defensible, and historically the most accurate of the index-based methods.
| 3 — Cost and schedule performance continue | EAC = AC + (BAC − EV) / (CPI × SPI) |  |  |  |  | Use when schedule pressure is itself driving cost — acceleration, overtime, extended preliminaries, out-of-sequence work. The most conservative index method. Some organisations weight the two indices (e.g. 0.8 CPI / 0.2 SPI); state the weighting if you do.
| 4 — Bottom-up estimate to complete | EAC = AC + bottom-up ETC |  |  |  |  | Use when the baseline no longer represents the work — major scope change, a re-tendered package, a new delivery strategy. The only method that does not extrapolate history, and the only one that needs the team to re-estimate. Enter the ETC on the Lists sheet.
feeds the EV Register and the Dashboard
TO-COMPLETE PERFORMANCE INDEX (TCPI) · the efficiency the remaining work must achieve
| Measure | Formula | Value | Reading
| TCPI to BAC — recover to the original budget | (BAC − EV) / (BAC − AC)
| TCPI to EAC — deliver the current forecast | (BAC − EV) / (EAC − AC)
SENSITIVITY · what the forecast does if cost performance shifts
| Scenario | CPI assumed |  |  | vs BAC |  | Comment
| CPI falls a further 0.10 | [5 empty] | A material deterioration — typically rework, a failed subcontractor or sustained lost productivity.
| CPI falls a further 0.05 | [5 empty] | A realistic downside if the current trend continues without intervention.
| CPI holds at today's level | [5 empty] | The central case. This is EAC method 2.
| CPI improves by 0.05 | [5 empty] | Requires a specific, funded, evidenced intervention — not optimism.
| CPI improves by 0.10 | [5 empty] | Rarely achieved after 20% complete. Do not report this as the forecast.
FUNDING VIEW
| Line |  | Basis
| Budget at Completion (BAC) |  | The performance measurement baseline. Everything in the EV Register.
| Contingency allowance |  | BAC x the contingency % on Lists. Held inside the BAC for identified, quantified risk.
| Estimate at Completion (selected method) |  | The forecast final cost of the work in the baseline.
| Forecast draw on contingency |  | How much of the contingency the current forecast consumes. Zero is the target.
| Management reserve (outside BAC) |  | Owner-held reserve for unknown-unknowns. It is NOT part of the BAC and is never used to improve a variance. Moving reserve into the BAC is a formal baseline change.
| Total funding requirement |  | EAC plus management reserve — the number the funder cares about.
None of these forecasts is a substitute for a schedule. EVM tells you the rate at which value is being earned and consumed; it does not tell you the completion date. Read the EAC alongside a current, logic-linked programme and an independent estimate of the time to complete.
Visit mastt.com

## Lists
Earned Value Analysis (EVM)
Lists · settings that drive every calculation, and every dropdown source
SETTINGS · referenced by the register, the dashboard and the forecast sheet
| Setting | Value | What it does
| Data date |  | Set on the Cover sheet — this cell mirrors it. Every planned %, every cumulative-to-date figure and the whole tie-out block keys off this one date. Change it once per period, not per sheet.
| EAC method | 2 — BAC / CPI | Which of the four forecast methods feeds the EAC column on the EV Register, the Dashboard tile and the funding view. Choose from the dropdown; the workbook recalculates everywhere.
| EAC method index |  | Reads the leading digit of the method above so the formulas can branch. Do not edit.
| Bottom-up ETC | 0 | Only used by EAC method 4. Enter the re-estimated cost to complete the remaining work, built up from the team's own estimate rather than extrapolated from an index.
| Bottom-up distribution factor |  | Spreads the bottom-up ETC across the register pro-rata to each element's remaining work, so the element EACs still add up to the project EAC. Do not edit.
| SPI / CPI red threshold | 0.9 | An index below this is reported Red. 0.90 is the common construction trigger — 10% off plan.
| SPI / CPI amber threshold | 0.98 | Between the red and amber thresholds the element is coloured amber and must be explained in the monthly report.
| SPI / CPI green threshold | 1 | At or above this an element is Green. Leave it at 1.00 unless your organisation runs a tolerance band.
| Contingency % | 5% | Contingency held inside the BAC, as a percentage of BAC. Used on the Forecast sheet to test whether the forecast overrun is covered.
| Management reserve (outside BAC) | 0 | Owner-held reserve for unknown-unknowns. It sits OUTSIDE the BAC and outside every index. Never use it to close a cost variance — releasing it is a formal baseline change.
| Currency |  | Set on the Cover sheet. The workbook uses the code you enter in every header — no currency symbol is hard-coded anywhere.
| Baseline periods loaded |  | How many periods of the time-phased baseline carry an end date. The S-curve plots this many points.
DROPDOWN SOURCE LISTS
To add an option, insert a row INSIDE a list (not below the last entry) so the validation range grows with it. Keep the EAC Method entries starting with their number — the workbook reads that digit.
| EV Technique | EAC Method | WBS Level | Status (calculated) | Yes / No
| % Complete | 1 — AC + (BAC − EV) | 1 | Green | Yes
| 0/100 | 2 — BAC / CPI | 2 | Amber | No
| 50/50 | 3 — AC + (BAC − EV) / (CPI × SPI) | 3 | Red
| 20/80 | 4 — AC + Bottom-Up ETC | 4 | Not started
| Milestone Weighted |  | 5 | Complete
Units Complete
Level of Effort
Apportioned Effort
EARNED VALUE TECHNIQUES · what each one means
| % Complete | A judged or measured percentage, claimed each period. Flexible, and the easiest to abuse — insist on a quantity basis or a signed measure.
| 0/100 | No credit until the element is finished, then 100%. Best for short, discrete tasks inside one period.
| 50/50 | 50% when the element starts, the balance when it finishes. Good for two-period tasks.
| 20/80 | 20% on start, 80% on completion. Use where starting is cheap relative to finishing — a conservative alternative to 50/50.
| Milestone Weighted | Value assigned to defined, verifiable milestones (design issued, off-site QA passed, installed, tested). The most defensible technique for façade, plant and commissioning.
| Units Complete | EV = units installed / total units x BAC. The most objective technique. Use it wherever the work is countable — piles, cubic metres, panels, luminaires.
| Level of Effort | Earns exactly to plan by definition (EV = PV), so it can never show a schedule variance. Restrict it to genuine support work — site management, cleaning, security — and keep it under ~15% of BAC.
| Apportioned Effort | Earns as a fixed ratio of a related discrete element (e.g. QA inspection earning with the work it inspects). Never let it earn against a Level of Effort account.
Visit mastt.com

## Notes & Assumptions
Earned Value Analysis (EVM)
Notes & Assumptions · read before issuing this template
WHAT THIS WORKBOOK DOES
Earned Value Management measures three things in the same unit — money — and compares them: what you planned to have done by now (PV), what you have actually done (EV), and what it cost you to do it (AC). Everything else in EVM is arithmetic on those three numbers.
This workbook implements the standard method described in the PMI Practice Standard for Earned Value Management and ISO 21508. Terminology is the international convention: PV (formerly BCWS), EV (formerly BCWP), AC (formerly ACWP).
It is jurisdiction-neutral. No statute, tax or contract clause is referenced, and no currency symbol is hard-coded — the workbook uses the currency code you enter on the Cover sheet.
WHICH SHEET OWNS WHAT — THE SOURCE OF TRUTH
EV Register — owns the position at the data date. BAC by control account, Actual % Complete, and Actual Cost are entered here, and the register total row is what the Dashboard reports. If a number on the Dashboard looks wrong, the register is where you fix it.
Time-Phased Data — owns the shape of the baseline over time. The 36-period grid is the performance measurement baseline (PMB); the S-curve and every trend index are plotted from it. It also owns the period splits used for the 'this period' column on the Dashboard.
The two must reconcile. The tie-out block on Time-Phased Data compares its cumulative PV, EV and AC at the data date with the register totals and flags any difference above 0.5% of BAC. A persistent difference means one of the two is not being maintained — usually the phasing.
Lists — owns every tunable setting: the EAC method, the bottom-up ETC, the RAG thresholds, the contingency percentage and the management reserve. Nothing is hard-coded in a formula that belongs on Lists.
THE THREE PREREQUISITES FOR MEANINGFUL EARNED VALUE
1. A scoped WBS. Every element in the register must have a defined, deliverable scope and a single accountable control account manager. If two people can each claim the same work, or if scope sits between elements, the EV is unreliable no matter how good the arithmetic is. 100% of the scope must be in the WBS, and nothing may appear twice.
2. A time-phased baseline. A budget without dates is not a baseline. Each element's BAC must be spread across the periods in which the work is planned to be earned — that spread is the PV curve, and without it there is no schedule variance to measure. Load it on the Time-Phased Data sheet and freeze it.
3. Disciplined actual cost capture. AC must cover the same scope, and the same cut-off, as the EV claimed against it. If the EV includes work done in the last week of the month but the AC excludes invoices not yet received, CPI will look better than reality every month and then correct violently. Accrue committed but uninvoiced cost, and be consistent.
DEFINITIONS — THE MEASURES
BAC — Budget at Completion. The total authorised budget for the scope in the baseline, excluding management reserve. The sum of the BAC column on the EV Register.
PV — Planned Value (BCWS). The budgeted cost of the work scheduled to be completed by the data date.
EV — Earned Value (BCWP). The budgeted cost of the work actually completed by the data date. EV is measured in budget currency, not in cost incurred — this is the single most misunderstood point in EVM.
AC — Actual Cost (ACWP). The cost actually incurred for the work included in the EV, on a consistent cut-off basis.
SV — Schedule Variance = EV − PV. Negative means less work has been earned than planned. Expressed in money, not time.
CV — Cost Variance = EV − AC. Negative means the completed work cost more than budgeted. This is the variance that rarely recovers.
SV % = SV / PV. CV % = CV / EV. Percentages make elements of different size comparable.
DEFINITIONS — THE INDICES AND FORECASTS
SPI — Schedule Performance Index = EV / PV. 1.00 is on plan. SPI is a rate, not a date: it says nothing about whether the work that is late is on the critical path.
CPI — Cost Performance Index = EV / AC. 1.00 means a unit of budget is buying a unit of work. Extensive research on completed projects shows cumulative CPI is stable to within about 0.10 from roughly 20% complete onward — treat a forecast that assumes CPI recovers as an exception requiring evidence.
EAC — Estimate at Completion. The forecast total cost of the baselined scope. Four standard methods are computed side by side on the Forecast & Scenarios sheet; the one you select on Lists drives the register and the Dashboard.
ETC — Estimate to Complete = EAC − AC. What the remaining work will cost.
VAC — Variance at Completion = BAC − EAC. Negative is a forecast overrun.
TCPI — To-Complete Performance Index. TCPI to BAC = (BAC − EV) / (BAC − AC) is the cost efficiency the remaining work must achieve to finish on the original budget. TCPI to EAC = (BAC − EV) / (EAC − AC) is the efficiency needed to land on your own forecast. If TCPI is far above the CPI you have achieved so far, the plan is not credible.
THE FORMULAS THIS WORKBOOK USES
PV = BAC x Planned % Complete · EV = BAC x Actual % Complete · SV = EV − PV · CV = EV − AC
SPI = EV / PV · CPI = EV / AC · SV % = SV / PV · CV % = CV / EV
EAC method 1 = AC + (BAC − EV) · method 2 = BAC / CPI · method 3 = AC + (BAC − EV) / (CPI x SPI) · method 4 = AC + bottom-up ETC
ETC = EAC − AC · VAC = BAC − EAC · TCPI to BAC = (BAC − EV) / (BAC − AC) · TCPI to EAC = (BAC − EV) / (EAC − AC)
Every division in this workbook is guarded: a blank or zero denominator returns an empty cell, never an error. If you see a blank where you expect a number, an input is missing — usually Actual Cost or Actual % Complete.
Element-level EAC applies the selected method row by row. For methods 2 and 3 the element EACs will not sum to the project EAC, because CPI and SPI are weighted averages. The project EAC on the total row and the Dashboard is computed from project totals and is the figure to report.
A register row with no Actual Cost recorded returns a blank EAC, ETC and CPI — there is no basis for a forecast until cost has been incurred against the element. Enter 0 where an element has genuinely cost nothing yet.
CHOOSING AN EARNED VALUE TECHNIQUE
Match the technique to how the work is actually measured, and fix it before the period starts — changing technique mid-stream is the easiest way to manufacture progress.
Prefer objective techniques. Units Complete and Milestone Weighted are defensible in an audit; a judged % Complete is not, unless it is backed by a measured quantity or a signed measure.
0/100, 50/50 and 20/80 are for discrete, short-duration work. The shorter the element relative to the reporting period, the more conservative the split should be.
Level of Effort earns to plan by definition, so it can never report a schedule variance — see the traps below.
Apportioned Effort should track a discrete base account, never a Level of Effort account.
TRAPS — THE THINGS THAT MAKE EARNED VALUE DATA MISLEADING
Level-of-effort distortion. LOE accounts earn EV equal to PV every period regardless of what happens, so they dilute the project SPI towards 1.00 and hide real schedule slippage in the discrete work. Keep LOE below roughly 15% of BAC, tag it clearly (use the EV Technique column), and read the SPI of the discrete accounts separately before you believe the project number.
Earning value on procurement and materials on site. Delivering a switchboard to site is not progress; installing it is. Claiming EV on delivery front-loads the curve and produces a flattering SPI followed by an unexplained collapse. If materials must be recognised, use a milestone technique with a small delivery weighting (typically 10-20%) and the balance on installation and test.
Actual cost cut-off versus claim certification. The most common cause of CPI whiplash. EV is claimed to the end of the month; AC often reflects only invoices processed, which lag by weeks. Accrue the uninvoiced but incurred cost, or the CPI you report is measuring your accounts payable process rather than your project.
Subcontractor claim timing. A subcontractor's certified claim reflects their assessment, at their cut-off, on their measurement basis. Reconcile it to your own EV measurement before it becomes AC.
SPI near completion. As the project finishes, PV converges on BAC and so does EV, dragging SPI towards 1.00 even on a project that is months late. In the last third, read the programme and the earned schedule, not the SPI.
Retention, escalation and provisional sums. Decide once whether AC is gross or net of retention, whether escalation sits in the BAC, and how provisional sums are treated — then apply it consistently across every element. Document the decision here.
Negative or reversed progress. Rework can genuinely reduce EV. Do not suppress it; a falling EV is information.
VARIATIONS AND APPROVED CHANGES TO THE BAC
The BAC changes only through an approved change to the baseline. Until a variation is approved, do not adjust the BAC of the affected element — the cost incurred still appears in AC, the cost variance still shows, and that is the correct signal.
When a variation is approved, add its value to the BAC of the affected control accounts, phase it into the Time-Phased Data sheet in the periods it will be earned, and record the change on the Cover sheet revision history with the variation reference. Both sheets move together; if only one moves, the tie-out block will tell you.
Never adjust EV retrospectively to make a past variance disappear. If a claimed percentage was wrong, correct it in the current period and note why in the Variance Explanation column — the audit trail matters more than a smooth curve.
Work done on instruction but not yet approved is a real risk. Track it outside the BAC and disclose it alongside the EAC so the forecast is not quietly understated.
CONTINGENCY AND MANAGEMENT RESERVE
Contingency sits inside the BAC. It is money set aside for identified, quantified risk within the current scope, and drawing on it is a project decision. Set the percentage on Lists; the Forecast sheet tests whether the forecast overrun is covered by it.
Management reserve sits outside the BAC. It is the owner's allowance for unknown-unknowns, it is excluded from every index and every variance, and it must never be used to close a cost variance. Releasing management reserve into the BAC is a formal baseline change with its own approval.
A CPI that only looks acceptable because reserve has been absorbed into the baseline is not a measurement — it is a presentation. Keep the two separate and the numbers stay honest.
REBASELINING DISCIPLINE
Rebaselining resets the comparison and destroys the trend you have built up. Do it only when the baseline no longer represents a plan anyone intends to follow — after a major scope change, a re-tender, or an agreed extension of time — and never simply because the variances have become uncomfortable.
When you do rebaseline: keep the old baseline as a separate saved copy, record the approval and the reason in the revision history, restate the BAC and the time-phased PV together, and state clearly in the next report that the comparison basis has changed and what the variance was immediately before the reset.
Between rebaselines, the PV column and the Time-Phased Data grid are read-only in practice, even though the cells are unlocked so that you can load them in the first place.
THE MONTHLY EVM CYCLE
1. Fix the data date on the Cover and hold it for every input in the cycle.
2. Collect Actual % Complete for every control account, on the technique recorded in the register, evidenced by measure, milestone or unit count.
3. Collect Actual Cost on the same cut-off, including accruals for work done but not invoiced.
4. Enter both in the EV Register; enter the period EV and AC on the Time-Phased Data sheet.
5. Check the tie-out block. Resolve any difference before you look at the indices.
6. Read the Dashboard: SPI, CPI, the four EAC methods and the top five worst-performing elements.
7. Write a Variance Explanation and a Corrective Action for every amber and red element. A variance without a named owner and a dated action is a statistic, not management.
8. Issue, then archive a copy of the workbook. The trend is only useful if the history is intact.
LIMITATIONS OF THIS WORKBOOK
EVM measures cost-loaded progress. It does not model the critical path, float, or resource constraint, and SV expressed in money is not the same as delay in days. Use it alongside a current, logic-linked programme.
The workbook carries 200 register rows and 36 monthly periods as supplied. To extend either, insert rows inside the existing range so the formulas, validation and named ranges expand with them.
Earned schedule (ES, SV(t), SPI(t)) is not implemented here. If your organisation reports earned schedule, derive it from the cumulative EV and PV curves on the Time-Phased Data sheet.
The example rows describe a mid-rise commercial building and exist only to show the shape of a coherent WBS. Delete them before use — they are flagged in the Notes column of each sheet.
Visit mastt.com