## Cover
Stakeholder Management Plan
A register, a grid that redraws itself, and the commitments sheet most templates leave out
List who matters, score how much they can affect the project and how closely they are watching, and say what you are promising each of them. The grid draws itself from the scores, the next contact date works itself out from the log, and every promise you make sits in a register with the evidence that discharges it.
HOW TO USE IT
1. Fill in Setup |  | Project, the data date, the two thresholds that decide which stakeholders are high influence and high interest, and how often a stakeholder has to be contacted before the register flags it.
2. List the stakeholders, not the people |  | One row per group or organisation. Score influence and interest, set where they are now and where you need them, and name one person here who owns the relationship.
3. Say what you are promising them |  | On the Engagement Plan, and separately from how they feel about you. What you promise sets what you have to do; how they feel is the result.
4. Put every promise in Commitments the moment it is made |  | Whether it came out of a meeting, a condition of approval or a public statement. This is the sheet that gets looked at in an audit, and the one most stakeholder templates leave out.
5. Write the log entry the same day |  | What was raised, and what you did about it - including where you said no and why. That second half is the whole point of the column.
6. Read the Check columns |  | They name what is wrong in words: a commitment overdue with no evidence, a high-influence stakeholder nobody has spoken to, a gap between where they are and where you need them with no engagement planned.
WHAT IS IN THE WORKBOOK
Setup |  | The project, the data date, the two thresholds and the contact cadence.
Register |  | One row per stakeholder: influence, interest, where they are, where you need them, who owns it, and how sensitive the row is.
Matrix |  | The register drawn as an influence and interest grid. It redraws itself.
Engagement Plan |  | What you promise each stakeholder, who leads, how often, and when it is next due.
Commitments |  | Every promise made, what secures it, who owns it, when it is due and what evidence discharges it.
Log |  | What was raised, and how it was taken into account or why it was not.
Reference |  | The colour key and every dropdown source.
The colour key, the other names this document goes by, and every dropdown source are on the Reference sheet.
IMPORTANT | This workbook is a planning and record-keeping tool, not a substitute for whatever your funder, lender or consent authority requires. Where a condition of approval, a financing standard or a participation policy sets the engagement process, that document governs and this one records against it. Write every row as though it will be read outside the project team. If you are a public authority, or hold this on behalf of one, freedom-of-information and environmental-information regimes can reach a register like this; if you are a contractor it is usually reached another way - through your client, a planning submission, an audit or a dispute. Use the disclosure column, and keep personal contact details somewhere else.
Built for teams delivering capital projects, programs and portfolios · mastt.com

## Setup
STAKEHOLDER MANAGEMENT PLAN · SETUP
The project, the date everything is measured against, what counts as high influence and high interest, and the two windows the flags use.
1 · THE PROJECT
Project | EXAMPLE - Brayford Interchange upgrade
Project number | EX-2026-207
Client or business unit | Infrastructure Delivery
Plan owned by | L. Okafor, Community and Stakeholder Lead
Data date | 2026-08-19 | Everything overdue, due soon or in hand is measured against this date, not against today. Set it to the date you are reporting and the whole workbook reports as at that day.
2 · WHAT COUNTS AS HIGH
Influence at or above this is high | 4 | Influence is scored 1 to 5 on the Register. This is the line between the top two quadrants of the Matrix and the bottom two. Move it and the Matrix redraws.
Interest at or above this is high | 4 | The same, for the other axis. Nothing else in the workbook hard-codes a 4.
3 · THE TWO WINDOWS THE FLAGS USE
Treat anything due within this many days as due soon | 14
Flag a stakeholder with no engagement planned after this many days | 60 | Only applies to stakeholders who have no row on the Engagement Plan. Everyone who does is measured against their own cadence instead.
There is no "last contacted" field to keep up to date anywhere in this workbook, and that is deliberate. Last contact is read off the Log, and the next due date is worked out from it. Write the log entry and everything else follows; skip it and the Register says so by name.
Visit mastt.com

## Register
STAKEHOLDER MANAGEMENT PLAN · REGISTER
EXAMPLE DATA - type your own project name on Setup to clear this.
One row per group or organisation, not per person. Score influence and interest, say where they are and where you need them, and name one person who owns the relationship. Everything else on this sheet is worked out.
ID | Stakeholder | Category | What it affects | Influence (1-5) | Interest (1-5) | Priority | Where they are now | Where you need them | Gap | Who owns the relationship | Where the details are held | Disclosure | Last contact | Check
S01 | Brayford City Council - development assessment | Approval authority | Approval or consent | 5 | 4 | Work with them | Neutral | Supportive | 1 | Approvals Manager | Approvals contacts | Internal | 2026-08-03 | last contact 16 days ago - the plan says every 2 weeks | 1 | 1 | 1 | 2 | 1 | red
S02 | State roads authority | Approval authority | Approval or consent | 5 | 4 | Work with them | Supportive | Supportive | 0 | Approvals Manager | Approvals contacts | Internal | 2026-08-07 |  | 2 | 2 | 2 | 4 | 1
S03 | Rail operator - Brayford line | Utility or service provider | Programme | 5 | 3 | Keep on side | Neutral | Supportive | 1 | Interface Manager | Interface agreements | Internal | 2026-07-15 | last contact 35 days ago - the plan says every 2 weeks | 3 | 1 | 1 | 2 | 1 | red
S04 | Electricity network operator | Utility or service provider | Programme | 4 | 2 | Keep on side | Neutral | Supportive | 1 | Services Coordinator | Utility register | Internal | 2026-08-01 |  | 4 | 1 | 2 | 4 | 1
S05 | Water authority | Utility or service provider | Design | 3 | 2 | Watch | Neutral | Neutral | 0 | Services Coordinator | Utility register | Internal | 2026-07-10 |  | 5 | 1 | 1 | 8 | 1
S06 | Environment regulator | Regulator | Approval or consent | 4 | 3 | Keep on side | Neutral | Supportive | 1 | Environment Manager | Approvals contacts | Internal | 2026-07-26 |  | 6 | 1 | 3 | 4 | 1
S07 | Adjoining landowners - Halloway Road frontage | Landowner or occupier | Access or land | 3 | 5 | Keep in the loop | Resistant | Neutral | 1 | Community Lead | Property acquisition file | Restricted | 2026-08-10 |  | 7 | 1 | 1 | 2 | 1
S08 | Brayford Chamber of Commerce | Business | Reputation | 3 | 4 | Keep in the loop | Resistant | Neutral | 1 | Community Lead | Stakeholder contact list | Public | 2026-07-20 | last contact 30 days ago - the plan says every 4 weeks | 8 | 1 | 2 | 4 | 1 | red
S09 | Halloway Road traders | Business | Access or land | 2 | 5 | Keep in the loop | Resistant | Neutral | 1 | Community Lead | Stakeholder contact list | Internal | 2026-08-14 |  | 9 | 1 | 3 | 2 | 1
S10 | Brayford Residents Association | Community | Reputation | 2 | 5 | Keep in the loop | Neutral | Supportive | 1 | Community Lead | Stakeholder contact list | Public | 2026-07-29 |  | 10 | 2 | 4 | 6 | 1
S11 | Cycling advocacy group | Interest group | Design | 2 | 4 | Keep in the loop | Resistant | Neutral | 1 | Design Manager | Stakeholder contact list | Public | 2026-08-05 |  | 11 | 1 | 5 | 8 | 1
S12 | Brayford Primary School | Community | Operations | 2 | 4 | Keep in the loop | Neutral | Supportive | 1 | Community Lead | Stakeholder contact list | Public | 2026-07-17 |  | 12 | 2 | 6 | 8 | 1
S13 | Bus operator | Utility or service provider | Operations | 3 | 3 | Watch | Neutral | Supportive | 1 | Interface Manager | Interface agreements | Internal | 2026-07-24 |  | 13 | 1 | 2 | 4 | 1
S14 | Member for Brayford | Elected representative | Reputation | 4 | 3 | Keep on side | Neutral | Supportive | 1 | Project Director | Executive contact list | Restricted | 2026-07-06 |  | 14 | 2 | 4 | 12 | 1
S15 | Emergency services | Regulator | Operations | 3 | 3 | Watch | Neutral | Supportive | 1 | Interface Manager | Emergency services list | Internal | 2026-06-29 |  | 15 | 2 | 3 | 8 | 1
S16 | Principal contractor | Delivery partner | Programme | 4 | 5 | Work with them | Supportive | Leading | 1 | Project Director | Contract register | Internal | 2026-08-17 |  | 16 | 1 | 3 | 1 | 1
S17 | Local newspaper | Media | Reputation | 2 | 2 | Watch | Neutral | Neutral | 0 | Communications Lead | Media contact list | Internal | 2026-06-20 |  | 17 | 1 | 4 | 12 | 1
[15 empty] | 18 | 0 | 0 | 0 | 0 | grey
[15 empty] | 19 | 0 | 0 | 0 | 0 | grey
[15 empty] | 20 | 0 | 0 | 0 | 0 | grey
Last contact is read off the Log. There is nothing to keep up to date here.
Visit mastt.com
Formulas:
Last contact = IF([ID]="","",IF(SUMPRODUCT(MAX((Log!$C7:C26=[ID])*Log!$B7:B26))=0,"",SUMPRODUCT(MAX((Log!$C7:C26=[ID])*Log!$B7:B26))))

## Matrix
STAKEHOLDER MANAGEMENT PLAN · MATRIX
EXAMPLE DATA - type your own project name on Setup to clear this.
Drawn from the Register every time it recalculates. There is no picture to update and no second list to keep in step - change a score on the Register and this changes.
WHERE THIS PLAN STANDS
17 | 3 | 4 | 14 | 3 | 2
On the register | Work with them | Not with you yet | Gaps to close | Engagement overdue | Commitments overdue
INFLUENCE AND INTEREST
| Interest 1 | Interest 2 | Interest 3 | Interest 4 | Interest 5
Influence 5 |  |  | 1 S03 | 2 S01 S02
Influence 4 |  | 1 S04 | 2 S06 S14 |  | 1 S16
Influence 3 |  | 1 S05 | 2 S13 S15 | 1 S08 | 1 S07
Influence 2 |  | 1 S17 |  | 2 S11 S12 | 2 S09 S10
Influence 1
The shading follows the two thresholds on Setup, so it moves when you move them. Anyone with no influence or interest score does not appear in the grid at all - the Register says so on their row.
WORK WITH THEM high influence, high interest 3 of them
S01 | Brayford City Council - development assessment |  |  | Neutral - needs to be Supportive
S02 | State roads authority |  |  | Supportive
S16 | Principal contractor |  |  | Supportive - needs to be Leading
KEEP ON SIDE high influence, lower interest 4 of them
S03 | Rail operator - Brayford line |  |  | Neutral - needs to be Supportive
S04 | Electricity network operator |  |  | Neutral - needs to be Supportive
S06 | Environment regulator |  |  | Neutral - needs to be Supportive
S14 | Member for Brayford |  |  | Neutral - needs to be Supportive
KEEP IN THE LOOP lower influence, high interest 6 of them
S07 | Adjoining landowners - Halloway Road frontage |  |  | Resistant - needs to be Neutral
S08 | Brayford Chamber of Commerce |  |  | Resistant - needs to be Neutral
S09 | Halloway Road traders |  |  | Resistant - needs to be Neutral
S10 | Brayford Residents Association |  |  | Neutral - needs to be Supportive
S11 | Cycling advocacy group |  |  | Resistant - needs to be Neutral
S12 | Brayford Primary School |  |  | Neutral - needs to be Supportive
WATCH lower influence, lower interest 4 of them
S05 | Water authority |  |  | Neutral
S13 | Bus operator |  |  | Neutral - needs to be Supportive
S15 | Emergency services |  |  | Neutral - needs to be Supportive
S17 | Local newspaper |  |  | Neutral
Visit mastt.com

## Engagement Plan
STAKEHOLDER MANAGEMENT PLAN · ENGAGEMENT PLAN
EXAMPLE DATA - type your own project name on Setup to clear this.
What you promise each stakeholder, who leads it and how often. The next due date is worked out from the last contact on the Log plus the cadence - the only date you type is one that is already in the diary.
ID | Stakeholder | Priority | What we promise them | How | Who leads it | Every (weeks) | Last contact | Next due | Booked for | Status | Check
S01 | Brayford City Council - development assessment | Work with them | Collaborate | Meeting | Approvals Manager | 2 | 2026-08-03 | 2026-08-17 |  | Overdue | overdue by 2 days | red
S02 | State roads authority | Work with them | Collaborate | Meeting | Approvals Manager | 4 | 2026-08-07 | 2026-09-04 |  | In hand
S03 | Rail operator - Brayford line | Keep on side | Collaborate | Meeting | Interface Manager | 2 | 2026-07-15 | 2026-07-29 |  | Overdue | overdue by 21 days | red
S04 | Electricity network operator | Keep on side | Consult | Email | Services Coordinator | 4 | 2026-08-01 | 2026-08-29 |  | Due soon |  | orange
S05 | Water authority | Watch | Inform | Email | Services Coordinator | 8 | 2026-07-10 | 2026-09-04 |  | In hand
S06 | Environment regulator | Keep on side | Consult | Meeting | Environment Manager | 4 | 2026-07-26 | 2026-08-23 |  | Due soon |  | orange
S07 | Adjoining landowners - Halloway Road frontage | Keep in the loop | Involve | Meeting | Community Lead | 2 | 2026-08-10 | 2026-08-24 | 2026-08-24 | Due soon |  | orange
S08 | Brayford Chamber of Commerce | Keep in the loop | Consult | Meeting | Community Lead | 4 | 2026-07-20 | 2026-08-17 |  | Overdue | overdue by 2 days | red
S09 | Halloway Road traders | Keep in the loop | Involve | Site visit | Community Lead | 2 | 2026-08-14 | 2026-08-28 | 2026-08-22 | Due soon |  | orange
S10 | Brayford Residents Association | Keep in the loop | Consult | Public session | Community Lead | 6 | 2026-07-29 | 2026-09-09 | 2026-09-05 | In hand
S11 | Cycling advocacy group | Keep in the loop | Consult | Meeting | Design Manager | 8 | 2026-08-05 | 2026-09-30 |  | In hand
S12 | Brayford Primary School | Keep in the loop | Inform | Letter | Community Lead | 8 | 2026-07-17 | 2026-09-11 |  | In hand
S13 | Bus operator | Watch | Consult | Meeting | Interface Manager | 4 | 2026-07-24 | 2026-08-21 |  | Due soon |  | orange
S14 | Member for Brayford | Keep on side | Inform | Meeting | Project Director | 12 | 2026-07-06 | 2026-09-28 |  | In hand
S15 | Emergency services | Watch | Consult | Meeting | Interface Manager | 8 | 2026-06-29 | 2026-08-24 |  | Due soon |  | orange
S16 | Principal contractor | Work with them | Collaborate | Meeting | Project Director | 1 | 2026-08-17 | 2026-08-24 | 2026-08-20 | Due soon |  | orange
S17 | Local newspaper | Watch | Inform | Email | Communications Lead | 12 | 2026-06-20 | 2026-09-12 |  | In hand
grey
grey
grey
Visit mastt.com
Formulas:
Last contact = IF([ID]="","",IF(COUNTIF(Register!$B7:B26,[ID])=0,"",IF(VLOOKUP([ID],Register!$B7:O26,14,FALSE())="","",VLOOKUP([ID],Register!$B7:O26,14,FALSE()))))
Next due = IF(OR([Last contact]="",[Every (weeks)]="",[Every (weeks)]=0),"",[Last contact]+[Every (weeks)]*7)

## Commitments
STAKEHOLDER MANAGEMENT PLAN · COMMITMENTS
EXAMPLE DATA - type your own project name on Setup to clear this.
Every promise you have made and what discharges it. Put it here the moment it is made - out of a meeting, out of a condition of approval, out of something said in public. This is the sheet that gets read in an audit.
Ref | What was committed to | To whom | Stakeholder | Where it came from | What secures it | Phase | Owner | Due | Evidence it is discharged | Status | Check
C01 | No construction traffic on Halloway Road between 8.00 and 9.30 am on school days | S12 | Brayford Primary School | Condition of approval | Consent condition 34 | Construction | Site Manager | 2026-08-31 |  | Due soon |  | orange
C02 | Maintain two-way access to every Halloway Road business frontage at all times | S09 | Halloway Road traders | Consultation | Construction traffic management plan | Construction | Site Manager | 2026-08-13 |  | Overdue | overdue by 6 days, and no evidence recorded | red
C03 | Reinstate the shared path to its existing width or better | S11 | Cycling advocacy group | Public statement | Design report section 6 | Design | Design Manager | 2026-09-15 | Drawing DR-214 rev C, issued for construction | Discharged
C04 | Give landowners 20 working days' notice before any survey on their land | S07 | Adjoining landowners - Halloway Road frontage | Agreement or deed | Access deed clause schedule | Design | Property Lead | 2026-07-31 |  | Overdue | overdue by 19 days, and no evidence recorded | red
C05 | Publish a monthly construction update on the project page | S10 | Brayford Residents Association | Our own undertaking | Communications plan | Construction | Communications Lead | 2026-08-23 | Last month's update published on the project page | Discharged
C06 | Keep one rail possession per quarter and give 16 weeks' notice of each | S03 | Rail operator - Brayford line | Agreement or deed | Rail interface agreement | Construction | Interface Manager | 2026-09-28 |  | In hand
C07 | Hold a pre-construction briefing for the Chamber before works start | S08 | Brayford Chamber of Commerce | Consultation | Engagement plan | Construction | Community Lead | 2026-08-28 |  | Due soon |  | orange
C08 | Relocate the bus stop rather than remove it | S13 | Bus operator | Consultation | Design report section 4 | Design | Design Manager | 2026-09-21 | Design change note DCN-08, approved | Discharged
grey
grey
grey
A commitment with evidence against it is discharged. A commitment past its due date with the evidence column empty is the row this register exists to surface.
Visit mastt.com

## Log
STAKEHOLDER MANAGEMENT PLAN · LOG
EXAMPLE DATA - type your own project name on Setup to clear this.
Write it the same day. What was raised, and what you did about it - including where you said no and why. That second half is the column an auditor, a review or a disclosure request actually reads.
Date | Who with | Stakeholder | How | Who from us | What was raised | How it was taken into account, or why it was not | Action needed | Commitment it created | Check
2026-08-17 | S16 | Principal contractor | Meeting | Project Director | Contractor raised a clash between the rail possession window and the utility diversion | Accepted. The diversion moved to the following window and the programme reissued. | Yes
2026-08-14 | S09 | Halloway Road traders | Site visit | Community Lead | Traders asked for loading access to be kept during the daytime, not overnight only | Accepted in part. Daytime loading kept on the northern frontage; the southern frontage cannot be kept open during the deck pour and that was explained on site. | Yes | C02
2026-08-10 | S07 | Adjoining landowners - Halloway Road frontage | Meeting | Community Lead | Landowners objected to the survey notice period and to the acquisition boundary | Notice period accepted and recorded as C04. The boundary is fixed by the approved alignment and cannot change; the reason was given to them in writing. | Yes | C04
2026-08-07 | S02 | State roads authority | Meeting | Approvals Manager | Roads authority asked for the road occupancy programme before the works approval issues | Accepted. The programme was issued and the approval is expected before mobilisation. | Yes
2026-08-05 | S11 | Cycling advocacy group | Meeting | Design Manager | Cycling group asked for a separated path rather than a shared path | Not accepted. A separated path does not fit the approved corridor width. The shared path will be reinstated wider than existing - recorded as C03. | No | C03
2026-08-03 | S01 | Brayford City Council - development assessment | Meeting | Approvals Manager | Council asked how construction parking would be managed | Answered, and carried into the construction traffic management plan. | Yes
2026-08-01 | S04 | Electricity network operator | Email | Services Coordinator | Network operator confirmed the diversion design and asked for 12 weeks' notice of the outage | Accepted. The notice date is in the programme and the outage window is booked. | Yes
2026-07-29 | S10 | Brayford Residents Association | Public session | Community Lead | Residents raised noise from night work and asked for a single point of contact | Both accepted. Night work limited to the two deck pours, and the site manager's number published on the hoarding and in the monthly update - recorded as C05. | Yes | C05
2026-07-26 | S06 | Environment regulator | Meeting | Environment Manager | Regulator asked how sediment would be managed during the deck works | Answered. The erosion and sediment control plan was submitted for approval. | Yes
2026-07-24 | S13 | Bus operator | Meeting | Interface Manager | Bus operator asked whether the stop would be removed for the duration of the works | Not removed. It will be relocated 40 m north for the duration - recorded as C08. | Yes | C08
2026-07-20 | S08 | Brayford Chamber of Commerce | Meeting | Community Lead | Chamber asked to be briefed before works start rather than after | Accepted and recorded as C07. | Yes | C07
2026-07-17 | S12 | Brayford Primary School | Letter | Community Lead | School asked that heavy vehicle movements avoid both drop-off and pick-up times | Accepted for the morning and recorded as C01. The afternoon cannot be avoided during the deck pour; that was put in writing with the dates it applies. | Yes | C01
2026-07-15 | S03 | Rail operator - Brayford line | Meeting | Interface Manager | Rail operator set the possession regime and the notice period | Accepted and recorded as C06. | Yes | C06
2026-07-10 | S05 | Water authority | Email | Services Coordinator | Water authority confirmed no assets are affected within the works footprint | Noted. Nothing to action, and the confirmation is filed with the utility register. | No
2026-07-06 | S14 | Member for Brayford | Meeting | Project Director | Briefing on scope, cost and programme. Nothing raised. | Nothing to action. The next briefing is at the start of construction. | No
2026-06-29 | S15 | Emergency services | Meeting | Interface Manager | Emergency services asked to be told of any overnight lane closure 10 days ahead | Accepted and built into the traffic management plan notification process. | Yes
2026-06-20 | S17 | Local newspaper | Email | Communications Lead | Newspaper asked for comment on the acquisition of the Halloway Road frontage | Referred to the approved statement. No further comment while negotiations are open. | No
grey
grey
grey
Visit mastt.com

## Reference
STAKEHOLDER MANAGEMENT PLAN · REFERENCE
The colour key, what the words mean, and every dropdown source. Edit a list here and every dropdown in the workbook follows it.
THE COLOUR KEY - THE SAME SIX MEANINGS ON EVERY SHEET
Colour | It means |  |  |  |  | When you will see it
ACT NOW | Act now |  |  |  |  | An overdue commitment, or a high-influence stakeholder who is resistant with no engagement planned.
DUE SOON | Due soon |  |  |  |  | Inside the window you set on Setup, or a gap between where they are and where you need them.
MISSING SOMETHING | Missing something |  |  |  |  | A field the rest of the sheet needs before it can calculate.
IN HAND | In hand |  |  |  |  | Planned, current, and somebody owns it.
DONE | Done |  |  |  |  | Discharged, with evidence recorded.
NOT APPLICABLE | Not applicable |  |  |  |  | Out of scope, or nothing to calculate yet.
HOW TO READ A CELL
Pale blue | You type in it.
Off-white | Calculated. Typing in it breaks the sheet.
Red row | Needs action now.
Orange row | Due soon, or a gap nobody is closing.
Grey row | Not applicable, or nothing to calculate yet.
THE SAME THING UNDER ANOTHER NAME
This workbook calls it | You will also see it called |  |  |  |  | Where it is in here
Stakeholder management plan | Stakeholder engagement plan, SEP, communications and engagement plan |  |  |  |  | This workbook. A lender or a consent authority will ask for a stakeholder ENGAGEMENT plan: PMI renamed the plan from management to engagement in 2017, and IFC Performance Standard 1 and World Bank ESS10 both require a Stakeholder Engagement Plan by that name. Those standards set content this workbook does not cover - information disclosure, consultation method, and a grievance mechanism. Plan and record against your SEP with this. It is not the SEP.
Commitment | Undertaking, obligation, register of environmental actions and commitments (REAC), commitments register, consolidated mitigation measures |  |  |  |  | The Commitments sheet. UK road schemes must have one - DMRB LA 120 requires the environmental management plan to include a register of environmental actions and commitments - and REACs are submitted on road and energy projects. For Nationally Significant Infrastructure Projects the Planning Inspectorate advises the title Commitments Register and publishes a standard template for it. In NSW the equivalent is the consolidated mitigation measures schedule in the environmental impact statement.
Influence | Power, authority, ability to affect the outcome |  |  |  |  | A score on the Register
What we promise | Level of participation, engagement level |  |  |  |  | The Engagement Plan. Not the same thing as how supportive they are.
Grievance | Complaint, objection, issue raised |  |  |  |  | The Log, with the action it produced
DROPDOWN SOURCES - EDIT THESE AND EVERY LIST IN THE WORKBOOK FOLLOWS
Category | Where it came from | What it affects | How | Phase | What we promise | Position | Disclosure | Yes or no
Approval authority | Consultation | Approval or consent | Meeting | Business case | Inform | Unaware | Public | Yes
Regulator | Condition of approval | Access or land | Call | Design | Consult | Resistant | Internal | No
Utility or service provider | Agreement or deed | Design | Email | Approvals | Involve | Neutral | Restricted
Landowner or occupier | Public statement | Programme | Letter | Procurement | Collaborate | Supportive
Business | Contract | Cost | Public session | Construction | Empower | Leading
Community | Our own undertaking | Reputation | Site visit | Commissioning
Interest group |  | Operations | Written submission | Operations
Delivery partner |  | Nothing directly | Site notice
Internal |  |  | Door knock
Elected representative
Media
Visit mastt.com