Construction Project Management Meeting Agenda

The agenda that becomes the minutes, and the actions that carry to the next one

EXAMPLE CONTENT - this form is filled in for one worked meeting so you can see what each field wants. Replace every entry with your own, and delete this banner, before you issue it.

| 1 THE MEETING |
| --- |
| Project | EXAMPLE - Ashgrove Primary School, new teaching block |  |  |
| Project number | EX-4471 | Meeting | Progress meeting - weekly |
| Meeting number | 14 | Date | Wednesday 19 August |
| Time | 9.00 to 10.05 am | Place | Site office, and by video link |
| Chaired by | A. Bello, Contract Administrator | Minutes taken by | N. Ferreira |
| Next meeting | Wednesday 26 August, 9.00 am, site office |  |  |
| These minutes go to | All present and all apologies, plus the school Principal, the Regional Facilities Manager, and the services subcontractor for item 3. Issued within two working days. |  |  |

| 2 WHO WAS THERE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name | Organisation | Role | Attended | Initials |
| Mark each person Present, Apologies or Distribution only. The last one matters: a minute is only useful against a party who actually received it. |  |  |  |  |
| A. Bello | Hartley Reid | Contract Administrator | Present |  |
| N. Ferreira | Hartley Reid | Project Coordinator | Present |  |
| M. Cassar | Department of Education | Client Project Manager | Present |  |
| D. Whitfield | Norland Construction | Project Manager | Present |  |
| S. Okafor | Norland Construction | Site Manager, HSE | Present |  |
| P. Lindqvist | Norland Construction | Contract Administrator | Present |  |
| R. Achebe | Vellacott Architects | Project Architect | Present |  |
| T. Moreau | Vellacott Architects | Services Coordinator | Apologies |  |
| J. Rivera | Hartley Reid | Quantity Surveyor | Present |  |
| K. Doulton | Ashgrove Primary School | Business Manager | Present |  |
| L. Prakash | Department of Education | Regional Facilities | Distribution only |  |

| 3 THE LAST MEETING, AND WHAT IT LEFT OPEN |
| --- |
| Minutes of the last meeting | Meeting 13 (12 August) accepted as a true record, with one amendment: item 5 should read claim 8 certified at $398,200, not $389,200. |  |  |

| Ref | Action carried forward | Owner | Due | Status | Where it stands at this meeting |
| --- | --- | --- | --- | --- | --- |
| The reference is the meeting number and the item number it was agreed under, so 14.3 is item 3 of meeting 14. Copy this table forward every meeting. Close what is done and leave the closed row in place with its date - that row is the record. |  |  |  |  |  |
| 11.4 | Issue the revised roof safety mesh detail | R. Achebe | 5 Aug | Closed | Issued 4 Aug as SK-118. Closed. |
| 12.2 | Confirm the switchboard delivery date in writing | D. Whitfield | 14 Aug | Overdue | Supplier has not confirmed. Longest lead item - see item 7. |
| 12.7 | Answer RFI-041, balustrade fixing to the level 2 edge | R. Achebe | 6 Aug | Overdue | Still open. Holding the level 2 edge - see item 3. |
| 13.1 | Re-mark the crane exclusion zone, reissue the lift study | S. Okafor | 22 Aug | Open | Zone re-marked 13 Aug. Lift study due this week. |
| 13.3 | Issue the resequenced programme | D. Whitfield | 21 Aug | Open | In preparation. Due before the next meeting. |
| 13.5 | Approve or reject CH-07, additional switchboard | M. Cassar | 26 Aug | Open | With the Department. No work until instructed. |
| 13.8 | Lodge the acoustic report for consent condition 12 | M. Cassar | 5 Sep | Open | Consultant engaged. On track. |

| 4 THE AGENDA, AND THE MINUTES OF IT |  |  |  |
| --- | --- | --- | --- |
| No. | Item, and what to cover | What was discussed and decided | Action by and when |
| The item numbers do not change between meetings - that is what keeps the action references stable. An item with nothing to report still gets a line: "nothing this meeting" is a record, a blank cell is not. |  |  |  |
| 1 | Safety, health and environment Incidents and near misses. Inductions and permits. Environmental controls. | No injuries. Near miss 12 Aug - load swung near the site office walkway. Exclusion zone re-marked, lift study being reissued. Two inductions. | S. Okafor 22 Aug |
| 2 | Programme and progress Progress against programme. What is on the critical path now. Days lost. | Complete to level 2, six days behind - four wet weather, two the slab set-down detail. Critical path is the level 2 edge, held by RFI-041. Saturday recovery proposed, not yet accepted. | D. Whitfield 21 Aug |
| 3 | Information and design RFIs open and overdue, and what each one holds. Submittals awaiting review. | Nine RFIs open, three overdue. RFI-041 due 6 Aug and on the critical path - to be answered by 21 Aug, interim direction if unresolved. Four shop drawing packages with the architect. | R. Achebe 21 Aug |
| 4 | Variations and change Instructed, priced, awaiting decision. Anything proceeding with no instruction. | CH-07, additional switchboard, $34,800, with the Department. CH-09 raised for the level 1 ceiling - no instruction issued, no work started, confirmed to the contractor. Wet weather allowance drawn to four of eight days. | M. Cassar 26 Aug |
| 5 | Cost and payment Claim submitted, certified and paid. Next claim date. Anything in dispute. | Claim 8 submitted 31 Jul, $412,600, certified $398,200 - the difference is CH-07, held not disputed. Paid 14 Aug. Claim 9 due 31 Aug. Retention 5 per cent, nothing released. | J. Rivera 29 Aug |
| 6 | Quality, inspections and defects Hold points witnessed and passed. Test results. Non-conformances. Defects. | Level 1 slab reinforcement passed 8 Aug. Pour 6 twenty-eight day results conforming. NCR-03 open, sealant to the level 1 facade joint - method NOT yet accepted, manufacturer's written agreement wanted first. | A. Bello 22 Aug |
| 7 | Risks, issues and delay events New risks. Anything escalated, and to whom. Delay events, and notices served. | Unforeseen ground condition, rock at the northern footings - found 10 Aug, notified 11 Aug, acknowledged 12 Aug. Escalating: switchboard lead time now 16 weeks against 10 in the programme. Order it or reprogramme. | D. Whitfield 25 Aug |
| 8 | Approvals, permits and authorities Permits held, applied for, outstanding. Conditions due, and who discharges each. | Building permit issued and on site. Road occupancy for the 23 Aug crane approved. Fire services connection lodged 8 Aug, 15 business days quoted. Consent condition 12, acoustic report, due before fitout. | M. Cassar 5 Sep |
| 9 | Site, access and neighbours Access, deliveries, traffic. Complaints, and what was said back. | Two complaints about early deliveries - now booked from 7.30 am, gate log kept. School still in the existing block, fencing checked 11 Aug. The 23 Aug lift is out of hours. | S. Okafor 20 Aug |
| 10 | Other business, and the next meeting Anything not covered above. Next meeting, and who is needed at it. | As-built drawings to be updated monthly and submitted with each claim, so nothing is left to the end. Next meeting 26 Aug, 9.00 am, site office. Services subcontractor for item 3 only. | N. Ferreira 21 Aug |

5 ISSUED BY

| Chaired by |  |  | Minutes taken by |  |  | Date issued |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

ANNEX A THE FIRST MEETING ONLY - PRECONSTRUCTION CONFERENCE, PRE-CONTRACT OR KICK-OFF

Used once, then delete this annex. From the next meeting on, use the form in front of it.

| No. | Settle this | What that means in practice | Confirmed, or the action needed |
| --- | --- | --- | --- |
| 1 | Roles and authority | Who chairs, who minutes, who may instruct a change - and by what document. |  |
| 2 | Contacts and out of hours | One contact list, and the number somebody rings at 2 am. |  |
| 3 | Contract status | Possession or notice to proceed. Dates for start and completion. Cost of running late. |  |
| 4 | Correspondence | Who writes to whom, in what form, and what being copied does not amount to. |  |
| 5 | Programme | The baseline programme, its critical path, and when it is reissued. |  |
| 6 | Meeting cycle | Which meetings, how often, who chairs, and how soon the minutes go out. |  |
| 7 | Submittals and shop drawings | What is submitted, in what form, the review period, and what a review does not do. |  |
| 8 | Requests for information | How one is raised, who answers, the response period, and what happens when it is missed. |  |
| 9 | Variations and directions | How a direction is issued and by whom. A price request is not authority to start. |  |
| 10 | Payment | Claim date, assessment, certification, retention, and any declaration or release. |  |
| 11 | Insurances and securities | What is required, what is held, what has been checked, and when each expires. |  |
| 12 | Permits and approvals | Permit and plans on site. Every condition, when it falls due, who discharges it. |  |
| 13 | Underground services | Enquiry lodged and dated, services located and marked, and the notice required. |  |
| 14 | The site itself | Where it starts and stops. Gates, routes, hours, laydown. Temporary services, hoarding. |  |
| 15 | Safety | Inductions, licences and competency cards, permits to work, emergency arrangements. |  |
| 16 | Environment | Erosion and sediment control, waste, noise limits, and the hours work may be done. |  |
| 17 | Survey and set out | Who sets out, who checks, what is recorded, and who carries it if it is wrong. |  |
| 18 | Quality | The inspection and test plan, the points work stops at, and who witnesses each. |  |
| 19 | Records and completion | Site diary, photographs, monthly as-builts, and what completion and handover need. |  |

HOW TO USE THIS FORM

| One form per meeting, and keep them all. | Save it as the meeting number. The set of them is the project's narrative, and the first thing anybody asks for in an argument. |
| --- | --- |
| The action reference is the meeting number and the item number. | An action agreed under item 3 of meeting 14 is 14.3. That is why the item numbers never change: the reference alone tells you where to look. |
| Section 3 is copied forward, not retyped. | Bring every open action across, close what is done, and leave the closed rows with their dates. The closures are what make it a record. |
| An item with nothing to report still gets a line. | "Nothing this meeting" is a record. A blank cell tells you nobody looked. |
| Annex A is used once, then deleted. | It is the first-meeting agenda - the preconstruction conference, the pre-contract meeting, the kick-off. |
| If the person minuting can also instruct, assume the minute instructs. | The chair is often the person who can direct a change. Then anything you write as a decision may be read as one. Say "to be instructed" instead. |
| Fill in the distribution list, and mean it. | A minute is only useful against a party who received it. Record everyone it went to, including anyone who was not in the room. |

IMPORTANT What these minutes are, and are not. They record what was said and decided. They are not a substitute for anything your contract requires in a particular form: where a notice is required - delay, an unforeseen or differing site condition, a claim, a defect, a payment - serve it separately, in the form and within the period the contract states, and cross-reference it here. Some contracts require a notice to be identified as a notice, or sent separately from every other communication. But do NOT assume a minute has no effect either: depending on your contract, and on who writes it, a recorded instruction, approval, agreed price or agreed date can bind the person who gave it. Attribute every decision to the person who made it, and mark anything not yet done as not yet instructed.

Built for teams delivering capital projects, programs and portfolios