## Cover
CONSTRUCTION DAILY LOG
One row per day. The check column tells you what a row is missing, and the gap check tells you which day has no row at all.
SET THIS UP ONCE
Project |  | e.g. Northbank Health Precinct - Stage 2
Project number |  | e.g. NB2-2026-014
Site address |  | e.g. 118 Riverside Drive
General contractor |  | e.g. Halbrook Construction
Log kept by |  | e.g. M. Delgado, Superintendent
Data date |  | The date the workbook reports as at. Leave it and it uses today.
WHAT IS IN THIS FILE
Daily Log | One row per day. Sixteen columns, one screen, and a check column that tells you what the row is missing before somebody else finds out.
Gap Check | The reason this file exists. It counts the working days between your first and last entry that have no row at all, and names the first one.
Day Sheet | A one-page printable form for the person who writes the log by hand on site. Print it, fill it in, then type the row.
Dashboard | Nothing typed. Days logged, days with lost time, labor hours, average crew, and the gap count.
Lists | Weather, ground condition and safety dropdowns. Edit them here.
Notes & Assumptions | What was assumed, what to change first, and what this file is not.
HOW TO USE IT
Fill it in the same day | A log written on Friday for the whole week is a reconstruction, and it reads like one.
Write what happened, not what was planned | "Continued framing" records nothing. Name the area, the quantity and the trade.
Record lost time in hours, with the cause | Hours lost and the reason are the two fields that matter most later. A blank cause with hours in it is worse than nothing.
Log the day you did nothing | A day with no work is a day that needs a row saying so. Those are the rows the gap check cannot invent for you.
Name who wrote it | An unsigned log is a document with no author.
Do not edit history | Correct a later row, do not rewrite an earlier one. If you must, note the correction and the date you made it.
IMPORTANT What this log is, and what it is not. It is a contemporaneous record of what happened on site. It is not a notice, and it is not a claim. Where your contract requires notice of a delay, of a differing site condition, of a change, or of an intent to seek time or money, serve that notice in the form and within the period the contract requires - writing it in the log does not serve it, and a log entry is not a substitute for a change order request. But do not assume the log has no effect either: it is the record both sides will read, an instruction or an agreement recorded in it can be relied on against the person who gave it, and a gap in it will be read against whoever kept it. Nothing here is legal advice.
Visit mastt.com

## Daily Log
CONSTRUCTION DAILY LOG · DAILY LOG
EXAMPLE CONTENT - five worked days, including a weather day, a lost-time day and a deliberate four-day gap so the gap check has something to find. Delete the rows and this banner disappears.
One row per day, newest last. Day, and the check column, are calculated - everything else is typed on the day it happened.
THE LOG
Date | Day | Weather | Temp | Ground | Crew on site | Labor hours | Work performed today | Hours lost | Why time was lost | Deliveries received | Visitors and inspections | Safety | Change / instruction received | Prepared by | Check | Skipped | Gap?
2026-08-13 | 1 | Clear | 78 | Dry | 34 | 272 | Level 3 slab: reinforcement placed bays 3A to 3D; formwork stripped bays 2A to 2C. Underground drainage continued at the north boundary. | 0 |  | Reinforcement 12 t; formwork panels 40 no. | Building official - footing inspection, passed | Nothing to report |  | M. Delgado |  | 0 | 0
2026-08-14 | 2 | Rain - heavy | 61 | Muddy | 22 | 132 | Slab pour postponed. Crew redeployed to interior framing on level 1 and to protecting exposed reinforcement. | 5.5 | Rain 1.8 in from 06:00; standing water in bays 3A to 3D | None - concrete supplier stood down |  | Nothing to report | Verbal instruction to protect reinforcement, confirmed in writing same day | M. Delgado |  | 0 | 0
2026-08-15 | 3 | Cloudy | 66 | Damp | 31 | 248 | Bays 3A to 3D dewatered and re-prepped. Slab pour completed 3A and 3B, 96 cu yd. Cylinders taken. | 0 |  | Concrete 96 cu yd; curing blankets 20 no. | Testing lab - cylinder pickup | Near miss |  | M. Delgado | Safety flag raised - name where the incident record is | 0 | 0
2026-08-16 | 4 | Clear | 71 | Dry | 29 | 232 | Slab pour completed 3C and 3D, 88 cu yd. Interior framing continued level 1. Drainage tie-in at the north boundary completed and backfilled. | 0 |  | Concrete 88 cu yd |  | Nothing to report |  | M. Delgado |  | 0 | 0
2026-08-20 | 5 | High wind | 69 | Dry | 18 | 108 | Crane stood down from 10:20, sustained wind above the manufacturer's limit. Crew redeployed to ground-level work and site cleanup. | 4 | Wind above the crane's operating limit, logged from the site anemometer |  | Safety consultant - monthly walk | Nothing to report |  | M. Delgado |  | 2 | 1
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
GAP CHECK - THE DAYS WITH NO ROW AT ALL
Working days with no row |  |  | 2 | Biggest gap | 2 | First gap before | 2026-08-20
A gap is a working day, Monday to Friday, between your first and last entry with no row against it. The workbook does not know your holidays or shutdowns - add a row saying the site was closed and the gap closes. A log with holes in it is the first thing an opposing expert looks for, and by the time anyone notices, the people who were there have moved on.
Visit mastt.com
Formulas:
Skipped = IF(OR([Date]="",[Date, row above]=""),0,MAX(0,NETWORKDAYS([Date, row above],[Date])-2))

## Day Sheet
CONSTRUCTION DAILY LOG · DAY SHEET
Print this, fill it in on site, then type the row on the Daily Log. The PDF beside this workbook is this sheet.
THE DAY
Project
Project number
Date
Day number
Prepared by
CONDITIONS
Weather
Temperature
Ground condition
PEOPLE AND HOURS
Crew on site
Labor hours worked
Subcontractors on site
WORK PERFORMED TODAY
TIME LOST
Hours lost
Why time was lost
DELIVERIES RECEIVED
VISITORS AND INSPECTIONS
SAFETY
Flag
Incident record kept at
CHANGES AND INSTRUCTIONS RECEIVED
SIGNED
Prepared by | Date
Reviewed by | Date
Fill this in the same day. A sheet completed on Friday for the whole week is a reconstruction, and it reads like one.
Visit mastt.com

## Dashboard
CONSTRUCTION DAILY LOG · DASHBOARD
Nothing typed. Every figure is a formula over the Daily Log.
▲ 2 WORKING DAY(S) WITH NO ROW - a day nobody logged is a day nobody can reconstruct
DAYS LOGGED |  | DAYS WITH NO ROW |  | HOURS LOST | SAFETY FLAGS
5 |  | 2 |  | 9.5 | 1
rows with a date |  | working days, Mon to Fri |  | as recorded on the log | days above Nothing to report
DAYS BY WEATHER CONDITION
Clear | 2 | ████████████████████████
Cloudy | 1 | ████████████
Rain - light | 0
Rain - heavy | 1 | ████████████
Storm | 0
Snow | 0
Ice | 0
High wind | 1 | ████████████
Extreme heat | 0
Smoke or dust | 0
Weather is what the log says was observed, not what a weather station recorded. If you rely on a station record in a claim later, cite the station - this chart is the trigger for that, not the substitute.
THE RECORD
| Value |  | Where it comes from
First day logged | 2026-08-13 |  | Date column
Last day logged | 2026-08-20 |  | Date column
Biggest single gap, working days | 2 |  | Daily Log gap check - a run of missing days is worse than the same count spread out
Total labor hours | 992 |  | Labor hours column
Average crew on a logged day | 26.8 |  | Crew column
Days with time lost | 2 |  | Hours lost column
Days with hours lost and no cause given | 0 |  | Hours lost and Why columns - each of these is a hole in the record
Days a change or instruction was received | 1 |  | Change / instruction column
Rows the check column is questioning | 1 |  | Daily Log, Check column
Visit mastt.com

## Lists
CONSTRUCTION DAILY LOG · LISTS
The three dropdowns. Edit a list here and the Daily Log follows it.
DROPDOWNS
Weather | Ground | Safety | Notes on the lists
Clear | Dry | Nothing to report | Weather is what you observed, not what a forecast said. Ground condition is the one that gets left out and the one that decides whether plant could work. Safety is a flag, not a report - anything above "Nothing to report" needs its own incident record, and the log row should say where that record is.
Cloudy | Damp | Near miss
Rain - light | Wet | First aid
Rain - heavy | Muddy | Recordable injury
Storm | Frozen | Property damage
Snow | Flooded | Environmental
Ice |  | Stop work
High wind
Extreme heat
Smoke or dust
Visit mastt.com

## Notes & Assumptions
CONSTRUCTION DAILY LOG · NOTES & ASSUMPTIONS
What this file assumes, what to change first, and what it is not.
What this file assumes | One general contractor keeping one log for one site, written by the superintendent or a field engineer. Not a multi-site portfolio log, and not a subcontractor's own log - though a subcontractor can use it unchanged.
Why it is one row per day | Mastt's Construction Daily Report is the eleven-tab version, with labor, plant, materials, delays and weather each on their own sheet. Use that one when the project needs that level of record. Use this one when the alternative to a simple log is no log at all - which is the usual alternative.
Hours, not days | Lost time is recorded in hours because that is how it is actually observed. Converting hours to days is a judgment about the working day and about concurrency, and it belongs in the analysis, not in the log.
The gap check counts working days | Monday to Friday, using the workbook's own weekend assumption. It does not know your holidays or your shutdowns - add a row saying the site was closed and the gap closes.
Weather is observed, not sourced | Record what you saw and where you read it. If you rely on a station record for a claim later, cite the station and the date - the log is the trigger for that, not the substitute.
It does not replace photographs | Photograph the condition, and reference the photo set in the row. A described condition and a photographed one are not the same evidence.
IMPORTANT What this log is, and what it is not. It is a contemporaneous record of what happened on site. It is not a notice, and it is not a claim. Where your contract requires notice of a delay, of a differing site condition, of a change, or of an intent to seek time or money, serve that notice in the form and within the period the contract requires - writing it in the log does not serve it, and a log entry is not a substitute for a change order request. But do not assume the log has no effect either: it is the record both sides will read, an instruction or an agreement recorded in it can be relied on against the person who gave it, and a gap in it will be read against whoever kept it. Nothing here is legal advice.
Visit mastt.com