## Cover
INVOICE VERIFICATION CHECKLIST
One payment application per copy. The arithmetic first, then the paperwork, then a recommendation that will not read certify while a mandatory check is open.
SET THIS UP ONCE
Project |  | e.g. Northbank Ambulatory Care Center
Contract |  | One contract per copy
Contractor |  | The contracting entity
Claim or invoice number |  | As it appears on the claim
Period claimed |  | e.g. to 31 of the month
Date received |  | When it arrived, not the date on it
Reviewed by |  | The person answering the checks
Data date |  | Leave it blank and it uses today.
WHAT IS IN THIS FILE
Reconciliation | Five numbers in, and the sheet computes what should be certified this period and the difference against what was claimed.
Verification Checklist | 35 checks in 7 groups, each carrying what it costs you if it fails, each Mandatory or Advisory.
Certification | The recommendation, and it will not read certify while a mandatory check is open.
Lists | Result, severity and recommendation values. Edit them here.
Notes & Assumptions | What was assumed, what to change first, and what this file is not.
HOW TO USE IT
Do the arithmetic before the paperwork | A claim that does not add up goes back before anybody opens a certificate.
A blank is not a pass | "Not checked" is a result, and the gate treats it as open. "Not applicable" needs a reason in the notes.
Mandatory means the gate stays shut | One open mandatory check and the recommendation cannot read certify.
Change what is mandatory on your project | The severity column is a starting position. Set it from your contract.
One copy per claim | Copy the workbook for each period. The reconciliation only makes sense against one claim.
Record who checked, and when | A certificate is a decision somebody made. The name and the date are the record of it.
IMPORTANT This is a working paper, not a payment certificate and not legal advice. Completing it does not certify a payment, satisfy any condition of the contract, or extend any deadline. Payment periods, retainage limits, lien waiver forms and notice requirements are set by the contract and by state law, and in several states cannot be varied by agreement - so a check that passes here may still leave a payment non-compliant. The severities shipped here are a starting position. Read your payment clause, check your state's rules, and get advice before withholding or reducing a payment.
Visit mastt.com

## Reconciliation
INVOICE VERIFICATION CHECKLIST · RECONCILIATION
Five numbers in. The sheet works out what should be certified and the difference against what was claimed.
WHAT YOU ENTER
| Amount | Where it comes from
Contract sum including approved change orders |  | Executed change orders only
Value of work in place, cumulative |  | What you say is in place
Value of stored materials allowed |  | On site, or stored with title passed
Previously certified, cumulative |  | Your record, not the contractor's
Retainage rate |  | From the contract
Retainage released this period |  | Against the contract milestone
Deductions the owner may make |  | Backcharges, utilities, cleanup
Amount claimed by the contractor |  | The figure on the claim
WHAT THE SHEET WORKS OUT
| Amount | How it is calculated
Work in place plus stored materials |  | The two lines above, added
Less retainage held |  | Your rate, applied to both lines above
Plus retainage released |  | As entered
Total earned to date |  | The three lines above
Less previously certified |  | As entered
Less owner deductions |  | As entered
AMOUNT THAT SHOULD BE CERTIFIED |  | Earned, less certified, less deductions
Amount claimed by the contractor |  | As entered
DIFFERENCE - CLAIMED LESS CERTIFIED |  | Positive means over-claimed
TWO CHECKS ON THE NUMBERS
What it means
Does the claim exceed the contract sum? | Enter the contract sum and the work in place | Either a change order is missing, or a line is overstated.
Is anything claimed more than the calculation supports? | Enter the numbers above | Resolve the disagreement before certification, not after.
Retainage is applied to work in place and stored materials at the rate you enter. Contracts differ on the base, on reductions at milestones and on whether retainage is held against stored materials at all - read yours and change the formula if it does not match. Nothing here decides what is in place; that is what the checklist and the site walk are for.
Visit mastt.com

## Verification Checklist
INVOICE VERIFICATION CHECKLIST · VERIFICATION CHECKLIST
Every check carries what it costs you if it fails. A blank is not a pass, and one open mandatory check keeps the gate shut.
1 THE CLAIM ADDS UP
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
1.1 | The claimed amount equals the sum of the line items on the claim | A claim whose total does not match its own lines has been edited after it was priced | Mandatory |  |  |  | Not answered
1.2 | Every line on the claim appears on the schedule of values, at the same line number | A line that is not on the schedule of values is unpriced work, a change order, or a duplicate of something already claimed | Mandatory |  |  |  | Not answered
1.3 | Percent complete claimed on each line is supported by what is on site | Percent complete is the single easiest number to overstate and the hardest to unwind once it has been certified | Mandatory |  |  |  | Not answered
1.4 | Previously certified amounts on the claim match your own certified record | If the contractor's opening figure is wrong, every number below it is wrong | Mandatory |  |  |  | Not answered
1.5 | The arithmetic on the retainage line matches the contract rate | Retainage is a percentage of a moving number and it is routinely calculated on the wrong base | Mandatory |  |  |  | Not answered
1.6 | Any release of retainage is supported by the milestone the contract ties it to | Retainage released early is retainage you do not have when you need it | Mandatory |  |  |  | Not answered
GROUP |  | Not started | 6 | 0
2 CHANGE ORDERS AND EXTRAS
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
2.1 | Every change order claimed has an executed change order, not just an email | An instruction is not a change order until it is executed, and paying against one weakens your position on every other change | Mandatory |  |  |  | Not answered
2.2 | No line claims work that is inside the original contract sum | Work already priced in the base scope claimed again as a change is the most common form of double payment on a construction project | Mandatory |  |  |  | Not answered
2.3 | Change order values on the claim match the executed change order amounts | A change order claimed at more than it was approved for is an overpayment nobody looks for twice | Mandatory |  |  |  | Not answered
2.4 | Allowance drawdowns are supported by actual cost, with backup | An allowance is reconciled against real cost - drawn down as a lump it becomes a margin | Advisory |  |  |  | Not answered
2.5 | No claim for work covered by a pending change order that has not been priced | Paying against an unpriced instruction sets the price | Mandatory |  |  |  | Not answered
GROUP |  | Not started | 4 | 0
3 STORED MATERIALS AND OFF-SITE WORK
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
3.1 | Materials claimed but not installed are on site, or properly stored off site | Materials paid for and not present are an unsecured advance | Mandatory |  |  |  | Not answered
3.2 | Title to stored materials passes to the owner, and it is evidenced | Without transfer of title you have paid for goods that belong to somebody else and may be claimed by a creditor | Mandatory |  |  |  | Not answered
3.3 | Stored materials are insured, identified as the owner's, and separately stored | Insurance and identification are what turn a payment into an asset | Mandatory |  |  |  | Not answered
3.4 | Materials claimed in a previous period are not claimed again as installed | The double claim happens at the moment a stored material becomes installed work | Mandatory |  |  |  | Not answered
GROUP |  | Not started | 4 | 0
4 DUPLICATES AND VENDOR DETAIL
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
4.1 | The invoice or claim number has not been paid before | The straightforward duplicate: the same claim submitted twice, in different periods | Mandatory |  |  |  | Not answered
4.2 | The amount, date and vendor combination does not match an earlier payment | A duplicate submitted under a new number is invisible to a number check | Mandatory |  |  |  | Not answered
4.3 | The payee name and bank details match the contract and the vendor record | A changed bank detail on an otherwise correct invoice is the most common payment fraud, and it succeeds because the invoice itself is genuine | Mandatory |  |  |  | Not answered
4.4 | Any change to payee or bank details was verified by a call to a known contact, not by replying to the email that requested it | Verifying a change by replying to the requesting email verifies nothing | Mandatory |  |  |  | Not answered
4.5 | The vendor is the contracting entity, not a related company | Payment to the wrong entity in a group can leave you without a contractual defence | Advisory |  |  |  | Not answered
GROUP |  | Not started | 4 | 0
5 CONTRACTUAL PRECONDITIONS TO PAYMENT
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
5.1 | The claim was submitted on the date the contract requires, for the period it covers | A claim outside its window may not be due yet, and certifying it early starts your own clock early | Advisory |  |  |  | Not answered
5.2 | The claim is in the form the contract requires, with the certificates it names | A payment application in the wrong form is often not a payment application at all | Mandatory |  |  |  | Not answered
5.3 | Insurance certificates covering this period are current and on file | An expired certificate discovered after an incident is discovered too late | Mandatory |  |  |  | Not answered
5.4 | Bonds required by the contract remain in force for the current contract sum | A bond written against the original sum may not cover the sum after change orders | Mandatory |  |  |  | Not answered
5.5 | Certified payroll or labor compliance records are provided where the contract or the funding requires them | On publicly funded work this is frequently a condition of payment and of the funding | Mandatory |  |  |  | Not answered
GROUP |  | Not started | 4 | 0
6 THE WORK ITSELF
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
6.1 | Inspections and tests due for the claimed work have been passed and recorded | Paying for work that has not passed its inspection pays for work that may be removed | Mandatory |  |  |  | Not answered
6.2 | Open non-conformances against the claimed work are identified and valued | Certifying defective work in full removes the leverage to have it fixed | Mandatory |  |  |  | Not answered
6.3 | Work claimed as complete has no outstanding punch list value against it | Complete and accepted are different states and only one of them is worth full payment | Advisory |  |  |  | Not answered
6.4 | Quantities on measured or unit-rate work have been verified independently | A unit rate multiplied by an unverified quantity is an estimate, not a claim | Advisory |  |  |  | Not answered
6.5 | Deductions the owner is entitled to make have been applied | Backcharges, utilities, cleanup and liquidated damages are easier to deduct now than to recover later | Advisory |  |  |  | Not answered
GROUP |  | Not started | 2 | 0
7 SUBCONTRACTORS, LIENS AND RELEASES
No. | What to check | What it costs you if it fails | Severity | Result | Checked by | Notes and evidence | Check
7.1 | Conditional lien waivers for this claim have been provided by the contractor and its subcontractors | An unwaived lien right survives the payment that should have extinguished it | Mandatory |  |  |  | Not answered
7.2 | Unconditional lien waivers for the previous payment have been received | The previous period is the one that gets forgotten, and it is the one that becomes a lien | Mandatory |  |  |  | Not answered
7.3 | The subcontractor and supplier list on the claim matches who is actually on site | A party on site and not on the list is a party whose lien rights you are not tracking | Advisory |  |  |  | Not answered
7.4 | No notice of non-payment or intent to lien has been received from anybody on the claim | Paying the contractor after a notice can leave you paying twice | Mandatory |  |  |  | Not answered
7.5 | Joint check or direct payment arrangements the contract allows have been considered where a subcontractor has raised non-payment | The remedy exists in most contracts and is rarely used until it is too late | Advisory |  |  |  | Not answered
GROUP |  | Not started | 3 | 0
The severity column is a starting position, not a standard - set it from your own payment clause and your funding conditions before you rely on the gate. "Not applicable" needs a reason in the notes, because an unexplained N/A is a check somebody skipped.
Visit mastt.com

## Certification
INVOICE VERIFICATION CHECKLIST · CERTIFICATION
Nothing typed above the signature block. Everything else is read off the reconciliation and the checklist.
● NOT STARTED - answer the checks on the Verification Checklist
MANDATORY CLEAR |  | FAILED |  | SHOULD BE CERTIFIED |  | CLAIMED LESS CERTIFIED
0 |  | 0
of 27 mandatory checks |  | any severity |  | from the reconciliation |  | positive means over-claimed
THE GATE, GROUP BY GROUP
1 The claim adds up |  |  | 0% |  | ● 6 open
2 Change orders and extras |  |  | 0% |  | ● 4 open
3 Stored materials and off-site work |  |  | 0% |  | ● 4 open
4 Duplicates and vendor detail |  |  | 0% |  | ● 4 open
5 Contractual preconditions to payment |  |  | 0% |  | ● 4 open
6 The work itself |  |  | 0% |  | ● 2 open
7 Subcontractors, liens and releases |  |  | 0% |  | ● 3 open
The bar is how many mandatory checks in the group have been answered Pass or Not applicable. The words beside it are what matters: a group at eighty percent with one failed mandatory check is not eighty percent certifiable.
THE RECOMMENDATION
Recommendation |  |  |  | Choose a recommendation
Amount recommended |  |  |  | Enter the figure you are recommending. It does not have to equal the calculation - but where it does not, say why in the notes below.
Reasons and conditions
SIGNED
Reviewed by
Date reviewed
Recommended by
Date recommended
A recommendation is not a certificate. Certifying is a contractual act with a form and a deadline, and in most states a statutory clock runs from the claim, not from this sheet. Issue the certificate the contract requires, on time, and keep this working paper with it.
Visit mastt.com
Checks answered | 0
Checks failed, any severity | 0
Mandatory checks | 27
Mandatory answered Pass or Not applicable | 0
Mandatory checks failed | 0
Answered with nobody named | 0
Mandatory checks still open | 27

## Lists
INVOICE VERIFICATION CHECKLIST · LISTS
The dropdowns. Edit them here and the checklist follows.
DROPDOWNS
Result | Severity | Recommendation | Yes / No | Notes
Pass | Mandatory | Certify in full | Yes | Only Pass and Not applicable let the gate open. "Not checked" counts as open, because a blank is not a pass and neither is an intention to look later. If you add a result, decide which of those two families it belongs to before you use it.
Fail | Advisory | Certify in part | No
Not applicable |  | Return to contractor
Not checked |  | Hold - awaiting information
Visit mastt.com

## Notes & Assumptions
INVOICE VERIFICATION CHECKLIST · NOTES & ASSUMPTIONS
What this file assumes, what to change first, and what it is not.
What this file assumes | One owner certifying one contractor's payment application on one construction contract in the United States. It is not an accounts payable process for trade invoices, and it is not a contractor's own claim preparation tool.
The severity column is a starting position | Nothing here is authoritative about what your contract makes a condition of payment. Read the payment clause and set the severities from it before you use the gate.
Retainage is calculated, not assumed | The sheet applies the rate you enter to the value of work in place. Contracts vary on the base, on reductions at milestones and on retainage held against stored materials - check yours.
The file does not value work | It reconciles what was claimed against what you say is in place. Deciding what is in place is the job the file cannot do for you.
Lien and payment rules are state law | Waiver forms, notice periods, prompt-payment deadlines and retainage limits differ by state and several of them cannot be varied by the contract. The checks ask the question; your jurisdiction supplies the answer.
It records a recommendation, not a certificate | Certifying is a contractual act with a form and a deadline. This workbook is the working paper behind it.
IMPORTANT This is a working paper, not a payment certificate and not legal advice. Completing it does not certify a payment, satisfy any condition of the contract, or extend any deadline. Payment periods, retainage limits, lien waiver forms and notice requirements are set by the contract and by state law, and in several states cannot be varied by agreement - so a check that passes here may still leave a payment non-compliant. The severities shipped here are a starting position. Read your payment clause, check your state's rules, and get advice before withholding or reducing a payment.
Visit mastt.com