## How To
Definition & How To
Definition
The RACI matrix describes the roles of those involved in business analysis activities. It describes stakeholders as having one or more of the following responsibilities for a given task or deliverable:
[R]esponsible – Think of this person as the project owner. There can be multiple people responsible for a task and if help is needed, they may ask a supportive member(s) to assist.
[A]ccountable – This person has final control over a project task and the resources associated with it. They will generally assign and delegate project work responsibilities. It is highly recommended to only use one person accountable to one task.
[C]onsulted – The people who provide information for the activity and with whom there is two-way communication. This is usually several people, often subject matter experts.
[I]nformed – These are people who need to be kept in the loop during the project life-cycle. Due to their status as a project stakeholder or the fact they will be impacted by the project, they will need to be informed about progress, at all stages, up-to and including project completion.
How to complete the template
1. Identify the tasks/deliverables and list them down the left side of the chart.
2. Identify the roles and list them along the top of the chart.
3. Complete the cells of the chart assigning RASCI.
4. Ensure every task/deliverable has a role responsible and a role accountable for it.

## Project RACI
Project Name:
Date:
Responsible | R
Accountable | A
Consulted | C
Informed | I
RACI Matrix
Program / Project Role | Management Office | Project Control Group | Financial Operations | Portfolio Manager | Program Manager | Project Manager | Consultant Team… | Quantity Surveyor | Architect | Building Services | Building Surveyor
Name | John Doe
Project Controls
Budget & Forecast |  | R
Project Cost Control | A
Project Minutes
Project Monthly Report | C
Issues Register
Risk Register
Project schedule
Project Plans
Project Charter
Change Management Plan
Risk Management Plan
Quality Management Plan
Security Management Plan
Project Management Plan
Procurement Plan
Stakeholder Management Plan
Design
Functional Design Brief
Planning Proposal
Development Application
Procurement
Proposal Documentation
EOI
Tender / RFQ Release
Tender Board
Tender Recommendation
Construction
Operations & Maintenance Manuals
Site Photographs
Safety Reporting
Completion certificates
Handover
Handover checklist
Key Register

## Deliverable Descriptions
Deliverable Descriptions
Deliverable | Level | Key activities and program/project requirements
Program Health Check | Program | Undertake periodic project health checks on a rolling program
Program Health Check | Program | Provide advice on program management requirements
Program Management Plan | Program | Participate in Steering Committee as an invitee
Program Management Plan | Program | Provide updates on selected projects in delivery phase if and as required
Program Management Plan | Program | Prepare consolidated Steering Committee papers
Program Management Plan | Program | Provide secretarial support for governance committees (meeting coordination, agendas and minutes)
Program Management Plan | Program | Review and monitor overall program governance structure performance
Program Management Plan | Program | Provide general Project Assurance for Project Management and ensuring provision of standard methodology, tools and templates
Program Management Plan | Program | Provide Project Assurance for cost, risk, schedule and resource management
Program Management Plan | Program | Provide program resource planning support
Program Resource Plan | Program | Review overall resource management plans
Program Resource Plan | Program | Engagement and performance management of WG Program Manager
Program Schedule | Program | Provide program scheduling support
Program Status Report | Program | Monthly review and reporting of PD/PM milestone performance
Stakeholder Engagement & Communication Strategy | Program | Identify all stakeholders, assess and recommend approach for engagement and communications
Issues Register | Program & Project | Monitor project risks and mitigation actions
RACI | Program & Project | Deliverable identifications and level of engagement
Resource Management Plan | Program & Project | Document and process procurement and/or HR requirements
Resource Management Plan | Program & Project | Manage recruitment
Resource Management Plan | Program & Project | Participate in interviews
Resource Management Plan | Program & Project | Arrange inductions and briefings and logistics
Resource Management Plan | Program & Project | Provide and/or procure project support officer resources
Risk Management Plan | Program & Project | Review and monitor risk management process for program and projects
Risk Register | Program & Project | Establish appropriate risk identification protocols (eg risk workshop)
Risk Register | Program & Project | Ensure risk management practices are documented and followed
Risk Register | Program & Project | Review risk register
Budget & Forecast | Project | Monitoring of project cost control processes
Change Management Plan | Project | Stakeholder assessment and change plan
Communications & Stakeholder Engagement Plan | Project | Engage with key stakeholders and obtain approval for governance structure
Communications & Stakeholder Engagement Plan | Project | Develop and implement internal project communication plan
Communications & Stakeholder Engagement Plan | Project | Review of stakeholder engagement plan
Communications & Stakeholder Engagement Plan | Project | Lead and organise stakeholder engagement
Project Cost Control | Project | Establishment of contracts and purchase orders
Project Cost Control | Project | Establishment of cost plan for project
Project Cost Control | Project | Cost planning, estimating and management
Project Initiation Meeting | Project | Organise kick off meeting
Project Initiation Meeting | Project | Participate in kick off meeting
Project Management Plan | Project | Document project team structure; ensure key responsibilities and accountabilities are appropriately identified
Project Management Plan | Project | Prepare project management plan
Project Management Plan | Project | Review and comment on project management plan
Project Management Plan | Project | Develop job descriptions and scope of work
Project Agenda | Project | Prepare papers for governance committees
Project Meetings | Project | Participate in PCGs and support effective project governance processes
Project Meetings | Project | Lead and coordinate meetings and working groups
Project Minutes | Project | Provide secretarial support for governance committees (meeting coordination, agendas and minutes)
Project Schedule | Project | Confirm appropriate project planning and schedule
Project Schedule | Project | Establishment of schedule for project
Project Schedule | Project | Establish project Work Breakdown Structure
Project Schedule | Project | Monitoring of project schedule
Project Schedule | Project | Scheduling and planning
Project Status Report | Project | Monitoring of supplier and vendor performance review process
Project Status Report | Project | Coordinate monthly status reporting
Project Status Report | Project | Review of project status reports
Terms of Reference | Project | Develop and document governance structure
Marketing Strategy | Program | Develop the marketing approach to distribute and support the narrative identified in the Communication & Stakeholder Engagement Strategy