## Setup
CONSTRUCTION QUOTE · SETUP
Set this up once. The tax label and rate, the margin, the retention and the validity date are read by every formula in the workbook.
THE QUOTATION
Quotation to |  | e.g. Northbank Health Authority
Project |  | e.g. Level 3 fit-out, 118 Riverside Drive
Quotation number |  | e.g. Q-2026-0142
Date |  | The date you issue it
Valid until |  | After this date the price is repriced - see Exclusions
Prepared by |  | e.g. D. Nkemelu, Estimating Manager
Builder |  | Your legal entity name and licence number
Documents priced |  | Drawings and specification, at revision, and any addenda
Contract intended |  | e.g. AS 4000-1997, JCT Minor Works, or your own form
TAX, MARGIN AND CONTRACT TERMS
Tax label | GST | GST for Australia, New Zealand, Singapore and South Africa; VAT for the United Kingdom and Ireland
Tax rate | 10% | 0.10 for Australian GST, 0.15 for New Zealand, 0.20 for UK VAT
Currency | AUD | Shown on the summary. Amounts are unformatted numbers, so any currency works
Margin on provisional work | 12% | Applied when a provisional sum is reconciled
Retention | 5% | Held on each progress claim, per the contract
Defects liability period | 12 months from practical completion | From the contract, not from this file
WHAT IS IN THIS FILE
Quotation | The priced offer, section by section, with quantity, unit and rate on every line. Nothing here is typed twice: the amount, the subtotals, the tax and the total all calculate.
Provisional sums and prime cost items | Kept off the fixed price on purpose, and totalled separately, because they are the part of the price that can still move.
Exclusions and qualifications | The two sections that define the price as much as the number does. A quotation with a thin exclusions list transfers risk you have not priced.
Variations | A register, so the quotation becomes the baseline rather than a dead document. Each variation carries its own status and the revised contract sum follows it.
Quote Summary | The quotation on one screen - and the number nobody else publishes: what proportion of the price is provisional and can therefore still move.
Lists | Units, variation statuses, and the tax setting. Edit them here.
Notes & Assumptions | What was assumed, what to change first, and what this file is not.
HOW TO USE IT
Set the tax up first | The label and the rate are at Setup. GST 10% for Australia, 15% for New Zealand, VAT 20% for the United Kingdom, and so on. Every formula reads them.
Price the work, then the exclusions | The exclusions decide who pays for a surprise. Write them before you send the number, not after somebody asks.
Keep provisional sums out of the fixed price | They are listed and totalled separately so the client can see what is fixed and what is not. That is the honest way to present it and it protects you as well.
Read the provisional percentage before you send it | If a third of your price is provisional, say so out loud at the presentation. The client will find out anyway.
Log every variation, including the rejected ones | A rejected variation is a record that you raised it. Those are the rows that matter twelve months later.
Do not delete a superseded line | Mark it and leave it. The history of the price is part of the record.
IMPORTANT What this quotation is, and what it is not. It is an offer to carry out the work described, on the terms described, until the validity date at Setup. It is not a contract, and accepting it does not replace the contract the parties intend to sign. Read the exclusions and the qualifications with the price: those sections define it as much as the number does. Nothing in this file is legal or tax advice, and nothing in it should be relied on as a statement of your obligations under security of payment, home building or consumer legislation, which differ in every jurisdiction and are frequently mandatory. The tax rate, the margin, the retention and the defects liability period are examples only. Have the final document reviewed by your own adviser before you issue it.
Visit mastt.com

## Quotation
CONSTRUCTION QUOTE · QUOTATION
Quantity times rate is calculated, never typed. The fixed price at the foot excludes the provisional sums and prime cost items, which are priced on their own sheet.
THE PRICED WORKS
No. | Section | Description | Unit | Quantity | Rate | Amount | Check
1 | Preliminaries | Site establishment, temporary fencing, amenities and site services | item | 1 | 14800 | 14800
2 | Preliminaries | Site supervision and programme management, 14 weeks | week | 14 | 1850 | 25900
3 | Preliminaries | Waste management, skip bins and final clean | item | 1 | 4600 | 4600
4 | Demolition | Strip-out of existing partitions, ceilings and floor coverings | m2 | 420 | 46 | 19320
5 | Demolition | Cart away and lawful disposal | item | 1 | 5200 | 5200
6 | Structure | Steel lintels and associated propping to the two new openings | no. | 2 | 3400 | 6800
7 | Structure | Concrete infill to the redundant stair void | m2 | 12 | 285 | 3420
8 | Carpentry | Stud framing to new partitions, including noggings and blocking | m2 | 186 | 92 | 17112
9 | Carpentry | Joinery: reception desk and two tea point units, as drawn | item | 1 | 28400 | 28400
10 | Linings and finishes | Plasterboard linings, set and stopped to Level 4 | m2 | 372 | 54 | 20088
11 | Linings and finishes | Painting, two coats to walls and ceilings | m2 | 640 | 22 | 14080
12 | Linings and finishes | Vinyl plank flooring, including levelling to 3 mm in 3 m | m2 | 420 | 78 | 32760
13 | Linings and finishes | Suspended ceiling grid and tiles | m2 | 380 | 68 | 25840
14 | Services | Mechanical: modification of existing supply and return, testing and balancing | item | 1 | 62400 | 62400
15 | Services | Electrical: power, lighting and data rough-in to the new layout | item | 1 | 54800 | 54800
16 | Services | Fire services: sprinkler head relocation and detection modification | item | 1 | 21600 | 21600
17 | Services | Hydraulic: tea point rough-in and connection | item | 1 | 8900 | 8900
18 | Completion | Commissioning, as-built markups and operating manuals | item | 1 | 6800 | 6800
Ten blank lines are pre-formatted. Insert rows inside the block, never below it, so the totals and the summary follow.
FIXED PRICE - THE PRICED WORKS ABOVE | [5 empty] | 372820
Visit mastt.com

## Provisional & PC Items
CONSTRUCTION QUOTE · PROVISIONAL & PC ITEMS
Held out of the fixed price on purpose. These are the amounts that will be reconciled, and the client should see them as a separate number.
PROVISIONAL SUMS AND PRIME COST ITEMS
No. | Item | Amount | What it covers | How it is reconciled
1 | Provisional sum - unforeseen conditions in the existing structure | 24000 | Making good conditions not visible at the site inspection | Actual cost plus the margin at Setup, adjusted by variation
2 | Provisional sum - floor levelling beyond the allowance | 9500 | Screeding where the existing slab exceeds 3 mm in 3 m | Measured on site against the rate in the quotation
3 | Prime cost item - light fittings | 18000 | Decorative fittings to reception and the meeting rooms, client to select | Actual supply cost, adjusted up or down by variation
4 | Prime cost item - floor coverings to reception | 7200 | Client selection from the supplier's range | Actual supply cost, adjusted up or down by variation
TOTAL PROVISIONAL AND PC ITEMS |  | 58700
A provisional sum is a placeholder for work that cannot be priced yet. It is not a budget and it is not a cap: it is reconciled against actual cost plus the margin at Setup, and the difference is a variation either way. A prime cost item is the same idea for a supply the client will select. Say all of that at the presentation, not afterwards.
Visit mastt.com

## Exclusions & Qualifications
CONSTRUCTION QUOTE · EXCLUSIONS & QUALIFICATIONS
These two sections define the price as much as the number does. Read them with the quotation, not after it.
EXCLUDED FROM THIS QUOTATION
Asbestos and hazardous materials | No survey, removal or disposal of any kind is included. If suspect material is found, work in that area stops and you are notified the same day.
Structural certification | Engineer's design and certification of the new openings is excluded and assumed to be provided by you.
Statutory approvals and fees | Development and building approval fees, and any long service levy, are excluded.
Out-of-hours work | The price assumes 7:00 am to 3:30 pm Monday to Friday. Work required outside those hours is a variation.
Latent conditions below the slab | Anything below the existing slab is excluded and will be a variation if encountered.
Furniture, loose fittings and equipment | Supply and installation are excluded.
Data and communications cabling | Rough-in only is included. Cabling, patching, devices and commissioning are excluded.
Escalation | The price holds until the validity date at Setup. After that date, materials and labour are repriced.
QUALIFICATIONS AND ASSUMPTIONS
What this price is based on | The drawings and specification listed at Setup, at the revisions stated. A later revision is a variation.
Access assumed | Continuous access to the work area during the hours above, with one goods lift available and the laydown area shown on the site plan.
Existing services | Assumed to be as shown on the documents provided. Services found elsewhere are a variation.
Programme assumed | Continuous work with no shutdown, and no more than two client-directed hold points.
Measurement | Quantities are as measured from the documents. Where an item is marked as measured on site, the rate applies to the quantity actually installed.
This is a quotation, not a contract | Acceptance of it is an instruction to proceed on these terms. The parties will sign the contract named at Setup, and where that contract and this quotation differ, the contract prevails.
Anything not written into the quotation or listed as a provisional sum is not in the price. That is not a technicality - it is the whole basis on which the number was built.
Visit mastt.com

## Variations
CONSTRUCTION QUOTE · VARIATIONS
The quotation is the baseline; this is what moves it. Only an APPROVED variation changes the contract sum - everything else is recorded and waiting.
VARIATIONS
No. | Date | What changed, and why | Status | Amount | Effect on the programme | Check
APPROVED VARIATIONS ONLY |  |  |  | 0
A variation marked Instructed - price to follow does NOT move the contract sum. That is deliberate: the sum only changes on an approved amount. It is flagged red because it is the state that costs money - work directed, price unagreed.
Visit mastt.com

## Quote Summary
CONSTRUCTION QUOTE · QUOTE SUMMARY
Nothing typed. The whole quotation on one screen - including the number nobody else publishes.
● 14% OF THIS PRICE IS PROVISIONAL - say which items, and how they reconcile, at the presentation
FIXED PRICE | PROVISIONAL AND PC |  |  | APPROVED VARIATIONS | TOTAL INCLUDING TAX
372820 | 58700 |  |  | 0 | 474672
AUD - the priced works | 14% of the sub-total |  |  | approved amounts only | incl. GST at 10%
HOW THE TOTAL IS BUILT
|  | Amount | Where it comes from
Fixed price - the priced works |  | 372820 | Quotation, foot of the Amount column
Provisional sums and prime cost items |  | 58700 | Provisional & PC Items, total
Approved variations |  | 0 | Variations, approved rows only
SUB-TOTAL before tax |  | 431520 | The three lines above
Tax |  | 43152 | GST at 10%, from Setup
TOTAL PAYABLE |  | 474672 | Sub-total plus tax
Retention held on each progress claim |  | 21576 | Sub-total times the retention percentage at Setup - a contract term, not a price
PRICED WORKS BY SECTION
Preliminaries |  | 45300 | ███████
Demolition |  | 24520 | ████
Structure |  | 10220 | ██
Carpentry |  | 45512 | ███████
Linings and finishes |  | 92768 | ███████████████
Services |  | 147700 | ████████████████████████
Completion |  | 6800 | █
Section labels are read from Lists, so adding a section there adds it here. One hue: this is magnitude, not identity.
Visit mastt.com

## Lists
CONSTRUCTION QUOTE · LISTS
Units, variation statuses and the sections. Edit a list here and every dropdown follows it.
DROPDOWNS
Unit | Variation status | Section | Notes
item | Submitted | Preliminaries | A variation marked Instructed - price to follow is the one to watch: the work has been directed and the money has not been agreed. It counts in the variation register and NOT in the revised contract sum, which is deliberate - the sum only moves on an approved variation.
no. | Approved | Demolition
m | Rejected | Structure
m2 | Withdrawn | Carpentry
m3 | Instructed - price to follow | Linings and finishes
kg |  | Services
tonne |  | Completion
hour
day
week
lump sum
Visit mastt.com

## Notes & Assumptions
CONSTRUCTION QUOTE · NOTES & ASSUMPTIONS
What this file assumes, what to change first, and what it is not.
What this file assumes | One builder quoting a lump sum to one client for a commercial fit-out or a light-construction job. Not a cost-plus quotation, not a design-and-construct quotation, and not a residential contract in a jurisdiction that mandates a particular form of contract and a particular form of quotation with it.
Why the tax is a setting | The demand for this template is spread across Australia, the United Kingdom, New Zealand, Ireland, South Africa, Singapore and Malaysia. A hard-coded 10% would have made it an Australian file with a global name.
Provisional sums are the honest part of a quotation | Every job has work that cannot be priced yet. Naming it, pricing it separately and saying how it will be reconciled is what separates a quotation from a guess. Hiding it inside the lump sum is how disputes start.
The provisional percentage is a judgement, not a rule | There is no threshold at which a quotation stops being fixed. The number is there so both parties can see it and talk about it, not so the file can pass or fail your quote.
Retention and defects liability are contract terms | The figures at Setup are examples. They come from the contract you sign, not from this file.
Rates are examples and will be wrong for you | Every rate in the worked example is illustrative. Replace all of them. They are not a benchmark and they are not indexed to any market.
IMPORTANT What this quotation is, and what it is not. It is an offer to carry out the work described, on the terms described, until the validity date at Setup. It is not a contract, and accepting it does not replace the contract the parties intend to sign. Read the exclusions and the qualifications with the price: those sections define it as much as the number does. Nothing in this file is legal or tax advice, and nothing in it should be relied on as a statement of your obligations under security of payment, home building or consumer legislation, which differ in every jurisdiction and are frequently mandatory. The tax rate, the margin, the retention and the defects liability period are examples only. Have the final document reviewed by your own adviser before you issue it.
Visit mastt.com