## Projects
MULTIPLE PROJECT TRACKING
One row per project. Type over the white cells; everything shaded is computed. 15 example projects, and they are deliberately not all healthy.
RIDGEMONT COUNTY CAPITAL PROGRAM · PROJECT TRACKER
ID | Project | Program | Phase | Project manager | Approved | Forecast | Variance | % comp. | Baseline finish | Forecast finish | Days var. | Cont. drawn | Open risks | Over- due | Last updated |  | Health
CP-101 | Ridgemont Public Safety Building | Public Safety | Construction | A. Whitfield | 48000000 | 49350000 | 1350000 | 62% | 2027-04-30 | 2027-06-18 | 49 | 71% | 9 | 2 | 2026-08-22 | 3 | ATTENTION - 3 signals | 3992
CP-102 | Fairbrook Fire Station 7 | Public Safety | Commissioning | R. Osei | 12400000 | 12310000 | -90000 | 94% | 2026-09-15 | 2026-09-22 | 7 | 58% | 3 | 0 | 2026-08-20 | 0 | ON TRACK | 991
CP-103 | Wexler Park Aquatic Center | Parks & Rec | Design | D. Kaplan | 21000000 | 21000000 | 0 | 22% | 2028-02-28 | 2028-02-28 | 0 | 12% | 6 | 1 | 2026-08-15 | 0 | ON TRACK | 990
CP-104 | Halstead Avenue Bridge Rehab | Transportation | Construction | M. Trejo | 9600000 | 10480000 | 880000 | 55% | 2026-11-30 | 2027-02-13 | 75 | 96% | 11 | 4 | 2026-08-23 | 5 | ATTENTION - 5 signals | 5989
CP-105 | Northside Transit Hub | Transportation | Procurement | A. Whitfield | 33500000 | 33500000 | 0 | 8% | 2029-06-30 | 2029-06-30 | 0 | 4% | 7 | 0 | 2026-08-17 | 0 | ON TRACK | 988
CP-106 | County Courthouse HVAC Renewal | Facilities | Construction | S. Lindqvist | 6800000 | 6735000 | -65000 | 78% | 2026-10-31 | 2026-11-07 | 7 | 64% | 2 | 1 | 2026-08-21 | 0 | ON TRACK | 987
CP-107 | Milbrook Water Treatment Upgrade | Water & Sewer | Construction | R. Osei | 54200000 | 53930000 | -270000 | 71% | 2027-08-31 | 2027-08-31 | 0 | 66% | 8 | 0 | 2026-07-08 | 2 | STALE - 49 days | 2986
CP-108 | Eastgate Library Renovation | Facilities | Closeout | D. Kaplan | 4300000 | 4298000 | -2000 | 99% | 2026-07-31 | 2026-08-08 | 8 | 88% | 1 | 0 | 2026-08-24 | 0 | ON TRACK | 985
CP-109 | Sanders Creek Trail Extension | Parks & Rec | Construction | M. Trejo | 2900000 | 2845000 | -55000 | 66% | 2026-12-15 | 2026-12-15 | 0 | 41% | 3 | 0 | 2026-08-18 | 0 | ON TRACK | 984
CP-110 | Vale Street Sewer Replacement | Water & Sewer | Construction | M. Trejo | 15700000 | 16920000 | 1220000 | 48% | 2027-03-31 | 2027-07-09 | 100 | 100% | 12 | 6 | 2026-08-25 | 5 | ATTENTION - 5 signals | 5983
CP-111 | Ridgemont Animal Shelter | Facilities | Design | A. Whitfield | 7100000 | 7100000 | 0 | 15% | 2028-05-31 | 2028-05-31 | 0 | 6% | 4 | 0 | 2026-08-12 | 0 | ON TRACK | 982
CP-112 | Fleet Maintenance Facility | Facilities | On hold | R. Osei | 18900000 | 18900000 | 0 | 5% | 2029-12-31 | 2029-12-31 | 0 | 2% | 5 | 3 | 2026-06-25 | - | ON HOLD
CP-113 | Grantham Elementary Field Lighting | Parks & Rec | Procurement | D. Kaplan | 1450000 | 1450000 | 0 | 12% | 2027-01-29 | 2027-01-29 | 0 | 8% | 2 | 0 | 2026-08-19 | 0 | ON TRACK | 980
CP-114 | Interchange 40 Signal Upgrade | Transportation | Commissioning | M. Trejo | 3250000 | 3244000 | -6000 | 92% | 2026-09-30 | 2026-10-16 | 16 | 74% | 2 | 1 | 2026-08-16 | 0 | ON TRACK | 979
CP-115 | Harlow Reservoir Liner | Water & Sewer | Feasibility | S. Lindqvist | 26000000 | 26000000 | 0 | 3% | 2030-03-31 | 2030-03-31 | 0 | 0% | 6 | 0 | 2026-08-07 | 0 | ON TRACK | 978
Insert rows inside the block above rather than typing below it, so the formulas and the portfolio ranking follow. Everything from Variance rightward is computed.
Visit mastt.com

## Portfolio
MULTIPLE PROJECT TRACKING
Which projects need attention, ranked. Everything here is read off the Projects sheet - there is nothing to type on this page.
4 of 14 active projects need attention this week
PORTFOLIO FORECAST |  | OVER APPROVED BUDGET |  | BEHIND BASELINE |  | STALE
268062000 |  | 3 |  | 3 |  | 1
against $265,100,000 approved |  | projects forecasting above approved |  | more than 30 days late |  | not updated in 21+ days
RANKED BY ATTENTION · THE TOP EIGHT
Rank | Project | Program | Approved | Forecast | Variance | Days | Health
1 | Halstead Avenue Bridge Rehab | Transportation | 9600000 | 10480000 | 880000 | 75 | ATTENTION - 5 signals
2 | Vale Street Sewer Replacement | Water & Sewer | 15700000 | 16920000 | 1220000 | 100 | ATTENTION - 5 signals
3 | Ridgemont Public Safety Building | Public Safety | 48000000 | 49350000 | 1350000 | 49 | ATTENTION - 3 signals
4 | Milbrook Water Treatment Upgrade | Water & Sewer | 54200000 | 53930000 | -270000 | 0 | STALE - 49 days
5 | Fairbrook Fire Station 7 | Public Safety | 12400000 | 12310000 | -90000 | 7 | ON TRACK
6 | Wexler Park Aquatic Center | Parks & Rec | 21000000 | 21000000 | 0 | 0 | ON TRACK
7 | Northside Transit Hub | Transportation | 33500000 | 33500000 | 0 | 0 | ON TRACK
8 | County Courthouse HVAC Renewal | Facilities | 6800000 | 6735000 | -65000 | 7 | ON TRACK
Projects on hold are excluded from this ranking. A paused project failing a schedule test tells you nothing you did not already know.
BY PROGRAM · WHERE THE MONEY AND THE TROUBLE ARE
Program |  | Projects | Approved | Forecast | Variance | Need | Position
Public Safety |  | 2 | 60400000 | 61660000 | 1260000 | 1 | 1 of 2 needs attention
Parks & Rec |  | 3 | 25350000 | 25295000 | -55000 | 0 | All clear
Transportation |  | 3 | 46350000 | 47224000 | 874000 | 1 | 1 of 3 needs attention
Facilities |  | 4 | 37100000 | 37033000 | -67000 | 0 | All clear
Water & Sewer |  | 3 | 95900000 | 96850000 | 950000 | 2 | 2 of 3 need attention
BY PROJECT MANAGER · WHO IS CARRYING WHAT
Active projects per manager before load is flagged |  |  |  | 4 | Set it to how your program actually runs.
Project manager |  | Projects | Approved | Forecast | Variance | Need | Load
A. Whitfield |  | 3 | 88600000 | 89950000 | 1350000 | 1 | 1 needs attention
R. Osei |  | 3 | 85500000 | 85140000 | -360000 | 1 | 1 needs attention
D. Kaplan |  | 3 | 26750000 | 26748000 | -2000 | 0 | Inside the load
M. Trejo |  | 4 | 31450000 | 33489000 | 2039000 | 2 | 2 in trouble - over-committed
S. Lindqvist |  | 2 | 32800000 | 32735000 | -65000 | 0 | Inside the load
A manager with two projects in trouble is a resourcing decision, not a project one - and it is the reading a per-program roll-up cannot give you, because trouble spread across three programs can still be one person.
Visit mastt.com

## Reference
MULTIPLE PROJECT TRACKING
The six thresholds every project is scored against, and the dropdown sources. Change a number here and every row on the Projects sheet re-scores.
THE SIX TESTS
Test | Value | What it means
Forecast over approved by more than | 2 | % · Cost variance. A forecast above the approved budget by more than this fails the test.
Forecast finish behind baseline by more than | 30 | days · Schedule variance against the approved baseline, not against last month.
Contingency drawn ahead of percent complete by | 15 | points · The earliest honest warning. Arithmetic, not judgment, so it moves before the forecast does.
No status update in more than | 21 | days · STALE. A project nobody has touched is not green, it is unknown - see the notes.
Open risks at or above | 8 | risks · Volume, not severity. Severity is the risk register's job; this is a load signal.
Overdue actions at or above | 3 | actions · Actions past their due date on the project's own action log.
DROPDOWN SOURCES
Edit these lists and the Projects sheet dropdowns follow.
Phase |  | Program | Project manager
Feasibility |  | Public Safety | A. Whitfield
Design |  | Parks & Rec | R. Osei
Procurement |  | Transportation | D. Kaplan
Construction |  | Facilities | M. Trejo
Commissioning |  | Water & Sewer | S. Lindqvist
Closeout
On hold
Visit mastt.com

## Notes & Assumptions
MULTIPLE PROJECT TRACKING
How the scoring works, and where this file stops.
HOW TO USE IT
Replace the fifteen example projects and nothing else | Every column to the right of Last updated is computed. Type over the white cells only; the shaded ones will recalculate.
Update the whole portfolio on one day each month | A tracker where half the rows are current and half are six weeks old is worse than no tracker, because the comparison between projects stops meaning anything. That is what Last updated is for and what the STALE flag catches.
Attention is a count of signals, not an opinion | Six objective tests run on every row. A project's score is how many it fails, and the portfolio sheet ranks on it. Nobody has to argue about whether something is amber.
Projects on hold are excluded from the ranking, not from the list | They keep their row and their budget and they drop out of the attention count, because a paused project failing a schedule test tells you nothing you did not already know.
NOTES
The six tests, and the numbers behind them | Forecast above approved by more than 2%. Forecast finish more than 30 days behind baseline. Contingency drawn more than 15 points ahead of percent complete. No status update in 21 days. Open risks at 8 or more. Overdue actions at 3 or more. Change any of them on the Reference sheet and every row re-scores.
STALE beats GREEN, and that is the whole point | A project reporting green that nobody has touched in six weeks is not green, it is unknown. Every other multi-project template treats a blank update date as neutral. This one treats it as a finding, because the commonest way a portfolio surprises an owner is a project that stopped reporting rather than one that reported badly.
Contingency ahead of progress is the earliest honest warning | Cost variance shows up late, because a forecast is a judgment and judgments lag. Contingency drawn against percent complete is arithmetic and it moves first. A project 48% complete that has spent all of its contingency is in trouble whatever its forecast says - see CP-110.
This is a tracker, not a list and not a report | A directory of what projects exist, who runs them and what they are worth is a project list, and Mastt publishes a Construction Project List Template for that. The monthly narrative for a sponsor is a report, and Mastt publishes a Monthly Project Report Template. This file is the status layer between them.
WHAT THIS FILE IS NOT
One row per project, not per task | This tracks a portfolio. Tasks, dependencies and the critical path belong in the project schedule, and a portfolio tracker that grows a task column stops being usable at about project six.
It does not replace the individual project's controls | Each project still needs its own schedule, risk register, change log and cost report. This file reads the top line off each of them; it is not a substitute for any of them.
The money columns are a control total, not an accounting record | Approved, committed and forecast here should reconcile to the finance system monthly. Where they disagree, the finance system governs and this file is corrected.
IMPORTANT
This is a template and a worked example, not advice. The portfolio, the projects, the people and every figure in it are invented and illustrative. The thresholds on the Reference sheet are starting points chosen to make the example demonstrate each test; set them to your own delegations and your own tolerance before you use this to make a decision. Figures here are a management summary and are not an accounting record - reconcile them to your finance system before reporting them externally, and have anything carrying financial or contractual consequence reviewed before you issue it.
Visit mastt.com