## Register
STAKEHOLDER REGISTER
One row per stakeholder, and the row every other sheet reads. Type over the white cells; Priority and Check are computed. Nineteen worked entries, and they are deliberately not all healthy.
WYNFORD CROSSING TRANSIT CENTER AND PARKING STRUCTURE · STAKEHOLDER REGISTER
ID | Stakeholder | Organization | Role | Type | Category | Email | Phone | Influence 1-5 | Interest 1-5 | Priority | What they need from the project | Main concern | Owner | Status | Check
S-01 | D. Ashworth | Ashfield County Transit Authority | Board Chair | Internal | Client and governance | d.ashworth@example.gov | (559) 555-0100 | 5 | 3 | Keep satisfied | A project that opens on the date announced to the public, inside the approved budget | A public opening date was announced before the permits were secured | Project Director | Active | OK | At target | -18
S-02 | M. Anyabwile | Ashfield County Transit Authority | Executive Director | Internal | Client and governance | m.anyabwile@example.gov | (559) 555-0101 | 5 | 5 | Manage closely | Weekly cost and schedule position, and no surprises at board meetings | Federal funding milestones are tied to construction start | Project Director | Active | OK | At target | -4
S-03 | R. Vandermeer | Ashfield County Transit Authority | Finance Director | Internal | Client and governance | r.vandermeer@example.gov | (559) 555-0102 | 4 | 3 | Keep satisfied | Drawdown forecast that matches the appropriation calendar | Cash flow ahead of the grant reimbursement cycle | Cost Manager | Active | OK | At target | -22
S-04 | City of Wynford | Planning Department | Site plan review | Statutory | Statutory and regulatory | planning@example.gov | (559) 555-0104 | 5 | 4 | Manage closely | A complete site plan submission and a traffic impact study | Parking structure height against the overlay district limit | Approvals Lead | Active | OK | MOVE +1 level | -14
S-05 | City of Wynford | Building Department | Building permit | Statutory | Statutory and regulatory | building@example.gov | (559) 555-0105 | 5 | 3 | Keep satisfied | Stamped construction documents and structural calculations | Phased permit for foundations ahead of the full set | Approvals Lead | Active | OK | At target | -29
S-06 | State Department of Transportation | District 4 | Highway access permit | Statutory | Statutory and regulatory | d4.permits@example.gov | (559) 555-0106 | 5 | 3 | Keep satisfied | An access permit application with signal warrant analysis | The bus entry conflicts with the planned interchange upgrade | Approvals Lead | Active | OK | MOVE +1 level | -7
S-07 | State Environmental Agency | Water Division | Stormwater discharge permit | Statutory | Statutory and regulatory | stormwater@example.gov | (559) 555-0107 | 5 | 2 | Keep satisfied | A stormwater pollution prevention plan and a detention design | First submission was refused on detention volume | Design Lead | Active | High influence, low interest - brief them | MOVE +1 level | -13
S-08 | Fire Marshal | Wynford Fire District | Life safety review | Statutory | Statutory and regulatory | firemarshal@example.gov | (559) 555-0108 | 4 | 2 | Keep satisfied | Egress, standpipe and access routes reviewed before the building permit | Aerial apparatus access to the upper parking deck | Design Lead | Active | High influence, low interest - brief them | MOVE +1 level | 16
S-09 | Federal Grant Agency | Grants management office | Grant compliance | Statutory | Statutory and regulatory | region5@example.gov | (559) 555-0109 | 5 | 4 | Manage closely | Quarterly reporting, Buy America certification, and milestone evidence | Schedule slip against the grant agreement milestones | Project Director | Active | OK | At target | -39
S-10 | Ashfield Electric | Utility provider | Service connection | External | Utilities and service providers | connections@example.com | (559) 555-0110 | 4 | 3 | Keep satisfied | Load calculations and a connection application eleven months ahead of energization | Substation capacity in the Wynford feeder | Project Manager | Active | OK | MOVE +1 level | -25
S-11 | T. Brennan | Ashfield County Transit Authority | Operations Manager | Internal | End users and operations | t.brennan@example.gov | (559) 555-0103 | 4 | 2 | Keep satisfied | A facility their drivers and dispatchers can actually run from day one | Operations has not been consulted on bay layout or driver facilities | Project Manager | Active | High influence, low interest - brief them | MOVE +4 levels | -8
S-12 | L. Hidalgo | Wynford Accessibility Advisory Committee | Chair | External | Community and neighbors | chair@example.org | (559) 555-0112 | 3 | 5 | Keep informed | ADA compliance reviewed by users, not only by code | Path of travel from the parking structure to the platforms | Engagement Lead | Active | OK | MOVE +1 level | -21
S-13 | Wynford Business Coalition | Local business group | Executive Director | External | Community and neighbors | director@example.org | (559) 555-0113 | 3 | 5 | Keep informed | Access to storefronts maintained through construction | Loss of on-street parking during the eighteen-month build | Engagement Lead | Active | OK | MOVE +1 level | -41
S-14 | P. Okwuosa | Wynford Neighborhood Association | President | External | Community and neighbors | president@example.org | (559) 555-0114 | 3 | 5 | Keep informed | Construction hours, noise limits and haul routes agreed in writing | Night work and the height of the parking structure against the residential edge | Engagement Lead | Active | OK | MOVE +2 levels | -26
S-15 | G. Adeyemi | Wynford Retail Holdings | Adjacent property owner | External | Community and neighbors | g.adeyemi@example.com | (559) 555-0115 | 4 | 4 | Manage closely | An access easement negotiated before the site is mobilized | Construction traffic across their loading area | Project Director | Active | OK | MOVE +1 level | -19
S-16 | Ashfield Water and Sewer District | Utility provider | Connections manager | External | Utilities and service providers | connections@example.org | (559) 555-0111 | 3 | 3 | Monitor | Connection application and a backflow prevention detail | Main capacity on Wynford Avenue | Project Manager | Active | OK | At target | -34
S-17 | County Emergency Management | Ashfield County | Planning liaison | External | End users and operations | emergency@example.gov | (559) 555-0116 | 3 | 2 | Monitor | The facility included in the county evacuation and shelter plan | Transit center role during regional incidents is undefined |  | Active | No owner named | MOVE +2 levels | -34
S-18 | K. Rasmussen | Vellinge Design Partnership | Design Lead | External | Delivery team | k.rasmussen@example.com | (559) 555-0117 | 4 | 5 | Manage closely | Decisions inside the turnaround set in the contract | Owner review turnaround on submittals | Project Manager | Active | OK | MOVE +1 level | -5
S-19 | J. Castellanos | Barrow Construction | Construction Manager at Risk | External | Delivery team | j.castellanos@example.com | (559) 555-0118 | 4 | 5 | Manage closely | Site access on the date warranted, and permits in hand before mobilization | Utility relocations are on the critical path and not yet applied for | Project Manager | Active | OK | MOVE +1 level | -5
0
0
0
0
0
0
19 stakeholders · 6 to manage closely · 6 statutory · 4 row(s) the Check column flagged
Insert rows inside the block above rather than typing below it, so the totals and every companion sheet follow. Priority and Check are computed and cannot be typed over.
Visit mastt.com

## Engagement
STAKEHOLDER REGISTER
Where each stakeholder is, where the project needs them, and when contact is next due. The ID and the name come from the Register - type the ID and the name follows.
ENGAGEMENT · CURRENT AGAINST TARGET
ID | Stakeholder | Priority | Current | Target | Gap | Phase of most interest | Method | Frequency | Last contact | Next due | Days | Check
S-01 | D. Ashworth | Keep satisfied | 4 | 4 | At target | Planning | Formal meeting | Monthly | 2026-08-14 | 2026-09-14 | -18 | OK
S-02 | M. Anyabwile | Manage closely | 5 | 5 | At target | Construction | Formal meeting | Weekly | 2026-08-24 | 2026-08-31 | -4 | OK
S-03 | R. Vandermeer | Keep satisfied | 4 | 4 | At target | Planning | Email | Monthly | 2026-08-18 | 2026-09-18 | -22 | OK
S-04 | City of Wynford | Manage closely | 3 | 4 | MOVE +1 level | Planning | Formal meeting | At milestones | 2026-08-20 | 2026-09-10 | -14 | OK
S-05 | City of Wynford | Keep satisfied | 3 | 3 | At target | Design | Written submission | At milestones | 2026-08-12 | 2026-09-25 | -29 | OK
S-06 | State Department of Transportation | Keep satisfied | 2 | 3 | MOVE +1 level | Design | Formal meeting | At milestones | 2026-08-06 | 2026-09-03 | -7 | OK
S-07 | State Environmental Agency | Keep satisfied | 2 | 3 | MOVE +1 level | Design | Written submission | At milestones | 2026-08-19 | 2026-09-09 | -13 | OK
S-08 | Fire Marshal | Keep satisfied | 3 | 4 | MOVE +1 level | Design | Formal meeting | Quarterly | 2026-06-11 | 2026-08-11 | 16 | Contact overdue by 16 days
S-09 | Federal Grant Agency | Manage closely | 4 | 4 | At target | Construction | Written submission | Quarterly | 2026-08-05 | 2026-10-05 | -39 | OK
S-10 | Ashfield Electric | Keep satisfied | 3 | 4 | MOVE +1 level | Procurement | Formal meeting | Monthly | 2026-08-21 | 2026-09-21 | -25 | OK
S-11 | T. Brennan | Keep satisfied | 1 | 5 | MOVE +4 levels | Commissioning | Face to face | Monthly |  | 2026-09-04 | -8 | Never engaged
S-12 | L. Hidalgo | Keep informed | 4 | 5 | MOVE +1 level | Design | Face to face | At milestones | 2026-08-13 | 2026-09-17 | -21 | OK
S-13 | Wynford Business Coalition | Keep informed | 3 | 4 | MOVE +1 level | Construction | Public forum | Quarterly | 2026-08-07 | 2026-10-07 | -41 | OK
S-14 | P. Okwuosa | Keep informed | 2 | 4 | MOVE +2 levels | Construction | Public forum | Monthly | 2026-08-22 | 2026-09-22 | -26 | Gap of 2 levels
S-15 | G. Adeyemi | Manage closely | 3 | 4 | MOVE +1 level | Procurement | Face to face | Monthly | 2026-08-15 | 2026-09-15 | -19 | OK
S-16 | Ashfield Water and Sewer District | Monitor | 3 | 3 | At target | Procurement | Email | As required | 2026-08-04 | 2026-09-30 | -34 | OK
S-17 | County Emergency Management | Monitor | 1 | 3 | MOVE +2 levels | Operations | Email | Quarterly |  | 2026-09-30 | -34 | Never engaged
S-18 | K. Rasmussen | Manage closely | 4 | 5 | MOVE +1 level | Design | Formal meeting | Weekly | 2026-08-25 | 2026-09-01 | -5 | OK
S-19 | J. Castellanos | Manage closely | 4 | 5 | MOVE +1 level | Construction | Formal meeting | Weekly | 2026-08-25 | 2026-09-01 | -5 | OK
Days is negative until the date passes and positive after it, so a column of positive numbers is a register nobody has worked this month. The gap is what the engagement plan schedules; this sheet is what tells it where to start.
Visit mastt.com
Formulas:
Days = IF([Next due]="","",TODAY()-[Next due])

## Consents
STAKEHOLDER REGISTER
The stakeholders who hold something you need. A permit you have not applied for is a start date, not a communications task - and no amount of engagement is a substitute for the consent.
CONSENTS, PERMITS AND APPROVALS · WHO HOLDS WHAT
ID | Held by | What is held | Reference | Status | Submitted | Decision due | Typical lead time | Critical path | Check
S-04 | Planning Department | Site plan approval, including the traffic impact study | SP-2026-118 | Under review | 2026-06-30 | 2026-09-30 | 90 to 120 days | Yes | OK
S-05 | Building Department | Building permit - full construction documents | [Not yet issued] | In preparation |  | 2026-11-15 | 60 to 90 days | Yes | OK
S-06 | District 4 | Highway access permit for the bus entry on Wynford Avenue | [Not yet issued] | Not started |  | 2026-10-15 | 120 to 180 days | Yes | NOT STARTED, on the critical path
S-07 | Water Division | Stormwater discharge permit and pollution prevention plan | SW-2026-0442 | Refused | 2026-05-18 | 2026-10-30 | 90 to 150 days | Yes | REFUSED - resubmission lead time applies
S-08 | Wynford Fire District | Life safety and fire access sign-off | [Not yet issued] | In preparation |  | 2026-10-01 | 30 to 60 days | No | Decision due in 35 days, nothing submitted
S-09 | Grants management office | Federal grant milestone certification for construction start | FTA-5307-2026-11 | Submitted | 2026-08-05 | 2026-09-20 | 45 to 60 days | Yes | OK
S-10 | Utility provider | Electrical service connection and substation capacity confirmation | CE-CONN-8871 | Under review | 2026-07-14 | 2026-10-20 | 9 to 12 months | Yes | OK
S-15 | Wynford Retail Holdings | Access easement across the adjacent loading area | [Under negotiation] | In preparation |  | 2026-10-31 | 60 to 120 days | Yes | OK
S-16 | Utility provider | Water and sewer connection approval | WS-2026-2201 | Granted with conditions | 2026-06-02 | 2026-08-15 | 60 to 90 days | No | OK
3 of 9 consents need attention, and 7 critical-path consents are not yet granted
Lead times are indicative and vary by jurisdiction and by agency - confirm every one with the issuing authority. A consents block that records only what was granted cannot show you the one that went wrong, which is why a refused permit stays on this sheet.
Visit mastt.com

## Dashboard
STAKEHOLDER REGISTER
The register read three ways. Everything here is counted off the Register, the Engagement sheet and the Consents sheet - there is nothing to type on this page.
13 of 19 stakeholders are not yet at the engagement level this project needs
STAKEHOLDERS | MANAGE CLOSELY |  |  | NOT YET ENGAGED |  | CONSENTS OUTSTANDING
19 | 6 |  |  | 2 |  | 8
on the register | high influence, high interest |  |  | never contacted, or unaware |  | permits and approvals not yet granted
BY CATEGORY · WHERE THE REGISTER IS THIN
Category | Total | Manage closely | Statutory | Gap to close | Reading
Client and governance | 3 | 1 | 0 | 0 | All at target
Statutory and regulatory | 6 | 2 | 6 | 4 | 4 of 6 need to move
Utilities and service providers | 2 | 0 | 0 | 1 | 1 of 2 need to move
Community and neighbors | 4 | 1 | 0 | 4 | 4 of 4 need to move
Delivery team | 2 | 2 | 0 | 2 | 2 of 2 need to move
End users and operations | 2 | 0 | 0 | 2 | 2 of 2 need to move
An empty category is the finding. Most registers are heavy on the delivery team, who are under contract and easy to name, and thin on end users and operations - the group that will run the asset and is asked last.
BY OWNER · WHO IS CARRYING THE ENGAGEMENT
Owner | Stake- holders | At target | To move | Overdue | Position
Approvals Lead | 3 | 1 | 2 | 0 | 2 to move, none overdue
Cost Manager | 1 | 1 | 0 | 0 | All at target
Design Lead | 2 | 0 | 2 | 1 | 1 overdue for contact
Engagement Lead | 3 | 0 | 3 | 0 | 3 to move, none overdue
Project Director | 4 | 3 | 1 | 0 | 1 to move, none overdue
Project Manager | 5 | 1 | 4 | 0 | 4 to move, none overdue
Overdue counts the stakeholders whose next-contact date has passed. An owner with none of those and nobody to move is the only row on this block that should be green.
Visit mastt.com

## Log
STAKEHOLDER REGISTER
What was actually said, and what came out of it. A register that records who somebody is but never what happened is a contact list.
ENGAGEMENT LOG · MOST RECENT FIRST
Date | ID | Stakeholder | Method | What was discussed | Outcome or action | Action owner | Due
2026-08-25 | S-19 | J. Castellanos | Formal meeting | Weekly delivery meeting. CMAR raised utility relocation lead times against the mobilization date. | Owner to confirm the electrical connection date in writing before the GMP is set | Project Manager | 2026-09-05
2026-08-24 | S-02 | M. Anyabwile | Formal meeting | Executive briefing on the stormwater permit refusal and the revised detention design. | Revised submission to be filed; Executive Director to brief the board chair | Design Lead | 2026-09-09
2026-08-22 | S-14 | P. Okwuosa | Public forum | Neighborhood association meeting. Night work, haul routes and the height of the parking structure against the residential edge. | Draft construction management plan to be issued to the association for comment | Engagement Lead | 2026-09-12
2026-08-21 | S-10 | Ashfield Electric | Formal meeting | Connection application review with the utility. Substation capacity in the Wynford feeder confirmed as the constraint. | Load calculations to be reissued at 100% design; connection date to be confirmed in writing | Project Manager | 2026-09-18
2026-08-20 | S-04 | City of Wynford | Formal meeting | Planning department pre-decision meeting on the parking structure height against the overlay district limit. | Massing study and shadow diagrams to be submitted as a supplement | Approvals Lead | 2026-09-05
2026-08-19 | S-07 | State Environmental Agency | Written submission | Response to the stormwater refusal. Detention volume recalculated against the revised impervious area. | Resubmission package to be filed once the civil design is reissued | Design Lead | 2026-09-09
2026-08-15 | S-15 | G. Adeyemi | Face to face | Easement negotiation with the adjacent owner. Construction traffic across the loading area and hours of access. | Draft easement terms to be issued by counsel | Project Director | 2026-09-15
2026-08-13 | S-12 | L. Hidalgo | Face to face | Accessibility committee walkthrough of the path of travel from the parking structure to the platforms. | Two wayfinding changes accepted; committee to review the revised plan | Design Lead | 2026-09-17
2026-08-06 | S-06 | State Department of Transportation | Formal meeting | State DOT district meeting on the bus entry against the planned interchange upgrade. | Signal warrant analysis required before the access permit application can be filed | Approvals Lead | 2026-09-03
2026-06-11 | S-08 | Fire Marshal | Formal meeting | Fire marshal review of aerial apparatus access to the upper parking deck. | Turning analysis to be provided; no further contact since | Design Lead | 2026-07-15
10 entries · 1 action(s) past their due date
Type the ID and the stakeholder name follows. Log the meetings that changed something - a log of every email is a log nobody reads, and the entries that matter are the ones with an action against them.
Visit mastt.com

## Reference
STAKEHOLDER REGISTER
Every list the Register uses, and what each score means. Edit anything here and the dropdowns follow - the sheets index this one rather than carrying their own copy.
|  |  | Type | Phase | Method | Frequency | Status | Consent status | Owner
ENGAGEMENT LEVEL · WHERE A STAKEHOLDER IS, AND WHERE YOU NEED THEM |  |  | Internal | Planning | Formal meeting | Weekly | Active | Not started | Approvals Lead
Score | Level | What it means | External | Design | Face to face | Fortnightly | Dormant | In preparation | Cost Manager
1 | Unaware | Does not know the project exists, or does not know it affects them. | Statutory | Procurement | Email | Monthly | Closed | Submitted | Design Lead
2 | Resistant | Aware, and opposed. Will act to slow or stop the work. |  | Construction | Written submission | Quarterly |  | Under review | Engagement Lead
3 | Neutral | Aware, neither supportive nor opposed. The default for most of a register. |  | Commissioning | Public forum | At milestones |  | Granted | Project Director
4 | Supportive | Aware and in favor. Will not obstruct; will not advocate unprompted. |  | Operations | Newsletter | As required |  | Granted with conditions | Project Manager
5 | Leading | Actively engaged in making the project succeed. Rare, and worth naming. |  |  | Site visit |  |  | Refused
Scored 1 to 5 so the gap between current and target is arithmetic. A register that records only where somebody is cannot show whether the engagement is working.
PRIORITY · READ OFF INFLUENCE AND INTEREST, NOT TYPED
Quadrant | Where | What it means you do
Manage closely | Influence 4-5 and interest 4-5 | Face to face, on a named cadence, before decisions rather than after them.
Keep satisfied | Influence 4-5 and interest 1-3 | They can stop you and they are not watching. Brief them enough that they are never surprised. The riskiest group, because it looks quiet.
Keep informed | Influence 1-3 and interest 4-5 | They care and they talk. Regular, honest, unfiltered updates - an informed advocate here is worth more than a managed one.
Monitor | Influence 1-3 and interest 1-3 | General communications only. Re-score every cycle; interest moves faster than influence.
STAKEHOLDER CATEGORIES · THE BREAKDOWN THE REGISTER USES
Client and governance |  | The board, the sponsor, finance, and anyone inside the owner who can stop or fund the work.
Statutory and regulatory |  | Planning, building control, environment, transport, fire. They issue permits; they are not persuaded, they are satisfied.
Utilities and service providers |  | Power, water, sewer, gas, telecoms. Connections and relocations with lead times measured in months, not weeks.
Community and neighbors |  | Residents, associations, adjacent owners, local business. Rarely a direct cost; routinely a schedule risk.
Delivery team |  | Designers, contractors, consultants, cost and program managers under contract to the owner.
End users and operations |  | The people who run the asset after handover, and the people who use it. The group most often identified last and needed earliest.
THE OTHER LISTS · EDIT THEM IN THE HIDDEN COLUMNS G TO M
Type |  | Internal · External · Statutory
Phase |  | Planning · Design · Procurement · Construction · Commissioning · Operations
Method |  | Formal meeting · Face to face · Email · Written submission · Public forum · Newsletter · Site visit
Frequency |  | Weekly · Fortnightly · Monthly · Quarterly · At milestones · As required
Status |  | Active · Dormant · Closed
Consent status |  | Not started · In preparation · Submitted · Under review · Granted · Granted with conditions · Refused
Owner |  | Approvals Lead · Cost Manager · Design Lead · Engagement Lead · Project Director · Project Manager
Unhide columns G to M to edit these. They sit off the print area because a list of dropdown values is machinery, not content - but they are the machinery, so they are here rather than buried on a sheet nobody opens.
Visit mastt.com

## Notes & Assumptions
STAKEHOLDER REGISTER
How the register works, and where this file stops.
HOW TO USE IT
Fill the Register first. Everything else reads it. | The Engagement, Consents and Log sheets are keyed on the ID in column B. Type a stakeholder in once and their name follows them everywhere.
Score influence and interest separately, and honestly | Influence is what they can do to the project. Interest is how much they care. Somebody who can stop you and is not watching is the most dangerous entry in a register, and scoring them high on both because they feel important hides it.
Set a target engagement level, not just a current one | A register that records only where somebody is cannot show whether the engagement is working. The gap is the work, and the Engagement sheet ranks it.
Anyone holding a permit, an easement or a sign-off goes on the Consents sheet | That is the difference between a stakeholder you brief and a stakeholder who decides your start date. Flag the row on the Register and the Consents sheet picks it up.
Re-score at every stage gate | A neighbor who was Neutral during design is Resistant the week the piling starts, and an operations group nobody consulted is Unaware until handover. Interest moves faster than influence.
NOTES
A stakeholder with no owner against them is the commonest silent failure | Every other column can be filled in perfectly and nothing will happen. S-17 in the worked example has no owner and the Check column names it; a register with three of those is a register nobody is running.
Unaware is a real state and it belongs in the register | Most templates start at Neutral, which quietly assumes everyone has been told. S-11 is the operations manager at influence 4 and engagement 1 - the group that will run the building and has not been asked about the bay layout. That row is worth the whole file.
A refused permit stays in the register | S-07 was refused on detention volume and is being resubmitted. A consents log that records only what was granted cannot show you the one that went wrong, and the resubmission lead time is what moves the program.
Contact details are part of the record, not an afterthought | A register you cannot act from at 4pm on a Friday is a spreadsheet about stakeholders. Email and phone sit on the Register sheet for that reason.
This register holds personal information | Names, roles, contact details and assessments of identifiable people. Store it accordingly, keep the concern column factual rather than editorial, and be deliberate about who receives it - a leaked stakeholder register does more damage than not having one.
WHAT THIS FILE IS NOT
The matrix is the picture; this is the record | Mastt publishes a Stakeholder Matrix Template - a self-plotting influence and interest grid. Its stakeholder list is an INPUT to that grid, eight columns wide. This file is the source the grid reads from, and it carries the contact details, the consents and the log that a grid has no room for.
The analysis is a different piece of work | Working out what each stakeholder wants, what they are worried about and what they can do about it is stakeholder analysis, and Mastt publishes a Stakeholder Analysis Template. This register records the conclusion in two columns; that file is where the thinking happens.
The engagement schedule is a plan, not a register | Who talks to whom, saying what, through which channel, on what cadence, with what budget is a Stakeholder Management Plan, which Mastt publishes. The Engagement sheet here records the method and the frequency; it does not write the communications.
The Consents sheet is not a permit program | It records what each stakeholder holds and where it is up to, because that is an attribute of the stakeholder. Sequencing the applications, tracking the fees and managing the submissions is an approvals program and it is a bigger job than this file.
IMPORTANT
This is a template and a worked example, not legal or planning advice. The project, the agencies, the people and every figure in it are invented and illustrative - the permits, lead times and decision dates on the Consents sheet in particular are indicative only and vary by jurisdiction, by agency and by project. Confirm every consent, its lead time and its decision path with the issuing authority for your own project before you rely on them. This register also records contact details and assessments of identifiable individuals, which in most jurisdictions is personal information and in some is subject to privacy or data protection law; store, share and retain it accordingly.
Visit mastt.com