## Cover
CHANGE LOG
One row per change, claimed and approved kept apart, and a contract position that only moves on an agreed amount.
SET THIS UP ONCE
Project |  | e.g. Northbank Ambulatory Care Center
Project number |  | e.g. NB2-2026-014
Contract |  | One contract per workbook
Contractor |  | e.g. Halbrook Construction
Original contract sum |  | As awarded, before any change
Original completion date |  | As awarded, before any extension of time
Decision threshold, days |  | Undecided longer than this flags as overdue
Data date |  | Leave it blank and it uses today.
WHAT IS IN THIS FILE
Change Log | One row per change. Cost and time are recorded twice - claimed, then approved - and the check column says what the row is missing.
Contract Position | Approved changes only, against the original sum and date. Everything undecided is shown separately as exposure.
Change Summary | Nothing typed. Approved against claimed, the exposure, the oldest open change.
Lists | Status, type, origin and route. Edit them here and the workbook follows.
Notes & Assumptions | What was assumed, what to change first, and what this file is not.
HOW TO USE IT
Raise the row the day the change appears | Not the day it is priced. The date raised is what proves how long the decision took.
Keep claimed and approved apart | Leave the approved columns empty until somebody with authority decides. One column that gets overwritten destroys the record of what was asked for.
Only Approved moves the contract sum | "Approved - price to follow" does not - the file carries it as exposure instead.
Give every row a route | A change with no route is a change nobody has decided how to handle.
Watch the days open, not the status | Set the decision threshold on this Cover and anything past it flags, whatever its status.
Record where the documents are | The row is an index. Name the file, the email or the drawing revision.
IMPORTANT This is a record, not an approval, and not a contract document. Writing a change here does not create an entitlement, does not give notice, and does not change the contract sum or the completion date - only the contract's own change mechanism does that, in the form and within the time the contract requires. The worked example is invented and every figure in it is illustrative. Read your contract's change clause before you rely on any of this, and get advice on anything that may become a claim.
Visit mastt.com

## Change Log
CHANGE LOG
Claimed is not approved. Fill the claimed columns when the change is raised and leave the approved columns empty until somebody with authority decides.
Change no. | Date raised | Raised by | Title | What changed, and why | Type of change | Origin | Route | Cost claimed | Days claimed | Cost approved | Days approved | Cost variance | Status | Decided by | Date decided | Days open | Where the documents are | Check
CO-001 | 2026-05-19 | R. Delacroix | Switchgear relocation to level 2 riser | Utility connection point moved after the authority review, so the main switchgear and the riser above it relocate one level. | Regulatory or authority | Authority | Change order | 84500 | 12 | 71200 | 8 | -13300 | Approved | M. Okafor | 2026-06-10 | 22 | Change file CO folder, and the email of that date
CO-002 | 2026-06-13 | R. Delacroix | Rock in the south lift pit excavation | Rock encountered below the reduced level shown on the geotechnical report. Breaking and cart-away of 140 cubic yards. | Site condition | Existing conditions | Change order | 52800 | 9 | 41600 | 6 | -11200 | Approved | M. Okafor | 2026-07-02 | 19 | Change file CO folder, and the email of that date
CO-003 | 2026-07-10 | R. Delacroix | Nurse call system upgrade to the current standard | Owner elected to upgrade the nurse call heads and head-end to the current campus standard after the design was documented. | Owner request | Owner | Change directive | 118000 | 15 |  |  |  | Approved - price to follow | M. Okafor | 2026-07-14 | 4 | Change file CO folder, and the email of that date
CO-004 | 2026-07-25 | R. Delacroix | Acceleration to recover the shutdown window | Contractor proposal to add a second shift for four weeks to bring the level 3 shutdown back inside its original window. | Schedule only | Contractor | Change request - not instructed | 96400 | -14 |  |  |  | Priced - awaiting decision |  |  | 29 | Change file CO folder, and the email of that date | Overdue for decision
CO-005 | 2026-08-05 | R. Delacroix | Delete the external canopy glazing | Canopy glazing deleted from this contract and moved to the separate landscape package. | Scope deletion | Owner | Change order | -37500 | 0 | -37500 | 0 | 0 | Approved | M. Okafor | 2026-08-12 | 7 | Change file CO folder, and the email of that date
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL | [7 empty] | 314200 | 22 | 75300 | 14 | -24500 | 5 change(s) logged
Twenty-five blank rows are pre-formatted. Insert rows inside the block, never below it, so the totals, the contract position and the summary all follow. A negative cost is a credit and a negative day count is time recovered - both are added, so a deletion reduces the sum without a separate column. Date decided is the last column on the row: fill it when the decision is made and Days open stops counting.
Visit mastt.com
Formulas:
Days open = IF([Date raised]="",0,IF([Date decided]<>"",[Date decided]-[Date raised],IF(Cover!$C14="",TODAY(),Cover!$C14)-[Date raised]))

## Contract Position
CHANGE LOG · CONTRACT POSITION
Approved changes only. Everything claimed and not yet decided is exposure, not position.
THE CONTRACT SUM
| Amount | Days | Where it comes from
Original contract sum, as awarded |  |  | Cover - the sum before any change
Approved changes | 75300 | 14 | Change Log - status Approved only, cost and days approved
CURRENT CONTRACT SUM |  | 14 | Original plus approved changes. This is the only number that has been agreed.
Claimed and not yet decided | 214400 | 1 | Change Log - every status except Approved, Rejected and Withdrawn, at the CLAIMED amount
Instructed with no price agreed | 118000 | 15 | Change Log - work instructed, amount still open. Included in the line above.
WORST CASE IF EVERYTHING CLAIMED IS ALLOWED |  | 15 | Current sum plus everything claimed and undecided. Not a forecast - a boundary.
THE COMPLETION DATE
| Date | Days | Where it comes from
Original completion date, as awarded |  |  | Cover
Approved extension of time |  | 14 | Change Log - days approved on Approved rows only
CURRENT COMPLETION DATE |  |  | Original plus approved days. The agreed date.
Days claimed and not yet decided |  | 1 | Change Log - claimed days on every undecided row
Nothing on this sheet is typed. The current sum and the current completion date move only on a change whose status is Approved - an instruction with no agreed amount is shown as exposure and nothing else, because a sum cannot change on an intention. The worst case is a boundary, not a forecast: it assumes every open claim is allowed in full, which is the one thing you can say without pricing anything.
Visit mastt.com

## Change Summary
CHANGE LOG · CHANGE SUMMARY
Nothing typed. Every figure is a formula over the Change Log.
▲ 1 CHANGE(S) INSTRUCTED WITH NO PRICE AGREED - work is proceeding against an open amount
APPROVED | CLAIMED, UNDECIDED |  |  |  | UNPRICED INSTRUCTIONS |  | OLDEST OPEN, DAYS
75300 | 214400 |  |  |  | 1 |  | 29
on 3 approved change(s) | on 2 open change(s) |  |  |  | instructed, amount still open |  | threshold is 21 days
WHAT WAS CLAIMED, AND WHAT WAS APPROVED
Change |  | Claimed |  | Approved |  | Variance | Status
CO-001 Switchgear relocation to level 2 riser |  | 84500 |  | 71200 |  | -13300 | Approved
CO-002 Rock in the south lift pit excavation |  | 52800 |  | 41600 |  | -11200 | Approved
CO-003 Nurse call system upgrade to the current standard |  | 118000 |  |  |  |  | Approved - price to follow
CO-004 Acceleration to recover the shutdown window |  | 96400 |  |  |  |  | Priced - awaiting decision
CO-005 Delete the external canopy glazing |  | -37500 |  | -37500 |  | 0 | Approved
A negative variance means the change was approved for less than was claimed - that is your review working, and it is the number to show whoever asks what the cost management is buying. A row with a claim and no approved figure has not been decided.
APPROVED COST BY TYPE OF CHANGE
Scope addition |  | 0
Scope deletion |  | -37500 | █
Design change |  | 0
Site condition |  | 41600 | ██████████████
Owner request |  | 0
Regulatory or authority |  | 71200 | ████████████████████████
Error or omission |  | 0
Substitution |  | 0
Schedule only |  | 0
Correction - no cost or time |  | 0
One hue on purpose: this is magnitude, not identity. Approved cost only - the claimed figures are on the table above, because a chart of what people asked for is not a chart of what the project costs.
WHO CAUSED THE APPROVED CHANGES
Owner |  | -37500 | █
Designer |  | 0
Contractor |  | 0
Authority |  | 71200 | ████████████████████████
Third party |  | 0
Existing conditions |  | 41600 | ██████████████
Not established |  | 0
Origin is the column that answers who pays, and it is the one people leave blank. "Not established" is an honest entry and a prompt; an empty cell is neither.
Visit mastt.com

## Lists
CHANGE LOG · LISTS
The four dropdowns. Edit them here and the log follows.
DROPDOWNS
Status | Type of change | Origin | Route | Yes / No
Raised | Scope addition | Owner | Change order | Yes
Under review | Scope deletion | Designer | Change directive | No
Priced - awaiting decision | Design change | Contractor | Change request - not instructed
Approved | Site condition | Authority | Absorbed - no change order
Approved - price to follow | Owner request | Third party | Allowance drawdown
Rejected | Regulatory or authority | Existing conditions | Contingency drawdown
Withdrawn | Error or omission | Not established
Deferred | Substitution
Schedule only
Correction - no cost or time
Only "Approved" moves the contract sum. "Approved - price to follow" means the work has been instructed and the amount has not been agreed, so it is carried as exposure instead - which is the honest treatment and usually the uncomfortable one. If you add a status, add it to the Contract Position sheet's rule as well or it will be counted as open.
Visit mastt.com

## Notes & Assumptions
CHANGE LOG · NOTES & ASSUMPTIONS
What this file assumes, what to change first, and what it is not.
What this file assumes | One project under one contract, with one party deciding changes. Not a program-wide change register and not a software release log. If you run several contracts, use one workbook per contract - the contract position on sheet 3 only makes sense against a single contract sum.
Claimed and approved are different columns on purpose | The variance between them is the number that tells you whether your review is working. A log with one cost column cannot produce it.
Only Approved moves the sum | "Approved - price to follow" and "Priced - awaiting decision" are both shown as exposure and neither changes the contract position. That is the honest treatment, and it is why the exposure figure is usually the uncomfortable one.
Time is in calendar days | Every day column is calendar days unless your contract says otherwise. If it works in working days, say so in the route or the notes column and stay consistent - the file does not convert between them.
A negative number is a reduction | Deletions and credits go in as negatives, in both cost and days. The contract position adds them, so a credit reduces the sum without needing a separate column.
The file does not price anything | It records what was claimed and what was agreed. Whether an amount is reasonable, and whether an entitlement exists at all, are questions for your contract and your quantity surveyor.
Dates are yours | Nothing here calculates a decision date for you, because the period depends on your contract. Set the threshold on the Cover and the file will tell you when you have passed it.
IMPORTANT This is a record, not an approval, and not a contract document. Writing a change here does not create an entitlement, does not give notice, and does not change the contract sum or the completion date - only the contract's own change mechanism does that, in the form and within the time the contract requires. The worked example is invented and every figure in it is illustrative. Read your contract's change clause before you rely on any of this, and get advice on anything that may become a claim.
Visit mastt.com