## Cover
PROJECT MILESTONE CHART
One table of milestones, two views drawn from it. Set the two dates below first - both charts and every status word are measured from them.
SET THESE FIRST
Project name |  | Prints in the banner on every sheet.
Project number |  | Your own reference.
Project start date | 2024-03-01 | Column one of both charts is the month containing it. The timeline runs 48 months. Type your own date over it.
Report date | 2026-09-01 | What the sheet treats as today. Type a fixed date to freeze a chart for a meeting.
Prepared by |  | Who owns the dates in this file.
WHAT IS IN THIS FILE
Milestones | The table. One row per milestone: baseline, forecast, actual, and who owns it. Variance and status are calculated.
Milestone chart | The chart. Baseline and forecast marked on the same row against a monthly timeline, so the slip is the distance between them.
Gantt | The same milestones as spans - each bar runs from the milestone before it, so the length of each stretch of work is visible.
Summary | Nothing typed. Achieved, moved, the biggest slip, and what is due next.
Lists | The phase names, and what each status word means. Edit the phases here.
Notes & Assumptions | What this file is, what it is not, and which sheet answers which question.
HOW TO USE IT
Set the project start date and the report date first | Both charts and every status word are measured from them.
Type the baseline once and then leave it | A baseline you keep editing cannot show slippage. If the baseline is formally re-set, note the date and the reason on the Notes sheet.
Keep the forecast current and the actual empty until it happens | An actual date closes the row. Everything the sheet says about a milestone stops mattering once it has one.
Do not type the variance or the status | Both are calculated from the three dates. Typing over them is how a chart ends up disagreeing with its own table.
Say why it moved, in the row | The difference between a chart that reports a delay and one that explains it.
Delete the phases you do not use | A milestone chart with forty rows is a program, and it will not be read.
IMPORTANT This is a template and a worked example, not advice and not a program. The project and every date in it are invented and illustrative. A milestone chart records dates and the movement in them; it does not grant an extension of time, agree a date, prove a delay or establish who caused one, and where a contract requires a program, a notice or a claim in a particular form, this file does not satisfy it. Replace the content with your own dates, and have anything that may become a claim reviewed before you issue it.
Visit mastt.com

## Milestones
PROJECT MILESTONE CHART
EXAMPLE CONTENT - 18 worked milestones, 10 achieved and 9 that moved. Clear the example rows and this banner goes.
One row per milestone. Type the baseline once, keep the forecast current, and leave the actual empty until it happens. Variance and status are calculated.
No. | Milestone | Phase | Owner | Baseline | Forecast | Actual | Var (days) | Status | Predecessor | Why it moved | Check
1 | Business case approved | Initiation | Capital Projects | 2024-03-01 | 2024-03-01 | 2024-03-01 | 0 | Achieved
2 | Design team appointed | Initiation | Procurement | 2024-05-01 | 2024-05-01 | 2024-05-01 | 0 | Achieved | Business case approved
3 | Concept design accepted | Design | Design manager | 2024-08-01 | 2024-08-01 | 2024-08-01 | 0 | Achieved | Design team appointed
4 | Development approval granted | Approvals | Planning consultant | 2024-11-01 | 2025-01-01 | 2025-01-01 | 61 | Achieved | Concept design accepted | Two rounds of information requests from the authority
5 | Design development complete | Design | Design manager | 2025-02-01 | 2025-02-01 | 2025-02-01 | 0 | Achieved | Development approval granted
6 | Guaranteed maximum price agreed | Procurement | Commercial manager | 2025-04-01 | 2025-05-01 | 2025-05-01 | 30 | Achieved | Design development complete | Held for the approval condition on the loading dock
7 | Construction contract executed | Procurement | Commercial manager | 2025-05-01 | 2025-06-01 | 2025-06-01 | 31 | Achieved | Guaranteed maximum price agreed | Follows the price agreement
8 | Notice to proceed issued | Construction | Project manager | 2025-06-01 | 2025-06-01 | 2025-06-01 | 0 | Achieved | Construction contract executed
9 | Site established | Early works | Contractor | 2025-07-01 | 2025-07-01 | 2025-07-01 | 0 | Achieved | Notice to proceed issued
10 | Bulk excavation complete | Construction | Contractor | 2025-10-01 | 2025-11-01 | 2025-11-01 | 31 | Achieved | Site established | Rock in the south lift pit
11 | Structure complete | Construction | Contractor | 2026-05-01 | 2026-06-01 |  | 31 | Late | Bulk excavation complete | Carries the excavation delay; one week recovered on the slab cycle |  | 2026-06-01
12 | Building watertight | Construction | Contractor | 2026-09-01 | 2026-10-01 |  | 30 | At risk | Structure complete | Follows the structure |  | 2026-10-01
13 | Mechanical and electrical rough-in complete | Construction | Contractor | 2026-12-01 | 2027-02-01 |  | 62 | At risk | Building watertight | Long-lead switchgear delivery, and the level 2 riser hold |  | 2027-02-01
14 | Fit-out complete | Construction | Contractor | 2027-05-01 | 2027-06-01 |  | 31 | At risk | Mechanical and electrical rough-in complete | Follows rough-in |  | 2027-06-01
15 | Commissioning start | Commissioning | Commissioning agent | 2027-07-01 | 2027-08-01 |  | 31 | At risk | Fit-out complete | Agent not yet appointed - see the check column |  | 2027-08-01
16 | Substantial completion | Commissioning | Project manager | 2027-10-01 | 2027-10-01 |  | 0 | On track | Commissioning start | Two weeks of float in the commissioning sequence absorbs the rough-in delay |  | 2027-10-01
17 | Certificate of occupancy issued | Handover | Project manager | 2027-10-01 | 2027-10-01 |  | 0 | On track | Substantial completion |  |  | 2027-10-01
18 | Handover and closeout complete | Handover | Project manager | 2028-01-01 | 2028-01-01 |  | 0 | On track | Certificate of occupancy issued |  |  | 2028-01-01
Type in the blue cells. Variance, status and the check column are calculated and are locked, so clearing a row cannot take the formulas with it - select the blue cells and clear those. Variance is in days and it is the effective date - the actual if there is one, otherwise the forecast - less the baseline. The table holds 26 milestones, which is the capacity of both chart sheets.
Visit mastt.com

## Milestone chart
PROJECT MILESTONE CHART
EXAMPLE CONTENT - 18 worked milestones, 10 achieved and 9 that moved. Clear the example rows and this banner goes.
Baseline and forecast on the same row. The distance between the pale marker and the solid one is the slip. Nothing on this sheet is typed - change a date on the Milestones sheet and the chart redraws.
MILESTONE CHART
| Milestone | Status | Var (d) | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2026-09-01 | 2024-03-01
|  |  |  | 24 | [9 empty] | 25 | [11 empty] | 26 | [11 empty] | 27 | [11 empty] | 28
1 | Business case approved | Achieved | 0 | [48 empty] | 2024-03-01 | 2024-03-01 | Achieved | 2024-03-01
2 | Design team appointed | Achieved | 0 | [48 empty] | 2024-05-01 | 2024-05-01 | Achieved | 2024-05-01
3 | Concept design accepted | Achieved | 0 | [48 empty] | 2024-08-01 | 2024-08-01 | Achieved | 2024-08-01
4 | Development approval granted | Achieved | 61 | [48 empty] | 2024-11-01 | 2025-01-01 | Achieved | 2025-01-01
5 | Design development complete | Achieved | 0 | [48 empty] | 2025-02-01 | 2025-02-01 | Achieved | 2025-02-01
6 | Guaranteed maximum price agreed | Achieved | 30 | [48 empty] | 2025-04-01 | 2025-05-01 | Achieved | 2025-05-01
7 | Construction contract executed | Achieved | 31 | [48 empty] | 2025-05-01 | 2025-06-01 | Achieved | 2025-06-01
8 | Notice to proceed issued | Achieved | 0 | [48 empty] | 2025-06-01 | 2025-06-01 | Achieved | 2025-06-01
9 | Site established | Achieved | 0 | [48 empty] | 2025-07-01 | 2025-07-01 | Achieved | 2025-07-01
10 | Bulk excavation complete | Achieved | 31 | [48 empty] | 2025-10-01 | 2025-11-01 | Achieved | 2025-11-01
11 | Structure complete | Late | 31 | [48 empty] | 2026-05-01 | 2026-06-01 | Late | 0
12 | Building watertight | At risk | 30 | [48 empty] | 2026-09-01 | 2026-10-01 | At risk | 0
13 | Mechanical and electrical rough-in complete | At risk | 62 | [48 empty] | 2026-12-01 | 2027-02-01 | At risk | 0
14 | Fit-out complete | At risk | 31 | [48 empty] | 2027-05-01 | 2027-06-01 | At risk | 0
15 | Commissioning start | At risk | 31 | [48 empty] | 2027-07-01 | 2027-08-01 | At risk | 0
16 | Substantial completion | On track | 0 | [48 empty] | 2027-10-01 | 2027-10-01 | On track | 0
17 | Certificate of occupancy issued | On track | 0 | [48 empty] | 2027-10-01 | 2027-10-01 | On track | 0
18 | Handover and closeout complete | On track | 0 | [48 empty] | 2028-01-01 | 2028-01-01 | On track | 0
HOW TO READ IT
| Baseline | Where the milestone was promised. On a row that slipped there are two markers, and the gap between them is the slip.
| Achieved | An actual date is recorded, in the month it happened.
| On track | Forecast on or before the baseline.
| At risk or late | Forecast after the baseline, or behind the report date.
| Report date | The month containing the report date on the Cover.
Visit mastt.com

## Gantt
PROJECT MILESTONE CHART
EXAMPLE CONTENT - 18 worked milestones, 10 achieved and 9 that moved. Clear the example rows and this banner goes.
The same milestones as spans. Each bar runs from the milestone above it to this one, so the length of each stretch of work is visible. The bars are intervals between milestones - not duration estimates, and there is no logic or float in them.
GANTT VIEW
| Milestone | Status | Var (d) | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2026-09-01 | 2024-03-01
|  |  |  | 24 | [9 empty] | 25 | [11 empty] | 26 | [11 empty] | 27 | [11 empty] | 28
1 | Business case approved | Achieved | 0 | [48 empty] | 2024-03-01 | 2024-03-01 | Achieved | 2024-03-01
2 | Design team appointed | Achieved | 0 | [48 empty] | 2024-05-01 | 2024-05-01 | Achieved | 2024-05-01
3 | Concept design accepted | Achieved | 0 | [48 empty] | 2024-08-01 | 2024-08-01 | Achieved | 2024-08-01
4 | Development approval granted | Achieved | 61 | [48 empty] | 2024-11-01 | 2025-01-01 | Achieved | 2025-01-01
5 | Design development complete | Achieved | 0 | [48 empty] | 2025-02-01 | 2025-02-01 | Achieved | 2025-02-01
6 | Guaranteed maximum price agreed | Achieved | 30 | [48 empty] | 2025-04-01 | 2025-05-01 | Achieved | 2025-05-01
7 | Construction contract executed | Achieved | 31 | [48 empty] | 2025-05-01 | 2025-06-01 | Achieved | 2025-06-01
8 | Notice to proceed issued | Achieved | 0 | [48 empty] | 2025-06-01 | 2025-06-01 | Achieved | 2025-06-01
9 | Site established | Achieved | 0 | [48 empty] | 2025-07-01 | 2025-07-01 | Achieved | 2025-07-01
10 | Bulk excavation complete | Achieved | 31 | [48 empty] | 2025-10-01 | 2025-11-01 | Achieved | 2025-11-01
11 | Structure complete | Late | 31 | [48 empty] | 2026-05-01 | 2026-06-01 | Late | 0
12 | Building watertight | At risk | 30 | [48 empty] | 2026-09-01 | 2026-10-01 | At risk | 0
13 | Mechanical and electrical rough-in complete | At risk | 62 | [48 empty] | 2026-12-01 | 2027-02-01 | At risk | 0
14 | Fit-out complete | At risk | 31 | [48 empty] | 2027-05-01 | 2027-06-01 | At risk | 0
15 | Commissioning start | At risk | 31 | [48 empty] | 2027-07-01 | 2027-08-01 | At risk | 0
16 | Substantial completion | On track | 0 | [48 empty] | 2027-10-01 | 2027-10-01 | On track | 0
17 | Certificate of occupancy issued | On track | 0 | [48 empty] | 2027-10-01 | 2027-10-01 | On track | 0
18 | Handover and closeout complete | On track | 0 | [48 empty] | 2028-01-01 | 2028-01-01 | On track | 0
HOW TO READ IT
| Complete | The interval ended on a milestone that has an actual date.
| Ahead or on track | The interval ends on a milestone that has not slipped.
| At risk or late | The interval ends on a milestone that has.
| Report date | The month containing the report date on the Cover.
Visit mastt.com

## Summary
PROJECT MILESTONE CHART
EXAMPLE CONTENT - 18 worked milestones, 10 achieved and 9 that moved. Clear the example rows and this banner goes.
Nothing on this sheet is typed. Every figure comes from the Milestones table.
▲ 1 milestone behind the report date, and 4 at risk
MILESTONES |  | ACHIEVED |  | MOVED |  | BIGGEST SLIP
18 |  | 10 |  | 9 |  | 62
In the table |  | 56% of the milestones |  | Forecast or actual later than the baseline |  | days, on Mechanical and electrical rough-in complete
WHERE THE MILESTONES STAND
Achieved | 10 | ████████████████████████
On track | 3 | ███████
At risk | 4 | ██████████
Late | 1 | ██
Not set | 0
NEXT THREE DUE
Milestone |  |  | Forecast |  | Status
Structure complete |  |  | 2026-06-01 |  | Late
Building watertight |  |  | 2026-10-01 |  | At risk
Mechanical and electrical rough-in complete |  |  | 2027-02-01 |  | At risk
The three earliest milestones that have a forecast and no actual date. If fewer than three rows appear, that is how many are left.
Visit mastt.com

## Lists
PROJECT MILESTONE CHART · LISTS
The phase names, and exactly what each status word tests. Edit the phases; the status words are computed and cannot be typed.
PHASES
Initiation
Design
Approvals
Procurement
Early works
Construction
Commissioning
Handover
WHAT EACH STATUS WORD TESTS
Status | The test, in order of precedence
Achieved | An actual date is recorded. Nothing else about the row matters after that.
On track | No actual date, and the forecast is on or before the baseline.
At risk | Forecast is after the baseline but the milestone has not yet passed.
Late | The forecast or the baseline is behind the report date and there is no actual.
Not set | No baseline, so there is nothing to be on track against.
The status column on the Milestones sheet is a formula. There is no dropdown for it on purpose: a milestone chart where somebody types the status is a chart of opinions.
Visit mastt.com

## Notes & Assumptions
PROJECT MILESTONE CHART · NOTES & ASSUMPTIONS
What this file is, what it is not, and which sheet answers which question.
WHICH SHEET ANSWERS WHICH QUESTION
A milestone chart marks moments | One row per milestone, with the baseline and the forecast marked on the same line. The gap between the two markers is the slippage. Use it with an owner or a board, who want to know whether the dates that were promised are still the dates.
A Gantt chart shows spans | The same milestones, drawn as the intervals between them, so the length of each stretch of work is visible. Use it with a delivery team, who want to know how long they have.
Both sheets are drawn from the Milestones table | There is nothing to color in and nothing to keep in step. Type a date once and both views redraw.
This is not a construction program | A milestone chart has no logic in it beyond the predecessor column, no resources and no critical path. It reports a schedule; it does not produce one. Where a contract requires a program in a particular form, this file does not satisfy it.
It is not the project report either | The milestone table in a monthly report is a summary of this. Mastt publishes a project report template for that, and keeping the dates here and reporting from them is what stops the two disagreeing.
NOTES AND ASSUMPTIONS
What the timeline assumes | Forty-eight monthly columns from the project start date. A job longer than four years needs more columns; a job shorter than a year is better served by a weekly timeline, which means changing the month formula in row 4 of both chart sheets to add 7 days instead of a month.
Dates are compared as dates, not as months | The variance is in days, taken from the two dates you type. The columns are months only because that is what fits on a page - a milestone that moves eight days inside one month shows a variance of eight and no visible movement on the chart, and both are correct.
Status is derived and cannot be overridden | Achieved, on track, at risk, late or not set, in that order of precedence. The Lists sheet says exactly what each one tests. If you disagree with a status, change a date or change the test - do not type over the answer.
The Gantt bars are intervals, not durations | Each bar runs from the previous milestone to this one, which is the elapsed time between them. It is not an estimate of how long the work takes and it does not know about float, overlap or logic.
The predecessor column is a note, not a link | Nothing recalculates when a predecessor moves. It is there so a reader can see which slip caused which, and so you can check the chain by eye.
Re-baseline deliberately or not at all | The whole value of this file is that the baseline column does not move. If a formal re-baseline is approved, save the old version first.
IMPORTANT This is a template and a worked example, not advice and not a program. The project and every date in it are invented and illustrative. A milestone chart records dates and the movement in them; it does not grant an extension of time, agree a date, prove a delay or establish who caused one, and where a contract requires a program, a notice or a claim in a particular form, this file does not satisfy it. Replace the content with your own dates, and have anything that may become a claim reviewed before you issue it.
Visit mastt.com